## exam1
Exam Name | Question | quesimgsrc | Answer1 | Answer2 | Answer3 | Answer4 | Correct-Answer | Explanation | answerimgsrc
Exam 1 | #1. .You are creating a performance measurement baseline (PMB) for your project. In this context, all of the following statements related to performance measurement baseline (PMB) are correct EXCEPT: |  | A-) PMB is the authorized budget assigned to scheduled work. | B-) Sometimes PMB is referred to as Total of Earned Value. | C-) A spending plan can be used as a cost baseline to measure payments. | D-) At a given moment, PMB provides the physical work that should have been accomplished. | Answer: B | Total Earned Value is not a performance measurement baseline. The variables that help measure the performance on the project are Planned Value, Earned Value and Actual Cost. Planned Value (PV) is the authorized budget assigned to scheduled work. It is the authorized budget planned for the work to be accomplished for an activity or work breakdown structure component, not including management reserve. This budget is allocated by phase over the life of the project, but at a given moment, planned value defines the physical work that should have been accomplished. The total of the PV is sometimes referred to as the performance measurement baseline (PMB). The total planned value for the project is also known as the budget at completion (BAC). Total Earned Value is not a performance measurement baseline. The variables that help measure the performance on the project are Planned Value, Earned Value and Actual Cost. Planned Value (PV) is the authorized budget assigned to scheduled work. It is the authorized budget planned for the work to be accomplished for an activity or work breakdown structure component, not including management reserve. This budget is allocated by phase over the life of the project, but at a given moment, planned value defines the physical work that should have been accomplished. The total of the PV is sometimes referred to as the performance measurement baseline (PMB). The total planned value for the project is also known as the budget at completion (BAC). Answer: B Answer: B
Exam 1 | #2. .Your colleague, Lara, is a project manager for a construction project. While you were talking to her, she said that her project’s CPI is 0.82 and SPI is 1.21. What could have happened in Lara’s project? |  | A-) The most experienced architect resigned, which had not been anticipated earlier. | B-) Cost of labor increased due to annual salary increase | C-) The project was behind schedule; Lara increased the number of team members to compress the schedule and decrease the activities duration. | D-) The project was ahead of schedule; Lara released some team members to decrease the budget. | Answer: C | Answer C is correct. The project is ahead of schedule (SPI>1) and above budget (CPI<1). Crashing is a technique used to shorten the schedule duration for the least incremental cost by adding resources. Examples of crashing include approving overtime, bringing additional resources, or paying to activities on the critical path. Answer C is correct. The project is ahead of schedule (SPI>1) and above budget (CPI<1). Crashing is a technique used to shorten the schedule duration for the least incremental cost by adding resources. Examples of crashing include approving overtime, bringing additional resources, or paying to activities on the critical path. We don’t have any indication in the scenario that the lead architect resigned, and the project performance indicates that there are no schedule delays (Answer A). On the contrary, SPI is 1.21 which means that the project is 21% ahead of schedule. The increase of salaries will not put the project over budget, and the annual increases are usually planned in the budget (Answer B). If Lara released team members, then the schedule would have suffered, so Answer D is not correct either. We don’t have any indication in the scenario that the lead architect resigned, and the project performance indicates that there are no schedule delays (Answer A). On the contrary, SPI is 1.21 which means that the project is 21% ahead of schedule. The increase of salaries will not put the project over budget, and the annual increases are usually planned in the budget (Answer B). If Lara released team members, then the schedule would have suffered, so Answer D is not correct either. Answer: C Answer: C
Exam 1 | #3. .You worked on planning the activities of your project and attached is the activity diagram of your project. All units in the diagram are in weeks. Your management asks whether the project can be completed in 12 weeks. What is the project float? | images/image0.jpg | A-) -4 | B-) 1 | C-) 0 | D-) The provided information is not sufficient to calculate float. | Answer: A | All possible paths to complete the project are as below: All possible paths to complete the project are as below: Start -> Task1 -> Task2 -> Task4-> End: 10 weeks Start -> Task3 -> Task5 -> Task7-> End: 15 weeks Start -> Task6 -> Task7 -> End: 15 weeks Start -> Task1 -> Task2 -> Task3 -> Task5 -> Task7 -> End: 16 weeks Start -> Task1 -> Task2 -> Task4-> End: 10 weeks Start -> Task1 -> Task2 -> Task4-> End: 10 weeks Start -> Task3 -> Task5 -> Task7-> End: 15 weeks Start -> Task3 -> Task5 -> Task7-> End: 15 weeks Start -> Task6 -> Task7 -> End: 15 weeks Start -> Task6 -> Task7 -> End: 15 weeks Start -> Task1 -> Task2 -> Task3 -> Task5 -> Task7 -> End: 16 weeks Start -> Task1 -> Task2 -> Task3 -> Task5 -> Task7 -> End: 16 weeks The critical path is 16 weeks. The critical path is 16 weeks. Project float will be -4 weeks in order to complete the project in 12 weeks (12 – 16). Project float will be -4 weeks in order to complete the project in 12 weeks (12 – 16). If a project has a negative float, in order to complete the project on time, the project manager can fast-track or crash the project schedule. If a project has a negative float, in order to complete the project on time, the project manager can fast-track or crash the project schedule. Answer: A Answer: A
Exam 1 | #4. .The business representative for your lean team hasn't been available for a few weeks due to a crisis in a foreign subsidiary. Fortunately, the team has a good sense of the backlog priorities and has been able to continue making progress in her absence. However, there are now two work packages that haven't been approved yet-and at the end of this week, there will be three. The team can keep going for a while, but the longer they have to wait for feedback and approval the more likely it is that they will get off track. What is this an example of? |  | A-) Iterative development | B-) Waste | C-) Pull system | D-) Task switching | Answer: B | In the lean approach, waiting (for reviews, approvals, etc.) is considered to be a form of waste. The other options aren’t supported by the information given in the scenario–for example, we can’t tell whether this team is using a pull system or iterative development. Also, although the business representative has switched to another focus, that isn’t the main point being illustrated here. In the lean approach, waiting (for reviews, approvals, etc.) is considered to be a form of waste. The other options aren’t supported by the information given in the scenario–for example, we can’t tell whether this team is using a pull system or iterative development. Also, although the business representative has switched to another focus, that isn’t the main point being illustrated here. Answer: B Answer: B
Exam 1 | #5. .A plastic waste recycling project has been accomplished and helped the company to reduce the costs. The cost-saving was accomplished by adding a new step to the recycling process. The new step was implemented after a change request was submitted and approved during the project. This new step was implemented as a/an: |  | A-) Value-adding change | B-) Gold plating for satisfying the customer | C-) Risk response | D-) Contingency or workaround plan | Answer: A | Change requests are implemented usually to add value to the project deliverables. Change requests are implemented usually to add value to the project deliverables. Answer: A Answer: A
Exam 1 | #6. .A company is losing market share to competitors with new business models. The scrum team is asked to limit the number of features of a product and release a version more quickly to the market. In what way will this request impact the planning? |  | A-) The backlog will be prioritized to deliver basic functionality in small increments. | B-) The product vision will be updated to reflect a user-driven release roadmap. | C-) The sprint backlog will be reprioritized to work on the smallest and simplest stories first. | D-) The increments will be reduced to enable faster product releases. | Answer: A | Releasing a more basic version of a product early enables the company to obtain value from the work more quickly. Regarding planning, the team needs to figure out how to prioritize the backlog so that a product with basic functionality, that will still bring value to the customer, can enter the market. Releasing a more basic version of a product early enables the company to obtain value from the work more quickly. Regarding planning, the team needs to figure out how to prioritize the backlog so that a product with basic functionality, that will still bring value to the customer, can enter the market. Answer: A Answer: A
Exam 1 | #7. .Before you join the execution team on the project site, a senior manager from the PMO is showing you some charts. One of them shows the details regarding the existing departments of the performing organization that you have joined. This chart also shows details about different units and teams working on the project. Which of the following is it? |  | A-) Risk Breakdown Structure | B-) Organizational Breakdown Structure | C-) Work Breakdown Structure | D-) Schedule Breakdown Structure | Answer: B | An OBS is arranged according to an organization’s existing departments, units, or teams, with the project activities or work packages listed under each department. An OBS is arranged according to an organization’s existing departments, units, or teams, with the project activities or work packages listed under each department. Answer: B Answer: B
Exam 1 | #8. .A cross-functional team on Project STORM reports a delay in developing a prototype. The project manager believes that the cause is lack of knowledge in a specific, required skill on the team. In which three ways can the project manager prevent this situation on future projects? (Choose THREE.) |  | A-) Ask the team leader to recommend a solution. | B-) Identify required skills and organize the team based on the strength of those skills. | C-) Make a list of required specific skills for the project. | D-) Outsource the task to a skilled expert. | Answer: B, C, D | Developing the team and proactively strengthening individual team members’ skills is an important part of servant leadership. This means that the project manager needs to know the required strengths and skill sets needed for a project and recruit or be able to outsource the work to a resource with that skill. Developing the team and proactively strengthening individual team members’ skills is an important part of servant leadership. This means that the project manager needs to know the required strengths and skill sets needed for a project and recruit or be able to outsource the work to a resource with that skill. Answer: B, C, D Answer: B, C, D
Exam 1 | #9. .You are managing a software project. Because of the nature of software development, the development activities cannot start before the software design ends. This is an example of: |  | A-) Discretionary Dependency | B-) External Dependency | C-) Internal Dependency | D-) Mandatory Dependency | Answer: D | Mandatory dependencies are those that are legally or contractually required or inherent in the nature of the work. Mandatory dependencies are those that are legally or contractually required or inherent in the nature of the work. Since the development of modules cannot start before the design of modules, this is a mandatory dependency that is inherent in the nature of the work. Since the development of modules cannot start before the design of modules, this is a mandatory dependency that is inherent in the nature of the work. Answer: D Answer: D
Exam 1 | #10. .There are several methods to evaluate the return of investment in the projects in organizations. Your Company uses the “payback period” for project selection criteria. The payback period is the: |  | A-) Number of years a company spends to make a predefined profit | B-) Time required to regain the funds that are expended in an investment | C-) Duration of the project | D-) Total value of the project in terms of today’s value | Answer: B | The payback period refers to the period of time required to recover the funds expended in an investment or to reach the break-even point. The payback period refers to the period of time required to recover the funds expended in an investment or to reach the break-even point. Answer: B Answer: B
Exam 1 | #11. .You are trying to establish a cost performance baseline for your project while you are in the process of Determining Budget. You can use the following tools and techniques EXCEPT: |  | A-) Cost aggregation | B-) Bottom-up estimating | C-) Expert judgment | D-) Historical relationships | Answer: B | Tools and techniques used to Determine Budget Process are: Tools and techniques used to Determine Budget Process are: Cost aggregation Reserve analysis Expert judgment Historical relationships Funding limit reconciliation Cost aggregation Cost aggregation Reserve analysis Reserve analysis Expert judgment Expert judgment Historical relationships Historical relationships Funding limit reconciliation Funding limit reconciliation Bottom-up estimating is used in the Estimate Costs Process. Bottom-up estimating is used in the Estimate Costs Process. Answer: B Answer: B
Exam 1 | #12. .You are managing a project under the Cost Plus Fixed Fee Contract (CPFF). Following is the data of your project: Cost of Employee Salaries: $200,000 Cost of Leasing Machines: $50,000 Cost of Other Items: $50,000 Fixed-Fee Ratio: 20% What should be the final price of the contract? |  | A-) $160,000 | B-) $240,000 | C-) $300,000 | D-) $360,000 | Answer: D | In Cost Plus Fixed Fee Contracts (CPFF), the seller is reimbursed for all allowable costs for performing the contract work and receives a fixed-fee payment calculated as a percentage of the initial estimated project costs. A fee is paid only for completed work and does not change due to seller performance. Fee amounts do not change unless the project scope changes. In Cost Plus Fixed Fee Contracts (CPFF), the seller is reimbursed for all allowable costs for performing the contract work and receives a fixed-fee payment calculated as a percentage of the initial estimated project costs. A fee is paid only for completed work and does not change due to seller performance. Fee amounts do not change unless the project scope changes. Sum of all costs = Total Cost = $200,000 $50,000 $50,000 = $300,000 Sum of all costs = Total Cost = $200,000 $50,000 $50,000 = $300,000 Fixed-Fee = Total Cost x Fixed-Fee Ratio = $300,000 x 20% = $60,000 Fixed-Fee = Total Cost x Fixed-Fee Ratio = $300,000 x 20% = $60,000 Final Price = Total Cost Fixed-Fee = $300,000 $60,000 = $360,000 Final Price = Total Cost Fixed-Fee = $300,000 $60,000 = $360,000 Answer: D Answer: D
Exam 1 | #13. .Betty is working as a project manager for Banking company Integrity. The speed at which customers demand value is increasingly high. Todd, the bank CEO has determined that a new dynamic approach needs to be assessed when developing new applications to meet customer needs. In this scenario, Betty would recommend agile practices because: |  | A-) Project leaders and teams need to be able to adapt to advances in technology and meet the demands from customers for more immediate delivery of value. | B-) Project leaders and teams are concerned about delivering value at each sprint but improvising and adapting, not following a methodology. | C-) Project leaders and teams do not need to plan to deliver tangible increments. | D-) Project leaders and teams can make changes as long as they deliver working software. | Answer: A | Agile techniques and approaches enable organizations to deliver disruptive technologies quickly while providing value to customers faster. Agile techniques and approaches enable organizations to deliver disruptive technologies quickly while providing value to customers faster. Answer: A Answer: A
Exam 1 | #90. .In your project, you are trying to determine the cause and degree of difference between the baseline and actual performance. Which of the following techniques should you use? |  | A-) Reserve analysis | B-) Trend analysis | C-) Root cause analysis | D-) Variance analysis | Answer: D | Variance analysis is a technique for determining the cause and degree of difference between the baseline and actual performance. Variance analysis is a technique for determining the cause and degree of difference between the baseline and actual performance. Answer: D
Exam 1 | #15. .You are an expert developer in an organization that focuses on Agile frameworks to deliver products. The Product Owner asks your opinion to use Crystal as a framework to deliver a new product that is not well-defined yet by the client. You should like OR dislike the suggestions because: |  | A-) Crystal is based on individuals and interaction so it will be a good approach to deliver something that is not well defined. | B-) Crystal is weak so it may lead to scope creep due to lack of pre-defined tools and plans. | C-) Crystal is adaptive therefore the team may respond well to changing requirements by the client. | D-) Crystal lacks proper structure but the experienced team will overcome this issue since the product is new. | Answer: B | From all the selections above, (b) makes the best answer in this situation because the assumption is the product is new and the client is unsure about the final set of features, therefore the potential for scope creep is very high; as Crystal is not a structured framework, the potential for scope creep is even greater. From all the selections above, (b) makes the best answer in this situation because the assumption is the product is new and the client is unsure about the final set of features, therefore the potential for scope creep is very high; as Crystal is not a structured framework, the potential for scope creep is even greater. Answer: B Answer: B
Exam 1 | #16. .An organization adopts the Kanban approach and implements an incremental delivery strategy. What metrics should the team use to measure performance? |  | A-) Burndown charts, control charts, and lag time | B-) Burndown charts, lead time, cycle time, and throughput | C-) S-curve, burndown charts, and lag time | D-) Burnup charts, control charts, and lag time | Answer: B | Burnups, Burndowns (capacity measures) and lead time, and cycle time (predictability measures) are useful for “in-the-moment” measurements. They help the team to understand how much work they have and whether they can finish on-time. Project metrics ensuring the project had a measure of delivery performance was essential to ensure the project outcomes could be achieved. Metrics were put in place to measure tasks achieved, schedule, and cost. Be mindful to identify ways to show work effort visually (i.e. Velocity charts, burndown charts, and burnup charts are just a few to illustrate performance metrics quickly and easily). Burnups, Burndowns (capacity measures) and lead time, and cycle time (predictability measures) are useful for “in-the-moment” measurements. They help the team to understand how much work they have and whether they can finish on-time. Project metrics ensuring the project had a measure of delivery performance was essential to ensure the project outcomes could be achieved. Metrics were put in place to measure tasks achieved, schedule, and cost. Be mindful to identify ways to show work effort visually (i.e. Velocity charts, burndown charts, and burnup charts are just a few to illustrate performance metrics quickly and easily). Answer: B Answer: B
Exam 1 | #17. .Your Company is trying to buy an issue tracking system from one of the software companies. Based on your cost estimations, an issue tracking system should be $ 150.000. You asked for bids and the minimum price quoted for the software was $250.000. The reason for this estimation variance might be all of the following EXCEPT: |  | A-) There have not been major changes in the cost of software development labor since last year. | B-) The procurement statement of work was ambiguous. | C-) The prospective sellers misunderstood the procurement statement of work. | D-) The procurement statement of work was not covering all information about the requirements. | Answer: A | Significant differences in cost estimates can be an indication that the procurement statement of work was deficient, ambiguous, and/or the prospective sellers either misunderstood or failed to respond fully to the procurement statement of work. These are all reasons why the proposal was above the expected cost. Significant differences in cost estimates can be an indication that the procurement statement of work was deficient, ambiguous, and/or the prospective sellers either misunderstood or failed to respond fully to the procurement statement of work. These are all reasons why the proposal was above the expected cost. Answer: A Answer: A
Exam 1 | #18. .As a project manager, you monitor your team’s performance every minute because your team consists of people avoiding responsibility and work. You believe in: |  | A-) Theory Y (McGregor Model) | B-) Theory X (McGregor Model) | C-) Herzberg’s Theory | D-) Referent Power | Answer: B | McGregor’s theory of X and Y proposes that all workers fit either in Theory X: This assumes that the workers are inherently lazy and require supervision, or Theory Y: The average worker finds physical and mental effort on the job satisfying and likes his work. McGregor’s theory of X and Y proposes that all workers fit either in Theory X: This assumes that the workers are inherently lazy and require supervision, or Theory Y: The average worker finds physical and mental effort on the job satisfying and likes his work. Answer: B Answer: B
Exam 1 | #19. .You are creating a project schedule for your website development project. Your first milestone is “Delivery of Visual Designs Screen”. What should be the duration of this milestone? |  | A-) Total time spent for development of all screens’ visual designs | B-) Time spent on the development of the last screen’s visual design | C-) The developers who designed screens should determine the milestone duration | D-) Zero | Answer: D | Milestone is a significant point or event in the project. Milestones have a “zero” duration. Milestone is a significant point or event in the project. Milestones have a “zero” duration. Answer: D Answer: D
Exam 1 | #20. .You have documented all possible risks with appropriate risk responses in your risk management plan. All other remaining risks are called: |  | A-) Risk Triggers | B-) Unmanageable Risks | C-) Residual Risks | D-) Accepted Risks | Answer: C | Residual risks are expected to remain after planned responses have been implemented, as well as those that have been deliberately accepted. Residual risks are expected to remain after planned responses have been implemented, as well as those that have been deliberately accepted. Answer: C Answer: C
Exam 1 | #21. .While preparing the schedule for the project activities of a software project, you decided to use project parameters of a similar project completed in the past. You are creating statistical relationships between the number of codes of a screen and its total development duration. Which of the following estimating tools do you use? |  | A-) Expert judgment | B-) Three-point Estimating | C-) Parametric estimating | D-) Analogous estimating | Answer: C | Parametric estimating is an estimation technique where we use an algorithm to calculate cost or duration based on historical data and project parameters. Parametric estimating uses a statistical relationship between historical data and other variables (e.g., square footage in construction) to calculate an estimate for activity parameters, such as cost, budget, and duration. Parametric estimating is an estimation technique where we use an algorithm to calculate cost or duration based on historical data and project parameters. Parametric estimating uses a statistical relationship between historical data and other variables (e.g., square footage in construction) to calculate an estimate for activity parameters, such as cost, budget, and duration. Answer: C Answer: C
Exam 1 | #22. .You have been managing a subway line construction project which will have five stations. You have divided the project into five phases, one station for each phase, to ensure better control. Which of the following is a characteristic of a project phase? |  | A-) A project phase should not be divided into sub-phases even in complex projects, because it will be difficult to manage. | B-) All deliverables in the project phase should correspond to the project management process. | C-) Formal phase completion necessarily includes an authorization for the subsequent phase. | D-) Each project phase has a distinct focus that differs from any other phase. | Answer: D | Regardless of the number of phases in a project, all phases have similar characteristics: Regardless of the number of phases in a project, all phases have similar characteristics: The work has a distinct focus that differs from any other phase. This often involves different organizations, locations, and skill sets. The work has a distinct focus that differs from any other phase. This often involves different organizations, locations, and skill sets. The work has a distinct focus that differs from any other phase. This often involves different organizations, locations, and skill sets. Answer: D Answer: D
Exam 1 | #23. .You are managing a project which has a tight deadline, and your deliverables should be ready within 3 months. The procurement process will take time thus you decide to sign a contract with a supplier that your company has worked with before. You accept the following risk: |  | A-) Possibility of scope creep | B-) The capability of the supplier in delivering the required material | C-) Collusion between the supplier and your company | D-) Not having a legal contract | Answer: B | Even if the supplier had a contract with your company in the past, there is a risk that they might not be the suitable company to deliver the materials for your current project. Even if the supplier had a contract with your company in the past, there is a risk that they might not be the suitable company to deliver the materials for your current project. Answer: B Answer: B
Exam 1 | #24. .Your Company has awarded a contract to a vendor. After some time, you realized that the vendor representative is your old buddy from school. You inform your senior management about this situation. However, they insist that you will continue to administer the contract. So, to avoid any issues in this conflict of interest situation, you should _______ . |  | A-) Refrain from administering the contract. | B-) Resign from the project. | C-) Document all the decisions taken by you on the activities performed by the vendor. | D-) Remind your senior management of the conflict of interest. | Answer: C | In case of conflict of interest situations, the project manager should inform senior management, and distance oneself from the conflict of interest situation, if possible. However, in this context, as the senior management insists and the project manager has to continue in the current position, appropriate documentation can help in preventing any accusation of bias in conflict of interest situations. In case of conflict of interest situations, the project manager should inform senior management, and distance oneself from the conflict of interest situation, if possible. However, in this context, as the senior management insists and the project manager has to continue in the current position, appropriate documentation can help in preventing any accusation of bias in conflict of interest situations. Options A and D are not relevant – you had already mentioned the conflict of interest situation to the senior management and got approval to continue with the project. Options A and D are not relevant – you had already mentioned the conflict of interest situation to the senior management and got approval to continue with the project. Option B is an extreme step that is not relevant to this situation. Option B is an extreme step that is not relevant to this situation. Answer: C Answer: C
Exam 1 | #25. .Donald, an Agile Project Manager, is working with an agile team that has recently finished coding for the current iteration (Sprint). Which of the following is a continuous process improvement ceremony that the team will attend? |  | A-) Sprint Review Meeting | B-) Sprint Retrospective Meeting | C-) Backlog Grooming Meeting | D-) Release Planning Meeting | Answer: B | The iteration (Sprint) Retrospective meeting is a continuous process improvement ceremony allowing the team to identify what went well during the previous iteration (Sprint) and what processes can be improved for the next iteration (Sprint). The iteration (Sprint) Retrospective meeting is a continuous process improvement ceremony allowing the team to identify what went well during the previous iteration (Sprint) and what processes can be improved for the next iteration (Sprint). Answer: B Answer: B
Exam 1 | #26. .As a project manager, when you are monitoring and controlling your project, you must prevent scope creep. Which of the following statements define scope creep? |  | A-) Defects that customer found | B-) Accepted change requests | C-) Uncontrolled expansion to the scope | D-) Controlled change requests | Answer: C | The uncontrolled expansion to product or project scope without adjustments to time, cost, and resources is referred to as scope creep. The uncontrolled expansion to product or project scope without adjustments to time, cost, and resources is referred to as scope creep. Answer: C Answer: C
Exam 1 | #27. .Kevin is new to the Agile methodology. He is trying hard to learn about all the principles, terminology, and processes to be successful in applying all that in the projects that he is working on. He knows that he needs to follow the Agile Manifesto principles. Which of the following is an Agile Manifesto principle? |  | A-) Welcome changing requirements, early in development. Agile processes handle changes for the customer's competitive advantage | B-) Welcome changing priorities, early in development. Agile processes harness change for the customer's competitive advantage | C-) Welcome changing priorities, even late in development. Agile processes handle changes for the customer's competitive advantage | D-) Welcome changing requirements, even late in development. Agile processes harness change for the customer's competitive advantage | Answer: D | The correct wording of the principle is “Welcome changing requirements, even late in development. Agile processes harness change for the customer’s competitive advantage.” The agile principles do not speak to changing priorities or to welcoming only early changes. The correct wording of the principle is “Welcome changing requirements, even late in development. Agile processes harness change for the customer’s competitive advantage.” The agile principles do not speak to changing priorities or to welcoming only early changes. Answer: D Answer: D
Exam 1 | #28. .In your project, you are in the process of obtaining seller responses, selecting a seller, and awarding a contract. You can use all of the following tools and techniques in this process EXCEPT: |  | A-) Bidder conference | B-) Expert judgment | C-) Advertising | D-) Make-or-buy analysis | Answer: D | Conduct Procurements is the process of obtaining seller responses, selecting a seller, and awarding a contract. The following figure shows inputs, tools & techniques and outputs of the Conduct Procurements process. Conduct Procurements is the process of obtaining seller responses, selecting a seller, and awarding a contract. The following figure shows inputs, tools & techniques and outputs of the Conduct Procurements process. Answer: D Answer: D | images/image1.jpg
Exam 1 | #29. .You are in the process of Identifying Risks and at this time you determine and document the risks and their characteristics. Who should participate in this process? |  | A-) Project Manager and Relevant managers from customer | B-) Project Manager, project team members, subject matter experts, and customer | C-) Project Manager and senior team members | D-) All relevant stakeholders | Answer: D | Participants in risk identification activities may include the following: project manager, project team members, risk management team (if assigned), customers, subject matter experts from outside the project team, end-users, other project managers, stakeholders, and risk management experts. While these people are often key participants for risk identification, all project personnel should be encouraged to identify potential risks. Participants in risk identification activities may include the following: project manager, project team members, risk management team (if assigned), customers, subject matter experts from outside the project team, end-users, other project managers, stakeholders, and risk management experts. While these people are often key participants for risk identification, all project personnel should be encouraged to identify potential risks. Answer: D Answer: D
Exam 1 | #30. .You are expected to manage stakeholders’ expectations as a project manager. All of the following are interpersonal skills that you should apply EXCEPT: |  | A-) Building trust | B-) Resolving conflict | C-) Risk-taking | D-) Active listening | Answer: C | The project manager applies interpersonal skills to manage stakeholders’ expectations. For example: The project manager applies interpersonal skills to manage stakeholders’ expectations. For example: Building trust Resolving conflict Active listening Overcoming resistance to change Building trust Building trust Resolving conflict Resolving conflict Active listening Active listening Overcoming resistance to change Overcoming resistance to change Answer: C Answer: C
Exam 1 | #31. .Your Company uses the Internal Rate of Return (IRR) as a project selection criteria. The following are the possible projects for your organization including duration and IRR rates. In this context, the best project for the company is: |  | A-) Project Duration: 9 months, IRR = 22% | B-) Project Duration: 5 months, IRR = 17% | C-) Project Duration: 7 months, IRR = 13% | D-) Project Duration:12 months, IRR = 9% | Answer: A | Calculation of the IRR is complex but IRR with higher values are more profitable. Calculation of the IRR is complex but IRR with higher values are more profitable. Answer: A Answer: A
Exam 1 | #32. .You are in the closing phase of your project . Which of the following should you do LAST? |  | A-) Final product, service, or result transition | B-) Releasing project resources | C-) Organizational process assets updates | D-) Accepting deliverables | Answer: B | Close Project or Phase is the process of finalizing all activities across all of the Project Management Process Groups to formally complete the project or phase. The following figure shows inputs, tools & techniques, and outputs of this process. Close Project or Phase is the process of finalizing all activities across all of the Project Management Process Groups to formally complete the project or phase. The following figure shows inputs, tools & techniques, and outputs of this process. Although it is a project or phase closure, there you will still need resources to perform some final activities. The resources should be released at the last step. Although it is a project or phase closure, there you will still need resources to perform some final activities. The resources should be released at the last step. Answer: B Answer: B
Exam 1 | #33. .In your project, you used the power/interest grid classification model for your stakeholder analysis. Amanda is the Operations Director at your customer’s. She has a high level of authority but shows low interest in your project as a stakeholder. So, Amanda should be: |  | A-) Monitored | B-) Keep Informed | C-) Keep satisfied | D-) Managed Closely | Answer: C | Power/interest grid, grouping the stakeholders based on their level of authority (“power”) and their level of concern (“interest”) regarding the project outcomes. Power/interest grid, grouping the stakeholders based on their level of authority (“power”) and their level of concern (“interest”) regarding the project outcomes. Answer: C Answer: C | images/image2.jpg
Exam 1 | #34. .Change Consulting Inc. has been contracted to work with an IT team to change from planned-driven to agile-driven project management. The IT Team is half-way through their first project. While planning the next product increment, the team needs to determine the best approach. The BEST next step for them would be: |  | A-) A team meeting facilitated by you. | B-) A benchmarking study of the issue. | C-) Obtaining prototypes of the options. | D-) A team vote and usage of the winning approach. | Answer: D | A team meeting could be helpful, but the better answer is to have the team vote. This allows for the team to move forward with their work. The benchmarking study and prototypes will not help the team in this situation. A team meeting could be helpful, but the better answer is to have the team vote. This allows for the team to move forward with their work. The benchmarking study and prototypes will not help the team in this situation. Answer: D Answer: D
Exam 1 | #35. .You have been assigned as the project manager of a new project. You started to work with your customer to define the project work. Your customer doesn’t have a precise statement of work that needs to be done. However, you recognize that you need to increase the number of team members to deliver the project work on time. In this context, which of the following is the best contract type? |  | A-) Cost Plus Incentive Fee Contract | B-) Cost-reimbursable Contract | C-) Fixed-Price Contract | D-) Time and Material Contract | Answer: D | Time and material contracts are a hybrid type of contractual arrangement that contains aspects of both cost-reimbursable and fixed-price contracts. They are often used for staff augmentation, acquisition of experts, and any outside support when a precise statement of work cannot be quickly prescribed. Time and material contracts are a hybrid type of contractual arrangement that contains aspects of both cost-reimbursable and fixed-price contracts. They are often used for staff augmentation, acquisition of experts, and any outside support when a precise statement of work cannot be quickly prescribed. Answer: D Answer: D
Exam 1 | #36. .You are a project manager in the PerfectPro company, which has a balanced matrix organizational structure. In this context, all of the following are true, EXCEPT: |  | A-) You have a low to moderate level of authority. | B-) You work full-time on a project. | C-) Project resources availability is low to moderate. | D-) You manage the project budget by yourself. | Answer: D | The project budget is managed by the functional manager and the project manager together in a balanced matrix organizational structure. The project budget is managed by the functional manager and the project manager together in a balanced matrix organizational structure. Answer: D Answer: D | images/image3.jpg
Exam 1 | #37. .You are managing a software project and you have reached the end of the analysis phase. The next phase of your project is the software development phase. Which of the following should you do FIRST? |  | A-) Inform the project stakeholders about completion of the analysis phase | B-) Start the software development phase | C-) Define the scope that needs to be delivered in the next phase | D-) Review the outcomes of the analysis phase and check whether there is any additional work that was not included in the initial scope | Answer: A | The closure of a phase ends with some form of transfer or hand-off of the work product produced as the phase deliverable. This phase end represents a natural point to reassess the activities underway and to change or terminate the project if necessary. This point may be referred to as a stage-gate, milestone, phase review, phase gate, or kill point. The closure of a phase ends with some form of transfer or hand-off of the work product produced as the phase deliverable. This phase end represents a natural point to reassess the activities underway and to change or terminate the project if necessary. This point may be referred to as a stage-gate, milestone, phase review, phase gate, or kill point. Answer: A Answer: A
Exam 1 | #38. .You have the approved version of the scope baseline in your project management plan. All of the following are components of the scope baseline EXCEPT: |  | A-) Statement of work | B-) Scope statement | C-) WBS | D-) WBS Dictionary | Answer: A | The scope baseline is the approved version of a scope statement, work breakdown structure (WBS), and its associated WBS dictionary, which can be changed only through formal change control procedures and is used as a basis for comparison. It is a component of the project management plan. Components of the scope baseline include: The scope baseline is the approved version of a scope statement, work breakdown structure (WBS), and its associated WBS dictionary, which can be changed only through formal change control procedures and is used as a basis for comparison. It is a component of the project management plan. Components of the scope baseline include: Project scope statement WBS WBS Dictionary Project scope statement Project scope statement WBS WBS WBS Dictionary WBS Dictionary Answer: A Answer: A
Exam 1 | #39. .All of the following are constraints in the Estimate Activity Durations process EXCEPT: |  | A-) Available skilled resources | B-) Contract terms | C-) Contract requirements | D-) Availability of information | Answer: D | The assumptions and constraints from the project scope statement are considered when estimating activity durations. Examples of constraints include, but are not limited to: The assumptions and constraints from the project scope statement are considered when estimating activity durations. Examples of constraints include, but are not limited to: Available skilled resources, and Contract terms and requirements Available skilled resources, and Available skilled resources, and Contract terms and requirements Contract terms and requirements Answer: D Answer: D
Exam 1 | #40. .You are trying to figure out the ways that you can motivate your team members in a construction project. The HR manager of the company tells you that the employees are motivated by economic security, team spirit, and the need to belong in a group. Which of the following theories is the HR manager referring to? |  | A-) Theory Y | B-) Maslow’s Theory | C-) Herzberg’s Theory | D-) Hygiene Factors | Answer: B | Abraham Maslow’s hierarchy of needs states that people are at different levels in the need hierarchy. Usually, people start out looking for physiological needs and then progressively move up the needs hierarchy. Abraham Maslow’s hierarchy of needs states that people are at different levels in the need hierarchy. Usually, people start out looking for physiological needs and then progressively move up the needs hierarchy. Answer: B Answer: B | images/image4.jpg
Exam 1 | #41. .You have been assigned to a new project recently. You started to determine, document, and manage stakeholder needs and requirements to meet project objectives. You are in _______ process. |  | A-) Project Scope Statement | B-) Stakeholder Register | C-) Define Scope | D-) Collect Requirements | Answer: D | Collect Requirements is the process of determining, documenting, and managing stakeholder needs and expectations to meet project objectives. Collect Requirements is the process of determining, documenting, and managing stakeholder needs and expectations to meet project objectives. Answer: D Answer: D
Exam 1 | #42. .You are performing the Identify Stakeholders Process of your project. All of the following are Enterprise Environmental Factors that can influence the process of Identify Stakeholders EXCEPT: |  | A-) Stakeholder register templates | B-) Organizational culture and structure | C-) Governmental or industry standards | D-) Global, regional or local trends, and practices or habits. | Answer: A | The enterprise environmental factors that can influence the Identify Stakeholders process include, but are not limited to: The enterprise environmental factors that can influence the Identify Stakeholders process include, but are not limited to: Organizational culture and structure; Governmental or industry standards (e.g., regulations, product standards); and Global, regional or local trends, and practices or habits Organizational culture and structure; Organizational culture and structure; Governmental or industry standards (e.g., regulations, product standards); and Governmental or industry standards (e.g., regulations, product standards); and Global, regional or local trends, and practices or habits Global, regional or local trends, and practices or habits Stakeholder register templates are part of Organizational Process Assets that can influence the Identify Stakeholders Process. Stakeholder register templates are part of Organizational Process Assets that can influence the Identify Stakeholders Process. Answer: A Answer: A
Exam 1 | #43. .Roger, who is the scrum master for a healthcare informatics company, has been working for months to develop a COVID19 tracing app. The first two releases were successful. Nonetheless, in the current sprint, many things didn’t go as planned. The team is currently busy with the upcoming release that consists of a large number of highly sophisticated product backlog items, and every team member is worried about this next release due to the surging number of virus cases across the country and the pressure put by the product owner. Considering Roger’s role in the project, what do you think is the best course of action? |  | A-) Make sure the third release is delayed until the end of the project so the team can have time to mitigate current sprint pitfalls | B-) Hold the current sprint retrospective as planned, identify what went well in the sprint, concerning interactions as processes, tools, etc. Discuss and discover opportunities for improvement, and put an action plan for implementing these improvements | C-) Focus on the next release only, cancel the current sprint retrospective to avail additional time for the team to get the third release successful. It makes no sense to question what didn’t go well when we all know it | D-) Merge the current sprint retrospective with the next sprint retrospective, and make sure every team member has the opportunity to answer the following three questions; What do you think went well? What would you like to change? How should we implement that change? | Answer: B | Sprint retrospectives enable the scrum team to make informed decisions at the end of every sprint to enhance product quality, increase development team performance, and refine project processes. The retrospective shouldn’t be canceled or delayed or merged with any other event whatever the release challenges are. Sprint retrospectives enable the scrum team to make informed decisions at the end of every sprint to enhance product quality, increase development team performance, and refine project processes. The retrospective shouldn’t be canceled or delayed or merged with any other event whatever the release challenges are. Answer: B Answer: B
Exam 1 | #44. .You are managing a project which is behind schedule. Which of the following is the best action in this circumstance? |  | A-) Postpone the delivery dates of deliverables and report this to the customer | B-) Decrease scope to meet schedule | C-) Fast track or crash the project, and report the impact of this action on management | D-) Plan overtime for resources to meet the deadline | Answer: C | Schedule compression techniques are used to shorten the schedule duration without reducing the project scope, in order to meet schedule constraints, imposed dates, or other schedule objectives. Schedule compression techniques include, but are not limited to: Schedule compression techniques are used to shorten the schedule duration without reducing the project scope, in order to meet schedule constraints, imposed dates, or other schedule objectives. Schedule compression techniques include, but are not limited to: Crashing Fast-tracking Crashing Crashing Fast-tracking Fast-tracking Answer: C Answer: C
Exam 1 | #45. .Your Company is looking to hire a new project manager. Which of the following is the most important skill or asset of a project manager candidate? |  | A-) Expertise in the sector | B-) Active listener | C-) Sales skills | D-) Integration skills | Answer: D | In the project management context, integration includes characteristics of unification, consolidation, communication, and integrative actions that are crucial to controlled project execution through completion, successfully managing stakeholder expectations, and meeting requirements. Integration skills are the most important one among the options. In the project management context, integration includes characteristics of unification, consolidation, communication, and integrative actions that are crucial to controlled project execution through completion, successfully managing stakeholder expectations, and meeting requirements. Integration skills are the most important one among the options. Answer: D Answer: D
Exam 1 | #46. .You have completed many team development activities such as training and team building exercises to improve your team’s skills and cohesiveness in order to meet the project objectives. You want to check if these activities were efficient and assess the project team’s effectiveness. All of the following are the team’s effectiveness indicators EXCEPT: |  | A-) Improved skills of team members | B-) Delivery of the project deliverables before time | C-) Improved technical competencies of team members | D-) Reduced staff turnover rate | Answer: B | The evaluation of a team’s effectiveness may include indicators such as: The evaluation of a team’s effectiveness may include indicators such as: Improvements in skills that allow individuals to perform assignments more effectively Improvements in competencies that help the team perform better as a team Reduced staff turnover rate Increased team cohesiveness where team members share information and experiences openly and help each other to improve the overall project performance Improvements in skills that allow individuals to perform assignments more effectively Improvements in skills that allow individuals to perform assignments more effectively Improvements in competencies that help the team perform better as a team Improvements in competencies that help the team perform better as a team Reduced staff turnover rate Reduced staff turnover rate Increased team cohesiveness where team members share information and experiences openly and help each other to improve the overall project performance Increased team cohesiveness where team members share information and experiences openly and help each other to improve the overall project performance Answer: B Answer: B
Exam 1 | #47. .All the following statements related to “project management team” and “project team” are correct EXCEPT: |  | A-) The project team is responsible for activities like planning, executing, and closing. | B-) The project management team can be called a core, executive, or leadership team. | C-) The project management team is part of the project team as well. | D-) In a small project, project management responsibilities can be shared by the team members instead of a project manager. | Answer: D | The project management team is a subset of the project team and responsible for the project management and leadership activities such as initiating, planning, executing, monitoring, controlling, and closing various project phases. This group can also be referred to as the core, executive, or leadership team. Every project needs to have a Project Manager. The project management team is a subset of the project team and responsible for the project management and leadership activities such as initiating, planning, executing, monitoring, controlling, and closing various project phases. This group can also be referred to as the core, executive, or leadership team. Every project needs to have a Project Manager. Answer: D Answer: D
Exam 1 | #48. .You took over a project from a resigning project manager in your company. After talking with the team, you noticed that some features have been added to the deliverables although the customer did not request them. In this context: |  | A-) You are happy because the customer will be satisfied. | B-) You are concerned because the project team is gold-plating. | C-) You are worried because this will bring an extra cost to the project. | D-) You are worried because this will cause delays in the project. | Answer: B | Gold plating refers to continuing to work on a project or task well past the point where the extra effort is worth the value it adds (if any). After having met the requirements, the team member works on further enhancing the product, thinking the customer would be delighted to see additional or more polished features, rather than what was asked for or expected. Gold plating refers to continuing to work on a project or task well past the point where the extra effort is worth the value it adds (if any). After having met the requirements, the team member works on further enhancing the product, thinking the customer would be delighted to see additional or more polished features, rather than what was asked for or expected. Gold plating is not allowed in project management. Gold plating is not allowed in project management. Answer: B Answer: B
Exam 1 | #49. .While managing a project, the project manager can benefit from the knowledge of subject matter experts, consultants, and professional and technical associations. This is an example of: |  | A-) Expert judgment | B-) Organizational process assets | C-) Enterprise environmental factors | D-) Risk monitoring and control | Answer: A | Following is the explanation of Expert Judgment. Following is the explanation of Expert Judgment. Expert judgment: Additional expertise which is available from many sources, including: Expert judgment: Additional expertise which is available from many sources, including: Other units within the organization; Consultants and other subject matter experts (internal and external) Stakeholders, including customers, suppliers, or sponsors; and Professional and technical associations Other units within the organization; Other units within the organization; Consultants and other subject matter experts (internal and external) Consultants and other subject matter experts (internal and external) Stakeholders, including customers, suppliers, or sponsors; and Stakeholders, including customers, suppliers, or sponsors; and Professional and technical associations Professional and technical associations Answer: A Answer: A
Exam 1 | #50. .When referring to inputs for the Develop Schedule process, responsibility (e.g., who will perform the work), activity type (e.g., summary or detailed), and WBS classification belong to: |  | A-) Risks | B-) An account identifier | C-) Activity attributes | D-) Activity estimations | Answer: C | Activity attributes can be used to identify the person responsible for executing the work, geographic area, or place where the work has to be performed, and activity type such as level of effort (LOE), discrete effort, and apportioned effort (AE). Activity attributes are used for schedule development and for selecting, ordering, and sorting the planned schedule activities in various ways in reports. Activity attributes can be used to identify the person responsible for executing the work, geographic area, or place where the work has to be performed, and activity type such as level of effort (LOE), discrete effort, and apportioned effort (AE). Activity attributes are used for schedule development and for selecting, ordering, and sorting the planned schedule activities in various ways in reports. Answer: C Answer: C
Exam 1 | #51. .Denise is managing an agile project. The BEST tool to use to communicate to her stakeholders the plan for the project, including release dates and features included in each release, is a copy of the: |  | A-) Team’s Product Road Map | B-) Kanban board | C-) Product backlog | D-) Sprint Backlog | Answer: A | The Product Road Map is the only of the answers that includes features, release dates and the most comprehensive information about the project. The Product Road Map is the only of the answers that includes features, release dates and the most comprehensive information about the project. Answer: A Answer: A
Exam 1 | #52. .The following provides information on a particular task in your project: Early Start (ES): 15 days Late Start (LS): 22 days Early Finish (EF): 43 days Late Finish (LF): 50 days In this context, which of the following is TRUE? |  | A-) The task is on the critical path | B-) The task is not on the critical path | C-) The project float is 5 days. | D-) The project might get behind schedule. | Answer: B | A CPM critical path is normally characterized by zero float on the critical path. A CPM critical path is normally characterized by zero float on the critical path. LS – ES = LF – EF = 7 days. Since the task has 7 days of slack, it cannot be on the critical path. LS – ES = LF – EF = 7 days. Since the task has 7 days of slack, it cannot be on the critical path. Answer: B Answer: B
Exam 1 | #53. .A Product Owner is working on an Agile project that is progressing well. At the end of the second iteration, the project customer asked the Product Owner if the product will be finished within the planned six iterations. What should the Product Owner do next? |  | A-) Perform one-hour backlog refinement meetings midway through the upcoming iterations. | B-) Review the scrum backlog. | C-) Tell the customer the product will be finished on time. | D-) Review the burndown chart. | Answer: D | Review the burndown chart. A burndown chart shows the remaining time and work effort for the iteration, displaying the number of iterations on the horizontal axis and backlog items on the vertical items. At the end of each day, team members update their estimates of the remaining amount of work, which then updates the burndown chart. As the project progresses and iterations are completed, the amount of work will decrease. Review the burndown chart. A burndown chart shows the remaining time and work effort for the iteration, displaying the number of iterations on the horizontal axis and backlog items on the vertical items. At the end of each day, team members update their estimates of the remaining amount of work, which then updates the burndown chart. As the project progresses and iterations are completed, the amount of work will decrease. Answer: D Answer: D
Exam 1 | #54. .You are working in an automobile factory and your current project is an engine development project. Engine parts can be manufactured by either upgrading the current assembly lines or building a new assembly line. Your team calculates the opportunities, and threats of both options by taking the probability of the occurrence of the opportunities and threats into account. Depending on the output of this analysis, the project team will decide which is the best option to choose. Which of the following is the most appropriate for your purpose? |  | A-) Monte Carlo analysis | B-) Simulation | C-) Tornado Diagram | D-) Decision tree analysis | Answer: D | Expected monetary value (EMV) analysis is a statistical concept that calculates the average outcome when the future includes scenarios that may or may not happen (i.e., analysis under uncertainty). The EMV of opportunities is generally expressed as positive values, while those of treats are expressed as negative values. EMV requires a risk-neutral assumption – neither risk-averse or risk-seeking. EMV for a project is calculated by multiplying the value of each possible outcome by its probability of occurrence and adding the products together. A common use of this type of analysis is a decision tree analysis. Expected monetary value (EMV) analysis is a statistical concept that calculates the average outcome when the future includes scenarios that may or may not happen (i.e., analysis under uncertainty). The EMV of opportunities is generally expressed as positive values, while those of treats are expressed as negative values. EMV requires a risk-neutral assumption – neither risk-averse or risk-seeking. EMV for a project is calculated by multiplying the value of each possible outcome by its probability of occurrence and adding the products together. A common use of this type of analysis is a decision tree analysis. Answer: D Answer: D
Exam 1 | #55. .(1)__________________ is a structured, independent process to determine if project activities comply with organizational and project policies, processes, and procedures. And this is done during (2)________________ process. |  | A-) (1) Process Analysis, (2) Manage Quality | B-) (1) Process Analysis, (2) Control Quality | C-) (1) Quality Audit, (2) Manage Quality | D-) (1) Quality Audit, (2) Control Quality | Answer: C | A quality audit is a structured, independent process to determine if project activities comply with organizational and project policies, processes, and procedures. Quality audit is a tool & technique used in the Manage quality process. A quality audit is a structured, independent process to determine if project activities comply with organizational and project policies, processes, and procedures. Quality audit is a tool & technique used in the Manage quality process. Answer: C Answer: C
Exam 1 | #56. .Your project is in a bad shape and you need to identify how your department can take corrective actions to achieve the project quality expectations. This will help you achieve the required process and product improvements. Which document will help you the most in this situation? |  | A-) Risk Register | B-) Quality Report | C-) Quality Management Plan | D-) Final Report | Answer: B | Quality Report contains the information used by departments to take corrective actions to achieve the project quality expectations. The information presented in the quality reports includes recommendations for process, project, and product improvements. The quality management plan, on the other side, is a component of the project management plan that describes how the applicable policies, procedures, and guidelines will be implemented to achieve the quality objectives. Quality Report contains the information used by departments to take corrective actions to achieve the project quality expectations. The information presented in the quality reports includes recommendations for process, project, and product improvements. The quality management plan, on the other side, is a component of the project management plan that describes how the applicable policies, procedures, and guidelines will be implemented to achieve the quality objectives. Answer: B Answer: B
Exam 1 | #57. .A new senior manager has been given the responsibility of overseeing several projects. The manager asks an agile leader to share the monthly report summarizing the project status and the forecasted finish date. Which of the following is the best way in which the project leader should respond to the request of the manager? |  | A-) Suggest the senior manager attend the daily standup meetings | B-) Share the project burndown chart with the manager | C-) Ask the senior manager to use EVM to monitor the project progress | D-) Provide a detailed report of the project status as asked by the senior manager | Answer: B | Burndown chart is an information radiator that’s used for a visual demonstration of the progress of the project. The sprint burndown chart is updated after each iteration. Burndown chart shows the estimated and actual amount of the work to be completed with the time and therefore helps in tracking and monitoring the progress of the team – whether the team is on schedule or behind schedule. The burndown charts are generally placed at visible places and it is easy for everyone to see the current status and progress of the project. Burndown chart is an information radiator that’s used for a visual demonstration of the progress of the project. The sprint burndown chart is updated after each iteration. Burndown chart shows the estimated and actual amount of the work to be completed with the time and therefore helps in tracking and monitoring the progress of the team – whether the team is on schedule or behind schedule. The burndown charts are generally placed at visible places and it is easy for everyone to see the current status and progress of the project. Answer: B Answer: B
Exam 1 | #58. .In your project, when you are performing the stakeholder analysis, you are planning to group the stakeholders based on their level of authority and their level of concern about the project outcomes. Which classification model is appropriate for your purpose? |  | A-) Salience model | B-) Influence/impact grid | C-) Power/interest grid | D-) Power/influence grid | Answer: C | There are multiple classification models used for stakeholder analysis, such as: There are multiple classification models used for stakeholder analysis, such as: Power/interest grid, grouping the stakeholders based on their level of authority (“power”) and their level of concern (“interest”) regarding the project outcomes; Power/influence grid, grouping the stakeholders based on their level of authority (“power”) and their active involvement (“influence”) in the project; Influence/impact grid, grouping the stakeholders based on their active involvement (“influence” ) in the project and their ability to effect changes to the project’s planning or execution (“impact”); Salience model, describing classes of stakeholders based on their power (ability to impose their will), urgency (need for immediate attention), and legitimacy (their involvement is appropriate). Power/interest grid, grouping the stakeholders based on their level of authority (“power”) and their level of concern (“interest”) regarding the project outcomes; Power/interest grid, grouping the stakeholders based on their level of authority (“power”) and their level of concern (“interest”) regarding the project outcomes; Power/influence grid, grouping the stakeholders based on their level of authority (“power”) and their active involvement (“influence”) in the project; Power/influence grid, grouping the stakeholders based on their level of authority (“power”) and their active involvement (“influence”) in the project; Influence/impact grid, grouping the stakeholders based on their active involvement (“influence” ) in the project and their ability to effect changes to the project’s planning or execution (“impact”); Influence/impact grid, grouping the stakeholders based on their active involvement (“influence” ) in the project and their ability to effect changes to the project’s planning or execution (“impact”); Salience model, describing classes of stakeholders based on their power (ability to impose their will), urgency (need for immediate attention), and legitimacy (their involvement is appropriate). Salience model, describing classes of stakeholders based on their power (ability to impose their will), urgency (need for immediate attention), and legitimacy (their involvement is appropriate). Answer: C Answer: C
Exam 1 | #59. .Agile principle describes the rules of Agile philosophy through which many frameworks are developed. Crystal method is a framework that is focused on individuals and their respective interactions. What makes the Crystal method different? |  | A-) It is team based that the team could streamline their work and project whichever way they prefer. | B-) It is adaptive and requires modifying the process based on the project/task. | C-) It is human powered and comes in multiple variants. | D-) All of the above. | Answer: D | Crystal Agile is a framework that is focused on people and human interactions. Unlike any other project management methodology, Crystal is driven by human interactions and modalities of individuals rather than process and tools. Crystal Agile is a framework that is focused on people and human interactions. Unlike any other project management methodology, Crystal is driven by human interactions and modalities of individuals rather than process and tools. Answer: D Answer: D
Exam 1 | #60. .You have completed the kick-off meeting of your project and the team members started to meet each other and learn about the project. Based on the Tuckman ladder model, your team is in the _________ stage. |  | A-) Forming | B-) Storming | C-) Norming | D-) Meeting | Answer: A | Forming. This phase is where the team meets and learns about the project and their formal roles and responsibilities. Team members tend to be independent and not as open in this phase. Forming. This phase is where the team meets and learns about the project and their formal roles and responsibilities. Team members tend to be independent and not as open in this phase. Answer: A Answer: A
Exam 1 | #61. .You are trying to gather ideas related to project and product requirements. Which of the following techniques is appropriate for this activity? |  | A-) Brainstorming | B-) Nominal Group Technique | C-) Affinity Diagram | D-) Multicriteria Decision Analysis | Answer: A | Brainstorming is a technique used to generate and collect multiple ideas related to project and product requirements. Brainstorming is a technique used to generate and collect multiple ideas related to project and product requirements. Answer: A Answer: A
Exam 1 | #62. .Your Scrum team is preparing for the next iteration. During the planning meeting, they are discussing with the customer to hear more about the functionality they need to develop. They are in a story writing workshop, so the team is evaluating the following user story: "As a marketing manager, I want an online store so that I can increase sales." What would you say to your team about this particular user story? |  | A-) This story is missing the conversation component. | B-) This story is missing the functionality component. | C-) This story isn't testable. | D-) This story isn't negotiable. | Answer: C | Since this is the “card” part of the story, it isn’t missing a conversation–that is a separate component of a story. This story does have a functionality component (“I want an online store”). The biggest problem with this story is that it doesn’t provide any specifics or quantifiable targets to achieve, so it wouldn’t be testable. We can’t really tell from this scenario how negotiable the story is, but the description of an online store is broad, so it sounds like there is room for discussion. Since this is the “card” part of the story, it isn’t missing a conversation–that is a separate component of a story. This story does have a functionality component (“I want an online store”). The biggest problem with this story is that it doesn’t provide any specifics or quantifiable targets to achieve, so it wouldn’t be testable. We can’t really tell from this scenario how negotiable the story is, but the description of an online store is broad, so it sounds like there is room for discussion. Answer: C Answer: C
Exam 1 | #63. .Project deliverables, schedules, terms, conditions, payments, and many other details of procurement are written in contracts and signed by a buyer and a seller. The most commonly used contract type is: |  | A-) Time and Material Contracts | B-) Cost-plus fixed fee contracts | C-) Fixed-price incentive fee contracts | D-) Firm-fixed price contracts | Answer: D | The most commonly used contract type is Firm Fixed Price Contracts (FFP). If the project scope is clear, the buyer is not taking cost risks and prefers Firm Fixed Price Contracts. That is why it is the most popular contract type. The most commonly used contract type is Firm Fixed Price Contracts (FFP). If the project scope is clear, the buyer is not taking cost risks and prefers Firm Fixed Price Contracts. That is why it is the most popular contract type. Answer: D Answer: D
Exam 1 | #64. .In the Sprint Planning meeting, the newest member of your team is frustrated at the makeup of the requirements information. John has worked in plan-driven projects for all of his career and does not understand agile approaches. What can you share with John to help him understand the purpose of user stories in agile projects? |  | A-) User stories define the features of the product from the user’s perspective. | B-) User stories focus on “what,” rather than “why.” | C-) Creating user stories allows for the Product Owner to be an integral part of the project. | D-) All of the above. | Answer: D | User stories are a helpful way for the customer, or Product Owner, to provide their needs to teams in ways that address the practical needs of the users. User stories are a helpful way for the customer, or Product Owner, to provide their needs to teams in ways that address the practical needs of the users. Answer: D Answer: D
Exam 1 | #65. .You are managing a project to equip a medical lab in Israel. One of the main blood testing equipment machines is not showing accurate results and all things point to faulty installation of the sensitive equipment. The installer explained that the manufacturer’s installation manuals were in Hebrew, so he used Google translate to find out how to install the equipment. You are very upset and are considering firing the person and also reinstalling the whole lab. This scenario describes an internal failure cost, which is: |  | A-) The cost of replacing the equipment | B-) The cost of replacing the engineer | C-) The cost of replacing the equipment and replacing the engineer | D-) The cost of failed lab results due to installation problems | Answer: A | The cost of replacing the equipment. An internal failure cost is one that happens before the completion of a project and is usually the cost involved with rework. The cost of replacing the equipment. An internal failure cost is one that happens before the completion of a project and is usually the cost involved with rework. Answer: A Answer: A
Exam 1 | #66. .The customer has requested a new feature that will bring extra cost and new risks to the project. Besides, this change will also require two more resources to be acquired for the team. The project manager should rely on ________ to manage the changes that will happen during the project. |  | A-) Change Control Board | B-) Perform Integrated Change Control | C-) Change Requests | D-) Changes in the Project Plans | Answer: B | Perform Integrated Change Control is the process of reviewing all change requests; approving changes and managing changes to deliverables, organizational process assets, project documents, and the project management plan; and communicating their disposition. It reviews all requests for changes or modifications to project documents, deliverables, baselines, or the project management plan and approves or rejects the changes. Perform Integrated Change Control is the process of reviewing all change requests; approving changes and managing changes to deliverables, organizational process assets, project documents, and the project management plan; and communicating their disposition. It reviews all requests for changes or modifications to project documents, deliverables, baselines, or the project management plan and approves or rejects the changes. Answer: B Answer: B
Exam 1 | #67. .You are developing the schedule in your project. You are evaluating the scenarios to predict the positive or negative effects of the schedule durations on the project objectives. Which of the techniques do you use? |  | A-) What-if Scenario Analysis | B-) Sensitivity Analysis | C-) Resource Optimization | D-) Variance Analysis | Answer: A | What-if scenario analysis is the process of evaluating scenarios in order to predict the positive or negative effects of the schedule on project objectives. What-if scenario analysis is the process of evaluating scenarios in order to predict the positive or negative effects of the schedule on project objectives. Answer: A Answer: A
Exam 1 | #68. .Your company is using ISO 9000 standards for meeting quality requirements in produced products. All of the following about the quality are correct EXCEPT: |  | A-) Process analysis follows the steps outlined in the process improvement plan. | B-) The objective of a quality audit is to compare the project deliverables against the product requirements as defined in the WBS. | C-) Control quality is the process of monitoring and recording results of executing the quality activities to assess performance and recommend necessary changes. | D-) Quality management plan describes how the organization’s quality policies will be implemented. | Answer: B | A quality audit is a structured, independent process to determine if the project activities comply with organizational and project policies, processes, and procedures. A quality audit is a structured, independent process to determine if the project activities comply with organizational and project policies, processes, and procedures. Answer: B Answer: B
Exam 1 | #69. .Lisa, who works as a product owner in an e-commerce platform, possesses excellent technical skills in technical writing, and broad skills in other relevant areas, such as testing and user experience design. She is also very supportive of her team and can work successfully outside of her specialty when the need arises to help avoid bottlenecks. Lisa’s curiosity to learn is derived by which of the following? |  | A-) The desire to move to a specialized functional team later in her career | B-) The highly challenging role and work environment | C-) The willingness to work in a self-organizing team | D-) Long-term potential benefits and the opportunity to become a Scrum master | Answer: C | She wants to work in self-organized teams. Lisa has T-shaped skills, which means that she has one deep area of specialization and broad ability in the rest of the skills required by the team. This is a crucial requirement for a cross-functional team to operate effectively. She wants to work in self-organized teams. Lisa has T-shaped skills, which means that she has one deep area of specialization and broad ability in the rest of the skills required by the team. This is a crucial requirement for a cross-functional team to operate effectively. Answer: C Answer: C
Exam 1 | #70. .You place all of your most active project team members in the same meeting room to enhance their ability to perform as a team. This is known as: |  | A-) Ground Rule | B-) Dream Team | C-) Virtual Team | D-) Colocation | Answer: D | Colocation, also known as “tight matrix”, involves placing many or all of the most active project team members in the same physical location to enhance their ability to perform as a team. Colocation, also known as “tight matrix”, involves placing many or all of the most active project team members in the same physical location to enhance their ability to perform as a team. Answer: D Answer: D
Exam 1 | #71. .A scrum master wants to show the development team the patterns of their output and help them identify possible bottlenecks in the processes. What tool should be used in this context? |  | A-) Burndown chart | B-) Sprint backlog | C-) Product backlog | D-) Cumulative flow diagram | Answer: D | A cumulative flow diagram shows the work in progress across a board. A cumulative flow diagram shows the work in progress across a board. Answer: D Answer: D
Exam 1 | #72. .You have recently taken over a project from another project manager who resigned from your company. You realize that the project’s SPI is 0.9, and CPI is 0.8. Senior management is not aware of the project status. In this context, what should you do FIRST? |  | A-) Update the management about the status, and report to them that the project is behind schedule and over budget. | B-) Tell your management that you cannot continue with this project. | C-) Ask for an extra budget to crash the project. | D-) Fast-track the project. | Answer: A | The project’s both CPI and SPI are below 1 which means behind schedule and over budget. The first thing to do is to update management about the status of the project since they are unaware. The next steps might be fixing schedule and budget problems. The project’s both CPI and SPI are below 1 which means behind schedule and over budget. The first thing to do is to update management about the status of the project since they are unaware. The next steps might be fixing schedule and budget problems. Answer: A Answer: A
Exam 1 | #73. .To assess the quality of your project’s delivery, you planned a testing phase after the development of the product. You have to spend certain costs for testing. These costs are an example of: |  | A-) Cost of Nonconformance | B-) Failure Costs | C-) Prevention Costs | D-) Appraisal Costs | Answer: D | The cost of quality includes all costs incurred over the life of the product by investment in preventing nonconformance to requirements, appraising the product or service for conformance to requirements, and failing to meet requirements (rework). The following figure shows examples of the cost of conformance and cost of nonconformance. The cost of quality includes all costs incurred over the life of the product by investment in preventing nonconformance to requirements, appraising the product or service for conformance to requirements, and failing to meet requirements (rework). The following figure shows examples of the cost of conformance and cost of nonconformance. Testing is an example of Appraisal Costs. Testing is an example of Appraisal Costs. Answer: D Answer: D | images/image5.jpg
Exam 1 | #74. .You are preparing to manage a project in Thailand. This is the first time you will be managing a project outside your own country. You will be bringing a team of experienced people with you for the first month. The aim is to have the local team follow the US team and learn on the job. What is this knowledge transfer called? |  | A-) Business application | B-) Paired work | C-) Work shadowing | D-) Project work | Answer: C | Work shadowing is observing a professional in their job to gain a better understanding of the role. Work shadowing is observing a professional in their job to gain a better understanding of the role. Answer: C Answer: C
Exam 1 | #75. .Which of the following techniques include measuring, examining, and validating whether work and deliverables meet requirements and product acceptance criteria? |  | A-) Workshops | B-) Surveys | C-) Expert Judgment | D-) Provide sufficient resources and time for risk management activities | Answer: D | The inspection includes activities such as measuring, examining and validating to determine whether work and deliverables meet requirements and product acceptance criteria. The inspection includes activities such as measuring, examining and validating to determine whether work and deliverables meet requirements and product acceptance criteria. Answer: D Answer: D
Exam 1 | #76. .There are several types of PMO structures in organizations. Each type of PMO structure has varying degrees of control and influence on the projects of the organization. All of the following are types of PMO structures in organizations EXCEPT: |  | A-) Supportive | B-) Consulting | C-) Controlling | D-) Directive | Answer: B | There are several types of PMO structures in organizations, each varying in the degree of control and influence they have on projects within the organization, such as: There are several types of PMO structures in organizations, each varying in the degree of control and influence they have on projects within the organization, such as: Supportive Controlling Directive Supportive Supportive Controlling Controlling Directive Directive Answer: B Answer: B
Exam 1 | #77. .Your project scope is developing the avionics systems for a helicopter model. For project success, you see that the coordination of activities with other groups and dividing your project into several phases is crucial for better project management. For this purpose, you should ________________ . (choose the BEST option): |  | A-) Create a very comprehensive project charter. | B-) Develop specific deliverables, which are approved by the sponsor. | C-) Break the project into several sub-projects. | D-) Use the life cycle approach to manage the project. | Answer: D | A project life cycle is the series of phases that a project passes through from its initiation to its closure. The phases are generally sequential, and their names and numbers are determined by the management and control needs of the organization or organizations involved in the project, the nature of the project itself, and its area of application. A project life cycle is the series of phases that a project passes through from its initiation to its closure. The phases are generally sequential, and their names and numbers are determined by the management and control needs of the organization or organizations involved in the project, the nature of the project itself, and its area of application. Answer: D Answer: D
Exam 1 | #78. .Your colleague David, who is the Project manager, shared the following information about his project’s stakeholders. Which statement given by David is NOT correct? |  | A-) “My project has several stakeholders from varying levels of responsibility and authority.” | B-) “Operation manager Linda is always negative in meetings thus I will ignore her inputs in order to complete the project successfully.” | C-) “Key stakeholders of my project are operations management, project manager, project team, customers and sponsor” | D-) “Business Manager’s requirements conflict with Operations Manager’s requirements and it is difficult to manage these stakeholder’s expectations” | Answer: B | In the case of stakeholders with positive expectations for the project, their interests are best served by making the project successful. In contrast, the interests of negatively affected stakeholders must be monitored and managed closely. Ignoring negative stakeholder interests can result in an increased likelihood of failures, delays, or other negative consequences to the project. In the case of stakeholders with positive expectations for the project, their interests are best served by making the project successful. In contrast, the interests of negatively affected stakeholders must be monitored and managed closely. Ignoring negative stakeholder interests can result in an increased likelihood of failures, delays, or other negative consequences to the project. Answer: B Answer: B
Exam 1 | #79. .You are a project manager of a software development project. Your customer mentioned in the contract that the development should be done with a specific programming language and specific version of components. This is an example of: |  | A-) Constraint | B-) Risk | C-) Assumption | D-) Change request | Answer: A | Constraints. A limiting factor that affects the execution of a project or process. Constraints identified with the project scope statement list and describe the specific internal or external restrictions or limitations associated with the project scope that affect the execution of the project, for example, a predefined budget or any imposed dates or schedule milestones that are issued by the customer or performing organization. When a project is performed under an agreement, contractual provisions will generally be constraints. Information on constraints may be listed in the project scope statement or in a separate log. Constraints. A limiting factor that affects the execution of a project or process. Constraints identified with the project scope statement list and describe the specific internal or external restrictions or limitations associated with the project scope that affect the execution of the project, for example, a predefined budget or any imposed dates or schedule milestones that are issued by the customer or performing organization. When a project is performed under an agreement, contractual provisions will generally be constraints. Information on constraints may be listed in the project scope statement or in a separate log. Answer: A Answer: A
Exam 1 | #80. .In the context of a desirable model of communication between a sender and a receiver, all of the following statements are correct EXCEPT: |  | A-) Noise should be at a minimum level. | B-) The receiver must reply to the message after decoding the message. | C-) The receiver should acknowledge first and then agree with the message sent by the sender. | D-) The receiver should send a feedback message to the sender. | Answer: C | As part of the communications process, the sender is responsible for the transmission of the message, ensuring the information being communicated is clear and complete and confirming the communication is correctly understood. The receiver is responsible for ensuring that the information is received in its entirety, understood correctly, and acknowledged or responded to appropriately. However, the receiver may not agree with the received message. As part of the communications process, the sender is responsible for the transmission of the message, ensuring the information being communicated is clear and complete and confirming the communication is correctly understood. The receiver is responsible for ensuring that the information is received in its entirety, understood correctly, and acknowledged or responded to appropriately. However, the receiver may not agree with the received message. Answer: C Answer: C
Exam 1 | #81. .You are an agile practitioner working on a hybrid project. You are responsible to perform the duties of the project scrum master and to submit reports periodically to the senior management. The project sponsor suggests that you track the velocity of each team member individually instead of tracking the team velocity as a whole in order to monitor the progress of the project. What is the best practice in Agile projects? |  | A-) Track and report on individual velocity to monitor the team performance | B-) Track either individual velocity or team velocity to monitor the team performance | C-) Track and report only team velocity to monitor the team performance | D-) Track and report both the individual velocity and team velocity to monitor the team performance | Answer: C | Agile best practices prefer to track and report the velocity of the team rather than the individual’s velocity for monitoring the project. Some Agile teams track the velocity of each team member individually in terms of completed story points or ideal days. This is not a good approach; it can cause behavioral issues and can work against the success of the project team. Agile best practices prefer to track and report the velocity of the team rather than the individual’s velocity for monitoring the project. Some Agile teams track the velocity of each team member individually in terms of completed story points or ideal days. This is not a good approach; it can cause behavioral issues and can work against the success of the project team. Answer: C Answer: C
Exam 1 | #82. .You are managing a project and want to use the “expert judgment” technique for a specific topic. Expert judgment can be provided from all of the following EXCEPT: |  | A-) Competitors | B-) Other units within the organization | C-) Industry groups | D-) Subject Matter Experts | Answer: A | Expert judgment can be requested when the company or the sponsor develop the project charter. Expert judgment can be applied to all technical and management details during this process. Such expertise is provided by any group or individual with specialized knowledge or training and is available from many sources. The following three are the examples to these sources: Expert judgment can be requested when the company or the sponsor develop the project charter. Expert judgment can be applied to all technical and management details during this process. Such expertise is provided by any group or individual with specialized knowledge or training and is available from many sources. The following three are the examples to these sources: Other units within the organization Industry groups Subject Matter Experts Other units within the organization Other units within the organization Industry groups Industry groups Subject Matter Experts Subject Matter Experts Answer: A Answer: A
Exam 1 | #83. .New Life company is building communications towers in 30 countries around the world. The lead in the project management office (PMO) wants more timely progress reporting and experience sharing between project managers in each of the geographically distant projects. Which two agile methods might the PMO use to fulfill this need? (Choose TWO). |  | A-) Definition of Done | B-) Electronic Kanban board | C-) Backlog refinement | D-) Virtual daily stand-up meetings | Answer: B & D | Electronic Kanban board and Virtual daily stand-up meetings Electronic Kanban board and Virtual daily stand-up meetings Answer: B & D Answer: B & D
Exam 1 | #84. .In your project, you identified the “fire risk in storage” which may cause you to lose some of the materials needed for your project. During the meetings, the project team decided to acknowledge the risk, and the sponsor recommended allocation of a contingency reserve (7% of the project budget). This contingency reserve can be used in case of fire in the storage. Which of the following strategies has been used for this risk? |  | A-) Risk mitigation | B-) Risk acceptance | C-) Risk avoidance | D-) Risk transfer | Answer: B | Risk acceptance is a risk response strategy whereby the project team decides to acknowledge the risk and not take any action unless the risk occurs. The most common active acceptance strategy is to establish a contingency reserve, including amounts of time, money, or resources to handle the risks. Risk acceptance is a risk response strategy whereby the project team decides to acknowledge the risk and not take any action unless the risk occurs. The most common active acceptance strategy is to establish a contingency reserve, including amounts of time, money, or resources to handle the risks. Answer: B Answer: B
Exam 1 | #85. .You have been engaged as the project manager of an innovative project to develop a new type of thermal power station. You have great experience in the field and were given the opportunity to choose your team. You have a great team and trust them completely. They know that you have full trust in them, and you want them to develop both personally and professionally during the project. The team members are feeling confident that the project will be a success. What type of leadership are you promoting? |  | A-) Transactional leadership | B-) Charismatic leadership | C-) Servant leadership | D-) Laissez faire leadership | Answer: C | This is servant leadership when you are leading the team from behind. You support the team and trust them to perform at their best. This is servant leadership when you are leading the team from behind. You support the team and trust them to perform at their best. Answer: C Answer: C
Exam 1 | #86. .As a senior developer you also understand the importance of advertising your latest valuable features in the product. You decide to schedule a meeting with the marketing team and explain MMR (Minimum Marketable Release) technique in order to advertise the latest feature in the product you have been working on along with the team; how is MMR helpful within Agile marketing: |  | A-) MMR is an important approach because the products and features in Agile must be deployed at once; MMR helps advertise and attract the client before product release. | B-) MMR is an important approach because it reduces the time to market between each release and thus advertises value on an incremental basis. | C-) MMR is an important approach because it is focused on releasing the latest trend in the market; that is what attracts the client the most. | D-) MMR is an important approach because it is focused on advertising that does not exist in the market yet. | Answer: B | Minimum Marketable Release (MMR) is a Lean-Agile concept that is focused on releasing the smallest piece of functionality on increment basis thus reducing the time between each new release. Minimum Marketable Release (MMR) is a Lean-Agile concept that is focused on releasing the smallest piece of functionality on increment basis thus reducing the time between each new release. Answer: B Answer: B
Exam 1 | #87. .The project scope statement includes a description of the project scope. Project scope statement also includes: |  | A-) Scope Baseline | B-) Assumptions | C-) WBS | D-) WBS Dictionary | Answer: B | Project scope management includes a description of the project scope, major deliverables, assumptions, and constraints. Project scope management includes a description of the project scope, major deliverables, assumptions, and constraints. Answer: B Answer: B
Exam 1 | #88. .Which of the following documents allow prospective sellers to determine if they are capable of providing the required products, services, or results? |  | A-) Project Statement of Work | B-) Procurement Statement of Work | C-) Project Scope Statement | D-) Scope Baseline | Answer: B | The procurement statement of work describes the procurement item in sufficient detail to allow prospective sellers to determine if they are capable of providing the products, services, or results The procurement statement of work describes the procurement item in sufficient detail to allow prospective sellers to determine if they are capable of providing the products, services, or results Answer: B Answer: B
Exam 1 | #89. .Your colleague Wayne, a project manager, completed a mobile app development project. While he was discussing his experiences from the project, he mentioned that they delivered an “adjustable screen timeout duration” feature, without a deviation from the plan, although the customer did not require this feature. This feature was not in the scope of the project. He added that the customer was very surprised and happy when they saw this additional feature at the end of the project. Which of the following is correct about this story? |  | A-) Gold plating was done in the project. | B-) Customer satisfaction increased with an additional feature which they did not expect. | C-) A change request has been delivered successfully. | D-) An unnecessary risk has been taken by adding a new feature to the product. | Answer: A | Gold plating refers to continuing to work on a project or task well past the point where the extra effort is worth the value it adds (if any). After having met the requirements, the assignee works on further enhancing the product, thinking the customer would be delighted to see additional or more polished features, rather than what was asked for or expected. Gold plating refers to continuing to work on a project or task well past the point where the extra effort is worth the value it adds (if any). After having met the requirements, the assignee works on further enhancing the product, thinking the customer would be delighted to see additional or more polished features, rather than what was asked for or expected. Answer: A Answer: A
Exam 1 | #90. .When hiring a project manager, which one of the following is the most important skill that should be considered? |  | A-) Detail-oriented | B-) Negotiation | C-) Communication | D-) Persuasiveness | Answer: C | A project manager spends 90% of his time in communication. Thus, communication skills are the most important skills for project management. A project manager spends 90% of his time in communication. Thus, communication skills are the most important skills for project management. Answer: C Answer: C
Exam 1 | #91. .You and your contractor have a dispute regarding payment terms and what constitutes minimum viable product acceptance as described in the agreement. After several weeks of negotiation, an agreement has still not been reached. What should the project manager do next? |  | A-) Litigate in court, as the vendor is in default | B-) Escalate to your lawyers and determine a more effective course of action | C-) Initiate an alternative dispute resolution (ADR) program | D-) Renegotiate if possible and re-baseline the agreement | Answer: C | ADR should be initiated when mutual negotiation fails. After this, legal proceedings should be initiated only if it is required. ADR should be initiated when mutual negotiation fails. After this, legal proceedings should be initiated only if it is required. Answer: C Answer: C
Exam 1 | #92. .You need to collect votes from 17 stakeholders on the 3 options under review. After the voting is done, you collect the results. You find that 9 stakeholders have voted for the first option. You decide to go ahead with the first option and forward this decision to be implemented. Which voting technique did you use? |  | A-) Unanimity | B-) Majority | C-) Plurality | D-) Autocratic | Answer: B | The majority is a decision that is reached with support obtained from more than 50% of the members of the group. The majority is a decision that is reached with support obtained from more than 50% of the members of the group. Answer: B Answer: B
Exam 1 | #93. .John is a project manager of a complicated project. When he started creating a work breakdown structure for his project, he realized that it is too complex to fit in a single sheet. You, as a colleague of John, recommend him to use a work breakdown structure numbering system to: |  | A-) Determine the complexity of the project | B-) Automate the WBS using appropriate software | C-) Provide a hierarchical structure for each WBS element | D-) Present risks of the project | Answer: C | The WBS is finalized by assigning each work package to a control account and establishing a unique identifier for that work package from a code of accounts. These identifiers provide a structure for a hierarchical summary of costs, schedule, and resource information. The WBS is finalized by assigning each work package to a control account and establishing a unique identifier for that work package from a code of accounts. These identifiers provide a structure for a hierarchical summary of costs, schedule, and resource information. Answer: C Answer: C
Exam 1 | #94. .Sarah, a Perficient Agile Project Manager, is working for software company Greenleaf that is complex and slow to innovate, thus lagging when delivering solutions to customers. Recently, Sarah has been offered a chance to work for a small startup in need of delivering products often and incrementally. Sarah’s best chance to succeed in utilizing her Agile knowledge is: |  | A-) In the corporation | B-) In the startup | C-) In either the corporation or the startup | D-) In neither the corporation nor the startup | Answer: B | Startups tend to have decreased innovation barriers that can rapidly produce products and services fit for demanding customers. Startups tend to have decreased innovation barriers that can rapidly produce products and services fit for demanding customers. Answer: B Answer: B
Exam 1 | #95. .Casey’s team of 7 has been affected by a contagious virus and it will only have 5 Developers for the next week. The team is mid-Sprint and there is concern that all work will not be completed in this Sprint. What is Casey’s best next step? |  | A-) Request the staffing team provide staff augmentation. | B-) Request the team work overtime to make up the difference. | C-) Encourage the remaining team to complete as much as possible and return what is not completed to the backlog. | D-) Postpone the iteration delivery and, subsequently, the release date. | Answer: C | The team should be able to complete most of the work and return the remainder to the backlog. Staff augmentation will not be effective for one week as it requires time to plan and get the new member integrated within the team. Overworking staff is not one of the core tenets of agile methodology. If timeboxing has been done well, there will be no need for delivery and release delays. The team should be able to complete most of the work and return the remainder to the backlog. Staff augmentation will not be effective for one week as it requires time to plan and get the new member integrated within the team. Overworking staff is not one of the core tenets of agile methodology. If timeboxing has been done well, there will be no need for delivery and release delays. Answer: C Answer: C
Exam 1 | #96. .Jordan, the project manager for an agile project, recognizes that the quality of the deliverables is not meeting standards. Jordan sees the need for the agile project team to receive feedback on their work product. What is the best way for them to obtain this? |  | A-) Request that the sponsor review the team’s release plans. | B-) Request the QA team test all the features before release. | C-) Have you, the project manager, attend their reviews and retrospectives. | D-) Have the product owner carefully review each increment. | Answer: D | Department heads and QA teams are not part of agile teams. The project manager will be attending the reviews and retrospectives to help coach the team through agile practices, but the best way to obtain feedback is from the product owner who is the representative of the end user of the product. Department heads and QA teams are not part of agile teams. The project manager will be attending the reviews and retrospectives to help coach the team through agile practices, but the best way to obtain feedback is from the product owner who is the representative of the end user of the product. Answer: D Answer: D
Exam 1 | #97. .All of the following are hygiene factors according to Herzberg’s Theory EXCEPT: |  | A-) Salary | B-) Professional Growth | C-) Security | D-) Relationships at work | Answer: B | According to Herzberg’s Theory, there are hygiene factors and motivating agents. Inadequate Hygiene factors may destroy motivation but sufficient hygiene factors themselves are not enough to motivate people. Hygiene factors are: According to Herzberg’s Theory, there are hygiene factors and motivating agents. Inadequate Hygiene factors may destroy motivation but sufficient hygiene factors themselves are not enough to motivate people. Hygiene factors are: Working card Salary Personal Life Relationships at work Security Status Working card Working card Salary Salary Personal Life Personal Life Relationships at work Relationships at work Security Security Status Status Professional growth is a motivating agent based on Herzberg’s Theory. Professional growth is a motivating agent based on Herzberg’s Theory. Answer: B Answer: B
Exam 1 | #98. .Ishikawa or fishbone diagrams are useful for identifying the causes of risks. These diagrams are also known as: |  | A-) Cause and effect diagrams | B-) System or process flow charts | C-) Simulation diagrams | D-) Influence diagrams | Answer: A | Cause and effect diagrams: These are also known as Ishikawa or fishbone diagrams and are useful for identifying the causes of risks. Cause and effect diagrams: These are also known as Ishikawa or fishbone diagrams and are useful for identifying the causes of risks. Answer: A Answer: A
Exam 1 | #99. .You are working in an international company which has several offices around the globe. Your Company asks you to manage a project for its subsidiary unit in another country. You quickly realize that employees in the subsidiary unit have poor work ethics compared to employees in your base country. In this context, which of the following will be the most appropriate course of action? |  | A-) Ask your new team to emulate the work ethics of the teams of your parent company | B-) Take steps to change the work culture of your new team | C-) Regard your new team as lazy and impose sanctions. | D-) Treat it as cultural differences, and try to determine the ways to improve productivity | Answer: D | The PMI Code of Ethics and Professional Conduct requires a project manager to address things with an open mind and accept the cultural and ethical diversity that exists between different countries. So, it is not the responsibility of the project managers to enforce the work-ethics of their country on the people of another country. The PMI Code of Ethics and Professional Conduct requires a project manager to address things with an open mind and accept the cultural and ethical diversity that exists between different countries. So, it is not the responsibility of the project managers to enforce the work-ethics of their country on the people of another country. Answer: D Answer: D
Exam 1 | #100. .Your Company agreed in a joint venture with a Service Company to develop a software program. Which of the following should be cooperatively prepared by both the buyer and the seller during the “Teaming Agreement” process? |  | A-) Contract | B-) Contract, Procurement statement of work | C-) Request for proposal | D-) Human Resource Plan | Answer: B | In some cases, the seller may already be working under a contract funded by the buyer or jointly by both parties. The effort of the buyer and seller in this process is to collectively prepare a procurement statement of work that will satisfy the requirements of the project. The parties will then negotiate a final contract for an award. In some cases, the seller may already be working under a contract funded by the buyer or jointly by both parties. The effort of the buyer and seller in this process is to collectively prepare a procurement statement of work that will satisfy the requirements of the project. The parties will then negotiate a final contract for an award. Answer: B Answer: B
Exam 1 | #101. .Two engineers of your project team disagree on implementing the software on the customer site. You ask these engineers to write down the advantages and disadvantages of their proposals and submit their recommendations. Then, you provide a solution that satisfies both engineers. Which conflict resolution technique have you used? |  | A-) Force/Direct | B-) Compromise/Reconcile | C-) Collaborate/Problem Solve | D-) Smooth/Accommodate | Answer: B | Compromise/Reconcile: Searching for solutions that bring some degree of satisfaction to all parties in order to temporarily or partially resolve the conflict. Compromise/Reconcile: Searching for solutions that bring some degree of satisfaction to all parties in order to temporarily or partially resolve the conflict. Answer: B Answer: B
Exam 1 | #102. .To document and monitor the resolution of project issues, you are using an issue log. Issue log helps to: |  | A-) Escalate activities to project team | B-) Determine risks in the project | C-) Monitor who is responsible for resolving specific issues by a target date | D-) Determine the schedule of the project | Answer: C | An issue log is used to document and monitor the resolution of issues. It may be used to facilitate communication and ensure a common understanding of issues. A written log documents and helps to monitor who is responsible for resolving specific issues by a target date. An issue log is used to document and monitor the resolution of issues. It may be used to facilitate communication and ensure a common understanding of issues. A written log documents and helps to monitor who is responsible for resolving specific issues by a target date. Answer: C Answer: C
Exam 1 | #103. .A team is transitioning from a predictive approach to an Agile approach. Historically, the team has delivered work products with poor quality. What Agile practice can help the team to mitigate this? |  | A-) Consider using the various test-driven development practices | B-) Consider using timeboxed research or experiments | C-) Consider building a product roadmap using story mapping and impact mapping methods | D-) Consider training team members in the fundamentals of the Agile mindset and principles | Answer: A | Consider using the various test-driven development practices. This mistake-proofing discipline makes it difficult for defects to be undetected. Timeboxed research or experiments are useful for learning and may be used in circumstances like estimation and defining acceptance criteria. Consider using the various test-driven development practices. This mistake-proofing discipline makes it difficult for defects to be undetected. Timeboxed research or experiments are useful for learning and may be used in circumstances like estimation and defining acceptance criteria. Answer: A Answer: A
Exam 1 | #104. .Now that you have recommended the MVP approach, the Product Owner along with the rest of stakeholders are excited about this approach. You also remind them to consider MBI (Minimum Business Increment) for their existing products. What is MBI technique used for: |  | A-) It is a technique used to capture the smallest increment of value in a product which can be built and released. | B-) It is a technique used to define the steps needed to complete the MVP and introduce the initiative. | C-) It is a technique used to capture the unused features of a product and eliminate them from the process. | D-) It is a technique used by Product Owners to highlight the business aspects of their product backlogs. | Answer: A | Minimum Business Increment (MBI) is a Lean-Agile concept that is focused on finding the smallest piece of value that can be added to a product/service to improve the business. Minimum Business Increment (MBI) is a Lean-Agile concept that is focused on finding the smallest piece of value that can be added to a product/service to improve the business. Answer: A Answer: A
Exam 1 | #105. .Your project has a very strict deadline and must be completed in nine months. You have a business background and have experience in project work, however, the project scope statement is not ready. Your management insists on proceeding without having an approved project scope statement since the clock is ticking. What would you do in this case? |  | A-) Arrange a meeting with the management and explain the consequences and problems that might occur if you start the project without an approved scope statement | B-) Since the clock is ticking, start the project work from clear points, and try to clarify other parts during the project | C-) Tell your management that you cannot work under these conditions. | D-) Write down this issue as a risk item | Answer: A | The project scope statement is the description of the project scope, major deliverables, assumptions, and constraints. The project scope statement documents the entire scope, including project and product scope. It describes, in detail, the project’s deliverables and the work required to create those deliverables. The project scope statement is the description of the project scope, major deliverables, assumptions, and constraints. The project scope statement documents the entire scope, including project and product scope. It describes, in detail, the project’s deliverables and the work required to create those deliverables. Answer A is the best option. Answer A is the best option. Answer: A Answer: A
Exam 1 | #106. .You are working in “Money Talks” Finance Company. Your Company started a new portfolio which has three projects and two programs. Due to time constraints, the portfolio manager decided to subcontract one of the projects to a vendor and asked you to help find suitable vendors for this project. In order to select the most suitable vendor, you have determined the vendor evaluation standards which are also known as _____________. |  | A-) Project statement of work | B-) Source selection criteria | C-) Constraint | D-) Risk | Answer: B | Source selection criteria are often included as a part of the procurement documents. Such criteria are developed and used to rate or score sellers’ proposals, and can be objective or subjective. Source selection criteria are often included as a part of the procurement documents. Such criteria are developed and used to rate or score sellers’ proposals, and can be objective or subjective. Answer: B Answer: B
Exam 1 | #107. .Your team is attempting to calculate their work output. So far, they have completed three iterations, and the fourth is 50% completed. Iteration 1: 23 story points were completed. Iteration 2: 25 story points were completed. Iteration 3: 24 story points were completed. Iteration 4: 12 story points were completed, and 12 were not completed (50%). What is your team’s current throughput? |  | A-) 18 | B-) 19 | C-) 20 | D-) 21 | Answer: A | If you are using throughput to track performance, it is important to make sure that partial work is NOT included in your calculations. The goal is to focus on finished work and completed stories that have been accomplished. Calculate throughput by adding all of the story points together and then dividing by the total number of iterations. In this question, exclude the story points of iteration 4 because the iteration is not completed. Throughput = (23 25 24)/4 = 72/4 = 18 If you are using throughput to track performance, it is important to make sure that partial work is NOT included in your calculations. The goal is to focus on finished work and completed stories that have been accomplished. Calculate throughput by adding all of the story points together and then dividing by the total number of iterations. In this question, exclude the story points of iteration 4 because the iteration is not completed. Throughput = (23 25 24)/4 = 72/4 = 18 Answer: A Answer: A
Exam 1 | #108. .You are managing an Agile software project. Previously, you had managed only non-Agile projects. Which type of meetings would you find to be unique for your current project compared to your earlier projects? |  | A-) Design meetings | B-) Retrospective meetings | C-) Quality review meetings | D-) Vendor performance review meetings | Answer: B | Retrospective meetings are unique to Agile projects. Retrospective meetings are unique to Agile projects. Answer: B Answer: B
Exam 1 | #109. .You are dealing with an emergency situation and decide to implement a solution to overcome a pending issue. Although you have received multiple solutions from your team members, you decided to implement your solution. The conflict resolution technique you used is: |  | A-) Avoid | B-) Smooth | C-) Collaborate | D-) Forcing | Answer: D | Force/Direct. Pushing one’s viewpoint at the expense of others; offering only win-lose solutions, usually enforced through a power position to resolve an emergency. Force/Direct. Pushing one’s viewpoint at the expense of others; offering only win-lose solutions, usually enforced through a power position to resolve an emergency. Answer: D Answer: D
Exam 1 | #110. .Jerry, an Agile Project Manager, is working for insurance company SafeLife where top management values highly complex documented processes and uses complicated tools to analyze process efficiency. The COO, Mary, has commended Jerry for developing a project to improve the company's ERP system. What would Jerry advise the COO from the agile perspective? |  | A-) We need to change the ERP to an up-to-date solution. | B-) We must focus on redesigning the process before thinking about changing the ERP system. | C-) Projects must focus on individuals and interactions with each process, rather than the processes and tools. | D-) We need to place special attention on process controls to avoid mistakes and defects. | Answer: C | Although processes and tools are essential to managing projects, Agile principles emphasize greater value on individuals and interactions over the processes and tools. Valuing people over processes allows all related stakeholders to respond to business needs and drive the development process. Although processes and tools are essential to managing projects, Agile principles emphasize greater value on individuals and interactions over the processes and tools. Valuing people over processes allows all related stakeholders to respond to business needs and drive the development process. Answer: C Answer: C
Exam 1 | #111. .Your colleague Lisa, a junior project manager, is about to complete her project. Her customer requests an additional item to be delivered in the project. What would you recommend Lisa to do next? |  | A-) Deliver the additional requested item, because you will satisfy the customer | B-) Deliver the additional requested item, because the customer might not accept the final product | C-) Explain to the customer that the requested additional item does not have a business sense | D-) Process the requirement through the integrated change control process | Answer: D | Option #1 and #2 are not recommended, because the additional item is not in the initial scope of the project. You cannot evaluate the business sense of a deliverable for your customer, thus option #3 cannot be recommended as well. Option #4 is the best choice. Option #1 and #2 are not recommended, because the additional item is not in the initial scope of the project. You cannot evaluate the business sense of a deliverable for your customer, thus option #3 cannot be recommended as well. Option #4 is the best choice. Analysis of project performance and interaction with stakeholders often generates change requests. These change requests are processed through the Perform Integrated Change Control process. Analysis of project performance and interaction with stakeholders often generates change requests. These change requests are processed through the Perform Integrated Change Control process. Answer: D Answer: D
Exam 1 | #112. .To provide required information to project stakeholders on time, you have completed the Manage Communications process. Which of the following is NOT an output of the Manage Communications process: |  | A-) Feedback from stakeholders | B-) Stakeholder notifications | C-) Lessons learned documentation | D-) Change requests | Answer: D | Feedbacks from stakeholders, stakeholder notifications, and lessons learned documentation are part of Organizational Process Assets Updates which may be updated as an output of the Manage Communications Process. Change requests are an output of the Monitor Communications Process. Feedbacks from stakeholders, stakeholder notifications, and lessons learned documentation are part of Organizational Process Assets Updates which may be updated as an output of the Manage Communications Process. Change requests are an output of the Monitor Communications Process. Answer: D Answer: D
Exam 1 | #113. .A project manager is managing a software development project in a hybrid environment using both Waterfall and Agile frameworks. Overall the project was successful. However, the project manager realizes that there is confusion between team members about who is responsible for completion of the analysis work and the processes associated with the project. What should the project manager do next? |  | A-) Detail roles and responsibilities by developing the communication management plan. | B-) Develop the resource management plan by defining the roles and responsibilities of the team and other stakeholders listed in the stakeholder register. | C-) Detail the roles and responsibilities by developing the team charter. | D-) Invite the key stakeholders to the project kickoff meeting. | Answer: B | According to PMBOK, the resource management plan, a subsidiary component of the project management plan, documents who resources should be defined, staffed, managed/controlled, and released from the project when their activities are complete. The resource management plan defines the roles and responsibilities for each team member on the project (i.e. Testing Lead, Analyst, etc.) According to PMBOK, the resource management plan, a subsidiary component of the project management plan, documents who resources should be defined, staffed, managed/controlled, and released from the project when their activities are complete. The resource management plan defines the roles and responsibilities for each team member on the project (i.e. Testing Lead, Analyst, etc.) Answer: B Answer: B
Exam 1 | #114. .In your project, you performed a quantitative risk analysis. The results show that there is a risk of going over the budget and schedule threshold limits. Which of the following should you do to overcome this risk if it occurs? |  | A-) Crash the project | B-) Fast track the project | C-) Consider using contingency reserves | D-) Do additional risk response planning | Answer: C | Using contingency reserves will lower the risk of cost overruns and schedule delays to an acceptable level for the organization. Using contingency reserves will lower the risk of cost overruns and schedule delays to an acceptable level for the organization. Answer: C Answer: C
Exam 1 | #115. .A Scrum Master is assigned to a team that is new to Agile frameworks. The Scrum Master learns that some of the teams have developed detailed release plans and the team seems disinterested in the daily standup meetings. What should the Scrum Master do next? |  | A-) Explain that interactions are valued through the interactions held in stand-up meetings. | B-) Ask the Product Owner if the daily standup meetings can be skipped. | C-) Agree that the daily standup meeting should be avoided, since it slows down the progress of the team. | D-) Force the Agile team to attend the daily standup meetings since these meetings are essential for any Agile project. | Answer: A | Although daily standups are short and quick, team members may think it is OK to skip them and provide updates/issues ahead of time. Allowing team members to skip them could cause others to miss as well if they feel that they are no longer mandatory. So, the Scrum Master needs to communicate the importance of the daily standup meetings. Forcing the team is not recommended because Agile Team Members are self-organized and self-directed. Therefore, option A is the best answer to the question asked. Although daily standups are short and quick, team members may think it is OK to skip them and provide updates/issues ahead of time. Allowing team members to skip them could cause others to miss as well if they feel that they are no longer mandatory. So, the Scrum Master needs to communicate the importance of the daily standup meetings. Forcing the team is not recommended because Agile Team Members are self-organized and self-directed. Therefore, option A is the best answer to the question asked. Answer: A Answer: A
Exam 1 | #116. .You are performing the acquire resources process of your project. As a project manager, you may need to negotiate staff assignments with all of the following EXCEPT: |  | A-) Functional Managers | B-) Project Sponsor | C-) Other project management teams in the organization | D-) External organizations, vendors, suppliers, contractors, etc. | Answer: B | Staff assignments are negotiated on many projects. For example, the project management team may need to negotiate with: Staff assignments are negotiated on many projects. For example, the project management team may need to negotiate with: Functional managers, to ensure that the project receives appropriately competent staff in the required time frame and that the project team members will be able, willing, and authorized to work on the project until their responsibilities are completed; Other project management teams within the performing organization, to appropriately assign scarce or specialized human resources; and External organizations, vendors, suppliers, contractors, etc. for appropriate, scarce, specialized, qualified, certified, or other such specified human resources. Special consideration should be given to external negotiating policies, practices, processes, guidelines, legal, and other such criteria. Functional managers, to ensure that the project receives appropriately competent staff in the required time frame and that the project team members will be able, willing, and authorized to work on the project until their responsibilities are completed; Functional managers, to ensure that the project receives appropriately competent staff in the required time frame and that the project team members will be able, willing, and authorized to work on the project until their responsibilities are completed; Other project management teams within the performing organization, to appropriately assign scarce or specialized human resources; and Other project management teams within the performing organization, to appropriately assign scarce or specialized human resources; and External organizations, vendors, suppliers, contractors, etc. for appropriate, scarce, specialized, qualified, certified, or other such specified human resources. Special consideration should be given to external negotiating policies, practices, processes, guidelines, legal, and other such criteria. External organizations, vendors, suppliers, contractors, etc. for appropriate, scarce, specialized, qualified, certified, or other such specified human resources. Special consideration should be given to external negotiating policies, practices, processes, guidelines, legal, and other such criteria. Once the negotiations are completed, you need to inform the project sponsor about the final project assignments. You don’t negotiate with the sponsor. Once the negotiations are completed, you need to inform the project sponsor about the final project assignments. You don’t negotiate with the sponsor. Answer: B Answer: B
Exam 1 | #117. .Your company is transitioning from a predictive project management approach to an Agile approach. Historically, the team members have not had any experience with an Agile project management approach. What should the organization do next? |  | A-) Hire a technical expert on Agile | B-) Replace existing resources with new ones that have agile knowledge | C-) Ask the team members to learn Agile individually | D-) Organize internal and external team training for all team members on the agile team | Answer: D | In case the project team members are inexperienced in the use of Agile, consider starting by training the team members in the fundamentals of the Agile mindset and principles. If the team decides to use a specific Agile approach (i.e. Scum, XP), provide a workshop on that approach to inform the team on its processes In case the project team members are inexperienced in the use of Agile, consider starting by training the team members in the fundamentals of the Agile mindset and principles. If the team decides to use a specific Agile approach (i.e. Scum, XP), provide a workshop on that approach to inform the team on its processes Answer: D Answer: D
Exam 1 | #118. .You have been a team leader on a project for almost 10 months now. The project is going well, but you feel that you are not motivated to put in your best performance because you get almost no guidance and direction from the project manager. He also never asks how your work is progressing and what have you been doing for all of these months on the project. You feel like you must make a lot of project decisions by yourself. You wonder if the project manager doesn’t like you, but when you speak with other team members about it, say that he is the same with them as well. What kind of management style is the project manager using? |  | A-) Transactional | B-) Servant Leader | C-) Laissez-faire | D-) Autocratic | Answer: C | Laissez-faire. This management style means that the manager does not interfere with the work on the project and with the team. He/she lets the team work as he/she trusts the team to do their best. Laissez-faire. This management style means that the manager does not interfere with the work on the project and with the team. He/she lets the team work as he/she trusts the team to do their best. Answer: C Answer: C
Exam 1 | #119. .Aaron is an Agile Project Manager in a global marketing company Modify. The CEO envisions a company where the cost of poor quality is driven to a minimum to deliver value to the customers, but mainly to provide a more profitable business to the shareholders. Therefore, he has designed a new business model based on Agile principles to execute projects with high levels of risk and uncertainty. What would be a critical success factor for Aaron’s proposal to work? |  | A-) It must have clear procedures that have proven successful in the past. | B-) It must be based on benchmarking best practices from the industry's leader. | C-) It requires a defined project plan upfront in order for all project work to be conducted. | D-) It requires collaboration at the team level to help solve problems to create a solution. | Answer: D | High-uncertainty projects have a high change, complexity, and risk rates. Agile practices promoted team collaboration over documentation to quickly create working solutions and ultimately bring business value to the organization. High-uncertainty projects have a high change, complexity, and risk rates. Agile practices promoted team collaboration over documentation to quickly create working solutions and ultimately bring business value to the organization. Answer: D Answer: D
Exam 1 | #120. .During a Sprint review meeting, the Product Owner expresses concern that the ongoing sprint does not produce any business value. What should the Product Owner do next? |  | A-) Cancel the product and product backlog | B-) Determine if the sprint should continue | C-) Postpone the current sprint to the next sprint | D-) Cancel the ongoing sprint and a new sprint can be planned | Answer: D | In Sprint Review Meetings, the Product Owner is responsible for canceling, inspecting, accepting, or declining deliverables of the Scrum Team. If the ongoing sprint does not make any business value, it can be canceled, and a new sprint can be planned. The Scrum team should only concentrate on delivering client value by building potentially shippable product increments. Without the focus on client value, the agile team may create features that are insufficient, therefore wasting time and effort. In Sprint Review Meetings, the Product Owner is responsible for canceling, inspecting, accepting, or declining deliverables of the Scrum Team. If the ongoing sprint does not make any business value, it can be canceled, and a new sprint can be planned. The Scrum team should only concentrate on delivering client value by building potentially shippable product increments. Without the focus on client value, the agile team may create features that are insufficient, therefore wasting time and effort. Answer: D Answer: D
Exam 1 | #121. .You are currently in the execution phase of your project. You will be doing all of the following EXCEPT: |  | A-) Expending most of the project budget | B-) Implementing planned methods and standards with the team | C-) Reviewing all prior information from the previous phase closures. | D-) Managing risks and implementing risk response activities with the team | Answer: C | When closing the project, the project manager reviews all prior information from previous phase closures to ensure that all project work is completed and the project has met its objectives. All other options are done during project execution. When closing the project, the project manager reviews all prior information from previous phase closures to ensure that all project work is completed and the project has met its objectives. All other options are done during project execution. Answer: C Answer: C
Exam 1 | #122. .You have recently joined an organization that uses Agile delivery techniques to carry out projects. The Product Owner and the client are in talks to develop a new software, but the client is unsure about the entire set of features. Since you have extensive experience in product development, you recommend the MVP (Minimum Viable Product) approach. What is MVP? |  | A-) It is a technique to produce a software without investing too much into testing because testing can take longer and be more expensive. | B-) It is a technique to produce a product with just enough features to test its functionality and receive early feedback. | C-) It is a technique used by newcomers in the market to deliver a product at the lowest available cost in the market. | D-) It is a technique that is used by new hired staff to show off their skills without spending too much time on a task. | Answer: B | Minimum Viable Product (MVP) is a Lean-Agile concept that is focused on delivering products with the minimum amount of features needed to make it functional. It allows early feedback on the product from the stakeholders before investing too much into it. Minimum Viable Product (MVP) is a Lean-Agile concept that is focused on delivering products with the minimum amount of features needed to make it functional. It allows early feedback on the product from the stakeholders before investing too much into it. Answer: B Answer: B
Exam 1 | #123. .Scrum is a very popular Agile framework; it consists of rules, roles, events, and artifacts. It is founded on three (3) pillars of empiricism. What are the three (3) pillars? |  | A-) Adaptation, Transparency, Customer Satisfaction | B-) Adaptation, Efficiency, Productivity | C-) Transparency, Adaptation, Inspection | D-) Inspection, Quality, Customer Collaboration | Answer: C | As defined in Scrum, the empirical process consists of three (3) Agile pillars: Transparency, Adaptation, and Inspection. As defined in Scrum, the empirical process consists of three (3) Agile pillars: Transparency, Adaptation, and Inspection. Answer: C Answer: C
Exam 1 | #124. .There are five prospective projects on the agenda of your company. Your sponsor has asked you to use the payback period method as a selection criterion to select among five competing projects. All of the following statements related to the payback period are correct EXCEPT: |  | A-) The payback period is the number of years required to get back the initial investment in the project. | B-) The payback period is a project selection criterion widely used in conjunction with NPV and IRR to determine the most suitable project. | C-) The initial investment in the project will not impact the selection criteria when the payback period is used for project selection. | D-) The payback period takes the discount rate into account to determine the best possible option. | Answer: D | The discount rate is not considered in calculations for the payback period. The discount rate is not considered in calculations for the payback period. Answer: D Answer: D
Exam 1 | #125. .You are the project manager of a twelve-million-dollar budget project. You have more than 100 stakeholders in your project, and you decided to classify the stakeholders of your project. All of the following are the classification models used for the stakeholder analysis EXCEPT: |  | A-) Power/interest grid | B-) Power/influence grid | C-) Organizational Level Model | D-) Salience Model | Answer: C | There are multiple classification models used for stakeholder analysis, such as: There are multiple classification models used for stakeholder analysis, such as: Power/interest grid Power/influence grid Influence/impact grid Salience model Power/interest grid Power/interest grid Power/influence grid Power/influence grid Influence/impact grid Influence/impact grid Salience model Salience model Answer: C Answer: C
Exam 1 | #126. .A multi-year, hybrid pharmaceutical project adds new fixed-date activities for the team to run Machine Learning (ML) processing of medical scans. The output from the ML analysis is used by an agile team of doctors to determine next steps in a patient case. The project manager has updated the scope statement and schedule. In which three other documents should the project manager record this new process? (Choose THREE.) |  | A-) Stakeholder Register | B-) Sprint Backlog | C-) Definition of Ready | D-) Risk Register | Answer: A, B, C | Stakeholder Register, Sprint Backlog and Definition of Ready Stakeholder Register, Sprint Backlog and Definition of Ready Answer: A, B, C Answer: A, B, C
Exam 1 | #127. .You are the project manager of a new hand cream development project. In the scope of the project, there is a “survey of the target audience requirement”. You decided to use a statistical sampling method to avoid the probable problems of surveying the entire population. All of the following are disadvantages of surveying the entire population EXCEPT: |  | A-) Very expensive | B-) Provides inaccurate data | C-) Takes longer time | D-) Needs more resources | Answer: B | Survey of the entire population provides the most accurate data. However surveying the entire population is expensive, takes a longer time, and needs many resources. Survey of the entire population provides the most accurate data. However surveying the entire population is expensive, takes a longer time, and needs many resources. Answer: B Answer: B
Exam 1 | #128. .You are in the process of determining whether to buy or make a software tool for your project. Which of the following documents will guide you for make-or-buy decisions? |  | A-) Risk management plan | B-) Procurement document | C-) Procurement management plan | D-) Request for Proposal | Answer: C | Procurement management plan can include guidance for many points. One of them is: Procurement management plan can include guidance for many points. One of them is: Handling the make-or-buy decisions and linking them into the Estimate Activity Resources and Develop Schedule processes Handling the make-or-buy decisions and linking them into the Estimate Activity Resources and Develop Schedule processes Handling the make-or-buy decisions and linking them into the Estimate Activity Resources and Develop Schedule processes Answer: C Answer: C
Exam 1 | #129. .You are the project manager of a renewable energy system and the customer of the project is the State of Delaware. In your project, to get the approval of the state management, you have to pay a fee. You should: |  | A-) Reject to pay the fee, because it is a bribe and unethical | B-) Share this information with your management and convince them to pay the fee | C-) Instead of paying the fee, tell the state officers that you can give gifts | D-) Pay the fee to proceed | Answer: D | A project manager has the responsibility to refrain from offering or accepting inappropriate payments, gifts, or other forms of compensation for personal gain unless it is in conformity with applicable laws or customs of the country where the project management services are provided. In this scenario, since the law of the country requires payment of the fee to the government agencies, you won’t be in breach of the Code if you pay the same. A project manager has the responsibility to refrain from offering or accepting inappropriate payments, gifts, or other forms of compensation for personal gain unless it is in conformity with applicable laws or customs of the country where the project management services are provided. In this scenario, since the law of the country requires payment of the fee to the government agencies, you won’t be in breach of the Code if you pay the same. Please note that fees are ethical but tips, bribes, and kickbacks are unethical. Please note that fees are ethical but tips, bribes, and kickbacks are unethical. Answer: D Answer: D
Exam 1 | #130. .Your company has assigned a configuration specialist for your project. She has completed the identification of all configuration items on the project and started reporting the status of those items. However, she hasn’t configured a key activity in the project. What is she supposed to do with this item? |  | A-) Validate the configuration item | B-) Report on the configuration status | C-) List the configuration item | D-) Verify and audit the configuration item. | Answer: D | Verification and audit are one of the three key activities under configuration management, apart from identification and reporting of configuration items. Verification and audit are one of the three key activities under configuration management, apart from identification and reporting of configuration items. Answer: D Answer: D
Exam 1 | #131. .You are carefully performing risk management for your project. But, there are still some risks that may happen in the future. You can handle these risks if you: |  | A-) Plan Risk Responses | B-) Monitor Risks | C-) Identify Risks | D-) Plan Risk Management | Answer: B | Monitor Risks is the process of controlling the implemented risk response plans and whether the plans gave the expected results (resolved the risks), tracking identified risks, monitoring residual risks, identifying new risks, and evaluating risk process effectiveness throughout the project. Monitor Risks is the process of controlling the implemented risk response plans and whether the plans gave the expected results (resolved the risks), tracking identified risks, monitoring residual risks, identifying new risks, and evaluating risk process effectiveness throughout the project. Answer: B Answer: B
Exam 1 | #132. .As a project manager, you establish clear expectations regarding acceptable behavior of the project team members. You believe that early commitment to clear guidelines will decrease misunderstanding and increase productivity. These expectations and guidelines are also known as: |  | A-) Ground rules | B-) Code of conduct | C-) Communication rules | D-) Team base rules | Answer: A | Ground rules establish clear expectations regarding acceptable behavior by project team members. An early commitment to clear guidelines decreases misunderstandings and increases productivity. Ground rules establish clear expectations regarding acceptable behavior by project team members. An early commitment to clear guidelines decreases misunderstandings and increases productivity. Answer: A Answer: A
Exam 1 | #133. .You are a project manager in a factory producing spare parts for automobiles. The project team has found some defective parts and figured out possible reasons causing these defects: the material type, the manufacturing machine, fault of the measurement system, or other factors. Which option is the best to find the reason for defects? |  | A-) Check sheet | B-) Flowchart | C-) Fishbone diagram | D-) Histogram | Answer: C | Cause-and-effect diagrams, which are also known as fishbone diagrams or Ishikawa diagrams. The problem statement placed at the head of the fishbone is a starting point to trace the problem’s source back to its actionable root cause. The problem statement typically describes the problem as a gap to be closed or as an objective to be achieved. The causes are found by looking at the problem statement and asking “why” until the actionable root cause has been identified or until the reasonable possibilities on each fishbone have been exhausted. Cause-and-effect diagrams, which are also known as fishbone diagrams or Ishikawa diagrams. The problem statement placed at the head of the fishbone is a starting point to trace the problem’s source back to its actionable root cause. The problem statement typically describes the problem as a gap to be closed or as an objective to be achieved. The causes are found by looking at the problem statement and asking “why” until the actionable root cause has been identified or until the reasonable possibilities on each fishbone have been exhausted. Answer: C Answer: C
Exam 1 | #134. .As a senior developer who already implemented MVP and MBI within your organization, you are also aware of the MMF (Minimum Marketable Feature) approach, and you want to propose it to the Product Owner and the development Team. What benefit is associated with the MMF approach? |  | A-) It is a technique used to advertise the value of the product with special emphasis on the feature that is more useful to the user. | B-) It is a technique used to implement the most in-demand features in the market since the customer expectations change constantly. | C-) It is a technique used to identify the smallest piece of functionality in a product that can be delivered to the client to demonstrate value. | D-) It is a technique used to identify the most wanted features in a product in order to set the marketing strategy into play. | Answer: C | Minimum Marketable Feature (MMF) is a Lean-Agile concept that is focused on finding the smallest piece of functionality that can be delivered to demonstrate value to the client in the market. Minimum Marketable Feature (MMF) is a Lean-Agile concept that is focused on finding the smallest piece of functionality that can be delivered to demonstrate value to the client in the market. Answer: C Answer: C
Exam 1 | #135. .Hope is a project manager for the IT team that manages corporate systems. A key stakeholder calls Hope to discuss the project and requests changes be made to several of the user stories on the product backlog. What is Hope’s BEST response? |  | A-) Inform the stakeholder that the changes have been made. | B-) Refer the request to the product owner. | C-) Let the stakeholder know the backlog has been prioritized and cannot be changed. | D-) Refer the request to the change control board. | Answer: B | The product owner is responsible for the backlog and will be the deciding party on changes made to it. The project manager does not have the authority to change the backlog and it is not within their authority to refuse additions or changes. There is no change control board for agile projects. The product owner is responsible for the backlog and will be the deciding party on changes made to it. The project manager does not have the authority to change the backlog and it is not within their authority to refuse additions or changes. There is no change control board for agile projects. Answer: B Answer: B
Exam 1 | #136. .As a project manager, you depend on effective working relationships and connections with colleagues or other partners to plan your work and make progress in the project. To make this happen, you also employ some web-based collaboration tools in your work. What type of organization are you working in? |  | A-) Functional organization | B-) Virtual organization | C-) Organic organization | D-) Matrix organization | Answer: B | In virtual organizations, people network with each other and use technology to collaborate. In virtual organizations, people network with each other and use technology to collaborate. Answer: B Answer: B
Exam 1 | #137. .John’s organization is transitioning from a predictive, planned-driven project management practice to an agile one. He will be managing the first project with the new model. What is the BEST way for John to proceed? |  | A-) John will determine which methodology to use in each phase of the project. | B-) The team will use both methodologies in each phase of the project. | C-) John will balance using both agile and predictive methodologies throughout the project, based on the needs of your organization. | D-) In the planning portion of each iteration, John will decide on which methodology to use for that iteration. | Answer: C | A hybrid approach, using both agile and predictive approaches, does not set a prescriptive way to proceed. The project manager and the stakeholders will determine which aspects of both methodologies work best for their organization and create a custom set of processes to follow. A hybrid approach, using both agile and predictive approaches, does not set a prescriptive way to proceed. The project manager and the stakeholders will determine which aspects of both methodologies work best for their organization and create a custom set of processes to follow. Answer: C Answer: C
Exam 1 | #138. .During the management of a project to build a high technology radar, you have encountered a serious problem. The state has passed emergency legislation that restricted some functions of the radar device. You need to make sure to start with modifications of the radar right away and they should be submitted before the radars are installed. This is a major change in the scope of the original plan, and it will significantly impact the project schedule and the budget. Considering all of the above, what is the best thing to do first |  | A-) Submit a change request | B-) Change the project management plan to reflect the impact of the changes | C-) Do a cost-benefit analysis | D-) Call a meeting with the key stakeholders to present this change in requirements and initiate a change request | Answer: D | Call a meeting with the key stakeholders to present this change in requirements and initiate a change request. This is an urgent situation due to changes in the legal environment which has high-impact risks on the project as a whole. Call a meeting with the key stakeholders to present this change in requirements and initiate a change request. This is an urgent situation due to changes in the legal environment which has high-impact risks on the project as a whole. Answer: D Answer: D
Exam 1 | #139. .You have been working on a project for the last six months. Your management lets you know that you will receive an incentive of $5,000 if you complete the project one month ahead of schedule. When closing the project ahead of the schedule, your team informs you that the product contains a minor flaw and may not fully satisfy the customer`s needs. However, the rectification of the minor flaw will require a lot of changes and it will take two more months. In this context, you will: |  | A-) Review the situation with your customer and sponsor. | B-) Close out the project. | C-) Rectify the flaw and then close out the project. | D-) Close the project and then inform the sponsor about the flaw. | Answer: A | Option A: Since this is a “minor flaw,” but the rectification of that flaw would take a long time, it is better to discuss with the sponsor and customer and get their inputs. Option A: Since this is a “minor flaw,” but the rectification of that flaw would take a long time, it is better to discuss with the sponsor and customer and get their inputs. Options B and D: This is unethical – the project manager should definitely complete the project as per the specifications before closing the project. Options B and D: This is unethical – the project manager should definitely complete the project as per the specifications before closing the project. Option C: Rectification of a minor flaw can lead to a delay of 2 months in the project: so, the project manager should first inform the sponsor and customer before rectification of the flaw. Option C: Rectification of a minor flaw can lead to a delay of 2 months in the project: so, the project manager should first inform the sponsor and customer before rectification of the flaw. Answer: A Answer: A
Exam 1 | #140. .Your company decided to develop a new cell phone model. They have compared their current cell phone’s features with the competitors’ features. Then, they identified the best practices of their current cell phone and found new ideas for improvement. Your company used the following method to make a decision: |  | A-) Prototypes | B-) Benchmarking | C-) Questionnaires and surveys | D-) Requirement documentation | Answer: B | Benchmarking involves comparing actual or planned practices, such as processes and operations, to those or comparable organizations to identify best practices, generate ideas from improvement, and provide a basis for measuring performance. The organizations compared during benchmarking can be internal or external. Benchmarking involves comparing actual or planned practices, such as processes and operations, to those or comparable organizations to identify best practices, generate ideas from improvement, and provide a basis for measuring performance. The organizations compared during benchmarking can be internal or external. Answer: B Answer: B
Exam 1 | #141. .You are working with the supplies of your project regarding the materials needed for your project. All of the following regarding Procurement Negotiations is true EXCEPT: |  | A-) Negotiations are completed when the contract document is signed and can be executed only by the buyer. | B-) Procurement negotiations clarify the structure, requirements, and other terms of the purchases. | C-) Final contract reflects all agreements that have been reached. | D-) The project manager may not be the lead negotiator on procurements. | Answer: A | Negotiations conclude with a contract document that can be executed by both buyer and seller. Negotiations conclude with a contract document that can be executed by both buyer and seller. Answer: A Answer: A
Exam 1 | #142. .An international humanitarian organization is managing a hybrid project that combines many brief administrative tasks with small-scale public work. An agile track makes good progress on key objectives, but small tasks are accumulating in the backlog. Most tasks can be done in one day but are dependent on unpredictable triggering events. Which approach would be most effective to clear out these minor tasks faster? |  | A-) Combine multiple minor tasks to make story sizes consistent with key objectives. | B-) Reprioritize the backlog to favor the smallest stories and re-assign them daily. | C-) Daily reprioritize the backlog so that recent triggers boost story priority. | D-) Integrate the small tasks to either the Definition of Done or acceptance criteria. | Answer: D | Integrate the small tasks to either the Definition of Done or acceptance criteria. Integrate the small tasks to either the Definition of Done or acceptance criteria. Answer: D Answer: D
Exam 1 | #143. .Stakeholder engagement is critical to project success. Your project is about “changing the software development environment in a company”. When the project is completed, the new environment may lessen the authority of the expert developer. Because of this, the expert developer is always opposing the project and changes on every platform. The engagement level of this developer is: |  | A-) Unaware | B-) Neutral | C-) Resistant | D-) Leading | Answer: C | The current engagement levels of all stakeholders need to be compared to the planned engagement levels required for successful project completion. Stakeholder engagement throughout the life cycle of the project is critical to project success. The engagement level of the stakeholders can be classified as follows: The current engagement levels of all stakeholders need to be compared to the planned engagement levels required for successful project completion. Stakeholder engagement throughout the life cycle of the project is critical to project success. The engagement level of the stakeholders can be classified as follows: Unaware. Unaware of the project and potential impacts. Resistant. Aware of the project and potential impacts and resistance to change. Neutral. Aware of the project yet neither supportive nor resistant. Supportive. Aware of the project and potential impacts and supportive to change. Leading. Aware of the project and potential impacts and actively engaged in ensuring the project is a success. Unaware. Unaware of the project and potential impacts. Unaware. Unaware of the project and potential impacts. Resistant. Aware of the project and potential impacts and resistance to change. Resistant. Aware of the project and potential impacts and resistance to change. Neutral. Aware of the project yet neither supportive nor resistant. Neutral. Aware of the project yet neither supportive nor resistant. Supportive. Aware of the project and potential impacts and supportive to change. Supportive. Aware of the project and potential impacts and supportive to change. Leading. Aware of the project and potential impacts and actively engaged in ensuring the project is a success. Leading. Aware of the project and potential impacts and actively engaged in ensuring the project is a success. The developer is aware of the project and potential impacts and is resisting this change. Thus, he is resistant. The developer is aware of the project and potential impacts and is resisting this change. Thus, he is resistant. Answer: C Answer: C
Exam 1 | #144. .You are a project manager in a construction company. You are aggregating the estimated costs of project activities to establish an authorized cost baseline. You are performing the ______ process. |  | A-) Control Costs | B-) Estimate Costs | C-) Determine Budget | D-) Estimate Activity Resources | Answer: C | Determine Budget is the process of aggregating the estimated costs of individual activities or work packages to establish an authorized cost baseline. Determine Budget is the process of aggregating the estimated costs of individual activities or work packages to establish an authorized cost baseline. Answer: C Answer: C
Exam 1 | #145. .You are a project manager trying to decide whether to buy or make a testing tool for your project. If you buy, the cost of the tool is $60,000, and the additional cost of integration is $1,000. If you build it, the tool will be developed by eight engineers in two months. The salary of each software engineer is $4,000 per month and the other related costs will be $2,000. Which option will you prefer? |  | A-) Buying the testing tool | B-) Building the testing tool | C-) Neither build nor buy the testing tool | D-) Need more information on costs to make a decision | Answer: A | Budget constraints may influence make-or-buy decisions. A make-or-buy analysis should consider all related costs- both direct costs as well as indirect costs. For example, the buy-side of the analysis includes both the actual out-of-pocket costs to purchase the product, as well as the indirect costs of support/maintenance of the purchasing process and purchased item. Budget constraints may influence make-or-buy decisions. A make-or-buy analysis should consider all related costs- both direct costs as well as indirect costs. For example, the buy-side of the analysis includes both the actual out-of-pocket costs to purchase the product, as well as the indirect costs of support/maintenance of the purchasing process and purchased item. Cost of buying the tool: $60,000 $1000 = $61,000 Cost of buying the tool: $60,000 $1000 = $61,000 Cost of building the tool: $4,000 x 8 engineers x 2 months $2,000 (relevant costs) = $66,000 Cost of building the tool: $4,000 x 8 engineers x 2 months $2,000 (relevant costs) = $66,000 So, buying is cheaper than building. Buying is more reasonable. So, buying is cheaper than building. Buying is more reasonable. Answer: A Answer: A
Exam 1 | #146. .You are working in an information technology company. All big projects go through Initiation, Analysis, Design, Implementation, Testing, and Closure steps in your organization and each of these steps is called a phase. Thus, a project life cycle: |  | A-) Defines the product life cycle | B-) Defines the project phases | C-) Contains more than one product life cycle | D-) Has deliverables that must be completed before the start date of the next phase | Answer: B | A project life cycle is the series of phases that a project passes through from its initiation to its closure. The phases are generally sequential, and their names and numbers are determined by the management and control needs of the organization or organizations involved in the project, the nature of the project itself, and its area of application. A project life cycle is the series of phases that a project passes through from its initiation to its closure. The phases are generally sequential, and their names and numbers are determined by the management and control needs of the organization or organizations involved in the project, the nature of the project itself, and its area of application. Answer: B Answer: B
Exam 1 | #147. .You are the project manager of a hydroelectric power plant construction project. According to the government regulations, you must ensure the neighborhood will not be adversely affected by the construction. For your project, this regulation is considered to be a/an: |  | A-) Assumption | B-) Ethical Practice | C-) Activity | D-) Constraint | Answer: D | Project constraint is a limiting factor that affects the execution of a project, program, portfolio, or process. At this point, government regulations are constraints for your project. Project constraint is a limiting factor that affects the execution of a project, program, portfolio, or process. At this point, government regulations are constraints for your project. Answer: D Answer: D
Exam 1 | #148. .You are performing the plan resource management process of a project which has over 800 team members. You would like to use a common template to shorten the amount of time, cost, and effort needed to create the resource management plan. Thus, you aim to improve planning efficiency. In this context, you will need to employ the following theory: |  | A-) Theory Y | B-) Organizational theory | C-) Motivation theory | D-) Human resource management theory | Answer: B | The organizational theory provides information regarding the way in which people, teams, and organizational units behave. Effective use of common themes identified in organizational theory can shorten the amount of time, cost, and effort needed to create the Plan Resource Management process outputs and improve planning efficiency. The organizational theory provides information regarding the way in which people, teams, and organizational units behave. Effective use of common themes identified in organizational theory can shorten the amount of time, cost, and effort needed to create the Plan Resource Management process outputs and improve planning efficiency. Answer: B Answer: B
Exam 1 | #149. .Your team thinks that you’re fast-tracking the sprint review ceremony in your current project. As you have a one-week sprint rhythm at the moment, what would be the appropriate sprint review timebox for a two-week sprint? |  | A-) Four-hour timebox | B-) One-hour timebox | C-) Two-hour timebox | D-) Three-hour timebox | Answer: C | Many teams have found the one-hour-per-sprint-week rule helpful. Many teams have found the one-hour-per-sprint-week rule helpful. Answer: C Answer: C
Exam 1 | #150. .When you are performing the Monitor and Control Risks process for your project, you are always on alert for indications that risk has occurred or is about to occur. These indications can be called as: |  | A-) Risk triggers | B-) Warning signs | C-) Risk symptoms | D-) All of the above | Answer: D | When you are performing the Monitor and Control Risks process for your project, you are always on alert for indications that risk has occurred or is about to occur. These indications are called risk triggers or warning signs or symptoms. When you are performing the Monitor and Control Risks process for your project, you are always on alert for indications that risk has occurred or is about to occur. These indications are called risk triggers or warning signs or symptoms. Answer: D Answer: D
Exam 1 | #151. .The customer requests a change in the technical approach for a product in development. The project manager learns about this request during the Sprint review meeting. How should the project manager respond? |  | A-) Work with team members to immediately implement the new approach. | B-) Let the team decide on the appropriate approach, giving them authority to implement and validate their decision in talks with stakeholders. | C-) Discuss the pros and cons of the proposed approach with stakeholders, then select the approach that is best for the team and notify team members. | D-) Allow the team to benchmark the approach. | Answer: B | As this is a technical issue, the project manager should discuss the request with the team and empower them to assess and select the best options to solve the customer’s request and communicate it with them. As this is a technical issue, the project manager should discuss the request with the team and empower them to assess and select the best options to solve the customer’s request and communicate it with them. Answer: B Answer: B
Exam 1 | #152. .Paola is an experienced Scrum Master. She has successfully coached and mentored many teams to deliver their projects using the Agile methodology. She has been praised for her knowledge and ability to teach new skills. During her coaching sessions, many new team members confuse the terms “incremental delivery'' and “iterative delivery”. What does Incremental delivery mean? |  | A-) Delivering nonfunctional increments in the iteration retrospectives | B-) Releasing working software only after testing each increment | C-) Improving and elaborating the agile process with each delivery | D-) Deploying functional increments over the course of the project | Answer: D | Incremental delivery means that we deploy functional increments over the course of the project. It does not relate to retrospectives, testing, or changes to the process, so the other options are incorrect, or “less correct”. Incremental delivery means that we deploy functional increments over the course of the project. It does not relate to retrospectives, testing, or changes to the process, so the other options are incorrect, or “less correct”. Answer: D Answer: D
Exam 1 | #153. .Working in a Scrum team means that you need to be very closely aligned with your customers, sponsors, vendors. For that reason, you will need to create a well-developed and reliable document. After you create this document, you should perform a stakeholder analysis. Where would you save that information? |  | A-) Stakeholder register | B-) Impediment backlog | C-) Information radiator | D-) Backlog | Answer: A | One of the activities that help is a process known as stakeholder analysis. When performing stakeholder analysis, the stakeholders are identified, and their interest in the project is understood. All of this information is captured in a stakeholder register, which is a simple artifact. One of the activities that help is a process known as stakeholder analysis. When performing stakeholder analysis, the stakeholders are identified, and their interest in the project is understood. All of this information is captured in a stakeholder register, which is a simple artifact. Answer: A Answer: A
Exam 1 | #154. .During estimating activity costs, (e.g. the unit cost rates) all the following can be used EXCEPT: |  | A-) Gathering quotes | B-) Funding requirements | C-) The statistical relationship between historical data and other variables | D-) Commercial databases | Answer: B | Project funding requirements are irrelevant to estimating activity costs. Funding for a project does not affect the activity costs. Project funding requirements are irrelevant to estimating activity costs. Funding for a project does not affect the activity costs. Answer: B Answer: B
Exam 1 | #155. .Work performance reports are the physical or electronic representation of work performance information compiled in project documents, intended to generate decisions, actions, or awareness. All of the following can be used as work performance reports EXCEPT: |  | A-) Control charts | B-) Status reports | C-) Memos | D-) Justifications | Answer: A | Examples of work performance reports include status reports, memos, justifications, information notes, recommendations and updates. Control charts are used to measure quality related issues (in control and out of control data). Examples of work performance reports include status reports, memos, justifications, information notes, recommendations and updates. Control charts are used to measure quality related issues (in control and out of control data). Answer: A Answer: A
Exam 1 | #156. .There are three projects that are possible to be executed in your company: Project A: Payback period= 6 years & NPV = $ 3,000,000 Project B: Payback period=4 years & NPV = $ 2,000,000 Project C: Payback period=2 years & NPV = $ 1,000,000 Based on the Net Present Value (NPV) criterion, which project should be selected? |  | A-) Project A | B-) Project B | C-) Project C | D-) None of them, they all have an equal value | Answer: A | Project A has the highest NPV of $ 3,000,000. The time value of money is already considered when calculating the NPV of a project. Since Project A has the highest NPV, it should be selected. Project A has the highest NPV of $ 3,000,000. The time value of money is already considered when calculating the NPV of a project. Since Project A has the highest NPV, it should be selected. Answer: A Answer: A
Exam 1 | #157. .You are working as a project manager in a company. You have the highest degree of authority, you are working full-time for your project and you manage the budget of the project. What is the organizational structure of your company? |  | A-) Strong Matrix | B-) Projectized | C-) Functional | D-) Balanced Matrix | Answer: B | In a projectized organizational structure, the project manager has the highest level of authority, works full-time, and manages the budget of the project. In a projectized organizational structure, the project manager has the highest level of authority, works full-time, and manages the budget of the project. Answer: B Answer: B | images/image6.jpg
Exam 1 | #158. .Quality is an important concept to determine a project’s success in your company. In this context, all the following are examples of cost of conformance EXCEPT: |  | A-) Training | B-) Testing | C-) Inspections | D-) Rework | Answer: D | Cost of quality includes all costs incurred over the life of the product by investment in preventing nonconformance to requirements, appraising the product or service for conformance to requirements, and failing to meet requirements (rework). The following figure shows examples of the cost of conformance and cost of nonconformance. Cost of quality includes all costs incurred over the life of the product by investment in preventing nonconformance to requirements, appraising the product or service for conformance to requirements, and failing to meet requirements (rework). The following figure shows examples of the cost of conformance and cost of nonconformance. Answer: D Answer: D | images/image7.jpg
Exam 1 | #159. .In your project, you will share the confidential data of your company with the vendor. Which of the following should you do? |  | A-) Sign a non-disclosure agreement with the vendor before you share the information | B-) Sign a non-disclosure agreement with the vendor after you share the information | C-) Threaten the vendor that if the shared information is disclosed, the contract will be terminated | D-) Get a verbal promise from the vendor that the confidential information will not be disclosed | Answer: A | You need to sign a non-disclosure agreement before you share the confidential information of your company. You need to sign a non-disclosure agreement before you share the confidential information of your company. Answer: A Answer: A
Exam 1 | #160. .You are meeting your former colleague with whom you have worked on many predictive projects. He has heard that you have been working on Agile projects now and wants to discuss with you if there are any differences in the scope management practices of predictive and Agile life cycles? You answer the following: |  | A-) Only a predictive life cycle utilizes scope validation and scope control processes. | B-) Scope changes occur only in Agile life cycles. | C-) Requirements collection, scope definition, and WBS creation are done once in a predictive life cycle, unless changes occur, and once for each iteration in an Agile life cycle. | D-) Scope validation and scope control are done only once in an iterative life cycle. | Answer: C | C is the only correct statement. All others are incorrect. C is the only correct statement. All others are incorrect. Answer: C Answer: C
Exam 1 | #161. .Attached are the four tasks which are in the critical path of your project. Each of these four tasks requires 10 days of work effort and $10,000 cost. At the end of day 25, Task A and B are complete; Task C is 20% complete, and $21,000 has been spent in total. What is the status of the project? | images/image8.jpg | A-) Behind schedule, under budget | B-) Ahead of schedule, under budget | C-) Ahead of schedule, over budget | D-) Behind schedule, over budget | Answer: A | Earned value (EV) Earned value (EV) = The sum of the approved cost estimates for activities completed during a given period = The sum of the approved cost estimates for activities completed during a given period = Estimated cost of work that is completed after day 25 = Estimated cost of work that is completed after day 25 = $10,000 $10,000 ($10,000*0.20) = $22,000 (because Task A, Task B are complete, Task C is 20% complete) = $10,000 $10,000 ($10,000*0.20) = $22,000 (because Task A, Task B are complete, Task C is 20% complete) Present value (PV) Present value (PV) = Present work to be completed after day 25 = Present work to be completed after day 25 = $10,000 $10,000 ($10,000 *0.50) (because at end of day 25, according to our plan, Task A, Task B should be complete; and half of Task C, 5 days out of 10 days, should be complete, i.e., 50% complete ($ 5,000 of work should be done) = $10,000 $10,000 ($10,000 *0.50) (because at end of day 25, according to our plan, Task A, Task B should be complete; and half of Task C, 5 days out of 10 days, should be complete, i.e., 50% complete ($ 5,000 of work should be done) = $25,000. = $25,000. Actual cost (AC) Actual cost (AC) = Actual Cost of work completed = Actual Cost of work completed = $21,000 = $21,000 Schedule variance (SV) Schedule variance (SV) = EV – PV = $22,000 – $25,000 = -$3,000 = EV – PV = $22,000 – $25,000 = -$3,000 Since SV is negative, the project is behind schedule. Since SV is negative, the project is behind schedule. Cost variance (CV) Cost variance (CV) = EV – AC = $22,000 – $21,000 = $1000 = EV – AC = $22,000 – $21,000 = $1000 Since CV is positive, the project is under budget. Since CV is positive, the project is under budget. Answer: A Answer: A
Exam 1 | #162. .You are a project manager in a bicycle manufacturing company. Due to the recent flood in their region, RuBrake Inc. could not supply the rubber required for the bicycle brake mechanism on time. You expected this risk, registered it earlier, and based on your risk response plan, your team started to use rubber delivered one year ago. However, this response brought another risk – old rubber has higher fracture rates during implementation to the brake system. This new risk is called: |  | A-) Secondary risk | B-) Residual risk | C-) Contingency plan | D-) Unmanageable risks | Answer: A | Secondary risks are the risks that arise as a direct result of implementing a risk response Secondary risks are the risks that arise as a direct result of implementing a risk response Answer: A Answer: A
Exam 1 | #163. .During the meetings with your customer, you have agreed that the functional testing of your project will be executed by the customer’s test engineers. In your project scope statement, you explicitly define that the functional testing is out of scope for this project. This is an example of: |  | A-) Constraint | B-) Project exclusion | C-) Assumption | D-) Acceptance Criteria | Answer: B | Project Exclusion generally identifies what is excluded from the project. Explicitly stating what is out of scope for the project helps to manage stakeholder’s expectations. Project Exclusion generally identifies what is excluded from the project. Explicitly stating what is out of scope for the project helps to manage stakeholder’s expectations. Answer: B Answer: B
Exam 1 | #164. .As a project manager, you know that identifying the stakeholders that could impact your project is critical. In this context, which of the following is true? |  | A-) Stakeholder identification is done during the Planning of the project | B-) Stakeholder identification is done during the Execution of the project | C-) Stakeholder identification is done during the Initiation of the project | D-) Stakeholder identification might occur during different project stages | Answer: D | Stakeholders are first identified in the Initiation of the project (Initiation Process Group). However, the stakeholders are identified all throughout the project, at different stages and phases. Stakeholders are first identified in the Initiation of the project (Initiation Process Group). However, the stakeholders are identified all throughout the project, at different stages and phases. Answer: D Answer: D
Exam 1 | #165. .In your project, you are in the plan resource management process. All of the following affect this process as enterprise environmental factors EXCEPT: |  | A-) Lessons learned documentation | B-) Organizational culture and structure | C-) Geographical dispersion of team members | D-) Marketplace conditions | Answer: A | The enterprise environmental factors that can influence the process of planning for Resource Management include, but are not limited to: The enterprise environmental factors that can influence the process of planning for Resource Management include, but are not limited to: Organizational culture and structure Existing human resources Geographical dispersion of team members Personnel administration policies Marketplace conditions Organizational culture and structure Organizational culture and structure Existing human resources Existing human resources Geographical dispersion of team members Geographical dispersion of team members Personnel administration policies Personnel administration policies Marketplace conditions Marketplace conditions Answer: A Answer: A
Exam 1 | #166. .You believe in assigning “SMART” objectives to your team members. Letters of SMART stands for all of the following EXCEPT: |  | A-) Specific | B-) Measurable | C-) Achievable | D-) Trusted | Answer: D | SMART is a mnemonic acronym giving criteria to guide in the setting of objectives in project management. Letters are standing for Specific, Measurable, Achievable/Attainable, Relevant, and Time-specific respectively. SMART is a mnemonic acronym giving criteria to guide in the setting of objectives in project management. Letters are standing for Specific, Measurable, Achievable/Attainable, Relevant, and Time-specific respectively. Answer: D Answer: D
Exam 1 | #167. .You are working with a Project Manager who is highly motivated and focused on getting things done. Most of your team consists of volunteers and he has been very successful in managing them effectively. He takes the tasks in hand, he is available on the field to guide the young volunteers to develop their skills. The team members are encouraged to make their own decisions, but they know that the Project Manager is always there to support and back them up. Which of the following is his leadership style? |  | A-) Charismatic Leadership | B-) Inspirational Leadership | C-) Servant Leadership | D-) Delegate Leadership | Answer: C | Servant leader demonstrates a commitment to serve and put other people ﬁrst; focuses on other people’s growth, learning, development, concentrates on relationships, community, and collaboration; leadership is secondary and emerges after service. Servant leader demonstrates a commitment to serve and put other people ﬁrst; focuses on other people’s growth, learning, development, concentrates on relationships, community, and collaboration; leadership is secondary and emerges after service. Answer: C Answer: C
Exam 1 | #168. .A knowledge conference is in progress as part of your project. There are a lot of discussions in various rooms to share knowledge and create new knowledge. There are a lot of different tools that are used for the same purpose. What category of tools are they part of? |  | A-) Information management | B-) Knowledge management | C-) Knowledge process management | D-) Knowledge fair management | Answer: B | Knowledge management connects people to share and create knowledge. Information management creates information and connects people to that information. For example, lessons learned register. Knowledge management connects people to share and create knowledge. Information management creates information and connects people to that information. For example, lessons learned register. Answer: B Answer: B
Exam 1 | #169. .As a project manager, you are about to hand over the final deliverables of your project. The customer comes with a request which will result in a major scope change. You should: |  | A-) Tell the customer that this change is impossible at this time | B-) Deliver the required change | C-) Evaluate the impact of the change and then share with the customer | D-) Escalate the issue to the senior management since the customer will not accept the product | Answer: C | If there is a change in the scope, the following steps should be followed in sequence If there is a change in the scope, the following steps should be followed in sequence Evaluate the impact of the change within the team. Help the customer to understand the impact of the change. If the changes are required, proceed to the change control board. Obviously, you will have to inform the management and the change control board about the impact of the changes. If the change control board approves changes, then implement the changes by updating the necessary documents in the project plan. Evaluate the impact of the change within the team. Evaluate the impact of the change within the team. Help the customer to understand the impact of the change. Help the customer to understand the impact of the change. If the changes are required, proceed to the change control board. Obviously, you will have to inform the management and the change control board about the impact of the changes. If the changes are required, proceed to the change control board. Obviously, you will have to inform the management and the change control board about the impact of the changes. If the change control board approves changes, then implement the changes by updating the necessary documents in the project plan. If the change control board approves changes, then implement the changes by updating the necessary documents in the project plan. Answer: C Answer: C
Exam 1 | #170. .A merger of two companies results in combining an agile software project and a predictive electronics project into a single hybrid project. Two months later, requirements have changed in both tracks but neither has a full picture on status or importance of the requirements. How can the project manager best resolve the problem? |  | A-) Integrate the product backlog into the requirements specification and educate the software team on working with the new document. | B-) Create a requirements traceability matrix by combining the product backlog with the requirements specification and define both documents as input. | C-) Integrate the requirements specification into the product backlog and educate the electronics team on working with the new document. | D-) Integrate the revised work packages and updated product backlog items into a new master WBS for progress tracking. | Answer: B | Create a requirements traceability matrix by combining the product backlog with the requirements specification and define both documents as input. Create a requirements traceability matrix by combining the product backlog with the requirements specification and define both documents as input. Answer: B Answer: B
Exam 1 | #171. .A project manager is managing a new product. The project requires knowledge of the Kanban approach, but existing team members have no experience in the use of the Kanban approach. What should the project manager do to engage the team in work relating to Kanban? |  | A-) Tell senior management this is impossible | B-) Increase the timebox for the daily standup to 30 minutes, so the team members can learn more about how to use the Kanban approach | C-) Provide training and workshop session on the Kanban so the team members can learn how to use it | D-) Remove team members from the project, to acquire more skilled resources | Answer: C | Teams with little experience will need guidance and assistance with breaking down backlog items, estimating activities, and determining which tasks can be completed in an iteration. An approach to help train and support inexperienced teams is to establish agile centers of excellence where best practices, training, access to experienced team members, and support are available to help build their knowledge in agile processes and provide guidance. In an exam, in case team members are inexperienced in Agile approaches, consider starting by training team members in the fundamentals of the agile mindset and principles first. If the team decides to use a specific agile approach (Scrum, Kanban, XP, etc.), provide a workshop on that approach so the team members can learn how to use it. Option B is incorrect because Kanban, unlike other approaches, does not prescribe the use of timeboxed iterations. Iterations can be used within the Kanban method, but the principle of pulling single items through the process continuously and limiting work in progress (WIP) to optimize flow should always remain intact. Teams with little experience will need guidance and assistance with breaking down backlog items, estimating activities, and determining which tasks can be completed in an iteration. An approach to help train and support inexperienced teams is to establish agile centers of excellence where best practices, training, access to experienced team members, and support are available to help build their knowledge in agile processes and provide guidance. In an exam, in case team members are inexperienced in Agile approaches, consider starting by training team members in the fundamentals of the agile mindset and principles first. If the team decides to use a specific agile approach (Scrum, Kanban, XP, etc.), provide a workshop on that approach so the team members can learn how to use it. Option B is incorrect because Kanban, unlike other approaches, does not prescribe the use of timeboxed iterations. Iterations can be used within the Kanban method, but the principle of pulling single items through the process continuously and limiting work in progress (WIP) to optimize flow should always remain intact. Answer: C Answer: C
Exam 1 | #172. .Your company is deciding to switch to Agile. Some stakeholders are out of their comfort zone and are resistant to the change. What are the best activities to help senior management transition to Agile? |  | A-) Start the hiring process for a new team, replacing the existing one | B-) Issue a memo of understanding that agile principles should be implemented for all new projects | C-) Acquire an Agile Coach to train all staff and management teams | D-) No special activities are necessary, because these stakeholders will embrace the change | Answer: C | Proper training helps the team to achieve a common understanding of the process. Coaching skills bring to the team a new set of tools and processes, allowing them to execute the Agile process. Coaching is recommended to help with any company transition, and following the transition, responsibilities are often assigned to an assigned Scrum Master. Proper training helps the team to achieve a common understanding of the process. Coaching skills bring to the team a new set of tools and processes, allowing them to execute the Agile process. Coaching is recommended to help with any company transition, and following the transition, responsibilities are often assigned to an assigned Scrum Master. Answer: C Answer: C
Exam 1 | #173. .An organization adopts Agile practices and implements a Kanban methodology. The project manager learns that the customer wants an earlier completion date of the product without incurring additional costs. Which of the following considerations will the project manager mainly be concerned with? |  | A-) Working overtime | B-) Adding more resources | C-) Reducing lead time | D-) Increasing lead time | Answer: C | Most organizations want to get work done fast with as little cost as possible. Usually, the most effective way to get work done faster is to smooth out the flow and limit work to capacity, and not additional resources. Lead time = WIP/throughput. Lead time is affected by the increase or decrease of either WIP or throughput. If we assume throughput remains constant, increasing WIP will increase lead time. Decreasing it will reduce lead time. Also, inversely, if we assume WIP remains constant, increasing throughput will reduce lead time. Decreasing throughput will increase lead time. Most organizations want to get work done fast with as little cost as possible. Usually, the most effective way to get work done faster is to smooth out the flow and limit work to capacity, and not additional resources. Lead time = WIP/throughput. Lead time is affected by the increase or decrease of either WIP or throughput. If we assume throughput remains constant, increasing WIP will increase lead time. Decreasing it will reduce lead time. Also, inversely, if we assume WIP remains constant, increasing throughput will reduce lead time. Decreasing throughput will increase lead time. Answer: C Answer: C
Exam 1 | #174. .You have completed your project and delivered the project products to your customer. The customer completed quality tests, and the products did not meet their requirements. Based on your agreement with your customer, you must collect the defective parts and deliver the new ones. This is an example of: |  | A-) Prevention Costs | B-) Appraisal Costs | C-) Failure costs | D-) Cost of Conformance | Answer: C | The cost of quality includes all costs incurred over the life of the product by investment in preventing nonconformance to requirements, appraising the product or service for conformance to requirements, and failing to meet requirements (rework). The following figure shows examples of the cost of conformance and the cost of nonconformance. The cost of quality includes all costs incurred over the life of the product by investment in preventing nonconformance to requirements, appraising the product or service for conformance to requirements, and failing to meet requirements (rework). The following figure shows examples of the cost of conformance and the cost of nonconformance. Answer: C Answer: C | images/image9.jpg
Exam 1 | #175. .The customer of a large import-export company makes an urgent call to you and asks for a face to face meeting the next day. At the meeting, he informs you that there is a wide-spread political unrest in one of the countries where you are managing projects and he found out that the situation will deteriorate soon. After assessing the situation, you decide to prioritize the scope of the project to deliver the most important requirements first. What should you do as a project manager in this situation? |  | A-) Tell the client that you will terminate the project | B-) Discuss the situation with senior management | C-) Continue with the project as if nothing has happened | D-) Fast-track critical activities | Answer: D | Fast-track critical activities. Fast-tracking means performing activities on the critical path in an overlapping, or partially overlapping fashion, instead of sequentially. Overlapping the activities helps shorten the project schedule and finish the project earlier than planned. Fast-track critical activities. Fast-tracking means performing activities on the critical path in an overlapping, or partially overlapping fashion, instead of sequentially. Overlapping the activities helps shorten the project schedule and finish the project earlier than planned. Answer: D Answer: D
Exam 1 | #176. .All of the following statements regarding the activity duration estimates are correct EXCEPT: |  | A-) Mathematical analyses like CPM, GERT, and PERT indicate the dates when the activity can be scheduled, given resource limitations and other constraints. | B-) Schedule compression techniques, including fast-tracking and crashing, can help in decreasing the project duration. | C-) The duration of the project is the sum of the duration of all the tasks in the project. | D-) WBS classification allows useful activity ordering and sorting. | Answer: C | The duration of the project is calculated by the sum of the activities’ duration on the critical path only. The duration of the project is calculated by the sum of the activities’ duration on the critical path only. Answer: C Answer: C
Exam 1 | #177. .In a project, the customer may not be satisfied with the quality of the delivered product. These failure costs found by the customer are also known as: |  | A-) Quality cost | B-) Cost of conformance | C-) Change cost | D-) Cost of poor quality | Answer: D | Failure costs are often categorized as internal (found by the project) and external (found by the customer). Failure costs are also known as the cost of poor quality. Failure costs are often categorized as internal (found by the project) and external (found by the customer). Failure costs are also known as the cost of poor quality. Answer: D Answer: D
Exam 1 | #178. .You are working as a Project Manager at Maxim International and you have been repeatedly contacted by the customer to modify the deliverables. These modifications are beyond the scope of the project. You have explained twice to the customer’s Project Manager that these modifications were specifically clarified during planning and that they will not be included in the project scope. However, he is insisting that modifications are included in the original scope of the work. Which document would help you as a proof to support your argument? |  | A-) Requirements Documentation | B-) WBS | C-) WBS Dictionary | D-) Project Scope Statement | Answer: D | Project Scope Statement includes “Project exclusions” which identifies what is excluded from the project. This document should explicitly state what is out of scope for the project. Project Scope Statement includes “Project exclusions” which identifies what is excluded from the project. This document should explicitly state what is out of scope for the project. Answer: D Answer: D
Exam 1 | #179. .As a Project Manager, you are concerned because the variance analysis for the last three months has shown that the performance of scope and cost is going much behind the plan. Based on these past results, you have prepared a cost forecast so that a bad situation can be prevented in the future. Which technique has helped you prepare these forecasts? |  | A-) Earned value analysis | B-) Root cause analysis | C-) Trend analysis | D-) Variance analysis | Answer: C | Trend analysis is used to forecast future performance based on past results. It looks ahead in the project for expected slippages and warns the Project Manager ahead of time. Trend analysis is used to forecast future performance based on past results. It looks ahead in the project for expected slippages and warns the Project Manager ahead of time. Answer: C Answer: C
Exam 1 | #180. .Which of the following documents include the “code of account identifier”, “description of work”, “responsible organization”, and “list of schedule milestones”? |  | A-) PERT/CPM Charts | B-) WBS | C-) WBS Dictionary | D-) Roles and Responsibilities Matrix | Answer: C | The WBS dictionary is a document that provides detailed deliverables, activity, and scheduling information about each component in the WBS. WBS dictionary may include but is not limited to, code of account identifier, description of work, responsible organization, list of schedule milestones, etc. The WBS dictionary is a document that provides detailed deliverables, activity, and scheduling information about each component in the WBS. WBS dictionary may include but is not limited to, code of account identifier, description of work, responsible organization, list of schedule milestones, etc. Answer: C Answer: C

## exam2
Exam Name | Question | quesimgsrc | Answer1 | Answer2 | Answer3 | Answer4 | Correct-Answer | Explanation | answerimgsrc
Exam 2 | #1. Procurement audits review which of the following? |  | The procurement processes from Plan Procurement Management through Manage Procurements | The procurement processes from Plan Procurement Management through Control Procurements | The Plan Procurement Management and Conduct Procurements processes | The procurement processes from Plan Procurement Management through Close Project or Phase process | Answer b. | Answer b. The procurement processes from Plan Procurement Management through Control Procurements: Procurement Audits, which are Tool & Tech are structured reviews of the procurement process originating with Plan Procurement Management through Control Procurements. The objective of the audit identifies successes and failures to be used as lessons learned for other Procurement contracts on the project or projects within the performing organization. Answer a., is an incorrect choice as the audit reports are reviewed in Control Procurements. Answer c., is an incorrect choice as it excludes the Control Procurements process. Answer d., is incorrect as procurement audit is not done in the integration Knowledge area, and it should already be finished by the time the project enters Close Project or Phase.
Exam 2 | #2. Which of the following contract types needs to have clearly defined requirements at the time of contract signing? |  | Firm Fixed Price | Time and Material | Cost Reimbursable | CCP | Answer a. | Answer a. Firm Fixed Price: FFP contracts are typically used when there is a clear idea of what needs to be procured and the scope of the product will not change. The Price is known upfront and the seller is obligated to provide the product, service, or results as specified. Answers b., Time and Materials and c. Cost Reimbursable contracts are typically used when the buyer and seller need more latitude in providing goods or services contracted.
Exam 2 | #3. Tim is the Project Manager for the Doom Project. Two key team members have come to him for assistance in resolving their conflict. Tim intends to use a conflict resolution strategy that will result in what is frequently considered a win-win situation, in that the strategy’s goal is to achieve consensus and commitment from both parties. What type of conflict resolution strategy is described in this scenario? |  | Compromise/Reconcile | Force/Direct | Smooth/Accommodate | Collaborate/Problem Solve | Answer d. | Answer d. Collaborate/Problem Solve: option d., “Collaborate/Problem Solve,” is the correct answer here because it results in the optimal solution: consensus is achieved, and both parties are committed to the agreed-upon solution. Because of this outcome, it is also often considered a win-win resolution technique.
Exam 2 | #4. You have just been informed by the Project Sponsor that the customer intends to terminate the project in the middle of the execution. Which of the following will you do FIRST as a Project Manager? |  | Share this information with all stakeholders by email | Evaluate the impact of project closure | Initiate the Close Project or Phase process | Meet the sponsor to discuss the course of actions | Answer b. | Answer b. (FIRST) Evaluate the impact of project closure: All four of the answers ultimately need to happen so the issue becomes one of prioritizing the order. The first step would be to evaluate the impact of project closure. While it may be brief, it allows for collecting impact data. As the Sponsor informed you about the termination, meeting with the sponsor to discuss the next steps (possible courses of action) would be a sound second step. Depending on the outcome of the PM’s meeting with the sponsor, the third step would be to initiate the Close Project or Phase process to minimize further costs in the project. Finally, sharing information with Stakeholders might be a logical fourth step.
Exam 2 | #5. __Analysis is a technique used to gather and analyze qualitative and quantitative information that can be used to determine whose interests need to be considered throughout the Project Life Cycle. |  | Stakeholder | Perform Qualitative Risk | Perform Quantitative Risk | Both b and c | Answer a. | Answer a. Stakeholder (Analysis): A Tool & Tech used in identifying, analyzing, assessing, qualifying, and quantifying Stakeholder attributes to determine how they can be leveraged or influenced to the advantage of the project. Answer options b., c., and d. can be removed from consideration as they are associated with the Risk Management Process.
Exam 2 | #6. A Project Manager is managing a project where there will be several people working together. She wants to enhance the ability of the team to work together. One of the things that could maximize the ability of the team to do this is . |  | Cohabitation | Colocation | Staffing Plan | Work Breakdown structure | Answer b. | Answer b. Colocation: Colocation is considered a Tool & Tech used in Developing Project Teams. Sometimes referred to as ‘tight matrix’ it places team members into a physical location to enhance their ability to perform as a team. The Staffing Plan and WBS can be eliminated from the available options because they are either inputs or Outputs, not tools. Cohabitation is a personal living arrangement and not mentioned in the PMBOK.
Exam 2 | #7. Scrum framework is based on Scrum artifacts which define the work that must be done and present the information that the Scrum team uses to detail the product being developed. From the selections below, which is the proper sequence for task decomposition from high level to detailed: |  | Epic, Theme, User Story, Task | Theme, Epic, User Story, Task | Task, Theme, User Story, Epic | User Story, Task, Epic, Theme | Answer b. | Answer b. In Scrum framework, the hierarchy of what needs to be done begins with Theme on the top; followed by Epic, which is a group of related user stories; followed by a User Story which is the smallest unit of work; followed by a Task, which is a decomposed part of a User Story.
Exam 2 | #8. You are writing down the requirements documentation. One of the stakeholders has asked you to ensure that the team working on the planning must be given 2 weeks training by an international consultant so that they are well equipped for the task. Which type of requirement category will be assigned to this specific training requirement? |  | Business requirements | Stakeholder requirements | Solution requirements | Transition and readiness requirements | Answer d. | Answer d. Transition and readiness requirements: Transition and readiness requirements describe temporary capabilities, such as data conversion and training requirements.
Exam 2 | #9. You are the Project Manager for a subway line construction project. While planning the project risks, which of the following will NOT you select as a strategy for dealing with negative risks or threats? |  | Exploit | Avoid | Transfer | Mitigate | Answer a. | Answer a. (Not) Exploit: The question asks for a strategy that is “NOT…a strategy for dealing with negative risks or threats” – in other words, which is a positive risk strategy. Exploit is the only positive risk strategy among the answer options. All the other strategies provided are strategies “for dealing with negative risks or threats.”
Exam 2 | #10. The Staffing Management Plan, which is part of the Resource Management Plan, describes when and how human resources requirements will be met. Information in the Staffing Management Plan may vary according to the application area and project size. A Staffing Management plan does not include . |  | Staff acquisition | Resource calendars | Compliance | Work Items | Answer d. | Answer d. (Except) Work Items: The Staffing Management Plan defines what resources will be required, how they will be acquired (a.), when and how long they will be needed. It must consider resource calendars (b.), training needs, Compliance (c.) with government regulations, union contracts and HR Policies (c.); recognition and rewards plan, safety concerns, and a release plan. The Staffing Management Plan is an Output of the Plan Resource Management process.
Exam 2 | #11. A Schedule Compression technique with overlapping phases or activities that would normally happen sequentially is known as ______ . |  | Crashing | Fast Tracking | Float | Lag | Answer b. | Answer b. Fast Tracking: Answer c., Float, and d., Lag are both Critical Path Method concepts, not Schedule Compression techniques, and can be eliminated as possible answers. Answer a., Crashing and b., Fast Tracking are the only two Schedule Compression techniques. Crashing is “used to shorten the schedule duration by adding resources”; b., Fast Tracking is a “Schedule Compression technique in which activities or phases that are normally done in sequence are performed in parallel.”
Exam 2 | #12. A radio equipment vendor is running a hybrid project which includes some custom software development by an agile team. The team is progressing well, but customer approvals are slow which causes unnecessary delays. The customer insists that approval can only be given after repeating all the test cases in their environment. How can the project manager accelerate the approvals and build customer trust at the same time? |  | Invite the customer to send representatives to witness the team's testing to pre-approve the tests. | Work out an arrangement with the customer to defer as many tests as possible to the final release. | Propose the team members to work aside the customer testers to run tests in their environment. | Allow the team to progress at their pace while the customer continues to test and approve earlier builds. | Answer c. | Answer c. Propose team members to work aside the customer testers to run tests in their environment.
Exam 2 | #13. An international project consists of 150 project team members around the world. Each project team will be upgrading a piece of software in different facilities. The Project Manager needs to address the quality of the overall delivery. Which of the following is the most suitable quality planning tool? |  | Work Breakdown Structure | Checklists | PND | WBS Dictionary | Answer b. | Answer b. Checklists: Through the process of elimination, answer options a., the WBS and d., the WBS Dictionary are Inputs or Outputs (not tools) and are removed from consideration. PND is not an acronym used in Project Management, the top 10 uses include Post Natal Depression, Portable Navigation Device, and Punk’s Not Dead but they don’t quite apply. Checklists are used as a tool in Quality to verify that a set of required steps has been performed.
Exam 2 | #15. Which of the following documents include detailed plans about how the Project Manager might manage stakeholders and their expectations? |  | Stakeholder Management Plan | Stakeholder Engagement Assessment Matrix | Stakeholder Register | Communication Management Plan | Answer a. | Answer a. Stakeholder Management Plan: Arriving at the correct answer to this question is a good example of how the process of elimination can be used effectively. First, focus on the words in the problem that might strike you as key: “detailed plans,” “manage stakeholders,” and “their expectations.” You should know that answer option b., “Stakeholder Engagement Assessment Matrix,” is used to identify the engagement levels of stakeholders – and it is a Tool/Technique, not a document. Option c., “Stakeholder Register,” is a document – but it is all about identifying stakeholders and their characteristics. And option d., “Communications Management Plan,” is certainly not “composed primarily of detailed plans as to how the Project Manager might manage stakeholders and their expectations.” The only viable answer option is a., Stakeholder Management Plan.
Exam 2 | #16. Which of the following is MOST true regarding the Code of Accounts? |  | It allows the breakdown level of the item in the resource breakdown structure to be easily identified. | It describes the coding structure used by the performing organization to report financial information in its general ledger | It is the collection of unique identifiers generally assigned to WBS items | It defines ethical behavior in the project and the responsibilities to the customer and the profession | Answer c. | Answer c. (MOST TRUE) It is the collection of unique identifiers generally assigned to WBS items: Answer d. is eliminated out of the gate. Answer b. defines what it is and how it is used. Answer a. is true in that it is a good way to ‘hone in’ on a desired element within the WBS. The PMBOK Glossary defines the Code of Accounts as the numbering system used to uniquely identify each component of the work breakdown structure (WBS).
Exam 2 | #17. Your team is beginning to transition to an Agile way of work. You have previously engaged the team in weekly meetings, with email as the primary communication. What changes will you make to create a team more suited to Agile? |  | Setup teleconference calls with different members of the project team | Co-locate the team where possible and focus on face-to-face communication | Create executive reports to provide to the Steering Committee | Schedule recurring one-on-one sessions with each project team member to collect project status and feedback. | Answer b. | Answer b. Agile focuses on individuals and interaction, and heavily focuses on co-location in order to facilitate team communication.
Exam 2 | #18. Susan is the Scrum Master for an IT project delivering a new internal website for her company’s HR Benefits Team. The HR Benefits Director is the Scrum Product Owner. The Sprint Planning Meetings tend to go longer and longer with each week due to the Development Team experiencing conflict over the estimation of work required to complete the stories on the Product Backlog. The Development Team wants unanimity in their estimations. The attendees in the meeting are the Scrum Master and the 12 Developers. Which of the following are potential causes for the conflict and inefficiency within the Sprint Planning Meetings? |  | There are too many Developers. | The Developers should seek consensus, rather than unanimity. | The Product Owner is not present. | All of the above. | Answer d. | Answer d. Ideal size of the Development Team is between three and nine. The Development Team should use Planning Poker to attain consensus in estimating and the Product Owner should be present to answer any outstanding questions or concerns by the Development Team.
Exam 2 | #19. Bailey is an Agile Project Manager for company ABC that requires developing a new CRM system. Because of his experience, Bailey knows that an agile approach to the project will deliver value to the customer. However, the current company culture does not align with the Agile project management approach. Bailey will make one of the following requests to upper management: |  | She will be required to negotiate the contract terms during the project constantly. | She will expect to understand the nature of the business before carrying on with the project. | She will obtain better results if the customer is involved in the process until a final version of the CRM system is shown. | She will deliver the most outstanding value if the customer does not collaborate with her throughout the project. | Answer c. | Answer c. Customer collaboration is more important than negotiating a contract. Working with the customer side by side will better understand customer requirements to deliver value for the project.
Exam 2 | #20. In the iteration retrospective, the team's coach reminds the pair programming teams that everyone owns the code, and it is important that all of that knowledge be shared. Apparently, there were some inconsistencies in the refactoring that was done between different teams, and as a result, there are some unnecessarily complex structures that will need to be reworked and simplified. Someone suggests that the code standards should be updated once the differences are worked out, and everyone agrees. What methodology is your team using? |  | Scrum | Scrum-XP hybrid | XP | Lean | Answer c. | Answer c. XP: This scenario either mentions or implies several key terms and core practices of the XP methodology: iteration, coaching, pair programming, collective code ownership, refactoring, simple design, and code standards. Although this team might conceivably be using a Scrum-XP hybrid, there is nothing in the scenario to indicate that.
Exam 2 | #21. Mark is a Product Owner in a software development project that has completed four 2-week Sprints. One week into the fifth Sprint, an executive stakeholder requests an item from the product backlog be added onto the current Sprint. This item is currently prioritized mid-way down the backlog. The BEST response Mark can provide to the executive is an explanation that: |  | No changes are accepted mid-Sprint and the Product Backlog is already set and scheduled for the next 6 weeks. The item will be put into the Sprint in approximately 4 weeks. | Interrupting the work the development team is currently completing will result in delays to the project schedule and cannot be done. | The in-progress work cannot be stopped mid-Sprint, but Mark will review the product backlog and ensure the mentioned item is added to the Sprint that starts next week. | Mark will add the item into the current Sprint by end of day and ensure it is completed by the end of the Spring. | Answer c. | Answer c. While items in the Sprint Backlog cannot be removed or added to, the Product Backlog is a constantly changing artifact and priorities change regularly. Refusing to work with any stakeholder, especially an executive, is counterproductive and will not serve the team well. The best answer is to use your communication and interpersonal skills to work with the executive to reprioritize the next Sprint, to the best of your ability.
Exam 2 | #22. The process of subdividing project deliverables and project work into smaller, more manageable components is _ . |  | Create WBS | Validate Scope | Define Scope | Define WBS | Answer a. | Answer a. Create WBS: ‘Create WBS is the process of subdividing project deliverables and project work into smaller, more manageable components. For this reason, answer option a. is the correct answer. Validate Scope, Answer b. is the process associated with gaining Customer acceptance of the product of the project. Define Scope, answer c. develops the description of the project and the product of the project. Define WBS, answer d. is not a PMI Project Management Process.
Exam 2 | #23. When working with a globally distributed team, the most useful approach would be to: |  | Bring the entire team together for a diversity and sensitivity training day before starting the first iteration | Bring the entire group together for a big celebration at the end of the project | Bring the entire group together for a get-to-know session before starting the first iteration | Gather the entire team for a kickoff event and keep them working together for at least the first iteration | Answer d. | Answer d. Gather the entire team for a kickoff event and keep them working together for at least the first iteration: Having the team work together for an iteration would be a great way to help integrate a globally distributed team. Diversity training and get-to-know sessions are nice but having the team members actually work together would be the best opportunity for them to learn each other’s work habits and interaction modes.
Exam 2 | #24. At the sprint review, the team is allowed to present only completed work—work that meets the agreed-upon definition of done. Who is responsible to determine if the work is done or not? |  | The customer | The scrum master | The product owner | The development team | Answer c. | Answer c. The product owner: Ultimately it is the product owner’s responsibility to determine if the work is done or not.
Exam 2 | #25. The project team is struggling to assign new work among themselves as soon as an existing work is completed. This is because there is no proper reporting, nor is there control of work in progress and the work remaining. What do you suggest the team do in such a situation? |  | Use a Kanban signboard | Remove waste from the work to create extra capacity for work | Remove defects by applying the Six Sigma process | Use an Agile development approach | Answer a. | Answer a. The Kanban signaling and pull system may be used to address the given issue.
Exam 2 | #26. The WBS for your project has been prepared and distributed to the project team members. When the project execution begins, which document will provide the team with guidance on how to execute, monitor and control, and close the project? |  | WBS Dictionary | Scope Statement | Project Management plan | Project Statement of Work | Answer c. | Answer c. Project Management Plan: The key phrase in this question is “provide the team with guidance on how to execute, monitor and control, and close the project.” The WBS Dictionary is “a document that provides detailed deliverable, activity, and scheduling information about each component in the WBS”. The Scope Statement is “the description of the project scope, the major deliverables, assumptions, and constraints”. The Project Statement of Work is “a narrative description of the product, services, or results to be delivered by a project”. Only the Project Management Plan “defines how the project is executed, monitored and controlled, and closed” and, in so doing, “provide[s] the team with guidance” on the same.
Exam 2 | #27. A project manager is assigned to a new large and complex project. The budget is still undefined, but it is projected to be around $20,000,000 over about a 4-year period. It is very important that the project follows strict compliance regulations on air space equipment. There are many stakeholders, both external and internal involved and influenced by the project. Corporate management has already tasked someone to identify the required compliance needs and start managing stakeholder requirements. Who will the project manager be collaborating with? |  | The project sponsor | The chief engineer | The business analyst | The senior architect | Answer c. | Answer c. The business analyst: The business analyst (BA) is a key individual with whom the project manager should collaborate.
Exam 2 | #28. A Product Owner is managing a software development project. The development team has completed the software. However, the tester was away for two weeks of vacation and did not sign off. Regardless, the Product Owner is determined to release the software immediately according to the customer request. What should the Product Owner do next? |  | Delay the release until a suitably qualified tester is available. | Ask the Scrum Master to make the release, but tell them the quality risk belongs to them. | Escalate the issue to the project Sponsor. | Release the software to appease the customer and ensure continued business. | Answer a. | Answer a. Testing is needed to find errors, defects, bugs, and other nonconformance problems in order to provide a quality product. Answer B is incorrect, as it is unethical to place the ownership on the Scrum Master. Releasing the software without testing is against the PMI Code of Ethics so D is incorrect.
Exam 2 | #29. Rolling Wave Planning is a form of progressive elaboration planning where the work to be accomplished in the near term is planned in detail, and future work is planned at a summary level. Which of the following processes use the Rolling Wave Planning as a Tool/Technique? |  | Define Activities | Sequence Activities | Estimate Activity Resources | Develop Schedule | Answer a. | Answer a. Define Activities: Rolling Wave Planning focuses on near term Work Packages. Rolling Wave Planning is the process of project planning in waves as the project proceeds and later details become clearer. Work to be done in the near term is based on high level assumptions; also, high level milestones are set. As the project progresses, the risks, assumptions, and milestones originally identified become more defined and reliable.
Exam 2 | #30. Management wants to be sure that a project is following the defined quality policies. Of the following, which tool would they use to ensure that these quality policies are being followed? |  | Risk Management Plan | Work Breakdown Structure | Statement of Work | Quality Audit | Answer d. | Answer d. Quality Audit: Quality Audits are used in the Execution process of Manage Quality. Audits are used to ensure that Organizational or Project Specific quality processes are being followed as well as, identifying nonconformance issues to increase productivity, and verifying that approved changes have been implemented. Answer options a., b., and c. are not tools and can be removed from consideration.
Exam 2 | #31. Steven has joined Gambit LLC as a Project Manager. He is talking to a client of a new project and he is trying to explain to him that he cannot erect the superstructure until after the foundation has been built. Since this requirement is based on the nature of work for the construction industry. Which type of dependency is he mentioning to the client? |  | Mandatory dependency | Discretionary dependency | External dependency | Internal dependency | Answer a. | Answer a. Mandatory dependency: Mandatory dependencies are those that are legally or contractually required or inherent in the nature of the work.
Exam 2 | #32. The technique of determining the quality standards for the entire product range by measuring the quality standard of a few categories of products is an example of ____________? |  | Statistical Sampling | Statistical population | Statistical Independence | A mutual exclusivity | Answer a. | Answer a. Statistical Sampling: Statistical Sampling is among the tools and techniques available for use in Quality Control and if volume production is part of the project deliverables, it should be included in the Plan Quality repertoire of tools. Statistical Sampling allows taking a percentage of the products being produced at random and testing them against the product specification for compliance. Answer b. has to do with the part of the whole being produced and c. is a law of statistics that predicts probability. d. Mutual exclusivity means that the occurrence of one event is not caused by another and they cannot happen at the same time.
Exam 2 | #33. Gone are the days when your team had endless arguments over trivial work issues. You agree that your team consists of strong, knowledgeable, jet opinionated individuals. You know that you have spent countless hours resolving conflicts, from trivial to relevant. After several months, the agile team you are leading has finally reached the performing stage. What do the team members need from you as their leader now? |  | They need a lot of direction to keep them fully focused on their goals | They need your direction and support now, to make sure their performance stays high. | They don't need much direction or support now; they are mostly self-supporting and self-directing | Even though they won't admit it, they still need a lot of support. You can let them direct their own work, though | Answer c. | Answer c. When a team reaches the performing stage, the team members don’t need much direction or support from their leader; they work together smoothly and they are mostly self-supporting and self-directing.
Exam 2 | #34. Which one of the following documents determine the method and timing of releasing the team members, and also helps to mitigate human resource risks that may occur at the end of the project?Which one of the following documents determine the method and timing of releasing the team members, and also helps to mitigate human resource risks that may occur at the end of the project? |  | Staff acquisition | Staff release plan | Compliance | Safety | Answer b. | Answer b. Staff release plan: The Staffing Release plan (as well as the Acquisition Plan) is a component of the Staffing management plan, which is, in turn, a sub-component of the Resource Management. As important as acquisition, the release plan should consider both the project and the team members involved. From the project perspective, once released the costs of the resources can no longer be charged to the project. Morale is equally important and care in planning can allow a smooth transition (reduce risk) of resources to other projects. Compliance and Safety can be eliminated as distractors. ***
Exam 2 | #35. As the time in the Project Life Cycle passes by, the ability to influence risk and cost in the project . |  | Increases | Decreases | Increases and decreases | There is no fixed pattern | Answer b. | Answer b. Decreases: While a project progresses the ability to influence risk and control costs associated with changes decreases.
Exam 2 | #36. The project has been initiated and the Project Manager is in the process of defining and documenting the stakeholders’ needs required to meet the project objectives. The project manager is very careful in performing this process as he is aware that the project’s success is directly influenced by the effort applied to manage and complete project and product requirements. All of the following are Tools/Techniques that can assist him in preparing the requirements documentation except . |  | Facilitated workshops | Group decision making | Prototypes | Inspection | Answer d. | Answer d. (Except) Inspection: This question tests the student’s understanding of the ITTOs of the Collect Requirements process. By way of elimination, answer options a., b., and c. may be removed from consideration: all of these are Tools/Techniques that can assist him in preparing the requirements documentation of Collect Requirements process. The only exception is option d., Inspection. While a Tool & Tech, Inspection is found in Control processes (Validate Scope, Control Procurements, Control Quality).
Exam 2 | #37. In your project, a key team member has resigned. You’ve hired a new resource for replacement, and you plan to inform the management about the resigned resource and the replacement at Friday’s status meeting. Most likely, you are a Project Manager working in a(n) ______ organization. |  | Matrix | Projectized | Expeditor | Coordinator | Answer b. | Answer b. Projectized: Answer options c. and d. may be eliminated as they are project roles, not an organizational model. The organization forms, or types, that concern PMI are Functional, Matrix, and Projectized. The Project Manager has the most strength in a Projectized organization, and it is in this type of organization that he/she is most likely to have the authority to hire or fire without first having to consult senior management.
Exam 2 | #38. In Scrum projects, we plan to “learn as we go” because |  | It creates a better relationship between the developers and customer representatives | Many projects are evolutionary with many unknowns, and a better solution emerges this way | It is time-consuming to analyze everything at the beginning of a project | It prevents late delivery of a project | Answer b. | Answer b. In Scrum projects, it is more difficult to plan all activities in the beginning because of the rate at which industries and customer needs change at a given time. In a Scrum project, changes are welcomed, and customer’s needs are constantly addressed to provide a better product.
Exam 2 | #39. Your project team has just completed sprint planning for the web site search function, has added the story points and created an iteration burndown chart for the next 3 weeks. All of the following are true about an iteration burndown chart except: |  | It tracks work remaining in the iteration. | It shows work planned in the iteration. | It shows the forecasted remaining work in the iteration. | It tracks work left in the current release. | Answer d. | Answer d. It tracks work left in the current release: An iteration burndown chart does not track the work of the release. Though an iteration is part of a release, there may be several iterations planned within a single release.
Exam 2 | #40. All of the following are true about the Project Statement of Work except: |  | It should contain a product description describing the characteristics of the product the project will be undertaken to create, as well as descriptions of project activities, deliverables, quality, and timescale constraints. | It should contain some description of the market demand, legal requirement, regulation, or environmental consideration that meets a business need. | It should contain a high-level mission statement that aligns the proposed project with the strategic plan of the company. | The sponsoring management is responsible for creating it. | Answer d. | Answer d. (Except) The sponsoring management has the responsibility of creating it: Answers a., b., and c. align with definitions of the Product Scope Definition, the Business need, and the Strategic Plan requirements. While the Project Manager may or may not be involved in the creation of the Charter it is recommended he/she become engaged as early as possible in the process of scope development.
Exam 2 | #41. A longstanding, key team member in a virtual team has been unmotivated for weeks after the death of a family member. Because of this, several project activities are behind schedule, impacting the project’s critical path. How should the project manager handle this situation? |  | Replace the team member. | Discuss the situation with the team member and work with them to identify a workable solution. | Escalate this situation as an HR issue and ask other team members to work overtime. | Ask the functional manager for additional support on the project, including assignment of a new resource. | Answer b. | Answer b. A project manager is a servant leader. Servant leadership means listening and acting with empathy. Especially in virtual teams, facilitating servant leadership can be a challenge. Replacing the key team member is a unilateral action that project team members and others may perceive as drastic, considering the circumstances. Asking others, such as HR or the functional manager, to intervene is a good idea, but the team member should be consulted first, and asking the team to work overtime is always a gamble. Given all of this, the project is the priority here. Speak with the team member first, using emotional intelligence and empathy, but with a firm approach to completion of work as a priority.
Exam 2 | #42. During a Sprint Retrospective, the Scrum Master notices only one or two team members dominate the conversation and shut everyone else down. What should the Scrum Master do? |  | Escalate the issue to the Product Owner. | Increase the size of the group during the Retrospective. | Encourage all team members to participate. | Increase the time of the Retrospective. | Answer c. | Answer c. As Scrum Master, one should facilitate the meeting accordingly and call on other team members to ask for their thoughts. An effective Retrospective ensures that every team member has the ability to share feedback without one or two members taking over the conversation.
Exam 2 | #43. In contrast to operations or manufacturing industries, software engineering is knowledge-based, and relies on the power of collaboration and individuals talking to each other. Which of the following values represent this statement? |  | Working Software over Comprehensive Documentation | Individuals and Interactions over Processes and Tools | Responding to Change over Following a Plan | Customer Collaboration over Contract Negotiation | Answer b. | Answer b. Individuals and Interactions over processes and tools: The first value in the Agile Manifesto is “Individuals and interactions over processes and tools.” Valuing people more highly than processes or tools is easy to understand because it is the people who respond to business needs and drive the development process.
Exam 2 | #44. Your project has just been approved by management. You have developed the Project Charter and identified the project stakeholders. The information from these two initiating documents is an input into _________ Process Group. |  | Executing | Planning | Controlling | Monitoring | Answer b. | Answer b. Planning: If you have developed the Project Charter, identified the project stakeholders, and it has been approved by management, you are now ready to move on to Planning processes. In Planning, next would involve Developing the Project Management Plan, Scope, and the Scope Management Plan. While it may involve updating the Stakeholder Register moving forward the challenge is in the planning of the Project. Once Planned, Execute, Monitor & Control, and Close follow.
Exam 2 | #45. Typically, impediments are raised in the Daily Scrum, but urgent impediments should be presented in real-time rather than waiting for the Daily Scrum. What else should be discussed during the daily scrum meetings? |  | Each team member should answer the following questions; What did I accomplish since the last daily Scrum? What am I planning to work on till the next daily Scrum? | The project manager should be able to get an update on the project’s status by directly asking questions to the team members. | Communicate the status of sprint backlog items in development to the product owner. | Discuss what went well since the start of the current sprint and discover opportunities for improvement. | Answer a. | Answer a. Each team member should answer the following questions; What did I accomplish since the last daily Scrum? What do I plan to work on by the next daily Scrum?: In Daily Scrum meetings, participants are asked daily to report the following: What did they do yesterday? What will they do today? Are there any impediments or obstacles in their way? By focusing on what each person accomplished yesterday and will achieve today, the team gains an excellent understanding of what work has been done and what work remains. The daily Scrum meeting is not a status update meeting in which project managers or product owners collect information.
Exam 2 | #46. The attached diagram is the Work Breakdown Structure (WBS) for an engineering project. WBS item 1.1.2 could be a: | images/image10.jpg | Control Account | Work Package | Code of Accounts | WBS Dictionary | Answer a. | Answer a. Control Account: Through the process of elimination, answer options b., c., and d. can be removed from consideration. The Code of Accounts is the list of numerical identifiers that are attached to each node in the hierarchy. The WBS Dictionary is a separate document containing attributes that characterize the elements of the WBS. And a Work Package always occupies the lowest level of any “branch” on the WBS. Item 1.1.2, is not on the lowest level, therefore it might be considered to be a Control Account.
Exam 2 | #47. For the company review meeting, you have to prepare graphical charts to show the project performance trends. Which of the following two charts will help you to do that? |  | Pareto Chart and Control Chart | Control Chart and Run Chart | Gantt Chart and Control Chart | Histogram and Run Chart | Answer b. | Answer b. Control Chart and Run Chart: Both the Control Chart and Run Chart evaluate data or samples over time. Pareto, Gantt, and Histograms do not consider the influence of time on the variation that exists within a distribution.
Exam 2 | #48. You are the Project Manager of the MAX Project. While monitoring your project, you find that the project is experiencing unexpected flaws in production. Which analysis tool would allow you to determine the cause-and-effect of the production flaws? |  | Flow Chart | Ishikawa Diagram | Pareto Diagram | Control Chart | Answer b. | Answer b. Ishikawa Diagram: In this case we know that there are manufacturing issues and the challenge is to determine the causes and their effects. Ishikawa’s fishbone chart helps identify the issues that can then be sorted by the effect they have. Answer a., Flowcharts are process maps that define the sequence of steps and branching possibilities that exist for a process; c., Pareto analysis is an ordered histogram that can be used to identify the critical few sources that are responsible for causing most of the problems. Answer d., Control Charts evidence the number or magnitude of the deviations over time, but not necessarily the cause.
Exam 2 | #49. Sensitivity Analysis is one of the Tools/Techniques involved in performing Quantitative Risk Analysis. What are the advantages of using Sensitivity Analysis? |  | It determines the risk to the public only | It allows for independent answers | It helps the team understand which risks could have the most potential impact on the project | It provides insight into the project that the PM may be lacking | Answer c. | Answer c. It helps the team understand which risks could have the most potential impact on the project: Sensitivity Analysis is a Tool/Technique to Perform Quantitative Risk Analysis. The correct answer, taken directly from the PMBOK defines the purpose of the tool Sensitivity Analysis.
Exam 2 | #50. What type of contract would the buyer want to issue for a relatively new technology-oriented project to reduce or eliminate as much risk as possible for themselves? |  | Time & Materials (T&M) | Cost Plus Incentive Fee (CPIF) | Fixed Price Incentive Fee (FPIF) | Cost Plus Fixed Fee (CPFF) | Answer c. | Answer c. Fixed Price Incentive Fee (FPIF): Through the process of elimination, answer options a., b., and d. can easily be removed from consideration. A Buyer would be far more likely to sign any fixed-price contract “In order to reduce or eliminate as much risk as possible.
Exam 2 | #51. One of the functional managers in your organization is arguing that operations and projects are the same. Therefore, both operations and projects require similar planning techniques. What would be your best argument to stress your viewpoint that operations and projects are different? |  | Resources consumed by operations are different from the resources consumed by projects | Projects incur large expenses in comparison to operations | Projects are done by combining the efforts of various departments while the operations are done only by one department | Projects have a definite start and end date while operations do not | Answer d. | Answer d. Projects have a definite start and end date while operations do not. The definition of a Project is a temporary endeavor undertaken to create a unique product, service, or result. Operations are ongoing endeavors that produce repetitive outputs, with resources that do basically the same set of tasks. The same resources may be used by both operations and projects, expenses are aligned with the needs of either the project or operations and projects can be executed to satisfy the needs of a department or a company; Answer options a., b., and c. are removed from consideration, as they are considered false.
Exam 2 | #52. _______ document has the code of account identifier, description of work, responsible organization, and list of schedule milestones. |  | WBS | WBS Dictionary | PERT / CPM Charts | Role and Responsibility Matrix | Answer b. | Answer b. WBS Dictionary: Part of the Scope Baseline, the WBS Dictionary details every deliverable, activity as well as the scheduling for each component in the WBS. As the schedule and budget are established the WBS Dictionary is progressively elaborated to include Code of Accounts, Scheduling milestones, resources required, and other key information related to the corresponding activity. The WBS is a reference chart that can be viewed as a table of contents to the elements defined within the WBS Dictionary. Answers c and d can be eliminated as false.
Exam 2 | #53. In the Power/Influence Model, who are the powerful people who actively support the project? |  | Blockers | Champions | Supporters | Detractors | Answer b. | Answer b. Champions: According to the Power/Influence Model answer option a., “Blockers,” are “powerful people who will actively resist the project”; answer option c., “Supporters,” are “people with little power who are in favor of the project”; and answer option d., “Detractors,” are “people with little power who are against the project.” Only “Champions” are, as stated in the scenario, “powerful people who actively support the project.” The Power/Influence Grid is a classification model used in Stakeholder Analysis as a Tool & Tech used in the Identify Stakeholder process.
Exam 2 | #54. Which of the following is a Tool/Technique that displays the values of probability and impact and assists in prioritizing the risks qualitatively? |  | Probability and Impact | Probability and Impact Matrix | Probability Analysis | Exposure Matrix | Answer b. | Answer b. Probability and Impact Matrix: Identified risks are rated based on their levels of probability of occurrence and the impact in cost or time the risk could have on the project. They are mapped into the Probability and Impact Matrix to allow a visual prioritization. Answers c. and d. are removed from consideration: “Probability Matrix” and “Exposure Matrix” are not terms mentioned in the PMBOK. “Probability and Impact” is a vague and non-conclusive answer.
Exam 2 | #55. _____ is an iterative process that should be reviewed regularly by the Project Manager over the life of the project. |  | Plan Stakeholder Engagement | Develop WBS | Control Scope | Schedule Management | Answer a. | Answer a. Plan Stakeholder Engagement: Unlike a lot of processes, Stakeholders come first. Even in the Process Groups, they are introduced in the Initiating Processes. Almost as quickly, the Project Manager must discover, analyze, and include management strategies in the Stakeholder Register. The Plan Stakeholder Engagement Process allows strategizing and creating the Stakeholder Management Plan, that develops an actionable plan that defines how to interact with project stakeholders, and thus improve performance. This interaction changes throughout the Project Life Cycle and so must the plan to accommodate those needs. An Output of this process in Update Project Documents which includes the Stakeholder Management Plan itself. In this case, Plan Stakeholder Management is the best selection of the answers provided. Answer b., Develop WBS is a process used to decompose the Scope Statement into Work Packages. There may be a degree of flexibility at the beginning, but once completed, the process is (usually) complete. Control Scope, answer c., likewise will follow rules developed early on in the Plan Scope Management process. It also may be changed; however, it is less animated than the human characteristics associated with Stakeholders. Answer d., Schedule Management is a knowledge area, not a process.
Exam 2 | #56. Senior management needs to be informed regarding the progress of your project. You will be making reports based on comparing the current cost, schedule, and scope to details found in . |  | Project Management Plan | Project Charter | Earned Value calculations | PERT and CPM | Answer a. | Answer a. Project Management Plan: The Project Management Plan defines, prepares, and coordinates all subsidiary plans governing both HOW the Project will be managed and WHAT the product of the project will entail. It is a central document that defines the basis of all project work. Scope, Schedule, Cost, and even the timing and content format of the reports themselves will be contained in the Project Management Plan. The Project Charter is a high level document that describes the goal or gives an overview of the project. Earned Value calculations play a significant role in creating cost/progress reporting; PERT and CPM are Estimating and Scheduling techniques.
Exam 2 | #57. You are approaching the end of your project. The deliverables have been accepted by the customer. Your team is about to adjourn as the project is completed. They all tell you that they are happy with the training they have received, and that they have improved their skills and knowledge during the project. Although you received individual feedback from your team, you need to do the following as a support to their statements: |  | Make sure there is knowledge transfer in place | Collect project or phase final documents | Receive feedback from the customers | Measure and evaluate the training outcomes in the project | Answer d. | Answer d. Measure and evaluate the training outcomes in the project: Measure and evaluate the training outcomes in the project. This will be performed at the end of the project when you find what the team member learned from the training. How they applied the knowledge in the project and project deliverables.
Exam 2 | #58. As part of finishing her project notebook, Carmen is compiling the paperwork for the project auditor to review. As she completes her final reports for the project closeout, she realizes that she has mistakenly included the _______ . |  | Project files | Return on Investment (ROI) | Project Closure/transfer and transition documents | Lessons Learned | Answer b. | Answer b. Return on Investment (ROI): Through the process of elimination, answer options a., c., and d. may be eliminated; they are all documents that should be completed as part of the Close Project or Phase process. Answer option b. is the exception, and therefore the correct answer here, because the deliverables (or even the project’s) ROI is not so much the concern of the Project Manager as it is the concern of the Product Manager or, in general, Senior Management.
Exam 2 | #59. You are an experienced PM and discuss with your junior team members about your experience managing past projects and especially your ways of managing and mitigating specific risks. How can managing knowledge transfer be useful when implementing risk responses? |  | Helps risk owners update the risk status periodically | Helps risk owners determine proper risks response strategies based on lessons learned | Helps risk owners take actions, particularly risk owners who are considered external to the team | Helps risk owners perform periodical risk audits | Answer b. | Answer b. Helps risk owners to determine proper risk response strategies based on lessons learned: The question is talking about applying lessons learned during risk response implementation. This is typically done during team meetings when discussing risk response strategies.
Exam 2 | #60. Which of the following is an on-going and coordinated management of a group of projects that may be either interrelated or independent and contribute to common strategic objectives? |  | Project Management | Program Management | Portfolio Management | Personal Management | Answer c. | Answer c. Portfolio Management: Through the process of elimination, options a., b., and d. may be removed from consideration: Project Management is the management of single projects, not the “management of a group of projects”; Program Management is about the management of projects (and/or Operations) that are interrelated, and Personal management is obviously not a PMBOK concept. The answer is option c., Portfolio Management is clearly the correct answer. By definition, “a portfolio refers to a collection of projects, programs, sub-portfolios, and operations managed as a group to achieve strategic objectives.
Exam 2 | #61. A hybrid project combines network integration and software development tasks. The predictive and agile teams seem to be working in silos, resulting in misaligned deliverable scheduling. Which two measures would most effectively enable the teams to better synchronize their deliveries? (Choose TWO.) |  | Alter the story size to ensure more complete integration to the IT build requirements. | Use the IT predictive schedule to limit the features the software team starts to develop. | Create a common Kanban board to queue and track progress of both teams' deliverables. | Break down IT work packages into more granular tasks to align to the software releases. | Correct An | Correct Answer is c and d. Create a common Kanban board to queue and track progress of both teams’ deliverables and Break down IT work packages into more granular tasks to align to the software releases.
Exam 2 | #62. Tom is a Project Manager on an industrial design project. He is always monitoring when the team members come into the office, when they take a break, and when they leave. He periodically walks around the office to be sure that everyone is doing work when they are at their desks, and he insists that he makes every project decision, even minor ones. What kind of manager is he? |  | Theory X | Theory Y | Cost Cutter | Effective Theory X | Answer a. | Answer a. Theory X: It should be clear from the Slide Presentation that a Theory X manager is, if nothing else, a micro-manager. The manager’s behavior, as described in this scenario, is the behavior of a micro-manager. Of the four answer options given, option a. is a clear choice.
Exam 2 | #63. You are working on a project in the electronics industry. Recently there were reports of instances where the circuit cards are, unexpectedly, not passing the quality tests. As Project Manager, you need to propose a quality tool to determine if production is within customer specifications. Which of the following Tools/Techniques might you use? |  | Control charts | Pareto Diagram | Ishikawa diagram | Flow Charts | Answer a. | Answer a. Control charts: Control Charts evidence the number or magnitude of the deviations over time, but not necessarily the cause. The issue is to determine if the manufactured units fall within Customer Specifications (and perhaps within internal Control Limits.) Pareto analysis is an ordered histogram that can be used to identify the critical few sources that are responsible for causing most of the problems. Ishikawa’s fishbone chart helps identify the issues but does not focus on the frequency of occurrence. Flowcharts are process maps that define the sequence of steps and branching possibilities that exist for a particular process.
Exam 2 | #64. Your organization uses Earned Value Management to assess a project’s health. As a Project Manager, you will use EVM during which of the following? |  | Controlling processes | Executing processes | Entire project | Closing processes | Answer c. | Answer c. Entire project: While technically a Tool & Tech associated with Control Costs (part of the Controlling Processes) EVM can be used from the point the Schedule and Cost baselines are defined. Since Planning, Executing (b), Controlling (a), and Closing (d) activities are included in the costs associated with a project it would be logical to individually eliminate them in favor of the whole, the Entire Project (b.)
Exam 2 | #65. Brian is an Agile Project Manager working in a software company Prairie View. To improve the company's profitability, the CEO has decided to Scrum projects. A new system is developed to monitor the process's Work in Progress (WIP) closely. What will be valid under the agile mindset? |  | The creation of user manuals is key to the successful functioning of the new software module. | The whole software development before using it to monitor the WIP required. | Working software for all the increments required until the improvement experts can use it. | Documenting the whole development process before developing a prototype is a must. | Answer c. | Answer c. Agile focuses on delivering working software in increments, even though the final user may not be able to operate it yet. Each increment provides additional functionality to the product under development.
Exam 2 | #66. Project A has an Internal Rate of Return (IRR) of 20%, Project B has an IRR of 12%, Project C has an IRR of 22%, and Project D has an IRR of 10%. Which of these would be the BEST project from an investment point of you? |  | Project A | Project B | Project C | Project D | Answer c. | Answer c. Project C: You do not need to know how to actually calculate Net Present Value (NPV), Internal Rate of Return (IRR), Discounted Cash Flow (DCF), or other financial-based project selection methods. However, on the test you will need to know that “bigger is better,” the project opportunity that offers the biggest return (compared to those values of other opportunities) is the more desirable opportunity. For this reason, answer option c., Project C, is the correct answer.
Exam 2 | #67. A major scope change has been formally proposed to the project team. The next step that the Project Manager should do is to ____ . |  | Look for other changes. | Gain sign off on this change. | Assess the impact associated with this scope change. | Start with implementation of the scope change. | Answer c. | Answer c. (First) Assess the impact associated with this scope change: First would be to clearly understand what process would address this need. While one might assume Control Scope, as there is an implied major change to the scope proposed, the project team has identified the need; the specifications involved and has proposed the change. NEXT would be to engage the Integrated Change Control Process, to have those with Expert Judgment provide their expertise in understanding the impact the change will have on the project, and approve or reject the proposed change. Once the change request has been approved, b. signoff, a. look for other changes (and risk) and d. start execution of the said work would follow.
Exam 2 | #68. As a Project Manager, achieving customer satisfaction is an important objective for you. Which of the following will help you in attaining your objective? |  | Defining requirements | Providing more features than asked by the customer | Identifying project-related risks | Providing project justification | Answer a. | Answer a. Defining requirements: Answer option b. “gold plating,” which is frowned upon by PMI. It is next to impossible to identify “project related risks” unless you have defined requirements. And “providing project justification” is a task that should have been completed by senior management long before you began the project. Therefore, options b., c., and d. may be taken out of consideration. That leaves only Defining Requirements, option a. Customer satisfaction is defined in the Glossary as the state of fulfillment in which the needs of a customer are met or exceeded for the customer’s expected experiences as assessed by the customer at the moment of evaluation. It begins with clearly defining requirements.
Exam 2 | #69. You have found that the one‐week sprint length is no longer a viable rhythm for your current sprint. The development team can’t create tangible, tested, and approved products within one week. The sprint velocity is very low, which is very concerning to various stakeholders. As a scrum master, what should you do? |  | Increase the sprint length to two weeks. The capacity of a development team during a two‐week sprint will be higher. | Keep the current sprint length. Shorter sprints decrease the amount of time between feedback received from stakeholders. | Change the sprint goal. As the team can’t achieve the sprint goal, it becomes irrelevant. | Cancel the sprint and start a new one with a smaller number of story points. | Answer c. | Answer c. Change the sprint goal. As the team can’t achieve the sprint goal, it becomes irrelevant: Sprint lengths do not change after they begin and ideally do not change throughout a project unless they are being made shorter. Time-boxing forces an end to potentially unbounded work by establishing a fixed end date for the sprint by which a good solution must be done.
Exam 2 | #70. A buyer has floated a procurement document to buy cement for his construction company, and in response, received several price quotations. The buyer has used which of the procurement documents shown below? |  | Request for Proposal | Request for Quotation | Proposal | Invitation for Bid | Answer b. | Answer b. Request for Quotation: Procurement Documents are used to solicit proposals from prospective sellers. Such proposals include RFP a Request for Proposal, IFB Invitation for Bid, and the correct answer b., RFQ a Request for Quote. Since the buyer has received responses from his document and the responses were Quotes, you must assume he received a price quote as a response to the RFQ. Answer c., Proposal, would be a response to an RFP.
Exam 2 | #71. In your project, you invested a lot of time in team development to increase the team’s performance, which in turn increases the likelihood of meeting the project objectives. You will be using all of the following to evaluate your team’s effectiveness EXCEPT ________. |  | Improvement in skills of team members | Improvement in competencies and morale that help the team to perform better as a group | Decrease in staff-attrition (i.e., fewer people leaving the project team) | Delivery of project deliverables ahead of schedule | Answer d. | Answer d. (Not) Delivery of project deliverables before time: Develop and Manage the Project Team is all about increasing the team’s performance in order to meet the project’s objectives. Answer a., improving the skills of team members, b., team competencies and morale and c., decreasing attritions all are measured and documented as outputs of the two processes. Though developing and managing a Project Team can lead to an early completion of the product of the Project, its goal is to improve project performance, not the delivery of the product before time.
Exam 2 | #72. At ______ level of the WBS, the budget should be estimated to assist in budget control during the Monitoring and Controlling Process Group. |  | Highest | Lowest | Third | Major work effort | Answer b. | Answer b. Lowest: Determine Budget is the process of aggregating the estimated costs of individual activities or work packages (defined in the WBS) to establish an authorized cost baseline. The WBS decomposes the Scope Statement to increasingly detailed definitions of the project work called work packages, which are assigned a control account. (Remember, if it is not in the WBS, it doesn’t get done!) All costs, to the lowest (b.) in the WBS, are considered in creating the cost curve to assist in budget control.
Exam 2 | #73. During the project review, you learn that your project has a high likelihood of experiencing a schedule overrun. You know this because the EV is ___. |  | Lower than the Actual Costs | Higher than the Planned Valued | Lower than the Budgeted Cost of Work Scheduled | Lower than the cumulative CPI | Answer c. | Answer c. Lower than the Budgeted Cost of Work Scheduled: Remember that the Budgeted Cost of Work Scheduled (or BCWS) is the same as the Planned Value (PV). In the problem, if the work that has been accomplished, the EV (Earned Value) is lower than the work that was planned (the Planned Value, or Budgeted Cost of Work Scheduled), you know that you will need more time than planned to finish all of the work. And “more time than planned” effectively translates to mean a schedule overrun is likely. Schedule Variance (SV) and Schedule Performance Index (SPI) would be the tools used to identify how big the variance is and help understand what can be done going forward to make corrections.
Exam 2 | #74. You are the new Scrum coach and you have been assigned to train the team on Scrum framework, which is very popular among Agile frameworks and methods. From the selections below, which item is NOT a Scrum artifact? |  | Sprint Backlog | User Story Card | Gantt Chart | Product Backlog | Answer e: | Answer e: Artifacts of Scrum are outlined as: Product Backlog, Sprint Backlog, and Increment. Gantt Chart and User Story Cards are not Scrum Artifacts.
Exam 2 | #75. Dan has just completed the Validate Scope process and gained Customer Acceptance of his Project Deliverables. He is excited to be near the project completion. He finds that, while doing project closing, he needs to concentrate his efforts on many areas. Two of them are: |  | Control Schedule and Control Quality | Manage Communications and Control Procurements | Define Activities and Sequence Activities | Control Procurements and Close Project or Phase | Answer d. | Answer d. Control Procurements and Close Project or Phase: Projects don’t end until the paperwork is done. Answer a.,Control Schedule and Quality are completed; Answer b, Manage Communications and Control Procurements are also completed; Answer c., Define and Sequence Activities happened in Planning the project. While Customer Acceptance happened in the M&C Process of Validate Scope where both completeness and correctness were confirmed, the next steps in the project are: 1. confirm that all Procurement Contracts have been reconciled and closed; 2. release resources and 3. formally initiate the Close Project or Phase process.
Exam 2 | #76. Project information may be distributed using a variety of methods including project meetings, hard copy document distribution, and shared access to networked electronic databases, fax, electronic mail, voice mail, video conferencing, and electronic tools for project management. These methods are known as ____ . |  | Project controls | Project information management system | Project distribution systems | Communication Methods and Technology | Answer d. | Answer d. Communication Methods and Technology: Communication Technology represents the variety of technology available and suggests the appropriate methodology is chosen. Communication Methods focuses on ensuring the information that has been created and distributed has been received and understood to enable response and feedback.
Exam 2 | #77. Jason, the Project Manager, has recently earned his PMP Certification, and he is planning quality management with his project team. Since it is the first time he is performing this activity, help him identify which of the following quality Tools/Techniques will NOT be needed to plan quality in his project. |  | Quality Audits | Cost of Quality (COQ) | Benchmarking | Cost-Benefit Analysis | Answer a. | Answer a. Quality Audits: Answer options b., Cost of Quality (COQ), c., Benchmarking, and d., Cost-Benefit Analysis, are all Tools/Techniques of the Plan Quality Management process. The exception here is answer option a., Quality Audits, which is a Tool/Technique of the Manage Quality process, not the Plan Quality Management process.
Exam 2 | #78. Which of the following options is a term that is defined by the following statement: The amount of time an activity may be delayed or extended without affecting the total project duration? |  | Lag | Lead | Total Float | Free Float | Answer c. | Answer c. Total Float: Answer option c, “Total Float,” is correct as per the definition of the PMBOK because it is the concept defined by the wording that appears in the question scenario: “amount of time an activity may be delayed or extended without affecting the total project duration.”
Exam 2 | #79. A US based software development company announces releasing a product in the European Union (EU) next month. Right after the announcement, the compliance team recommends delaying the launch by three months to avoid legal penalties related to a new set of EU regulations. Which approach could the project manager take to advance the launch project while preparing the compliance measures? |  | Run a SWOT analysis to weigh priorities between compliance and consumer needs, and resume the project if the result favors consumers. | Estimate impact of penalties on the project, increase the contingency reserve accordingly and resume the project as planned. | Re-plan the predictive project as a Large-Scale Scrum life cycle, and use story points to estimate approval milestones. | Split out work affected by the regulations into an agile track, and re-plan unaffected work in the predictive schedule. | Answer d: | Answer d: Split out work affected by the regulations into an agile track, and re-plan unaffected work in the predictive schedule.
Exam 2 | #80. Within the Agile Manifesto, a line reads “over following a plan”. Which selection from the statements below completes the Manifesto: |  | Finalizing requirements | Asking the customer | Responding to change | Communicating regularly | Answer c. | Answer c. Agile Manifesto is focused on four main values; responding to change over following a plan is one. Agile embraces change and the development teams are expected to welcome change in requirements throughout.
Exam 2 | #81. Johnny is the Project Manager of the Galaxy Project. Quality audits of the deliverables show there are several problems with the product. The organization has asked Johnny to create a chart prioritizing the problems and their frequencies. Which of the following is the right Tool/Technique to assist Johnny? |  | Pareto Diagram | Ishikawa Chart | Control Chart | Flowchart | Answer a. | Answer a. Pareto Diagram: A Pareto analysis is a prioritized histogram that can be used to identify the vital few sources that are responsible for causing most of the problem’s effects. Resolving 20% of the identified issues can resolve 80% of the identified problems. Ishikawa’s fishbone chart helps identify the issues but does not focus on the frequency of occurrence. Control Charts evidence the number or magnitude of the deviations over time, but not the cause. Flowcharts are process maps that define the sequence of steps and branching possibilities that exist for a process.
Exam 2 | #82. You’re a project manager who has been assigned to a firewall replacement project where security features can be designed, built, and configured by one non-specialized, cross-functional team in a time frame ranging from two to four weeks. What is the best delivery approach for this project? |  | Scrum; The product could be delivered in time-boxes of 4 weeks or less where a potentially releasable increment of product is produced. | Kanban; we’re operating with one team only, and we need to limit the work in progress (WIP) to optimize workflow and reduce lead time. | Pure waterfall; we need a specialized team to support this product and a more sequential process flow considering the sensitive nature of the solution. | None of the above. | Answer a. | Answer a. Scrum; The product could be delivered in time-boxes of 4 weeks or less where a potentially releasable increment of product is produced: A sprint describes a time-boxed iteration in Scrum where a potentially releasable increment of product is produced.
Exam 2 | #83. You are a Project Manager for your organization. Joe, a Project Manager in training, wants to know when the Project Manager needs to be assigned to a project. Your BEST answer can be: |  | During the initiation stage | During the planning stage | When the stakeholders approve the budget | As soon as a Request for Quote is received | Answer a. | Answer a. During the initiation stage: As early as possible!!! Project Management Processes introduces the process groups with the Initiating Process Group outlining the processes associated with a new project. The initial scope and financial resources are committed, internal and external stakeholders that will interact with and influence the project are identified and the Project Manager will be selected and assigned. Answer d. RFQs present an opportunity for a company to respond to a need; however, it would help create a feasibility study that could lead to the initiation of a funded project. An approved Charter normally initiates a Project wherein the Project Manager is assigned and authorized to expend company resources by the Project Sponsor. The Charter is developed in the Initiation Stage.
Exam 2 | #84. Your client has terminated your project before it is complete. Which of the following is true? |  | You must stop all work and release the team immediately | You must initiate the Close Project or Phase process and work with the team to document the lessons learned | You must keep the team working on the project to give your senior management time to talk to the client | You must update the project management plan to reflect this change | Answer b. | Answer b. You must initiate the Close Project or Phase process and work with the team to document the lessons learned: The Close Project or Phase process also establishes the procedures to investigate and document the reasons for the action taken if a project is terminated before completion. In order to successfully achieve this, the project manager needs to engage all the proper stakeholders in the process. This includes exit criteria, transfer of the project’s product service, or results. Collection of project records, the audit of project success or failure, lessons learned, and archiving project information for future use.
Exam 2 | #85. PMI believes Professionalism and Ethical behavior are prerequisites to Project Management. Which of the following are NOT categories of people who are covered by the code of conduct? |  | All Project Managers | All PMI members | Non-members of PMI that hold a PMI Certification | Non-members of PMI that are PMI Volunteers | Answer a. | Answer a. (Not) All Project Managers: Unfortunately, ‘All Project Managers’ is a general statement that includes those that have and have not had training and or have been PMI certified. Answers a., b., and c. can be removed from consideration as they are taken directly from the code.
Exam 2 | #86. Jerry has been appointed as a Project Manager for a manufacturing facility Vita that produces shoes in Vietnam. The project's goal is to improve the flow of value-added activities. However, the IT infrastructure moves large batches of production. What should Jerry recommend using to adjust shoe production in small batches? |  | Six Sigma | Visual Management | Agile and Kanban methods | Process Mapping | Answer c. | Answer c. Agile and Kanban methods share lean concepts such as “focus on value,” “small batch sizes,” and “elimination of waste.” Answer c. Agile and Kanban methods share lean concepts such as “focus on value,” “small batch sizes,” and “elimination of waste.”
Exam 2 | #87. You are in the process of planning for your agile project. You have a team of highly skilled persons who have worked on agile projects for many years. You count on their experience to decide what tools they will use for the project. They are debating how they should show what they are working on at the moment. Of the following options, which tool are they most likely to select? |  | Taskboard | User story backlog | Product roadmap | Work breakdown structure | Answer a. | Answer a. Taskboard: Of the options presented, the best tool to show work in progress is a task board. The user story backlog shows what work is remaining to be done on the project. The product roadmap shows when work is planned to be completed. Work breakdown structure is mainly used in traditional (waterfall) projects.
Exam 2 | #88. Which of the following leadership styles supports “open the problem to the group for discussion and simultaneously allow or encourage the entire group to make a relevant decision”? |  | Coach | Facilitator | Director | Supporter | Answer b. | Answer b. Facilitator: The definition given for the Facilitator leadership style is: “Project Manager opens the problem to the team for discussion and simultaneously allows or encourages the entire team to make a relevant decision.”
Exam 2 | #89. You are planning to tailor the company's project management method to suit your project. Your company has established a method based on a certain and proven methodology for your industry. Which of the following statements is correct? |  | You should tailor the method in consultation with your peers. | You should go for a better method if this method does not support project-specific tailoring. | Tailoring should not be done, because the corporate method must be used for all projects. | You will be able to tailor the method for your project only if tailoring guidelines have been provided in the corporate method. | Answer d. | Answer d. You will be able to tailor the method for your project only if tailoring guidelines have been provided in the corporate method: Tailoring the project should be done based on tailoring guidelines provided in the corporate method. In case no tailoring guidelines are provided, management must be consulted before attempting to make a decision on your own.
Exam 2 | #91. A Project Manager is managing a hybrid project developing a new product, and midway through the sprint, identifies a new risk that has occurred. What should the Project Manager do next? |  | Review the risk management plan | Implement the contingency plan or fallback plan and update the risk register | Implement a workaround and update the risk register | Perform Qualitative and/or Quantitative risk analysis | Answer b. | Answer b. In this hybrid project, Risk management is similar to the traditional (Waterfall) Risk Management approach with slight deviations. According to the PMBOK, identified risks may be handled with the Contingency (Fallback) plans.
Exam 2 | #92. As a Project Manager, you make sure that the Control Costs process is being followed in your project. All of the following is true about Control Costs except: |  | The cost baseline is updated all the time | Work performance information such as CPI, SPI, TCPI, and VAC for control accounts are recorded and communicated to stakeholders | A calculated or bottom-up estimated EAC is documented and communicated. | Change Requests are generated and processed through the Perform Integrated Change Control process as needed to facilitate preventive or corrective action on the components of the Project Management Plan. | Answer a. | Answer a. (Except) The cost baseline is updated all the time: There are a LOT of Acronyms used in the PMBOK, and while the abbreviations serve their purpose the exam challenges the student’s memory. Answers b., c., and d. can be removed from consideration after carefully reviewing these abbreviations; they are clearly Outputs of Control Costs. The Cost Baseline is the reference against which the Actual Costs and Earned Value are compared to determine variances. If the variances prove the Baseline needs to be reassessed and changed, it would be done through (answer d.) a change request.
Exam 2 | #93. In your organization, a project management team has subcontracted a particular work to a service company. The process of ensuring that this service company's performance meets the contractual requirements is called: |  | Plan Procurement Management | Control Procurements | Procurement Management Plan | Staffing Management Plan | Answer b. | Answer b. Control Procurements: Through the process of elimination, answer options c., “Procurement Management Plan,” and d., “Staffing Management Plan,” can be removed from consideration. Both are Outputs and neither is a process, which is what the question asks for. Also, the fact that the project management team “has subcontracted work to a service company” implies that this project is beyond the planning period and is very likely in an executing phase. These rules out option a., “Plan Procurement Management,” as a viable option. Ensuring the service company meets contractual requirements happens in “Control Procurements,” the correct answer.
Exam 2 | #94. You are the Project Manager for a construction company. You are currently working on a project to build a new dam across a river. A recent change in a law governing ecological preservation will impact your project and change your project scope. What should you do? |  | Proceed as planned, and ignore the change in law | Create a documented change request | Consult with the project sponsor and the stakeholders | Stop all project work until the issue is resolved | Answer b. | Answer b. Create a documented change request: Change Requests allow for considered evaluation of documented, proposed changes by an individual or Change Control Board to understand the impact it will have on the project. Once understood, the change is approved or rejected, it is documented appropriately within the Project Management Plan, passed to Monitor and Control Project Work for implementation, Stakeholders are notified of the change (approved or rejected) and changes are implemented. Changes are expected, answer a. proposes ignoring the need; c. suggests consulting the sponsor; the PM has created a Change Control Process within the project Management Plan which the sponsor has agreed to do. Option D suggests stopping all project work, which may or may not be required. The Integrated Change Control Process is indeed project work in and of itself.
Exam 2 | #95. You are the Project Manager of a company in the aviation industry. You are engaged in a project that will create a new and improved product for your company. The company has high expectations for this product. More than five million users around the globe use other products made by this company. These users will be impacted by the new product. Which of the following is a technique that can be used to gather opinions about how to implement the new product with the least impact on existing users? |  | Identify Risks | Anonymous Trigger | Risk Mitigation | Delphi Technique | Answer d. | Answer d. Delphi Technique: This question tests the student’s understanding of the ITTOs. By way of elimination, answer options a., b., and c. may be removed from consideration. None of these are Tools/Techniques, which is what the question is asking for: Identify Risks is a process, Anonymous Trigger is not a concept mentioned in the PMBOK, and Risk Mitigation is a risk response strategy. The Delphi Technique is a key tool in Identifying risk as defined in the PMBOK.
Exam 2 | #96. You are the Project Manager of a BOT project being executed in Singapore. It’s a complex project and it involves 3 teams coming from different organizations and 150 Work Packages. These Work Packages have exactly 1650 activities associated with the project. Your assistant presents a structure that shows the connection between different work packages, or activities, and project team members. Now you can see which project resource is assigned to each work package. What is this structure called? |  | Responsibility Assignment Matrix (RAM) | Text Oriented Charts | Organizational Breakdown Structure | Work Breakdown Structure | Answer a. | Answer a. Responsibility Assignment Matrix (RAM): A Responsibility Assignment Matrix (RAM) shows the project resources assigned to each work package. It is used to illustrate the connections between work packages, or activities, and project team members.
Exam 2 | #97. What is NOT true about Management by Objectives (MBO)? |  | It is a system of managerial leadership that defines individual managerial responsibilities in terms of corporate objectives. | Managers and workers set individual goals that contribute to the achievement of the corporate objectives. | Goals and objectives should reflect project goals and align well with the client's goals. | It works well only when it is driven by the lower staff. | Answer d. | Answer d. (Not) It works well only when it is driven by the lower staff: MBO is an agreed-upon process where both the Manager and the staff define specific objectives and agree how to achieve each objective in sequence. In this system of management, individual goals are synchronized with the goals of the organization.
Exam 2 | #98. Your team has completed the project, and the customer has accepted the completed project scope. The Project Management Office has reported back to you, since you were the Project Manager, saying that the lessons learned have not been completed. What is the status of your project NOW? |  | The project is complete because the customer has accepted the deliverables. | The project is incomplete because the project needs to be re-planned. | The project is incomplete until all project and product deliverables are completed and accepted. | The project is completed because the project has reached the due date. | Answer c. | Answer c. The project is incomplete until all project and product deliverables are completed and accepted: Answer option c. is correct because lessons learned are deliverables of our project – just not direct deliverables to the customer. If the project was truly completed, we would disband the team but we cannot do that until all of our closing activities are completed – including submission of lessons learned. Option a. is incorrect because we have deliverables that are internal (to the organization), specifically, the lessons learned, as well as the deliverables to the customer. Answer option b. can be eliminated because there is no indication in the facts as presented in the scenario that “the project needs to be re-planned.” And option d. is incorrect because there is no indication in the scenario that “the project has reached the due date.” (It may well be ahead of schedule!) The only answer option that is supported wholly by the proposed scenario is option c.
Exam 2 | #99. The customer called to tell you that he has just learned that the paint for the interiors of the laboratory center which has a very particular purpose has been changed without notification or consultation. You have not been informed either and you need to investigate this issue further. You find out that one of the team members has changed the paint type, claiming that the original paint specified is not appropriate for lab work and causes fatigue with the lab workers. You discuss the matter with the paint experts, who confirm that the team member is correct. This is an example of: |  | The change effect theory | Risk-sharing | An ineffective change control system | A temporary solution | Answer c. | Answer c. An ineffective change control system: An ineffective change control system because no integrated change management process was followed. The team member could have been wrong, and this decision might have impacted other elements of the project of which the team member is unaware.
Exam 2 | #100. A time-boxed iteration of one month or less (typically two weeks) during which a “Done”, usable, and potentially releasable product increment is created is called a: |  | Meeting | Sprint | Deliverable | Product | Answer b. | Answer b. A Sprint is a time-boxed iteration of one month or less (typically two weeks) during which a “Done”, usable, and potentially releasable product increment is created.
Exam 2 | #101. Betty, an Agile Project Manager, is assigned to a project that requires the transformation of the whole organization. This transformation will allow the company to align its strategy to the projects that need to be planned and executed to maximize its profitability. What will be valued the most using Agile approaches? |  | The ability to respond to change instead of following a master plan. | The ability to create a deployment plan will not be changed. | Openness to adapt to change when required. | The ability to create multiple project plans as there is no way to finish all work with one master plan. | Answer a. | Answer a. Even though plans are good, project managers need to respond to changing conditions and not be stuck with one master plan under the agile mindset. Plans need to be flexible enough to allow changes to be incorporated without losing sight of the goal in place.
Exam 2 | #102. Kanban translates to “card you can see” in Japanese. It is a form of visual management taken from Lean Manufacturing for monitoring |  | The team creating management reports | Work Velocity and enabling user story creation | The Product Owner and the Product backlog | Work in Progress of the Development Team | Answer d. | Answer d. Kanban is a framework inspired by Lean Manufacturing and utilized in software development and knowledge work. It focuses on the Kanban board, which shows work in progress and limits of current work.
Exam 2 | #103. Rough Order of magnitude (ROM) estimate may be used during ________ project management process group. |  | Initiating | Planning | Executing | Closing | Answer a. | Answer a. Initiating: ROM estimating (ballpark) is used to approximate costs to develop the Project Charter in the Initiating process. Later, budgetary and definitive estimates are estimated when more accurate information is needed.
Exam 2 | #104. The Scrum approach to documentation is: |  | Do no documentation because it is a waste of time | Do sufficient documentation to prove you have done a good job | Do more documentation than usual, because all Agile is risky | Do the necessary documentation to support the development and use of the product | Answer d. | Answer d. Agile values doing the necessary work (i.e. documentation) to satisfy the requirements of the product and the customer requirements. Agile is not an excuse for lack of documentation on a project.
Exam 2 | #105. In a simple Project Life Cycle, activities such as Acceptance, Handover, and Archiving of records will occur during _____ . |  | Concept | Development | Execution | Termination | Answer d. | Answer d. Termination: Termination is considered a premature and special form of Closure. “activities such as Acceptance, Handover, and Archiving of records” would occur towards the end of the Project Life Cycle; and that would be part of the project closure.
Exam 2 | #106. An Agile mindset is crucial in management roles for organizations that are trying to undertake more quick and dynamic projects. Decisions, actions, directions, and vision often come from the management level, especially in the hybrid world. When an organization thinks about applying Scrum, they shouldn’t expect only changes in how teams work but also, they should start considering how the management team intends to operate. Who ensures that work is aligned with leadership's direction and Product Vision? |  | The Product Owner | The Scrum Master | The Team | The Agile Coach | Answer a. | Answer a. The Product Owner: The Product owner ensures work is aligned with the leadership’s direction and product vision.
Exam 2 | #107. Within the Agile Manifesto, a line reads “over processes and tools”. Which selection from the statements below completes the Manifesto: |  | Customer and employees | People and relationships | Individuals and interactions | Client and individual | Answer c. | Answer c. Agile Manifesto is focused on four main values; individuals and interactions over processes and tools is one. Agile signifies the importance of the human element in the process; per Agile, having the right group of individuals is more important than having the proper tools and the best tools with the wrong people are worthless.
Exam 2 | #108. A project running in India has been facing many problems of delay, rework, and other failures. You have been called up to sort it out. After a week of observation and analysis of documents you have found out, there is inefficiency, low productivity, and tardiness. You have redesigned the whole structure by setting goals and rewarding team members for increased productivity. After a few weeks of implementation, the project has started making deliverables as per the plan. What type of leader are you? |  | Transformational Leader | Charismatic Leader | Systematic Leader | Transactional Leader | Answer d. | Answer d. Transactional Leader: Transactional leader focuses on goals, feedback, and accomplishment to determine rewards; It is also called management by exception.
Exam 2 | #109. Ineffective project meetings cost a significant amount of time and cause a significant amount of labor. The application of some simple rules can make meetings much more effective. Which of the following does NOT contribute to making meetings more effective? |  | Have a meeting policy defined in the Communications Plan | Meet at least once a week | Circulate an agenda before the meeting and stick to it | Make all actions personal and timely and follow them up | Answer b. | Answer b. (Not) Meet at least once a week: Meetings are briefly covered in Resource Management, focused on establishing ground rules of etiquette and order. A concise definition of the purpose and schedule of meetings (including answer options a., c., and d. are better found as a Tool & Tech Meetings in Plan Communications Management.
Exam 2 | #110. As the Project Manager, you are currently estimating the costs for your project. You are using the Analogous Estimating technique, which is considered to be . |  | Least accurate | Bottom-Up estimating | Regression Analysis | Most accurate | Answer a. | Answer a. Least accurate: Through the process of elimination, answer options b. and c. are removed from consideration: Bottom-Up Estimating is the opposite of Analogous (or Top-Down) Estimating, and Regression Analysis is a statistical tool used in Monitoring and Controlling Project Work. Between the two options that remain, Least Accurate is the best option.
Exam 2 | #111. __________ is a key tool of project monitoring and control that consists of tools, procedures, and processes necessary to collect and disseminate the information generated as an outcome of the project management processes. |  | Earned Value Analysis | Project Management Information System | Project Management Plan | Project Charter | Answer b. | Answer b. Project Management Information System: Through the process of elimination, answer options c. The Project Management Plan and d. the Project Charter can be immediately removed from consideration as they are not tools or techniques. Back to the question, the statement defines tools, procedures necessary to collect and disseminate information… It eliminates Earned Value Analysis, an important tool used to monitor and control Cost, Schedule, and Scope. PMIS, the Project Management Information System, defined as a system containing tools and techniques to gather, integrate, disseminate the Outputs of project management processes used to support the project from Initiating to Closing and includes both manual and automated systems.
Exam 2 | #112. Management wants to be sure that the project is following the defined Corporate and Project quality standards. Which of the following would the management use to determine that the project is, in fact, following these defined quality standards? |  | Risk Management Plan | Work Breakdown Structure (WBS) | Statement of Work | Quality Audit | Answer d. | Answer d. Quality Audit: This question is rather easy using the process of elimination, answer options a., b. and c. are not tools, they would be inputs at best. On the deeper level, Quality Audits test the process and confirm the project work complies with Organizational policies, processes, and procedures. The Manage Quality process focuses on process compliance and improvement, not the actual product of the project.
Exam 2 | #113. The Precedence Diagramming Method creates a network of activities and uses boxes to show the activities and arrows to link them. This method is also known as_____. |  | Activity-on-Node | Activity-on-Arrow | Critical Path Method | None of the above | Answer a. | Answer a. Activity-on-Node: As discussed in the Slide Presentation, the Precedence Diagramming Method (PDM) is commonly referred to as Activity-on-Node, so answer option a. is the correct answer. Technically, “Activity-on-Node (AON) is one method of representing a Precedence Diagram,”
Exam 2 | #114. You are in the process of auditing the various project processes and their performance. Which of the following is the LEAST appropriate Tool/Technique to use in this process? |  | Process Decision Program Charts | Prioritization Matrices | Activity Network Diagrams | Variance Analysis | Answer d. | Answer d. Variance analysis: Variance analysis is a Tool & Tech used in controlling the project costs. It is a part of Earned Value Measurement, to help in forecasting future cost and schedule. Answers a., Process Decision Program Charts, and b., Prioritization Matrices, and c., Activity Network Diagrams, are Quality Management and Control tools described in the Tools and Techniques defined for Quality Assurance.
Exam 2 | #115. A pharmaceutical company wants to launch a new over-the-counter medication for Covid 19 in the USA. The project manager is identifying project communication constraints. Which of the following is NOT a valid constraint? |  | The Communications assistant on the project may not be available throughout the entire project | All the major key stakeholders should attend the project progress meetings. | The teams are working in different geographical locations. | Get an FDA approval before producing or selling the medicine | Answer d. | Answer d. Get an FDA approval before producing or selling the medicine. FDA approval is not a communication constraint in this situation but a dependency or a requirement. A constraint is a limiting factor that affects the execution of a project.
Exam 2 | #116. When it comes to project and product compliance, what is the key responsibility of the project manager in this respect? |  | The project manager needs to define compliance requirements which should be included in the project management plan. | The project manager should create a project management plan and project documents but not the compliance plan. | The project manager is in charge of monitoring and controlling the quality aspect of the project documents. | The project manager manages the project and the team as per the project management plan. | Answer a. | Answer a. The project manager needs to define compliance requirements that should be included in the project management plan: The project manager has to define compliance requirements that should be included in the project management plan (as part of the Quality Management Plan). The PM needs to plan and manage project compliance and classify compliance categories based on industry standards and requirements.
Exam 2 | #117. One of the Project Manager’s major responsibilities is to coordinate the project resources to carry out the project as per the Project Management Plan. In _______ process group, the processes help the Project Manager fulfill this responsibility. |  | Monitoring & Controlling | Closing | Planning | Executing | Answer d. | Answer d. Executing: Only the processes of the Executing Process Group match the description provided in this question: “coordinate project resources to carry out the project as per the Project Management Plan.” “This Process Group [Executing] involves coordinating people and resources…in accordance with the Project Management Plan.”
Exam 2 | #118. You are a new Project manager and you are already having issues with the stakeholders, particularly the group of customers who don’t seem to understand that they cannot change the scope any time they please. You need to explain that the change in the requirements will potentially impose a threat to the project quality compliance. Which of the following actions can you take? |  | Send emails to stakeholders asking them to stop requesting changes | Hide the scope statement and use it only with the team | In the scope statement, explicitly state what is out of scope for the project | Meet more often with stakeholders | Answer c. | Answer c. In the scope statement, explicitly state what is out of scope for the project: In the scope statement, explicitly state what is out of scope for the project. Project exclusions identify what is excluded from the project. Explicitly stating what is out of scope for the project helps manage stakeholders’ expectations and can reduce scope creep.
Exam 2 | #119. A new project manager needs to deliver a strategic agile project. The vendor working with the team is in another country. Though this vendor has delivered excellent quality work on time in the past, they are currently behind schedule. The team explains to the project manager that their attempts to get the vendor back on schedule have failed. They have sent emails and phoned, but the vendor only gives vague, noncommittal responses. The project sponsor insists that this vendor is essential to the success of the project and an important partner of the business. Which action should the project manager take? |  | Contact the vendor and be direct about the consequences of their actions and delays. | Create a virtual workspace for the team so that everyone is aware of and accountable for their tasks and aware of due dates. Include the project sponsor. | Work with procurement to amend the vendor’s service agreement, with specific terms and conditions for work. | Ask the project sponsor to use personal influence to get the vendor back on schedule. | Answer b. | Answer b. Communication in virtual teams can be challenging. Being direct may NOT leave a good first impression and revising a service agreement may be perceived as hostile by the vendor. This vendor is critical to the success of the project and important to the business, and the team may be getting demoralized by their unsuccessful attempts to manage the vendor. Be attentive of these factors using active listening and emotional intelligence. Creating a workspace that enables everyone on the project team to see the project work and be accountable for delivering their work on time is the best option here. Including the project sponsor in the virtual workspace as an informed party is a smart move.
Exam 2 | #120. Which of the following is NOT true about the Project Management Plan? |  | It is a living document and is subject to version control. | It forms the baseline against which future actions are measured. | Primary purpose of the Project Management Plan is to define and communicate how the project will be executed, monitored, and controlled. | Primary purpose of the Project Management Plan is to communicate the Project Manager’s intentions to the sponsor. | Answer d. | Answer d. (NOT) The primary purpose of the Project Management Plan is to communicate the Project Manager’s intentions to the sponsor and the management: Answers a., and b., make sense. The primary purpose of the Plan is to communicate how the project will be executed, monitored, and controlled to all Stakeholders, not limited to the Sponsor and management.
Exam 2 | #121. The Project Manager is the most interested in ______ as an outcome of the Validate Scope process. |  | Accuracy | Timeliness | Acceptance | Completeness | Answer c. | Answer c. Acceptance: The Validate Scope process is not successfully completed until the customer has accepted the deliverables – that is, until the major Output of the process, Accepted Deliverables, has been achieved. Accuracy, Timeliness, and Completeness are all desirable but they are secondary in comparison with Acceptance.
Exam 2 | #122. You have been managing a project within your organization for 13 months now and you are approaching the closing of the project. You send an email to the key stakeholders about the approaching final days in the project, but much to your surprise, you receive an email from one of your customers who says that he is disappointed in the project because one of the key components is missing. He thinks that the project is a failure and it doesn't correspond to the requirements. He sends you a copy of the project charter underlying the missing component. You explain to him that the requirement was removed several months ago during a meeting that he didn’t attend, although he was duly invited. He should have received meeting minutes, as he was copied to the email, but you never received a response. He is furious at this situation and says that he doesn't remember seeing the minutes and he will sue for breach of contract if the requirement is not delivered. What should you do? |  | Immediately plan to add the requirement back so that you don’t get sued | Tell the manager to request a new project to deliver the requirement | Phone senior management and ask for an emergency meeting to discuss the issue | Raise a change request | Answer d. | Answer d. Raise a change request: The requirement was removed, so the only way to get it back is by requesting a change. The change control board will decide.
Exam 2 | #123. John prepares the risk response strategies and provides a list of key risks to his manager as part of his Risk Management Plan activity. Why does his manager, Jeff, a PMP, ask him to redo his plan? |  | A list of project risks is an Output of risk identification | The Risk Management Plan defines the approaches, tools, and data sources used to perform risk management, roles and responsibilities, budgeting, timing, risk categories, revised stakeholders’ tolerances, reporting formats, and tracking, but not the identified risks | The risk list should also include triggers | John has not involved the project team | Answer b. | Answer b. The Risk Management Plan defines the approaches, tools, and data sources used to perform risk management …: In this problem, John has submitted a Risk Register (a list of key risks and states their risk response strategies) instead of the Risk Management Plan his manager, Jeff, has requested. Answer option b. underscores John’s mistake by describing in some detail the purpose and content of a Risk Management Plan, which was not what John has submitted.
Exam 2 | #124. In a Balanced Matrix organization, two projects have a concurrent need for identical resources. These resources have limited availability and a functional manager who is in charge of the skill in demand. Who is responsible for resolving this conflict over resources? |  | Senior management | Sponsor | Project Manager | Functional Manager | Answer a. | Answer a. Senior management: In a Balanced Matrix organization the Project Manager may have moderate power; however, resources typically are accountable to a functional manager. If the Functional Manager and the Project Manager can’t agree, arbitration to resolution would come from Senior Management.
Exam 2 | #125. A Scrum project team consists of following members EXCEPT: |  | Product Owner | Project Manager | Scrum Master | Development Team | Answer b. | Answer b. A scrum team consists of three roles – Product Owner, Scrum Master, and Development Team. There is no dedicated project manager on a Scrum Team.
Exam 2 | #126. Jess is consulting with a company to assist with their transition from predictive to agile methodology. The leadership team meets with her the first day to discuss their expectations for the Scrum teams. The expectations for internal resources include one Scrum Master, one Scrum Product Owner and 15 Developers per team. Jess’s best response to the leadership team is to: |  | Add the resource recommendations to the PMO Process Documentation. | Recommend the team size be set between three and nine developers. | Recommend team size to include two Scrum Masters. | Recommend a stakeholder analysis meeting to determine the appropriate project team size. | Answer b. | Answer b. The best team size is 3 – 9 developers. Fewer than three are unable to deliver enough in each Sprint and more than 9 will require too much administration
Exam 2 | #127. After a 3-week sprint during which your team has completed the sprint review, you conduct a retrospective. Your team discusses a number of defects that were captured during testing. After a discussion of various approaches to discover the cause of the defects, your team decides to use the following method: |  | Six Sigma | Value stream mapping | Monte Carlo analysis | Lean | Answer a. | Answer a. Six Sigma: Six Sigma helps remove defects from a process. Value stream mapping is used by Lean to remove lags or wasted time. That helps increase efficiency. Monte Carlo analysis is used to determine probabilistic outcomes. Answer a. Six Sigma: Six Sigma helps remove defects from a process. Value stream mapping is used by Lean to remove lags or wasted time. That helps increase efficiency. Monte Carlo analysis is used to determine probabilistic outcomes. Answer a.
Exam 2 | #128. As you develop your project closure documents, you begin to review the project deliverables and develop your checklist of project requirements. Of the options below, the BEST source document for contract closure requirements is the ______ . |  | Project Management Plan | Contract terms and conditions | Work Breakdown Structure | Project Charter | Answer a. | Answer a. Project Management Plan: This question confirms the student’s understanding that the Project Management Plan is a comprehensive plan that includes subsidiary plans; in this case, the Procurement Management Plan coordinates required Project Documents. The Procurement Plan would provide the checklist and project documents referred to in the question but as a subsidiary plan, it can be found in the Project Management Plan. Answer b., terms and conditions may satisfy the needs of controlling the contract but Project Closure requires that it is closed. Answers c. and d. have nothing to do with Procurements (contract) closure and can be removed from consideration.
Exam 2 | #129. A particular part of your project scope has to be outsourced. You are engaged in creating Source Selection Criteria for your contract. You are performing the _______ process. |  | Plan Procurement Management | Close Procurements | Conduct Procurements | Control Procurements | Answer a. | Answer a. Plan Procurement Management: Source Selection Criteria is an Input to the Conduct Procurements process but they are first an Output of the Plan Procurement Management process. If you “are engaged in creating Source Selection Criteria,” you are in the Plan Procurement Management process.
Exam 2 | #130. A Project Manager is working on a hybrid project involving multiple geographic locations. The project team is using emails as the only way to share information. The Project Manager learns that not all team members are receiving information quickly enough. What should the Project Manager do to improve knowledge sharing? |  | Setup a kickoff meeting in one city with all stakeholders. | Do nothing, sharing information is efficient enough as-is. | Setup ground rules. | Setup remote pairing by using virtual conferencing tools to share screens, including voice and video links. | Answer d. | Answer d. As stated by the Agile practice guide, setting up remote pairing and virtual conferences allows the team to better communicate and share project knowledge. This allows the Scrum team to interact on a daily basis.
Exam 2 | #131. The graphical display of accumulated costs and labor hours, plotted on a timeline is known as ______ . |  | Variance report | S curve | Trend analysis | Earned value report | Answer b. | Answer b. S curve: Earned Value and Actual Costs can be mapped against the Planned Value (the Performance Management Baseline (PMB)) Together and when plotted together the three lines form a lazy S-shaped curve and evidence performance (EV and AC) against expectations PV over time. Variance Reports examine the difference between (EV and AC) against PV, on more of a time-slice basis. A Trend Analysis examines performance over time and may use the S-Curve to help understand what is happening on the project. Earned Value Reports likewise evaluate and predict what has happened and help forecast future expectations.
Exam 2 | #132. The customer has been consistently late for approvals on design documentation. The Project Manager has raised the subject in the past, but the delays in approvals have not changed. The Project Manager has just been documenting the delays, nothing more. Which of the following conflict resolution techniques has the Project Manager been following? |  | Collaborate/Problem Solve | Withdraw/Avoid | Force/Direct | Compromise/Reconcile | Answer b. | Answer b. Withdraw/Avoid: In this problem, the Project Manager “has just been documenting the delays, nothing more.” This is fairly passive behavior, particularly compared with three of the answer options – Collaborate/Problem Solve, Force/Direct, and Compromise/Reconcile – all of which are proactive in ways that contrast with the Project Manager’s behavior. The answer option that most closely reflects his/her behavior is option b., “Withdraw/Avoid,” which is “Retreating from an actual or potential conflict situation; postponing the issue to be better prepared or to be resolved by others.”
Exam 2 | #133. You are asked to describe the difference between QA (quality assurance) and QC (quality control). You say that the difference between these two concepts is the following: |  | QA is performed by the team, but QC must be performed by senior management | QA involves planning, but QC involves checking | QA is a management function, but QC involves planning | QA involves planning, but QC is a management function | Answer b. | Answer b. QA involves planning, but QC involves checking: QC is controlling the activity/deliverable using tests, inspections, evaluations, and so on.
Exam 2 | #134. Within the Agile Manifesto, a line reads “over contract negotiation”. Which selection from the statements below completes the Manifesto: |  | Fixed pricing | Customer collaboration | Happy customer | Lump sum contract | Answer b. | Answer b. Agile Manifesto is focused on four main values; customer collaboration over contract negotiation is one. Agile emphasizes the importance of continuous collaboration between the development team and the client throughout the project in order to reach the optimum solution.
Exam 2 | #135. You have to ensure that appropriate Tools/Techniques are used when conducting Procurements. Which one of the following is NOT a Tool/Technique for this process? |  | Advertising | Proposal evaluation | Alternatives Generation | Procurement Negotiations | Answer c. | Answer c. (Not) Alternatives Generation: Through the process of elimination, answer options a., b., and d. can be removed from consideration as they are tools used in the Conduct Procurements process. It is important to mention that Alternatives Generation is used in Controlling Risk as well.
Exam 2 | #136. During the planning phase of your project, your project team has developed several different methods for completing a part of the project scope. This is an example of . |  | Risk Analysis | Alternatives Generation | Alternative Selection | Product Analysis | Answer b. | Answer b. Alternatives Generation: The key phrase in this scenario, “has developed several different methods for completing a part of the project scope,” should help narrow down the answer options. Alternatives Generation ‘is used to develop as many potential options as possible in order to identify different approaches to execute and perform the work on the project.’ Answer c., “Alternative Selection.” is wrong as there is no mention of a selection or choice being made by the team.
Exam 2 | #137. John, in his role as PMO Director, is putting together his quarter end report for the leadership team. One portion of his reporting responsibilities is forecasting internal labor cost of projects. To do so, they use a standard rate for each developer assigned to projects. He sends a request to each of the project managers in his organization requesting their anticipated completion dates for each of their projects. For the Scrum Masters, their BEST source of information to calculate this is: |  | Product Backlog | Burndown graph | Sprint backlog | Cost Management Plan | Answer b. | Answer b. For agile teams, each Sprint should provide similar volumes of work. The Burndown graph will show the volume being completed each sprint. This information can be used to estimate how many Sprints are required to complete the remaining work.
Exam 2 | #138. The Scrum Master notices that the project team discusses only what went right during the retrospective. What should the Scrum Master do? |  | Encourage the team to express the positives of the project only. | Ask the team members a specific question to identify the cause of discussing only the good things during the retrospective meeting. | Encourage the project team to express their negatives as well as their positives. | Encourage the project team to express their negatives but not their positives. | Answer c. | Answer c. A retrospective meeting is a timeboxed session in which the team discusses what went well, what did not go so well, and ways to improve in the next iteration.
Exam 2 | #139. Which of the following is a “hygiene factor” according to Herzberg’s Motivation-Hygiene Theory? |  | Recognition for excellent work | Self-actualization | Good relations with co-workers and managers | Clean clothing | Answer c. | Answer c. Good relations with co-workers and managers: Herzberg considers Recognition a Motivator and the hygiene factors being evaluated are corporate, not personal in nature; a Good relation among co-workers and managers is a hygiene factor. Self-Actualization is the top tier in Maslow’s Hierarchy of Needs.
Exam 2 | #140. Johnathan is the Scrum Master for a team responsible for the deployment of a new website. Mark is a team lead for the Inventory team and processes in his department will change after the website is implemented. He has requested to be part of all Scrum events throughout the project. Johnathan’s BEST course of action is: |  | Add Mark onto the invitation for the Daily Scrum meeting. | Add Mark onto the invitation for the Sprint Review meeting. | Add Mark onto the invitation for the Sprint Retrospective. | Inform Mark that only the Scrum Master, Scrum Product Owner and Development Team participate in Scrum Events. | Answer b. | Answer b. Stakeholders should not participate in Daily Scrums or in Sprint Retrospectives, but are encouraged to attend Sprint Review meetings.
Exam 2 | #141. The Perform Integrated Change Control process is concerned with controlling scope variances. The scope is also controlled by regular performance reviewing and Performance Reports. All of the following are TRUE about Performance Reports except ____. |  | Performance Reports are used to determine if the project is on track. | Performance Reports compare actual with planned time, cost, quality, and scope. | Performance Reports will have an acceptance test | Performance Reports provide an audit trail and project history. | Answer c. | Answer c. (Not) Performance Reports will have an acceptance test: Performance Reports may document and provide feedback regarding the results of Acceptance Testing but are not the Input or Output used to define them. Performance Reports are common inputs and Outputs of many M&C processes including Scope, Cost, Time, Quality Risk, and Procurement. Each section has a description of their use and content. Performance reports provide information about schedule (if the project is on track), Variance Analysis (comparing actual with planned) and summary of changes approved over time (audit trail). Answers a., b., and d. can be removed from consideration.
Exam 2 | #142. Taylor is a project manager in an IT department that has recently transitioned from predictive to agile practices. The team has many questions about what this transition means and how it will be helpful to their work. What should Taylor say to the team? |  | Agile isn’t a set of tools or a single methodology, but a philosophy put to paper in 2001 with an initial 17 signatories. | Agile was a significant departure from the heavyweight document-driven software development methodologies. | These new methods attempt a useful compromise between no process and too much process, providing just enough process to gain a reasonable payoff. | All of the above. | Answer d. | Answer d. All of these statements are true about agile practices.
Exam 2 | #143. The sponsor has asked you to provide the cost estimation for installation, maintenance, and customer support for as long as the product is expected to last. What kind of estimate is this referred to as? |  | Life Cycle Costing | Depreciation | Project Cost Baseline | Payback Period estimate | Answer a. | Answer a. Life Cycle Costing: Costs estimates associated with installation, maintenance, and customer support are considered part of the Product Life Cycle. Answers b., Depreciation would be part of the calculation, and c., Project Cost Baseline would be part of the cost of the Project portion of the product life cycle. Answer d, the Payback Period estimate would be calculated before the project is initiated and the project Charter is created and approved.
Exam 2 | #144. A new project team is setting early priorities, and they plan to gain the customer's trust by delivering value as quickly as possible. Team member C mentions that they have worked with the project sponsor on other projects. How should the project manager connect these two facts and create an advantage for the project team? |  | Make team member C the project leader since they already know the sponsor. | Ask team member C to tell the whole team everything they know about the sponsor so that the team can work better. | Explore how team member C can use personal influence with the sponsor to increase the project's potential for benefits realization | Discuss whether team member C has a conflict of interest in order to maintain an ethical standard. | Answer c. | Answer c. Personal influence is a leadership skill that enables project teams and individuals to use existing relationships, building on them to further project activities and goals. In this case, team member C has an existing relationship that may help the project team to understand more quickly the needs of the project sponsor.
Exam 2 | #145. As a Project Manager, you make sure that quality standards should be followed on your project. Which of the following PMBOK processes identifies the quality standards that need to be followed in the project? |  | Develop Project Charter | Collect Requirements | Plan Quality Management | Manage Quality | Answer c. | Answer c. Plan Quality Management: Through the process of elimination, answer options a., Develop the Project Charter and b., Collect Requirements can be removed from consideration. Manage Quality is worth a second look as it audits planned processes to confirm they are effective and look for opportunities for improvement.
Exam 2 | #146. If an employee is working towards the satisfaction of her safety needs, which of the following is the highest need she has already satisfied according to Maslow’s hierarchy of needs? |  | Physiological | Need for approval from the society | Need for self-esteem | Social | Answer a. | Answer a. Physiological: According to Maslow’s hierarchy of needs, if the employee is working towards the satisfaction of her safety needs, then she has achieved the level of needs directly below safety needs, the physiological needs level. The need for approval from society, the need for self- esteem, and social needs occupy levels above the safety and physiological needs levels.
Exam 2 | #147. A hybrid radio communications project is running an agile software track and a predictive installation track. Halfway into the project, delays are accumulating due to misaligned deliverable releases between the two tracks. Which two elements should the project manager combine to produce a common network diagram? |  | Definition of Ready with dependency milestones | Epic breakdown with work breakdown structure | Product backlog with critical path task sequence | Definition of Done with exit criteria | Answer a. | Answer a. Definition of Ready with dependency milestones.
Exam 2 | #148. When the ratio of Earned Value over Planned Value is greater than one, it would be correct to say that _____. |  | You have completed less work than the planned work. | You have completed more work than the planned work. | You are earning less than spending. | You are earning more than spending. | Answer b. | Answer b. You have completed more work than the planned work: Answer options c and d are removed from consideration as (typically) a project doesn’t make money until the product of the project transitions to its customer. The question asks if we have completed more or less work than planned. Since the question states the ratio is greater than one, more is the correct choice. The ratio compares the Planned Value (Performance Measurement Baseline), the Earned Value, and the Actual Cost. An easy way to remember this is by comparing the variance to a dollar. In this case, we are over 100% meaning we are gaining more in deliverables than planned in return for every dollar spent.
Exam 2 | #149. Peter is a Project manager in an Agile project. His team is working on incremental delivery and has frequent meetings with the team, the vendors, and customers. The main topic at the meetings is to do which one of the following? |  | Do more than minimum | Update activity list | Create a minimum viable product | Look for new opportunities | Answer c. | Answer c. Create a minimum viable product: Minimum Viable Product is a version of the product that has just enough features to satisfy early customers and provide feedback for future product development. This is one of the key features of the Agile project development approach.
Exam 2 | #150. You are the Project Manager for the Moon Project. As part of quality management activities, you have listed the cost of quality, both for conformance and non-conformance. Which of the following is not an attribute of the cost of non-conformance? |  | Safety measures | Downtime | Loss of customers | Rework | Answer a. | Answer a. Safety measures: the keywords in the question are Cost of Quality, conformance, and non-conformance. Costs of Non- Conformance are internal (found on the project) and included Rework (Downtime) and Scrap, and External (found by the customer) and include liabilities, Warranty Work, and Lost Business. Safety is not considered a Cost of Quality either Conformance or Non-conformance.
Exam 2 | #151. The Monitor Stakeholder Engagement process is all about watching the relationships and optimizing plans for effective stakeholder engagement. Which of the following is not a key input to this process? |  | Change Requests | Stakeholder Register | Work Performance Data | Issue Log | Answer a. | Answer a. (Not) Change Requests: While often an input (and Output) the process Monitor Stakeholder Engagement is designed to optimize the relationship with the Stakeholder Engagement and leverage the tools to propose changes to improve the processes involved. In this case, Change Requests are an Output of the process, not an input. Answers b., Stakeholder Register, c., Work Performance Data, and d., the Issue Log are all valuable inputs to the process.
Exam 2 | #152. Spencer is about to lead his first Stand-up Daily Scrum meeting with his new team. The previous Scrum Master was transferred to a different department, and he is taking over mid-Sprint. In his 9 am meeting, he knows to keep his team’s focus on all of the following EXCEPT: |  | What they have accomplished since yesterday’s meeting. | The operational work they completed yesterday. | What they expect to accomplish today. | The obstacles they have discovered that are impeding progress. | Answer b. | Answer b. Daily Scrums are to discuss project related work and should not include conversations about operational work that is unrelated to the Sprint.
Exam 2 | #153. Your sponsor wants to know how the knowledge gained from the project work is transferred for project continuity. He is requesting a chart that shows project responsibilities and the workflow within the team. You meet and explain the project communications flow using a chart. This chart depicts the involved people and departments as well as the workflow on the project. What kind of chart is this? |  | Influence chart | Context diagram | Cause and effect diagram | Affinity diagram | Answer b. | Answer b. Context diagram: A context diagram visually shows the involved people in the project and the work they are responsible for. It shows how project information is communicated with the relevant stakeholders.
Exam 2 | #154. You are currently planning your project activities. Some members of your organization are against taking up the project because they state that it's better to buy the same product from an outside source. Others within the organization feel that building the product in-house will provide exposure to new technologies. What Tool/Technique should the Project Manager use to choose between the options available? |  | Make-or-Buy Analysis | Fish Bone model | Ishikawa diagram | ROI analysis | Answer a. | Answer a. Make-or-Buy Analysis: Make or Buy Analysis is a Tool or Technique in the Plan Procurement Management process used to determine if it is possible and practical for the Project Team to accomplish the work required or if it would be better to purchase it from outside resources. Criteria used include current capability, budget or schedule constraints, direct and indirect costs. Once a decision is made (an Output of the process) it becomes an input to the Conduct Procurements process (Statement of work); the Procurement Management Plan dictates how the work is (re)introduced into the organization if it is to be made.
Exam 2 | #155. As a Project Manager, you are evaluating the better option between buying and making wood furniture. If you buy, the cost would be $225,000, and the cost of procurement and other related costs is $5,000. If you make the product in-house, you need 19 team members working for 6 months. The salary of each of the members would be $1,800 per month, and the overhead cost is $65,000. What should you do? |  | Buy the furniture | Make the furniture | Partly buy and partly make | Go for opportunity cost logic | Answer a. | Answer a. Buy the furniture: To Buy, the cost would be $230,000 (the $225,000 cost of the furniture, plus the related costs of $5,000). To Make, the cost would be $270,200 (19 workers at $1,800 per month for 6 months would cost $205,200, plus the overhead of $65,000). Buying is less costly.
Exam 2 | #156. You are in the middle of a performance review at the end of the first year of a $5,000,000 budget project. The earned value analysis shows that the PV is $2,500,000, the EV is $2,000,000, and the AC is $1,500,000. What can be determined from these figures? |  | The project is behind schedule and over budget. | The project is ahead of schedule and under budget. | The project is ahead of schedule and over budget | The project is behind schedule and under budget. | Answer d. | Answer d. The project is behind schedule and under budget: This question confirms the student’s understanding of two important Earned Value Measurements, Cost Performance Index (CPI), and Schedule Performance Index (SPI). The calculation of the former is CPI = EV (Earned Value)/AC (Actual Costs); and of the latter, SPI = EV/PV (Planned Value). In this problem, the CPI is 1.33. As you learned in class, any CPI result over 1.0 is a desirable result as it indicates the project is under budget. The SPI is 0.8. Also, as you learned in class, any SPI result under 1.0 is not good because it indicates the project is behind schedule. Answer option d., therefore, is the correct answer: “The project is behind schedule and under budget.”
Exam 2 | #157. Which of the following is known as the formal procedure for approving the project work to ensure that it’s done at the right time? |  | Project Planning | Work Authorization System | Cost Estimation | Organizational procedures | Answer b. | Answer b. Work Authorization System: The correct answer, answer option b., “Work Authorization System,” is a collection of procedures intended to “ensure that the work is done by the identified organization, at the right time, and in the proper sequence.” First introduced as a common internal Enterprise Environmental Factor it is considered part of Project Management Information Systems (PMIS) and is referenced as an input, tool, and Output throughout the Execution and M&C process groups.
Exam 2 | #158. ____ is the amount of time that “a successor activity can be advanced with respect to a predecessor activity.” |  | Float | Free Float | Lag | Lead | Answer d. | Answer d. Lead: This question tests the student’s recollection and understanding of Critical Path Method terms and concepts. The wording in the question describes answer option d., Lead.
Exam 2 | #159. There are five stages of development that teams may go through. Which of the following is the correct order in which these stages occur? |  | Forming, Storming, Norming, Performing, Adjourning | Norming, Storming, Forming, Performing, Adjourning | Forming, Norming, Performing, Storming, Adjourning | Forming, Performing, Norming, Storming, Adjourning | Answer a. | Answer a. Forming, Storming, Norming, Performing, Adjourning: Tuckman’s “five stages of development [in]…the correct order” is, as shown in answer option a., “Forming, Storming, Norming, Performing, Adjourning.” The other options display the five stages – but in incorrect orders.
Exam 2 | #160. Validate Scope is the process of formalizing acceptance of the completed project deliverables. When should this process be done? |  | At the beginning of project | During the planning processes | Before Close Project or Phase | At the end of the project | Answer c. | Answer c. At the end of each phase of the project: While Customer Acceptance happens in Validate Scope, the next steps are to confirm all Procurement Contracts have been reconciled and close and formally initiate the Close Project or Phase process.
Exam 2 | #161. In which of the following does the Project Manager manage and direct project resources in carrying out the Project Management Plan? |  | Resource planning | WBS | Monitoring work progress | Executing Process Group | Answer d. | Answer d. Executing Process Group: A key fundamental concept is that there are five process groups Initiating, Planning, Executing, Monitor and Controlling, and Closing. Executing the plans established and summarized in the Project Management Plan, work (carrying out the project specifications) happens in the Execution Process Group. Resource Planning determines how it will be accomplished, the WBS defines what needs to be done and Monitoring Work Progress is comparing what is happening in Execution against the plan.
Exam 2 | #162. The calculation of pricing for a project can be extremely complex. Accurate cost estimates and price quotes from vendors need to be evaluated. Which of the following facilitates cost estimation of a project by a structured decomposition of the total effort into individual activities, and by defining cost elements of labor, material, and equipment? |  | Cost Estimation Plan | Cost Management Plan | WBS | Bottom-up estimating | Answer c. | Answer c. WBS: Work Breakdown Structure decomposes the Scope Statement into smaller manageable components called Work Packages or Activities. The key advantage is that it becomes a visible, graphical, hierarchical structure that facilitates cost estimation. If it is not in the WBS, it will not be done in the project. Answer a., a Cost Estimation Plan sounds good but in fact, they are OPA Tools used in Estimating Activity Costs; b., the Cost Management Plan uses the Project Management Plan which includes the Scope Baseline (Scope Statement, WBS and WBS Dictionary) as key inputs to help define the approach of managing costs. Answer d. Bottom-up estimating is one of the estimating tools and techniques defined within the Cost Management Plan and is used to determine the costs of work packages and activities.
Exam 2 | #163. Donald, a Scrum Master on an Agile project, is planning the second sprint of an agile project. The team performed well in the first sprint, but he wants to improve the team's cohesiveness. Donald has noticed that a specific team member is not aligned with the team's expectations. As a project manager, he understands that it is not enough to have the technical ability to develop a product and deliver value. What should Donald do with the team member? |  | Take him out of the team. | Coach and mentor him to be aligned with all expectations. | Reorganize the team. | Do not do anything, as the team will adjust with time. | Answer b. | Answer b. The first action to take is to coach and mentor the team member who is not aligned.
Exam 2 | #164. Communicating and working with stakeholders to address their issues and meet their needs is an objective of _______ process. |  | Manage Communications | Identify Stakeholder Needs | Manage Stakeholder Engagement | Monitor Communications | Answer c. | Answer c. Manage Stakeholder Engagement: “Communicating and working with stakeholders to address their issues and meet their needs,” is a key feature and the stated purpose of the Manage Stakeholder Engagement process.
Exam 2 | #165. In Agile, each story should be deployed and tested into an integrated environment. The Product Owner would not sign off stories that were only running on a developer’s machine. The developers carried on with stubs, mocks, and local automated tests. Pretty soon it became apparent that the Product Owner was not willing to make the concession on quality and sign off work they had not seen running in a “proper” environment. Who is eligible to initiate a cancellation of the Sprint? |  | The Development Team | The Scrum Master | The Stakeholders | All answers are correct. | Answer d. | Answer d. All answers are correct: Sprint can be canceled before the Sprint time-box is over. Only the Product Owner has the authority to cancel the Sprint, although he or she may do so under influence from the stakeholders, the Development Team, or the Scrum Master.
Exam 2 | #166. When might it be helpful for the organization's Contracts Administration or Legal department to participate in discussions with the customer? |  | When the customer requests additional wording, not currently in the contract | When the project has cost overruns | When the project has a schedule slippage that includes changes to the critical path | When defects are detected | Answer a. | Answer a. When the customer requests additional wording not currently in the contract. The correct answer to this question is not stated in the PMBOK. However, it is common knowledge that only authorized personnel in the organization can actually make changes to the contract. The “authorized personnel” may be the organization’s legal and contract professionals but typically not its project managers. The test taker might also easily arrive at this conclusion by way of the process of elimination. Project cost overruns, schedule slippage impacting the critical path, and defects that have been discovered are all matters frequently handled by the project manager without the participation of – or need for – “the organization’s Contracts Administration or Legal department.”
Exam 2 | #167. You are currently in the planning process, and you have identified the risks associated with your project. What is the next step? |  | Assign probability and impact values using qualitative analysis | Use the Delphi Technique to confirm the identified risks | Identify the response strategies for the identified risks | Start working on the creation of the project schedule | Answer a. | Answer a. Assign probability and impact values using qualitative analysis: The planning processes associated with Risk are a good example of Progressive Elaboration. Plan Risk Management defines HOW Risk will be managed, identified, analyzed and how to create the risk register. Once the risks are Identified, they are qualified (P&I), quantified ($$$) and a risk response plan is determined. Each process updates the register which becomes a key input used in the Monitor Risk Process.
Exam 2 | #168. The________ is the document that is composed mainly of identification information, assessment information, and stakeholder classification information. |  | Stakeholder Management Plan | Stakeholder Engagement Assessment Matrix | Stakeholder Register | Project Management Plan | Answer c. | Answer c. Stakeholder Register: Answer a., the Stakeholder Management Plan establishes the processes to effectively engage Stakeholders through an analysis of their needs, interests, and potential impact on project success; b, the Stakeholder Engagement Assessment is a table used to rate Stakeholders as Unaware, Resistant, Neutral, Supportive and Leading toward a goal-setting relationship improvement plan; d., the Project Management Plan is a comprehensive plan that coordinates all the knowledge area process management plans. Each of these can be removed from consideration. The Stakeholder Register, option c is the repository for the identification, assessment information, and classification of Stakeholders.
Exam 2 | #169. Which of the following techniques is used to evaluate the degree to which the data about risks is useful for risk management? |  | Decision Tree | Probability-Impact Matrix | Simulation | Data Quality Assessment | Answer d. | Answer d. Data Quality Assessment: Risk Data Quality Assessment, is defined in the PMBOK as ‘a technique to evaluate the degree to which the data about risks is useful for risk management… the degree to which the risk is understood, and the accuracy, quality, reliability and integrity of the data about the risk.’ Eliminated answers include Decision Tree, and Simulation, Quantitative Risk analysis tools & techniques, and Probability-Impact Matrix. Those are the Tools/Techniques used to map identified risks based on their priority.
Exam 2 | #170. Close Project or Phase process differs from the Close Procurement process because: |  | Procurement closure involves validation that all work and deliverables are acceptable, whereas the Close Project or Phase does not. | Close Project or Phase is only a subset of Close Procurement. | Close Project or Phase finalizes all activities across all Process Groups, formally ending project or phase work; Control Procurements completes each project procurement, documenting agreements for future reference. | Procurement closure is performed by the Seller; the Close Project or Phase is performed by the Buyer. | Answer c. | Answer c. Close Project or Phase finalizes all activities across all Process Groups formally ending project or phase work; Control Procurements completes each project procurement, documenting agreements for future reference: Close Procurement formally ends each Contract or Agreement signed to deliverProduct, Service or Result not created/performed internally by the organization. Its purpose is to provide the seller with formal written notice that the contract has been completed. OPAs are updated including a Procurement file (the closed contract) Deliverables acceptance (in accordance with the terms of the agreement) and lessons learned on recommendations for improvement , the vendor experience, and if the vendor should be considered on other projects. Close Project or Phase is the final transition of the Product, Service, or Result of the phase or project; and OPA updates, Project Files (the results of the project), Project or phase closure documents (including Customer Acceptance, or perhaps the reason for termination), and Historical Information (lessons learned from the project).
Exam 2 | #171. You are in the Close Project or Phase process. Because of some unfortunate circumstances, the project was delayed, causing cost overruns at the end of the project. Which of the following statements is true? |  | You should document the circumstances as lessons learned. | You should pay particular attention to archiving the financial records for this project. | Your project ended because of starvation as a result of the cost overruns. | You should document the circumstances surrounding the project completion during the Scope Verification process | Answer a. | Answer a. You should document the circumstances as lessons learned: Historical Information is included as an element of Organizational Process Assets Updates, an Output of Close Project or Phase. Lessons learned are a critical asset used to leverage what went right and avoid what went wrong; it should include information on issues, risks as well as techniques that worked well. The causes of the delay that resulted in cost overruns should be included as a lesson learned as well. b., Archiving the financial records provides the detail but perhaps not the cause to be avoided. c., Cost Starvation could be the reason for the delay but doesn’t offer what to do about it. d., The Scope Validation Process formalizes the acceptance of the Project Deliverables which triggers the close project/phase process.
Exam 2 | #172. You have been assigned a high priority project. Your organization is pioneering in new technology with this project and has no previous experience in building a similar product. Management has requested that your estimates are as accurate as possible. Which technique should be used? |  | Top-Down estimating | Top-Down budgeting | Bottom-Up estimating | Bottom-Up budgeting | Answer c. | Answer c. Bottom-Up estimating: Through the process of elimination, answer options b. and d. are removed from consideration: Top-Down Budgeting and Bottom-Up Budgeting are not estimating tools; nor are they budgeting tools. Between the two options that remain, Top-Down Estimating and Bottom-Up Estimating, Bottom-Up is considered to be most accurate because the costs are estimated based on the work packages which represent activities that are decomposed to their lowest level; work package cost estimates are determined and rolled up to their higher level.
Exam 2 | #173. You are the subject matter expert in Scrum. Tara, who is new to Agile and Scrum, approaches you and asks about Scrum events. You explain to her in detail what Scrum events are. A few days later, you decide to test Tara’s knowledge by asking her, which item from the selections below is NOT a Scrum event? How should she answer: |  | Daily Standup | Sprint Planning | Sprint Review | Daily Planning | Answer d. | Answer d. There is no such thing as “Daily planning”. Scrum events are outlined as: The Sprint, Sprint Planning, Daily Standup, Sprint Review and Sprint Retrospective.
Exam 2 | #174. Which of the following BEST describes "when" you perform the Monitor and Control Project Work process? |  | Continuously throughout the project | As soon as every deliverable is completed | At scheduled milestones or intervals during the project | At the end of every project phase | Answer a. | Answer a. Continuously throughout the project: Monitoring is an aspect of project management (collecting, measuring, distributing performance information, assessing measurements and trends) performed throughout the project. Control includes determining corrective or preventive actions or re-planning and following up on action plans to determine their results. Answers a., b., and c., focus on completion points, not the processes and attention required of a Project Manager to get there.
Exam 2 | #175. You are examining the network paths for your project. Path A's duration is 1-2-3-5-8; Path B's duration is 1-3-5-6-7; Path C's duration is 1-2-5-4-9, and Path D's duration is 2-3-4-4-8. Which of the following is the Critical Path for this project? |  | Path A | Path B | Path C | Path D | Answer b. | Answer b. Path B: Identifying the Critical Path on any project is performed in two steps: Step 1, for each path in the network diagram, add the durations of all activities to arrive at a “path duration”; Step 2, compare the path durations of all paths on the network diagram – the path with the highest path duration is the Critical Path. In the problem, the path duration of Path A is 19 (1 2 3 5 8. The duration of Path B is 22 (1 3 5 6 7). The duration of Path C is 21 (1 2 5 4 9). And the path duration of Path D is 21 (2 3 4 4 8). Therefore, the Critical Path is path B, answer option b.
Exam 2 | #176. Your construction project has 190 specifications, 350 blueprints, and multiple parts. Which of the following would provide technical and administrative guidelines to identify the functional and physical characteristics of items and to control changes to those characteristics? |  | Configuration Management | Change Control Meetings | Inventory control | Operational definitions | Answer a. | Answer a. Configuration Management: Configuration Management is introduced as an Organizational Process Asset, as a component of the corporate knowledge base that contains the versions and baselines of all organizational standards, policies, procedures, and any project documentation. Configuration Management is defined as “a collection of formal documented procedures used to apply technical and administrative direction and surveillance to identify the functional and physical characteristics of a product…”. This is the best of the four answer options given.
Exam 2 | #177. A new project starts in a matrix organization. The Project Manager knows that the team is more responsive to their functional managers compared to their PM. To get more support for her project from the functional leaders, the Project Manager decides to prepare a _______ . |  | Project Management Plan | Project Charter | Scope Statement | Resource Management Plan | Answer d. | Answer d. Resource Management Plan: The Resource Management Plan defines the project roles and responsibilities, required skills, reporting relationships, and creates a staffing management plan. Particularly important in matrix organizations, the Resource Management Plan is typically approved by affected Functional Managers who agree to, respect, and help enforce the management roles and responsibilities required to deliver the goals of the project. The Resource Management Plan is a subsidiary plan of the Project Management Plan. The Charter and Scope Statement do not assist in managing resources.
Exam 2 | #178. The project performing organization has a policy that requires air travel by a particular airline to specified destinations. However, the Project Manager has a frequent flier program with another airline, which also flies to this particular destination with the same fares. What should the Project Manager do? |  | Make his travel arrangements | Travel by the company approved airline | Secure approval for travel by his preferred airline | Get the organization to arrange with the airline of his choice | Answer b. | Answer b. Travel by the company approved airline: This question is one of ethics. A good manager leads by example and complies with organizational policies or procedures. Answer a., outright violates a company policy; Answer c., Secure an approval for his preferred airline and d., get the organization to make arrangements with the airline of his choice are good answers that could be exercised as process improvements, but until the policy changes, b., is the best answer.
Exam 2 | #179. A bar chart representation that summarizes related items of work but does not show individual task details is known as _______ . |  | Detailed schedule | Milestone Schedule | Summary Schedule | Schedule Management | Answer c. | Answer c. Summary Schedule: Different Schedule representations are created to satisfy the needs of various stakeholders. The Summary Schedule fills the need of (peer) management where the need is limited to Work package or even more detailed Activity levels. Answer a., Detailed Schedules could be used at the engineering level, to evidence the nuts and bolts of what needs to be accomplished at the activity level; b., Milestone Schedules are used at the executive presentation level, to present the big picture. Answer d. can be eliminated from consideration as it is why such presentations are used.
Exam 2 | #180. What is the FIRST action a Project Manager should take when an unidentified risk event occurs? |  | Inform the customer of the possible consequences | Inform the senior management of the possible consequences | Redo the risk identification process to get prepared for other ‘known unknowns’ | Create a workaround | Answer d. | Answer d. Create a workaround. We know the project is in the execution stage as “an unidentified risk event occurs…” Workarounds are created and executed as PMBOK Recommended Corrective Actions. Workarounds are responses that were not initially planned, but are required to deal with risks that were previously unidentified or accepted passively. Informing the customer and senior management may be required and revisiting the risk identification, qualification, quantification, and planning a secondary response may follow but a Workaround, part of the Change Request process would be the FIRST action taken.

## exam3
Exam Name | Question | quesimgsrc | Answer1 | Answer2 | Answer3 | Answer4 | Correct-Answer | Explanation | answerimgsrc
Exam 3 | #1. Dan has recently joined a software rollout project. The project size is bigger than he is used to experiencing in his previous project. The project has a huge number of stakeholders. A senior member of his team advised him to refer to the project RACI chart for the responsibility clarification of the project team members. Which of the following stands for the C letter in RACI? |  | Consult | Consent | Capable | Collector | Answer option a. | Answer option a. “Consult” RACI stands for Responsible, Accountable, Consult and Inform Answer option a. “Consult” RACI stands for Responsible, Accountable, Consult and Inform
Exam 3 | #2. Mike is managing a large restaurant construction project. The restaurant should be able to host 600 guests on busy nights and for special events. He observes that the kitchen fridge dimensions are much bigger than restaurant doors. Which logical relationship should Mike use to indicate suitable activities sequencing between fridge delivery (activity A) and restaurant doors fixing (activity B)? |  | Finish-to-Start | Finish-to-Finish | Start-to-Start | Start-to-Finish | Answer option a. | Answer option a. “Finish-to-Start” since fridge delivery (activity A) should finish first before Restaurant doors fixing (activity B) can start. Answer option a. “Finish-to-Start” since fridge delivery (activity A) should finish first before Restaurant doors fixing (activity B) can start.
Exam 3 | #3. Alex used the “individual and team assessment” technique to identify the specific training, coaching, mentoring, assistance, or changes required to improve the team’s performance. Alex can expect _____ as an output. |  | Change request | Team performance assessment | Enterprise environmental factors updates | Organizational process assets updates | Answer option b. | Answer option b. “Team performance assessment” because of conducting an evaluation of the team’s overall performance, the project management team can identify the specific training, coaching, mentoring, assistance, or changes required to improve the team’s performance. Answer option b. “Team performance assessment” because of conducting an evaluation of the team’s overall performance, the project management team can identify the specific training, coaching, mentoring, assistance, or changes required to improve the team’s performance.
Exam 3 | #4. Within the Agile Manifesto, a line reads “over comprehensive documentation”. Which selection from the statements below completes the Manifesto: |  | Scope and plan | Processes and tools | Working software | Schedule and milestones | Answer option c. | Agile Manifesto is focused on four main values; working software over comprehensive documentation is one. This Agile statement doesn’t mean the development teams should neglect producing documentation but rather should focus on producing documents that provide value to the project and team.
Exam 3 | #5. You work for an organization that develops software systems under a U.S. Army contract. After creating a couple of features on the first sprint, you would like the team to demonstrate the artifacts that were produced during the sprint. When should this demonstration take place? |  | During the sprint review | During the weekly customer update meeting | In the sprint retrospective | In your next daily stand-up | Answer option a. | The sprint review meeting is used for the development team to demonstrate the work completed. During this meeting, the product owner, scrum master, and stakeholders are present to review the product and suggest changes or improvements.
Exam 3 | #6. The project team is investigating the extent to which the risk relates to other individual project risks. Which risk characteristic are they measuring? |  | Manageability | Controllability | Detectability | Connectivity | Answer option d. | Answer option d. “Connectivity” is the extent to which the risk relates to other individual project risks. Answer option d. “Connectivity” is the extent to which the risk relates to other individual project risks.
Exam 3 | #7. Jack is performing the “Control Resources” process. He intends to review the origin of different resources, whether they are internal to the organization or outsourced. Which input document contains this information? |  | Physical resource assignments | Issue log | Resource breakdown structure | Resource requirements | Answer option a. | Answer option a. Physical resource assignments document the material, equipment, supplies, locations, and other physical resources that will be used during the project. Answer option a. Physical resource assignments document the material, equipment, supplies, locations, and other physical resources that will be used during the project.
Exam 3 | #8. Which of the following is NOT one of the Agile Principles? |  | Welcoming changes - Welcome changing requirements, even late in development. Agile processes harness change for the customer's competitive advantage. | Working software - Working software is the primary measure of progress. | Technical Excellence – Detailed technical requirements and design enhance agility. | Sustainable development - Agile processes promote sustainable development. The sponsors, developers, and users should be able to maintain a constant pace indefinitely. | Answer option c. | Answer option c. Of the available options, C is the only one that is NOT an Agile Principle. The Agile Principle that refers to technical excellence reads: Continuous attention to technical excellence and good design enhances agility. Answer option c. Of the available options, C is the only one that is NOT an Agile Principle. The Agile Principle that refers to technical excellence reads: Continuous attention to technical excellence and good design enhances agility.
Exam 3 | #9. Your organization has been in the technology business for over 30 years. You have been pioneers in introducing fiber communications and that is what you are well known for. However, due to the changes in the global environment, you know that your company has to start using the Agile approach in the implementation of projects. The upcoming project will be the organization's first use of agile, and the sponsor asks you about tailoring the new methodology. How do you respond? |  | Customizing the methodology upfront will allow us to streamline the adoption process. | Adapting the new methodology will be a good way for the team to learn about agile practices. | The team should become comfortable with the new methodology before we consider changing it. | We should wait to adjust our practices until we see where the team runs into difficulties applying them | Answer option c. | Answer option c. Agile practices should be mastered and fully understood before we attempt to customize them. If we change the practices first and then encounter problems, we won’t be able to tell if those problems are due to the changes we made or other causes. Answer option c. Agile practices should be mastered and fully understood before we attempt to customize them. If we change the practices first and then encounter problems, we won’t be able to tell if those problems are due to the changes we made or other causes.
Exam 3 | #10. Amber is teaching a Scrum Master course and is reviewing Sprint Artifacts with her students. Which of the following would NOT be one of the descriptions of the Product Backlog in Amber’s materials? |  | It lists all features, requirements, enhancements, and fixes that constitute the changes to be made to the product in future releases. | Items at the top are more granular than items at the bottom. | It is an ordered list of everything that might be needed in the product. | The Scrum Master is responsible for the Product Backlog. | Answer option d. | The Product Owner is responsible for the Product Backlog contents and prioritization.
Exam 3 | #11. Sam is leading a project team and the team members are still new to each other. Despite the short period they spent together, they show a tendency to be able to work together and adjust their work habits and behaviors to support each other. The team is at the _____ stage. |  | Forming | Storming | Norming | Performing | Answer option c. | Answer option c. Teams can skip some stages thus even though the team is newly formed, the team behaviors are in the “Norming” stage. In this phase, team members begin to work together and adjust their work habits and behaviors to support the team. At this stage, the team members learn to trust each other. Answer option c. Teams can skip some stages thus even though the team is newly formed, the team behaviors are in the “Norming” stage. In this phase, team members begin to work together and adjust their work habits and behaviors to support the team. At this stage, the team members learn to trust each other.
Exam 3 | #12. The Agile manifesto has twelve principles to help project teams align with the Agile values. Which of the below is a correct principle? |  | No documentation is needed to conduct Agile, as it can overburden the team. | Business Drivers and Customers should dictate to the Scrum team how to do project work. | Business Drivers and Customers should work closely with the Development team frequently throughout the project lifecycle. | The team can deliver in increments that best suit them with no consistency for complete customization. | Answer option c. | Answer option c. Business and the Development team must work together daily throughout the project. Answer option c. Business and the Development team must work together daily throughout the project.
Exam 3 | #13. After the assessment of the project team skills, the results showed that one of the members needs more hands-on experience before he can carry out the work effectively. Accordingly, the project manager set a plan for him to shadow another colleague to gain the required skills. This is an example of_____ . |  | Colocation | Team building | Virtual teams | Training | Answer option d. | Answer option d. “Training” shadowing is an example of on the job training Answer option d. “Training” shadowing is an example of on the job training
Exam 3 | #14. A project manager is working on the “Manage communications” process. Which of the following organizational process assets would he consider? |  | Standardized guidelines for the development of information | Organizational communication requirements | Established communication channels | Only A and B | Answer option d. | Answer option d. “Standardized guidelines for the development of information” (Answer option a.), “Organizational communication requirements” (Answer option b.) are both organizational process assets. The best answer is “Only A and B” (option d) Answer option d. “ Standardized guidelines for the development of information ” (Answer option a.), “ Organizational communication requirements ” (Answer option b.) are both organizational process assets. The best answer is “ Only A and B ” (option d)
Exam 3 | #15. While performing the Plan Resource Management process, the project manager reviewed a traditional chart structure which shows positions and relationships in a graphical top-down format. Which of the following is a hierarchical chart? |  | RACI | Resource Assignment Matrix | Burndown chart | Resource Breakdown Structure | Answer option d. | Answer option d. “Resource Breakdown Structure” is the only hierarchical chart among the options. Answer option d. “Resource Breakdown Structure” is the only hierarchical chart among the options.
Exam 3 | #16. The main output of the Identify Stakeholders process is the stakeholder register. This document contains information about the identified stakeholders. Which of the following is not a part of this information? |  | Assessment Information | Identification Information | Assumptions Information | Stakeholder Classification | Answer option c. | Answer option c. “Assessment Information” (Answer option a.), “Identification Information” (Answer option b.) and “Stakeholder Classification“ (Answer option d.) are all part of the information listed in the stakeholder register. The best answer is “Assumptions Information” (Answer option c.). Answer option c. “Assessment Information” (Answer option a.), “Identification Information” (Answer option b.) and “ Stakeholder Classification “ (Answer option d.) are all part of the information listed in the stakeholder register . The best answer is “Assumptions Information” (Answer option c.).
Exam 3 | #17. During the review meeting with the vendor, the project manager was calculating the performance indexes to determine the degree of variance from the baseline. Which technique did the project manager use? |  | Performance Reviews | Earned Value Analysis (EVA) | Trend Analysis | Both A and B | Answer option b. | Answer option b. “Earned Value Analysis (EVA)”. Earned value analysis compares the performance measurement baseline to the actual schedule and cost performance. EVM integrates the scope baseline with the cost baseline and schedule baseline to form the performance measurement baseline. Answer option b. “Earned Value Analysis (EVA)”. Earned value analysis compares the performance measurement baseline to the actual schedule and cost performance. EVM integrates the scope baseline with the cost baseline and schedule baseline to form the performance measurement baseline.
Exam 3 | #18. The project team just performed the Direct and Manage Project Work process. Which of the following would you not expect as an output of this process? |  | Deliverables | Work performance data | Approved change requests | Change requests | Answer option c. | Answer option c. “Approved change requests” is an input to the process, not an output. Answer option c. “Approved change requests” is an input to the process, not an output.
Exam 3 | #19. Sam is working on a new system deployment project. The project has two key parts; a new application development that has unclear requirements and expected to have multiple changes, and a hardware setup part with a clear end-to-end scope of work. Which project life cycle should Sam use? |  | Predictive life cycle | Iterative life cycle | Incremental life cycle | Hybrid life cycle | Answer option d. | Answer option d. “Hybrid life cycle” since the project has a predictive part and an adaptive part it is best to use hybrid lifecycle. A hybrid life cycle is a combination of a predictive and an adaptive life cycle. Those elements of the project that are well known or have fixed requirements follow a predictive development life cycle, and those elements that are still evolving follow an adaptive development life cycle. Answer option d. “Hybrid life cycle” since the project has a predictive part and an adaptive part it is best to use hybrid lifecycle. A hybrid life cycle is a combination of a predictive and an adaptive life cycle. Those elements of the project that are well known or have fixed requirements follow a predictive development life cycle, and those elements that are still evolving follow an adaptive development life cycle.
Exam 3 | #20. _____ breaks down the causes of the problem statement identified into discrete branches, helping to identify the main or root cause of the problem. |  | Affinity diagrams | Fishbone diagrams | Histograms | Matrix diagrams | Answer option b. | Answer option b. “Fishbone diagrams”. Cause-and-effect diagrams are also known as fishbone diagrams, why-why diagrams, or Ishikawa diagrams. This type of diagram breaks down the causes of the problem statement identified into discrete branches, helping to identify the main or root cause of the problem. Answer option b. “Fishbone diagrams”. Cause-and-effect diagrams are also known as fishbone diagrams, why-why diagrams, or Ishikawa diagrams. This type of diagram breaks down the causes of the problem statement identified into discrete branches, helping to identify the main or root cause of the problem.
Exam 3 | #21. You are working through an iteration (Sprint) with your Agile team and are having trouble completing one of the stories in the sprint. It is dependent on something else being done and the contact is away. What will you do next? |  | Remove the feature from the iteration, to be added to the next one | Outsource the work to a third party, increasing project costs | Do the work yourself, as to not worry anyone else on the team | Raise a blocker at the next daily standup so the team and you discuss the go-forward approach on the story. | Answer option d. | Answer option d. Problem solving is done internally with the Agile team, by raising blockers as soon as possible during the daily standup meetings. Answer option d. Problem solving is done internally with the Agile team, by raising blockers as soon as possible during the daily standup meetings.
Exam 3 | #22. Sam is performing the control cost process. To measure the cost efficiency of the budgeted resources, he is using a metric expressed as a ratio. Which measure is he using? |  | Schedule performance index (SPI) | Cost performance index (CPI) | Cost variance (CV) | Schedule variance (SV) | Answer option b. | Answer option b. “Cost performance index (CPI)”. The cost performance index (CPI) is a measure of cost efficiency of budgeted resources, expressed as a ratio of earned value to actual cost. Answer option b. “Cost performance index (CPI)”. The cost performance index (CPI) is a measure of cost efficiency of budgeted resources, expressed as a ratio of earned value to actual cost.
Exam 3 | #23. Select the option that best completes the following statement: ____________ May add or remove a feature from the ____________ backlog at any time during the project life cycle? |  | The Product Owner; Sprint | The Product Owner; Product | The Scrum Master; Increment | The Team; Sprint | Answer option b. | b. In Scrum framework, the Product Owner owns the Product Backlog and is responsible for editing its content, availability, size, and order of sprints and tasks. No one else within the Scrum team shares this responsibility with the Product Owner.
Exam 3 | #24. A project manager is analyzing the relationship between the consumption of the project funds and the work accomplished for such expenditures. Which process is he performing? |  | Plan cost management | Estimate costs | Determine budget | Control cost | Answer option d. | Answer option d. “Control cost”. The process of monitoring the status of the project to update the project costs and manage changes to the cost baseline. Answer option d. “Control cost”. The process of monitoring the status of the project to update the project costs and manage changes to the cost baseline.
Exam 3 | #25. Darren is reviewing the resources’ shortages and delays in raw material supplies while he is performing the Control Resources process. Which input document contains this information? |  | Physical resource assignments | Issue log | Resource breakdown structure | Resource requirements | Answer option b. | Answer option b. The case is describing the project issues associated with resources thus, it will be recorded in the “Issue log”. Answer option b. The case is describing the project issues associated with resources thus, it will be recorded in the “Issue log”.
Exam 3 | #26. The project team identified a risk with potential negative impacts that can cause the failure of the project objectives. Which of the following risk strategies should they plan? |  | Escalate | Avoid | Exploit | Accept | Answer option b. | Answer option b. The best answer is “Avoid” (Answer option b.) usually selected for high priority risks. “Escalate” (Answer option a.) The case does not mention that the impact is beyond the project manager authority or transcends to other projects. “Exploit” (Answer option c.) is a strategy for opportunities not threats “Accept “(Answer option d.) usually used for low priority low impact risks. Answer option b. The best answer is “Avoid” (Answer option b.) usually selected for high priority risks. “Escalate” (Answer option a.) The case does not mention that the impact is beyond the project manager authority or transcends to other projects. “Exploit” (Answer option c.) is a strategy for opportunities not threats “ Accept “(Answer option d.) usually used for low priority low impact risks.
Exam 3 | #27. All projects are subject to changes during their life cycle. As Dan tries to Perform the Integrated Change Control process, he finds several methods for making decisions as part of the process tools and techniques. Which of the following is not a decision-making technique? |  | Voting | Alternative Analysis | Autocratic Decision Making | Multi-criteria Decision Analysis | Answer option b. | Answer option b. The best answer is” Alternative Analysis” (Answer option b.). It is not a decision-making technique. An alternative analysis is the evaluation of the various routes you can pursue to achieve the goal of a project or a particular project management objective. “Voting” (Answer option a.), “Autocratic Decision Making” (Answer option c.) and “Multi-criteria Decision Analysis” (Answer option d.) are decision-making techniques. Answer option b. The best answer is” Alternative Analysis” ( Answer option b. ). It is not a decision-making technique. An alternative analysis is the evaluation of the various routes you can pursue to achieve the goal of a project or a particular project management objective. “Voting” ( Answer option a. ), “Autocratic Decision Making” ( Answer option c. ) and “Multi-criteria Decision Analysis” ( Answer option d. ) are decision-making techniques.
Exam 3 | #28. Paul is working with the finance team of his company to determine a contract type for his new project. After considering the conditions of the project, they decided to proceed with a contract type that involves paying the seller all actual costs incurred for the completed work, plus a fee representing the seller’s profit. Which type of contract will they use? |  | Fixed price incentive fee (FPIF) | Time and material (T&M) | Cost-reimbursable contracts | Firm fixed price (FFP) | Answer option c. | Answer option c. “Cost-reimbursable contracts”. In cost-reimbursable contracts, the buyer and seller negotiate on a contract that the seller pays the costs of the project deliverables the profit for the seller. Generally, this can be a fixed profit over cost or a percentage of the cost as a profit. The case describes the cost-reimbursable contract. Answer option c. “Cost-reimbursable contracts”. In cost-reimbursable contracts, the buyer and seller negotiate on a contract that the seller pays the costs of the project deliverables the profit for the seller. Generally, this can be a fixed profit over cost or a percentage of the cost as a profit. The case describes the cost-reimbursable contract.
Exam 3 | #29. You are working on a project with unclear procedures and a high level of uncertainty. The product is not well defined, and risks are difficult to identify. Which is true from the below? |  | It is definable work, proceed with a predictive project lifecycle. | It is definable work, proceed with an iterative project lifecycle. | It is high-uncertainty work, proceed with a predictive project lifecycle. | It is high-uncertainty work, proceed with an Agile project lifecycle. | Answer option d. | When the situation is not clearly defined and has a high level of uncertainty/risks, use Agile, incremental, or iterative project lifecycles. Predictive project lifecycles are used for fairly definable and well-known project activities.
Exam 3 | #30. Quintin is conducting his project procurement. He is studying the bid documents he will use to solicit proposals from prospective sellers. Which of the following is not a bidding document? |  | Request for Solution (RFS) | Request for Proposal (RFP) | Request for Information (RFI) | Request for Quotation (RFQ) | Answer option a. | “Request for Solution (RFS)” is not a bid document.
Exam 3 | #31. Cooper is in the middle of an IT research project where the project’s first deliverable is complete. He is aware that Control Quality and Validate Scope processes should start soon. What is the correct sequence Cooper should follow in implementing these two processes? |  | Control Quality usually precedes Validate Scope | Control Quality usually follows Validate Scope | Control Quality and Validate Scope can’t be performed in parallel | None of the above | Answer option a. | Answer option a. “Control Quality usually precedes Validate Scope” Answer option a. “Control Quality usually precedes Validate Scope”
Exam 3 | #32. One of the models used to describe team development is the Tuckman ladder, which includes five stages of development that teams may go through. It is common for these stages to occur in order. The project team is currently in the performing stage. What is the next stage the team is going to enter? |  | Forming | Norming | Storming | Adjourning | Answer option d. | Answer option d. “Adjourning” is the stage that normally follows performing. One of the models used to describe team development is the Tuckman ladder, which includes five stages of development that teams may go through. Although it is common for these stages to occur in order, it is not uncommon for a team to get stuck in a particular stage or regress to an earlier stage. Projects with team members who worked together in the past might skip a stage. Answer option d. “Adjourning” is the stage that normally follows performing. One of the models used to describe team development is the Tuckman ladder, which includes five stages of development that teams may go through. Although it is common for these stages to occur in order, it is not uncommon for a team to get stuck in a particular stage or regress to an earlier stage. Projects with team members who worked together in the past might skip a stage. Forming. This phase is where the team members meet and learn about the project and their formal roles and responsibilities. Team members tend to be independent and not as open in this phase. Storming. During this phase, the team begins to address the project work, technical decisions, and the project management approach. If team members are not collaborative or open to differing ideas and perspectives, the environment can become counterproductive. Norming. In this phase, team members begin to work together and adjust their work habits and behaviors to support the team. The team members learn to trust each other. Performing. Teams that reach the performing stage function as a well-organized unit. They are interdependent and work through issues smoothly and effectively. Adjourning. In this stage, the team completes the work and moves on from the project. This typically occurs when staff is released from the project as deliverables are completed or as part of the Close Project or Phase process. Forming. This phase is where the team members meet and learn about the project and their formal roles and responsibilities. Team members tend to be independent and not as open in this phase. Forming. This phase is where the team members meet and learn about the project and their formal roles and responsibilities. Team members tend to be independent and not as open in this phase. Storming. During this phase, the team begins to address the project work, technical decisions, and the project management approach. If team members are not collaborative or open to differing ideas and perspectives, the environment can become counterproductive. Storming. During this phase, the team begins to address the project work, technical decisions, and the project management approach. If team members are not collaborative or open to differing ideas and perspectives, the environment can become counterproductive. Norming. In this phase, team members begin to work together and adjust their work habits and behaviors to support the team. The team members learn to trust each other. Norming. In this phase, team members begin to work together and adjust their work habits and behaviors to support the team. The team members learn to trust each other. Performing. Teams that reach the performing stage function as a well-organized unit. They are interdependent and work through issues smoothly and effectively. Performing. Teams that reach the performing stage function as a well-organized unit. They are interdependent and work through issues smoothly and effectively. Adjourning. In this stage, the team completes the work and moves on from the project. This typically occurs when staff is released from the project as deliverables are completed or as part of the Close Project or Phase process. Adjourning. In this stage, the team completes the work and moves on from the project. This typically occurs when staff is released from the project as deliverables are completed or as part of the Close Project or Phase process.
Exam 3 | #33. The project team is assessing the project stakeholders’ engagement level. While assessing the technical-support manager’s engagement level, this stakeholder is aware of the project’s existence, however, he did not show any sign of interest. What is his engagement level? |  | Unaware | Resistant | Neutral | Supportive | Answer option c. | Answer option c. “Neutral” means aware of the project but neither supportive or unsupportive. Answer option c. “Neutral” means aware of the project but neither supportive or unsupportive.
Exam 3 | #34. Darren is developing his project schedule. He aims to evaluate the potential impact of the combined effects of individual project risks and other sources of uncertainty on achieving the project objectives. Which technique is he using? |  | What-if scenario analysis | Simulation | Critical path method | Kanban Systems | Answer option b. | Answer option b. “Simulation” is a quantitative risk analysis that uses a model that simulates the combined effects of individual project risks and other sources of uncertainty to evaluate their potential impact on achieving project objectives. Answer option b. “Simulation” is a quantitative risk analysis that uses a model that simulates the combined effects of individual project risks and other sources of uncertainty to evaluate their potential impact on achieving project objectives.
Exam 3 | #35. A project manager is controlling the project schedule. He intends to measure the schedule performance by calculating the difference between the earned value and the planned value. Which measure is he using? |  | Schedule performance index (SPI) | Cost performance index (CPI) | Cost variance (CV) | Schedule variance (SV) | Answer option d. | Answer option d. “Schedule variance (SV)” measures the schedule performance by calculating the difference between the earned value and the planned value. Answer option d. “Schedule variance (SV)” measures the schedule performance by calculating the difference between the earned value and the planned value.
Exam 3 | #36. Donald is a project manager for a financial-solution software upgrade project. He is trying to determine which schedule methodology to use and how to combine various methods. This also includes determining the detail-level schedule, duration of waves for rolling wave planning, and how often the schedule should be reviewed and updated. The activity Donald is performing is called _____ . |  | Decision Making | Alternative Analysis | Rolling Wave Planning | Dependency Determination and Integration | Answer option b. | Answer option b. “Alternative Analysis” the case describes efforts to evaluate different alternatives to use while developing the project schedule. The key phrase in the question is “determine which schedule methodology to use”. Answer option b. “Alternative Analysis” the case describes efforts to evaluate different alternatives to use while developing the project schedule. The key phrase in the question is “determine which schedule methodology to use”.
Exam 3 | #37. Two developers work on the same task together. Developer A is writing code, while Developer B is thinking about the functionality. They switch these roles throughout the day. Because these developers are working together, they can quickly catch errors. This practice is an example of which of the following? |  | eXtreme Programming (XP) | Test‐Driven Development (TDD) | Continuous Integration (CI) | Crystal Methods | Answer option a. | Answer option a. eXtreme Programming is an agile software development method that leads to higher quality software, greater responsiveness to changing customer requirements, and more frequent releases in shorter cycles. Answer option a. eXtreme Programming is an agile software development method that leads to higher quality software, greater responsiveness to changing customer requirements, and more frequent releases in shorter cycles.
Exam 3 | #38. Juan is managing his project communications. He is trying to address the enterprise environmental factors that can influence this process. Which of the following should he not consider? |  | Standardized guidelines for development of information | Stakeholder risk thresholds | Established communication channels | Geographic distribution of facilities | Answer option a. | Answer option a. The best answer is “Standardized guidelines for development of information” (option a) is an organizational process asset. “Stakeholder risk thresholds” (Answer option b.), “Established communication channels” (Answer option c.), and “Geographic distribution of facilities” (Answer option d.) are all enterprise environmental factors that can influence this process. Answer option a. The best answer is “ Standardized guidelines for development of information ” (option a) is an organizational process asset. “ Stakeholder risk thresholds ” (Answer option b.), “ Established communication channels ” (Answer option c.), and “ Geographic distribution of facilities ” (Answer option d.) are all enterprise environmental factors that can influence this process .
Exam 3 | #39. The Monitor Communications process often results in the need for adjustment, alteration, and intervention in communications activities defined in the communications management plan. Which of the following is a possible result of communication change requests? |  | Amending deliverable nonconformance | New procedures to eliminate bottlenecks | Bridge a skill gap | All of the above | Answer option b. | Answer option b. “New procedures to eliminate bottlenecks”. Monitor communications process change requests may result in: Answer option b. “New procedures to eliminate bottlenecks”. Monitor communications process change requests may result in: Revision of stakeholder communication requirements, including stakeholders’ information distribution, content or format, and distribution method; and New procedures to eliminate bottlenecks. Revision of stakeholder communication requirements, including stakeholders’ information distribution, content or format, and distribution method; and Revision of stakeholder communication requirements, including stakeholders’ information distribution, content or format, and distribution method; and New procedures to eliminate bottlenecks. New procedures to eliminate bottlenecks.
Exam 3 | #40. _____ provides a written record used in reaching the legal agreement and may include older documents preceding the current project. |  | Agreements | Requirements documentation | Procurement documentation | Procurement management plan | Answer option c. | Answer option c. “Procurement documentation”. Procurement documentation provides a written record used in reaching the legal agreement and may include older documents predating the current project. Answer option c. “Procurement documentation”. Procurement documentation provides a written record used in reaching the legal agreement and may include older documents predating the current project.
Exam 3 | #41. Mark's project's deliverables have passed all acceptance approvals. As the project is ending, Mark is about to close the project and prepare the project’s final report. Which of the following information is not part of the project's final report? |  | Scope Objectives | Resources Objectives | Schedule Objectives | Quality Objectives | Answer option b. | Answer option b. “Resources Objectives”. The final report can include information about how scope, schedule, and quality objectives have been met or not met. Answer option b. “Resources Objectives”. The final report can include information about how scope, schedule, and quality objectives have been met or not met.
Exam 3 | #42. Mark is monitoring the project risks. Which document should he review if he wants to find out how and when to review risks and which policies and procedures to follow? |  | Issue log | Risk management plan | Risk report | Risk register | Answer option b. | Answer option b. “Risk management plan” is an input to the Monitor Risks process. Answer option b. “Risk management plan” is an input to the Monitor Risks process.
Exam 3 | #43. You are working on an Agile project. You look at the Product Backlog and ensure the minimum viable product (MVP) can be scheduled for delivery throughout the duration of the project. Why is this a good idea? |  | To enable the business to get value quickly as features are delivered incrementally. | To enable customers to test the product for quality and give feedback. | To provide senior management proof that progress is being made by the development team. | To keep the project ahead of the projected schedule. | Answer option a. | Answer option a. Minimum Viable Products are usable features that are delivered incrementally, allowing for business value to be gained more quickly, while gathering feedback on the use of included features. Answer option a. Minimum Viable Products are usable features that are delivered incrementally, allowing for business value to be gained more quickly, while gathering feedback on the use of included features.
Exam 3 | #44. A project team is still in the “storming” stage. Which of the following characteristics would the team exhibit? |  | Members tend to be independent in their performance and not as open to others | Members are not collaborative or open to differing ideas and perspectives | The environment can become counterproductive | Both B and C | Answer option d. | Answer option d. “Members tend to be independent in their performance and not as open to others” (Answer option a.) is a characteristic of the forming stage. “Members are not collaborative or open to differing ideas and perspectives” (Answer option b.) and “The environment can become counterproductive” (Answer option c.) are both characteristics of teams in the storming stage. The best answer is “Both B and C” (Answer option d.). Answer option d. “Members tend to be independent in their performance and not as open to others” ( Answer option a. ) is a characteristic of the forming stage. “Members are not collaborative or open to differing ideas and perspectives” ( Answer option b. ) and “The environment can become counterproductive” ( Answer option c. ) are both characteristics of teams in the storming stage. The best answer is “Both B and C” ( Answer option d. ). When the project team is in the storming stage, When the project team is in the storming stage, Members are not open to differing ideas and perspectives Members start to see each other trustworthy but don’t know how to work together Members tend to be independent Members are not open to differing ideas and perspectives Members are not open to differing ideas and perspectives Members start to see each other trustworthy but don’t know how to work together Members start to see each other trustworthy but don’t know how to work together Members tend to be independent Members tend to be independent
Exam 3 | #45. The Scrum Board is an information radiator that is utilized to manage the product and sprint backlogs and show the flow of work and its bottlenecks. What is the main difference between the Kanban board and the Scrum board? |  | Kanban board develops a shared view of the team's progress. | There is no limit on work in progress items in the Scrum board. | Daily stand-ups are only applicable if you’re using a Scrum board. | Cumulative flow diagrams can only be produced for Kanban boards. | Answer option b. | The work in progress (WIP) limits are at the top of each column in Kanban boards.
Exam 3 | #46. You are working with the product owner to determine a viable product iteration plan. As you discuss various features and prioritize them, you both are struggling with understanding what features should have a higher priority. What artifact should the project manager and product owner consult? |  | The task list. This will help the product manager and product owner understand what it takes to create a feature. | The iteration plan. This will break out the various features that are desired. | The release plan. This breaks out the iterations of the project. | The Scrum backlog | Answer option c. | Answer option c. The release plan shows high-level priorities. The task list is too detailed at this level of planning. The iteration plan draws its priorities from the release plan. The roadmap and vision documents are high level release plans. Answer option c. The release plan shows high-level priorities. The task list is too detailed at this level of planning. The iteration plan draws its priorities from the release plan. The roadmap and vision documents are high level release plans.
Exam 3 | #47. You are the project manager of a customer delivery project, and you are currently estimating project costs. Which of the following enterprise environmental factors would you consider? |  | Cost estimating policies | Published commercial information | Cost estimating templates | Lessons learned repository | Answer option b. | “Cost estimating policies” (Answer option a.), “Cost estimating templates” (Answer option c.), and “Lessons learned repository” (Answer option d.) are all organizational process assets. The best answer is “Published commercial information” (option b). It is the only enterprise environmental factor available in options.
Exam 3 | #48. Your development team is working on the latest iteration and is progressing very well. Early in the morning, your customer calls and asks for an urgent meeting to discuss requirements. You are surprised, as they have been quite comfortable with the dynamic of the project and were happy with the development of the product functionalities so far. You meet with them and they ask if they can have an additional feature done in this iteration. Is it acceptable to extend the iteration for a few days in order to finish with the requested feature? |  | It depends. | It is not acceptable. Iteration is time-boxed | Yes, you can extend an iteration in rare situations | Acceptable if the Scrum Master makes a decision | Answer option b. | Answer option b. You want to accommodate customers’ wishes but extending the iteration for a few days in order to finish everything the customer wants including new functionalities is not possible. Iterations are time-boxed, therefore the team needs to finish only what was planned for that iteration. The additional functionality will be reviewed and will be done in the next iteration. Answer option b. You want to accommodate customers’ wishes but extending the iteration for a few days in order to finish everything the customer wants including new functionalities is not possible. Iterations are time-boxed, therefore the team needs to finish only what was planned for that iteration. The additional functionality will be reviewed and will be done in the next iteration.
Exam 3 | #49. The agile team has been provided with limited wall space to indicate the project status or progress. The team members are confused about whether they should use a software tool for which the company has an unlimited license or use the whole space to display the index cards with notes on what they are currently working on. Which of the following is recommended for the agile team to do use? |  | Index cards and posted notes as it will offer stakeholders real-time updates on the project status | The software tool as the company has unlimited user license so there is no issue regarding the cost | Follow the same practices as used by other agile teams to indicate the project status or progress in the company | Use information radiators as they are better than high tech solutions | Answer option a. | Answer option a. Use index cards and posted notes, as it will offer the stakeholders real-time updates on the project status. The agile team should use the whole space to display index cards or post-it notes to display the current status of the project tasks. Answer option a. Use index cards and posted notes, as it will offer the stakeholders real-time updates on the project status. The agile team should use the whole space to display index cards or post-it notes to display the current status of the project tasks.
Exam 3 | #50. AC Co. initiated a new business transformation project to improve the efficiency of its operations. This is an example of_____ . |  | Meet regulatory, legal, or social requirements | Satisfy stakeholder requests or needs | Implement or change the business or technological strategies | Create, improve, or fix products, processes, or services | Answer option d. | Answer option d. “Create, improve, or fix products, processes, or services” Answer option d. “Create, improve, or fix products, processes, or services”
Exam 3 | #51. Decision making is a hurdle in your project management team. Mostly, the team members do not agree on at least one of the options available. This disagreement among them leads to waste of time and money. You have added a Senior Project Manager to this team and given him the right to singularly decide on behalf of the whole team. He will be exercising which of the following decision-making techniques? |  | Voting | Brainstorming | Autocratic decision making | Multicriteria decision making | Answer option c. | Answer option c. In this decision-making technique, one individual takes the responsibility for deciding for the entire group. Answer option c. In this decision-making technique, one individual takes the responsibility for deciding for the entire group.
Exam 3 | #52. You are the project manager for a medical office project. The project requires installation and configuration of 200 PCs. Your team wants to know why you haven’t allocated the same time for the final installation of 100 PCs as you allocated for the first batch of 100 PCs and argue that the time for the second batch should be 1.5 times the first batch. You explain that it is because of the “learning curve” theory. How do you explain the “learning curve” theory? |  | Installation time increases as the team becomes more familiar with the installation procedure. | Installation time decreases as the team becomes more familiar with the installation procedure. | Installation time remains the same as the team becomes more familiar with the installation procedure. | Learning time is inversely proportional to the number of PCs to be installed multiplied by the number of workers. | Answer option b. | Answer option b. Installation time decreases as workers become more familiar with the installation procedure. By gaining more experience in performing a task, performance time reduces, due to lessons learned associated with that task. Answer option b. Installation time decreases as workers become more familiar with the installation procedure. By gaining more experience in performing a task, performance time reduces, due to lessons learned associated with that task.
Exam 3 | #53. A new regulation requires consumer warnings on labels, but a company's product package is too small to fit the additional information. The regulatory specification does NOT provide a solution, so the agile team decides to solve the problem by displaying the information on a fold-out flap. The start of mass production of the new labels, the project's next milestone, is scheduled to begin in five days. What should the agile team do next? |  | Update the sprint backlog to reflect the additional product label requirement. | Contact the compliance team to determine validity of the selected format. | Request approval from the steering committee to proceed with the change. | Develop a prototype and submit it to the label manufacturer for approval. | Answer option b | . Contact the compliance team to determine validity of the selected format.
Exam 3 | #54. The absence of project management may result in _____ . |  | Resolving the problems and issues | Optimizing the use of organizational resources | Identifying, recovering, or terminating failing projects | Uncontrolled expansion of the project | Answer option d. | Answer option d. “Uncontrolled expansion of the project” due to the lack of scope control. Answer option d. “Uncontrolled expansion of the project” due to the lack of scope control.
Exam 3 | #55. Sally arranged a meeting for the project team to share their experience and insights to use them as lessons learned for the next project phases. What type of knowledge could the team share in this meeting? |  | Explicit knowledge | Tacit knowledge | Direct knowledge | All of the above | Answer option b. | Answer option b. “Tacit knowledge” includes experience, insights, and beliefs, which cannot be simply codified through words and images. Answer option b. “Tacit knowledge” includes experience, insights, and beliefs, which cannot be simply codified through words and images.
Exam 3 | #56. Thomas is examining the project cost performance over time to determine if performance is improving or degrading. Which technique is he using? |  | Earned value analysis | Trend analysis | Variance analysis | Reserve analysis | Answer option b. | Answer option b. “Trend analysis” is used to determine if performance is improving or deteriorating. Answer option b. “Trend analysis” is used to determine if performance is improving or deteriorating.
Exam 3 | #57. John is working on implementing the risk responses. He wants to identify the roles and responsibilities of the project team members and other stakeholders for risk management. _____ lists these details. |  | Risk management plan | Risk report | Risk register | Risk breakdown structure | Answer option a. | Answer option a. “Risk management plan” is a component of the project, program, or portfolio management plan that describes how risk management activities will be structured and performed. The risk management plan provides information on risk-related roles and responsibilities, indicates how risk management activities are included in the budget and schedule, and describes categories of risk, which may be expressed as a risk breakdown structure. Answer option a. “Risk management plan” is a component of the project, program, or portfolio management plan that describes how risk management activities will be structured and performed. The risk management plan provides information on risk-related roles and responsibilities, indicates how risk management activities are included in the budget and schedule, and describes categories of risk, which may be expressed as a risk breakdown structure.
Exam 3 | #58. Peter has been assigned to manage a small Agile project. He is not very familiar with Agile communication approaches but was appointed to cover the gap till an Agile certified project manager is hired. His knowledge of Agile is not extensive, but he understands some basic aspects of Agile project communications. Peter established a communication method not found in the traditional approaches. What was it? |  | Chat charts | Invite more stakeholders to attend project meetings | Create information radiators | Use Hangouts for communications | Answer option c. | Answer option c. Using information radiators is unique to Agile projects. They can be in different shapes and forms, such as handwritten, drawn, printed, and they are displayed in a highly visible location so that all team members and stakeholders can see the latest project information. Answer option c. Using information radiators is unique to Agile projects. They can be in different shapes and forms, such as handwritten, drawn, printed, and they are displayed in a highly visible location so that all team members and stakeholders can see the latest project information.
Exam 3 | #59. You are managing a contract-based project to build and furnish a medical practice. The project is nearing completion, and it is coming in significantly under budget because you discovered that some of the work and materials received underprivileged rates and tax deductions, which neither you nor the customer knew at the start of the project. The customer is happy about the news and asks you to use the leftover funds to fit out one of the offices as a medical lab, to “avoid all the red tape” involved in changing the contract. What should you do? |  | Fitting out the office as a medical lab will keep the customer happy and provide more income to your company. | Add an item to the contract for the additional work, then complete it. | Raise a change request for the CCB (change control board) to review. | Refuse the change because it was not considered in the original contract | Answer option c. | Answer option c. Raise a change request and submit it to the Change Control Board for their review. This is the correct course of action. Be aware of the ethical component. Always do the right thing! Answer option c. Raise a change request and submit it to the Change Control Board for their review. This is the correct course of action. Be aware of the ethical component. Always do the right thing!
Exam 3 | #60. Which procurement input contains formats and processes on how the sellers will provide configuration management in a way that is consistent with the buyer’s approach? |  | Requirements management plan | Configuration management plan | Procurement management plan | Cost baseline | Answer option b. | Answer option b. “Configuration management plan”. The configuration management plan defines items that are configurable, that require formal change control, and the process for controlling changes to such items. It includes formats and processes for how sellers will provide configuration management in a way that is consistent with the buyer’s approach. Answer option b. “Configuration management plan”. The configuration management plan defines items that are configurable, that require formal change control, and the process for controlling changes to such items. It includes formats and processes for how sellers will provide configuration management in a way that is consistent with the buyer’s approach.
Exam 3 | #61. The requirements for the new database are very vague to the product owner. After lengthy discussions with the customer, you discovered that you don’t have enough knowledge about the product or the process of building the product to move forward. As an agile practitioner, what should you do next? |  | Start creating your first user stories and requirements will eventually evolve | Start a spike to clarify the current risk due to the technical uncertainty within the project | Carry on with backlog refinement and inform senior stakeholders about the situation | Start a sprint Zero where you complete project setup, infrastructure provisioning, setting up of project document repository, standardizing tools, and building your team | Answer option b. | Answer option b. A Spike is a short time interval within a project, usually of fixed length, during which a team conducts research or prototypes an aspect of a solution to prove its viability. Answer option b. A Spike is a short time interval within a project, usually of fixed length, during which a team conducts research or prototypes an aspect of a solution to prove its viability.
Exam 3 | #62. Adam is a project manager and is managing the Stakeholder Engagement process. Which of the following organizational process assets would he consider? |  | Personnel administration policies | Stakeholder risk thresholds | Standardized guidelines for engagement | Established communication channels | Answer option c. | Answer option c. The best answer is “Standardized guidelines for engagement” (Answer option c.).“Personnel administration policies” (Answer option a.), “Stakeholder risk thresholds” (Answer option b.) and “Established communication channels” (Answer option d.) are enterprise environmental factors. Answer option c. The best answer is “Standardized guidelines for engagement” ( Answer option c. ).“Personnel administration policies” ( Answer option a. ), “Stakeholder risk thresholds” ( Answer option b. ) and “Established communication channels” ( Answer option d. ) are enterprise environmental factors.
Exam 3 | #63. You are managing a project to develop an electric mountain bike. The frame of the bike should be sturdy enough to carry the battery and there should be enough space to attach the battery. The engineering department has the skill to design the frame, but as you look at the design, this might not look like the most suitable option. In order to decide whether to manufacture the frames or outsource them while considering risk probabilities, which technique will be particularly helpful? |  | Decision tree analysis | Cost-Benefit analysis | Pareto chart | Return on Investment analysis | Answer option a . | Answer option a. Decision trees are used to support the selection of the best of several alternative courses of action. Alternative paths through the project are shown in the decision tree using branches representing different decisions or events, each of which can have associated costs and related individual project risks. Answer option a . Decision trees are used to support the selection of the best of several alternative courses of action. Alternative paths through the project are shown in the decision tree using branches representing different decisions or events, each of which can have associated costs and related individual project risks.
Exam 3 | #64. You are the new Agile coach in an organization that is fully focused on transforming into Agile practices. As a coach with lots of Agile capabilities and potential, what is the first action you are going to take in order to start transforming? |  | Hold meetings and interviews with the Scrum team and all the groups by role. | Assess the current Agile processes and tools within the organization. | Attend all the Scrum events for the team you are going to coach. | Train all individuals within the organizations on Agile and Scrum in order to create a common understanding and approach. | Answer option a. | Answer option a. As a new Agile coach coming into a transforming organization, the first thing you need to do is to hold meetings with all the relevant individuals and understand their conception and perspective on Agile before starting to transform. Answer option a. As a new Agile coach coming into a transforming organization, the first thing you need to do is to hold meetings with all the relevant individuals and understand their conception and perspective on Agile before starting to transform.
Exam 3 | #65. A key output of the Plan Risk Responses process is Project Management Plan updates. Any change to the Project Management Plan goes through the organization’s change control process via a change request. Which of the following is not a component of the Project Management Plan? |  | Cost Baseline | Scope Baseline | Quality Baseline | Schedule Baseline | Answer option c. | Answer option c. “Quality Baseline” is not a part of the Project Management Plan. Answer option c. “Quality Baseline” is not a part of the Project Management Plan.
Exam 3 | #66. The urgency, frequency, and format of the communicated information, the availability and reliability of communication technology, and the ease of use are _____ . |  | Factors that can affect the choice of communication technology | Organizational process assets that can influence Manage Communications process | Enterprise environmental factors that can influence Manage Communications process | Communication methods | Answer option a. | Answer option a. ”Factors that can affect the choice of communication technology” Answer option a. ”Factors that can affect the choice of communication technology”
Exam 3 | #67. John is investigating the optimal cost of quality that reflects the appropriate balance for investing in the cost of prevention and appraisal to avoid failure costs for his project. Which of the following is not an example of appraisal costs? |  | Training | Testing | Destructive testing loss | Inspections | Answer option a. | “Training” is a prevention cost
Exam 3 | #68. A senior Project Manager has been assigned to a high priority project. The client on this project is very sensitive to any unplanned changes about the project objectives. He has asked the Project Manager to create a framework of Risks which can help his team generate different ideas regarding the risk identification activity. Which of the following risk identification techniques can help in this? |  | Assumption and Constraint Analysis | Document Analysis | Prompt Lists | Root Cause Analysis | Answer option c. | Answer option c. A prompt list is a predetermined list of risk categories that might identify individual project risks and it could also list sources of overall project risk. The prompt list can be used as a framework to aid the project team in idea generation when using risk identiﬁcation techniques. The risk categories in the lowest level of the risk breakdown structure can be used as a prompt list for individual project risks. Answer option c. A prompt list is a predetermined list of risk categories that might identify individual project risks and it could also list sources of overall project risk. The prompt list can be used as a framework to aid the project team in idea generation when using risk identiﬁcation techniques. The risk categories in the lowest level of the risk breakdown structure can be used as a prompt list for individual project risks .
Exam 3 | #69. While calculating the project cost variance, Andy found that the value is negative. Which of the following represents the project cost status? |  | Project is under planned cost | Project is on budget | Project is over planned cost | None of the above | Answer option c. | Answer option c. “Project is over planned cost”. If the cost variance is less than zero, it means the project is over budget. Answer option c. “Project is over planned cost”. If the cost variance is less than zero, it means the project is over budget.
Exam 3 | #70. You've found a more efficient way to analyze the lab test results that you and your teammates are evaluating in the current spike. What's the most efficient way to share this information with the other developers? |  | Tell them in person | Document it in an email | Post it on the project wiki | Put a sticky note on the Kanban board | Answer option a. | Answer option a. “Tell them in person”. Like many questions you’ll encounter on the PMI-ACP exam, this one appears to be missing some key information you need to choose the right answer. Are these team members co-located or virtual? How often do they check the wiki? How complicated is the new process you want to explain? In a case like this, don’t overthink the question; just look at the information given. Agile Manifesto principle 6 states that the most efficient way of conveying information within a development team is a face-to-face conversation. This method includes instant two-way feedback and conveys nonverbal information. So the BEST way to share information is to tell the other developers in person. Answer option a. “Tell them in person”. Like many questions you’ll encounter on the PMI-ACP exam, this one appears to be missing some key information you need to choose the right answer. Are these team members co-located or virtual? How often do they check the wiki? How complicated is the new process you want to explain? In a case like this, don’t overthink the question; just look at the information given. Agile Manifesto principle 6 states that the most efficient way of conveying information within a development team is a face-to-face conversation. This method includes instant two-way feedback and conveys nonverbal information. So the BEST way to share information is to tell the other developers in person.
Exam 3 | #71. A Project Manager is explaining to the client how the work will proceed in the execution phase. She says that the general practice in construction work is that the first execution team will complete the plumbing and then they will proceed to the electrical work. She shares with the client that this would be her preferred way of proceeding forward. Which type of dependency is she explaining to the project client? |  | Mandatory dependency | Discretionary dependency | External dependency | Internal dependency | Answer option b . | Answer option b. Discretionary dependencies are established based on knowledge of best practices within a particular application area or some unusual aspect of the project where a speciﬁc sequence is desired, even though there may be other acceptable sequences. Answer option b . Discretionary dependencies are established based on knowledge of best practices within a particular application area or some unusual aspect of the project where a speciﬁc sequence is desired, even though there may be other acceptable sequences.
Exam 3 | #72. Sam is measuring the schedule performance of an agile project using a chart. He tracks the remaining work in the iteration backlog. Sam is using _____ . |  | Control chart | Agile release chart | Burndown chart | Earned value chart | Answer option c. | Answer option c. “Burndown chart” tracks the remaining work in the iteration backlog. Answer option c. “ Burndown chart ” tracks the remaining work in the iteration backlog.
Exam 3 | #73. Darren is reviewing the basis of estimates and comparing them to the actual results to improve the metrics for future projects. This is an example of _____ . |  | Document analysis | Regression analysis | Trend analysis | Variance analysis | Answer option d. | Answer option d. “Variance analysis” can be used to improve the metrics of the organization by comparing what was initially planned and the results. Answer option d. “Variance analysis” can be used to improve the metrics of the organization by comparing what was initially planned and the results.
Exam 3 | #74. The requirements traceability matrix is an important output of the Collect Requirements process. Which of the following is a key characteristic of the requirements traceability matrix? |  | It provides a means to track requirements throughout the project life cycle | It is a grid that links product requirements from their origin to cost estimate | It helps ensure that each requirement duration does not exceed the project critical path | It does not help with managing changes to the product scope | Answer option a. | Answer option a. “It provides a means to track requirements throughout the project life cycle” Answer option a. “It provides a means to track requirements throughout the project life cycle”
Exam 3 | #75. Your team finds it very useful to use burn up charts and burn down charts during monitoring the variances in the project. Your key stakeholder is not familiar with the terminology and needs an explanation on the difference between burn up and burn down charts. Which of the following is true about burn up charts? |  | Burn up charts separate out the rate of progress from the scope fluctuations | Burn up charts and burn down charts trend in opposite vertical directions | Burn up charts can be converted to cumulative flow diagrams by the addition of WIP | All of the above | Answer option d. | Answer option d. It is true that burn up charts can be converted to cumulative flow diagrams by the addition of WIP, and they trend in the opposite vertical direction from burn down charts. It is also true that burn up charts also track total scope (rather than burn down charts). Answer option d. It is true that burn up charts can be converted to cumulative flow diagrams by the addition of WIP, and they trend in the opposite vertical direction from burn down charts. It is also true that burn up charts also track total scope (rather than burn down charts).
Exam 3 | #76. John is trying to measure the project schedule efficiency using the ratio of earned value to planned value. Which measure is he using? |  | Schedule performance index (SPI) | Cost performance index (CPI) | Cost variance (CV) | Schedule variance (SV) | Answer option a. | Answer option a. “Schedule performance index (SPI)” measures the project schedule efficiency using the ratio of earned value to planned value. Answer option a. “Schedule performance index (SPI)” measures the project schedule efficiency using the ratio of earned value to planned value.
Exam 3 | #77. Your team is attempting to improve the design of the product by delivering incremental values to the functionality of the product, particularly improving the reliability and safety features. Which of the below techniques would you recommend? |  | Design of experiments | Value analysis | Cost-benefit analysis | Design for excellence | Answer option d. | Answer option d. “Design for excellence” (DfX) aims to improve reliability, safety, performance, and other features of the product or service or the result, simultaneously trying to improve customer satisfaction and reduce cost. Answer option d. “Design for excellence” (DfX) aims to improve reliability, safety, performance, and other features of the product or service or the result, simultaneously trying to improve customer satisfaction and reduce cost.
Exam 3 | #78. A product owner in an agile project complains of too many meetings in their monthly schedule. There is NOT enough time for project work. They instruct the project manager to prioritize some meetings and decrease the frequency of others. Which two of the product owner’s meetings could the project manager deprioritize so that they attend less frequently? (Choose TWO) |  | Sprint retrospectives | Product SME consultations | Daily stand-up meetings | Team performance reviews | Answer options c, d. | In agile projects, the customer is the highest priority, because this leads to end-user satisfaction and focus on delivery; administrative processes such as performance reviews are a lower priority. The product owner is NOT needed at every daily meeting.
Exam 3 | #79. While implementing risk responses, the project manager wants to ensure the effectiveness of the process. What is the common Risk Management problem he might encounter? |  | The team did not identify all risks | The team did not analyze the risks well | Risk owners would not take action to manage the risk | All of the above | Answer option c. | Answer option c. “Risk owners would not take action to manage the risk” A common problem with Project Risk Management is that project teams spend effort in identifying and analyzing risks and developing risk responses, then risk responses are agreed upon and documented in the risk register and risk report, but no action is taken to manage the risk. Answer option c. “Risk owners would not take action to manage the risk” A common problem with Project Risk Management is that project teams spend effort in identifying and analyzing risks and developing risk responses, then risk responses are agreed upon and documented in the risk register and risk report, but no action is taken to manage the risk.
Exam 3 | #80. John is working on project knowledge management in his project. Which of the following is a common knowledge management misconception that he should avoid? |  | It involves just documenting it | It involves just obtaining lessons learned at the end of the project | Only explicit knowledge can be shared through documents | Both A and B | Answer option d. | Answer option d. Common misconceptions include “It involves just documenting it” (Answer option a.) and “It involves just obtaining lessons learned at the end of the project” (Answer option b.). However, “Only explicit knowledge can be shared through documents” (Answer option c.) is not a misconception, it is a fact. The best answer is “Both A and B” (Answer option d.). Answer option d. Common misconceptions include “It involves just documenting it” (Answer option a.) and “It involves just obtaining lessons learned at the end of the project” (Answer option b.). However, “ Only explicit knowledge can be shared through documents” (Answer option c.) is not a misconception, it is a fact. The best answer is “Both A and B” (Answer option d.).
Exam 3 | #81. Which of the following categories of contracts set the price for the product but with a special condition allowing for predefined final modification in case of inflation changes or cost increases? |  | (FFP) | (FPIF) | (FPEPA) | (CPFF) | Answer option c. | Answer option c. “(FPEPA)” Fixed price with economic price adjustments (FPEPA) includes a special provision allowing for predefined final adjustments to the contract price due to changed conditions, such as inflation changes or cost increases Answer option c. “(FPEPA)” Fixed price with economic price adjustments (FPEPA) includes a special provision allowing for predefined final adjustments to the contract price due to changed conditions, such as inflation changes or cost increases
Exam 3 | #82. During the planning for an automation project, the company HR informed the project team that there is a very limited number of artificial intelligence engineers available to run all AI projects. Accordingly, which resource optimization technique can help improve the schedule accuracy? |  | Resource loading | Resource leveling | Resource smoothing | Resource assignment | Answer option b. | Answer option b. “Resource leveling” can be used when there are resource limitations or resource scarcity to fine-tune the project schedule and make it more realistic. Answer option b. “Resource leveling” can be used when there are resource limitations or resource scarcity to fine-tune the project schedule and make it more realistic.
Exam 3 | #83. Bill works for the product development department in a world-class shoe company Glide. As the leading designer, Bill needs to deliver a product that no other company has developed. The project uses a water-soluble thread that will dissolve when water is applied during the production process to provide a competitive advantage to athletes, as less thread means a lighter running shoe. What type of life cycle should Bill consider for developing this product? |  | Iterative life cycle | Predictive life cycle | Lean life cycle | All of the above | Answer option a. | Answer option a. Each iteration is about modifying and improving the work in the project. To deliver on such a specific thread, feedback from the research and development department is mandatory and provides a prototype product before production begins. Answer option a. Each iteration is about modifying and improving the work in the project. To deliver on such a specific thread, feedback from the research and development department is mandatory and provides a prototype product before production begins.
Exam 3 | #84. In a risk planning meeting, different stakeholders are discussing how to potentially respond to risk if it is realized in the future. This leads the discussion on who would potentially be the risk response owner in case of realization of a specific risk. It takes 3 rounds of meetings to finalize the features of the potential risk and the risk-response owners. This meeting is related to which process of risk management? |  | Plan Risk Management | Identify Risk | Plan Qualitative Risk Analysis | Plan Risk Response | Answer option b. | Answer option b. Identify risk is the process in which potential risk response and potential risk response owners are recorded into the risk register. Answer option b. Identify risk is the process in which potential risk response and potential risk response owners are recorded into the risk register .
Exam 3 | #85. Rupert has just been assigned to his first project in DINO Technologies Company. He knows that the company has a good reputation in project management, which comes from its PMO team’s experience and expertise. As Rupert tries to leverage the company’s tacit knowledge accordingly, he should_____. |  | Conduct Conversations | Review Lessons Learned repository | Review historical records | Review knowledgebase | Answer option a. | Answer option a. “Conduct Conversations”. Tacit knowledge is hard to be codified and documented accordingly. It is better to use networking and interpersonal communication like conversations to obtain this type of knowledge. Answer option a. “Conduct Conversations”. Tacit knowledge is hard to be codified and documented accordingly. It is better to use networking and interpersonal communication like conversations to obtain this type of knowledge.
Exam 3 | #86. During the project review, the project data shows PV as $100k, Earned value $95k. What is the Schedule Performance Index? |  | $5k | 0.95 | 1.05 | Cannot say | Answer option b. | Answer option b. “0.95” Schedule Performance Index (SPI) =EV/PV=95/100= 0.95 Answer option b. “0.95” Schedule Performance Index (SPI) =EV/PV=95/100= 0.95
Exam 3 | #87. In ______ process, identified quality requirements are used as test and evaluation instruments. |  | Plan Quality | Manage Quality | Control Quality | Monitor Quality | Answer option b. | During the “Manage Quality” process, quality requirements identified during the Plan Quality Management process are turned into test and evaluation instruments.
Exam 3 | #88. Estimate Costs is a critical process for project planning. Samantha knows that one of the techniques she can use for this process is reserve analysis. It aims to account for cost uncertainty and identified risks. Which of the following is an example of such costs? |  | Rework | Scope creep | Phase closure | Quality conformance | Answer option a. | Answer option a. “Rework” could be anticipated, while the amount of this rework is unknown. Contingency reserves may be estimated to account for this unknown amount of rework. Answer option a. “Rework” could be anticipated, while the amount of this rework is unknown. Contingency reserves may be estimated to account for this unknown amount of rework.
Exam 3 | #89. You are classifying your project stakeholders using the data-representation technique based on the directions of stakeholders’ influence . You are about to classify the top management. How would you classify them? |  | Upward | Downward | Outward | Sideward | Answer option a. | Answer option a. “Upward” Answer option a. “Upward”
Exam 3 | #90. Cause-and-effect diagram breaks down the causes of the problem statement into discrete branches, helping to identify the main or the root cause of the problem. All of the following are other names used for cause-and-effect diagrams except ______ . |  | Affinity diagrams | Fishbone diagrams | Why-why diagrams | Ishikawa diagrams | Answer option a. | Answer option a. “Fishbone diagrams” (Answer option b.), “Why-why diagrams” (Answer option c.) and “Ishikawa diagrams “(Answer option d.) are names used for cause-and-effect diagrams. Affinity diagrams (Answer option a.) are not the root cause diagrams. Affinity diagrams help sort out requirements based on their affinity (similarity). Answer option a. “Fishbone diagrams” (Answer option b.), “Why-why diagrams” (Answer option c.) and “ Ishikawa diagrams “(Answer option d.) are names used for cause-and-effect diagrams. Affinity diagrams (Answer option a.) are not the root cause diagrams. Affinity diagrams help sort out requirements based on their affinity (similarity).
Exam 3 | #91. A project manager in a virtual team realizes, during the third iteration of product development, that the team dashboard that shows progress on work is defective and is NOT showing updates. Which action should the project manager take? |  | Keep the team working and send daily email updates to the team. | Rank the need to fix the dashboard according to the business value for upcoming iterations. | Get the dashboard fixed. | Document the issue as a new project risk and propose a solution. | Answer option c. | In an agile virtual team, the project manager needs to keep work visible so that the team can see progress. This is essential. Changing the way the team works together in the middle of a project can be very disruptive. In this case, they are lucky that a problem did NOT arise. The project manager needs to protect the team against impediments and allow them to focus on their work.
Exam 3 | #92. You are working on the project communication management processes. Which trends and emerging practices for Project Communications Management would you consider? |  | Physical location | Communications technology | Knowledge management | Inclusion of stakeholders in project reviews | Answer option d. | Answer option d. ”Inclusion of stakeholders in project reviews” is the only trend and emerging practice for Project Communications Management. Answer option d. ”Inclusion of stakeholders in project reviews” is the only trend and emerging practice for Project Communications Management.
Exam 3 | #93. You are a project manager working on a project in a highly volatile environment. Your team is experienced but is quite concerned about all the external risks that might be affecting the project completion. You plan to do an analysis of the overall risks and analyze and interpret the data on external opportunities and threats. What risk categorization are you going to use? |  | PESTLE | FOCUS | SPECTRUM | RISK | Answer option a. | Answer option a. “PESTLE” is a risk categorization for exploring and listing the external factors that may impact your business and planning. PESTLE stands for Political, Economic, Social, Technological, Legal, and Environmental. Answer option a. “PESTLE” is a risk categorization for exploring and listing the external factors that may impact your business and planning. PESTLE stands for Political, Economic, Social, Technological, Legal, and Environmental.
Exam 3 | #94. _____ have an organizational scope that changes with the strategic objectives of the organization. |  | Projects | Programs | Portfolios | All of the above | Answer option c. | Answer option c. The best answer is “Portfolios” (Answer option c.), because the projects, programs, operations that are included in the portfolio need to be strategically aligned with the organizational goals and objectives. “Projects” (Answer option a.) The scope is defined and progressively elaborated throughout the project life cycle. “Programs” (Answer option b.) Programs produce benefits to an organization by ensuring that the outputs and outcomes of program components are delivered in a coordinated and complementary manner. Answer option c. The best answer is “Portfolios” ( Answer option c. ), because the projects, programs, operations that are included in the portfolio need to be strategically aligned with the organizational goals and objectives. “Projects” ( Answer option a. ) The scope is defined and progressively elaborated throughout the project life cycle. “Programs” ( Answer option b. ) Programs produce benefits to an organization by ensuring that the outputs and outcomes of program components are delivered in a coordinated and complementary manner.
Exam 3 | #95. Chris uses a set of technical guidelines applied during the design of a product for the optimization of a specific aspect of the design. These guidelines can control and improve the product’s final characteristics. Which technique is Chris using? |  | Histogram | Design for X | Forward Pass | Monte Carlo Simulation | Answer option b. | Answer option b. “Design for X”. Design for X (DfX) is a set of technical guidelines that may be applied during the design of a product for the optimization of a specific aspect of the design. DfX can control or even improve the product’s final characteristics. The X in DfX can refer to different aspects of product development, such as reliability, deployment, assembly, manufacturing, cost, service, usability, safety, and quality. Using the DfX may result in cost reduction, quality improvement, better performance, and customer satisfaction. Answer option b. “Design for X”. Design for X (DfX) is a set of technical guidelines that may be applied during the design of a product for the optimization of a specific aspect of the design. DfX can control or even improve the product’s final characteristics. The X in DfX can refer to different aspects of product development, such as reliability, deployment, assembly, manufacturing, cost, service, usability, safety, and quality. Using the DfX may result in cost reduction, quality improvement, better performance, and customer satisfaction.
Exam 3 | #96. Johnathan is a member of a Scrum of Scrum Team. This morning, after he attended his Scrum Meeting with the Developers, he attended the Scrum of Scrum meeting. In his discussion with the other Scrum Masters, he shared the work that his team had completed yesterday and the work that was beginning today. Of the following, choose which items should also be addressed. (More than one can be chosen) |  | Any impediments that his team is experiencing. | Any changes to his team’s Product Backlog. | Any obstacles that his team may be creating for the other Scrum Masters’ teams. | The conflict his team is currently experiencing and his strategy for addressing it. | Answer options a and c. | Answer options a and c. While many things may be discussed among the Scrum Masters after the Scrum of Scrum Meeting, the process only requires that they discuss: Answer options a and c. W hile many things may be discussed among the Scrum Masters after the Scrum of Scrum Meeting, the process only requires that they discuss: What has your team done since we last met? What will your team do before we meet again? Is anything slowing your team down or getting in their way? Are you about to put something in another team’s way? What has your team done since we last met? What will your team do before we meet again? Is anything slowing your team down or getting in their way? Are you about to put something in another team’s way?
Exam 3 | #97. Managing a project requires a wide range of skill sets. Which of the following is not one of the interpersonal and team skills that can be used during the Manage Team process? |  | Influencing | Decision making | Artificial Intelligence | Conflict management | Answer option c. | Answer option c. “Artificial Intelligence” is not interpersonal and team skills. Answer option c. “Artificial Intelligence” is not interpersonal and team skills.
Exam 3 | #98. Prior to a new product development decision, Rajesh is assessing the feasibility of the product using financial measures. Which of the following measures should he consider? |  | Strategic alignment | Customer satisfaction | Net present value | All of the above | Answer option c. | Answer option c. “Net present value” is the only financial measure within the offered answer options. Answer option c. “Net present value” is the only financial measure within the offered answer options.
Exam 3 | #99. Which of the following statements reflect the difference in scope management practices of Predictive (Waterfall) and Agile project life cycle development approaches? |  | Only the predictive approach utilizes scope validation and scope control processes. | Scope changes occur only in the Agile life cycle approach. | Collect requirements, define scope, and create WBS are done once in a predictive, unless changes occur, and once for each iteration in the Agile. | Scope validation and scope control are done only once in an iterative life cycle approach. | Answer option c . | Answer option c. “Collect requirements, define scope, and create WBS are done once in a predictive, unless changes occur, and once for each iteration in the Agile.” Answer option c . “Collect requirements, define scope, and create WBS are done once in a predictive, unless changes occur, and once for each iteration in the Agile.”
Exam 3 | #100. While developing the project benefits management plan, the project sponsor is identifying the project’s intangible benefits. Which of the following would he include? |  | Public benefit | Utility | Fixtures | Tools | Answer option a. | Answer option a. “Utility” (Answer option b.), “Fixtures” (Answer option c.), and “Tools” (Answer option d.) are all tangible benefits. The best answer is “Public benefit” (option a) is the only intangible benefit within the options. Answer option a. “ Utility ” (Answer option b.), “ Fixtures ” (Answer option c.), and “ Tools ” (Answer option d.) are all tangible benefits . The best answer is “ Public benefit ” (option a) is the only intangible benefit within the options.
Exam 3 | #101. In response to the country’s new health standards, Star and Co. decided to launch a new project to meet the required compliance recommendations. This is an example of _____ . |  | Meet regulatory, legal, or social requirements | Satisfy stakeholder requests or needs | Implement or change the business or technological strategies | Create, improve, or fix products, processes, or services | Answer option a. | Answer option a. “Meet regulatory, legal, or social requirements”. The country’s new health standard points to a “regulation”. Answer option a. “Meet regulatory, legal, or social requirements”. The country’s new health standard points to a “regulation”.
Exam 3 | #102. Your project has the following performance measures: CV= $5k, AC=$30k, and PV=$25k. What is the schedule variance? |  | $5k | $-5k | $10k | Cannot say | Answer option c. | Answer option c. “$10k” To calculate SV, EV is required. EV can be derived from CV=EV-AC then EV=30 5=35 then SV=EV-PV=35-25=$10k Answer option c. “$10k” To calculate SV, EV is required. EV can be derived from CV=EV-AC then EV=30 5=35 then SV=EV-PV=35-25=$10k
Exam 3 | #103. Alex just completed all of the project activities and started measuring whether the project achieved the planned business value or not. Which document would help him in his task? |  | Business case | Benefits management plan | Project charter | All of the above | Answer option b. | Answer option b. “Benefits management plan” can be used to measure whether the project achieved its planned business value or not as it contains the targeted business value. Answer option b. “Benefits management plan” can be used to measure whether the project achieved its planned business value or not as it contains the targeted business value.
Exam 3 | #104. In Alyssa’s consulting engagement with a major manufacturing company, she is working with the IT Director in the team’s first agile project. The IT Director has requested that the teams provide daily written reports to provide him with a summary of the work they completed. Alyssa explains that the written reports are not a necessity because of the Daily Scrum and which Agile Principle? |  | Deliver working software frequently, from a couple of weeks to a couple of months, with a preference to the shorter timescale. | Build projects around motivated individuals. Give them the environment and support they need, and trust them to get the job done. | Welcome changing requirements, even late in development. Agile processes harness change for the customer's competitive advantage. | Working software is the primary measure of progress. | Answer option b. | Answer option b. Of the available options, B is the one that represents the Agile Principle related to trusting the team and allowing them to be self-organizing. Answer option b. Of the available options, B is the one that represents the Agile Principle related to trusting the team and allowing them to be self-organizing.
Exam 3 | #105. A project manager is communicating with other project teams to negotiate for scarce resources. This is an example of_____ communication. |  | Formal | Hierarchical Downward | Hierarchical Horizontal | Official | Answer option c. | Answer option c. “Hierarchical Horizontal” other projects’ teams are considered equal in rank, therefore this is Horizontal communication. Answer option c. “Hierarchical Horizontal” other projects’ teams are considered equal in rank, therefore this is Horizontal communication.
Exam 3 | #106. Molly, an Agile Project Manager, is working with a customer to develop a new 3d design software. During the beginning of the project, the customer has made a request. He wants to see and validate the initial features of the software to determine future functionality of the software. What project lifecycle is Molly using? |  | Lean life cycle | Kanban life cycle | Predictive life cycle | Incremental life cycle | Answer option d. | Answer option d. Each increment provides working software, although full functionality may not be present. Additionally, incremental improvements add a set of specific functionalities to the software. Answer option d. Each increment provides working software, although full functionality may not be present. Additionally, incremental improvements add a set of specific functionalities to the software.
Exam 3 | #107. Attitudinal surveys, specific assessments, structured interviews, ability tests, and focus groups are all tools for ____ . |  | Team building | Virtual teams | Individual and team assessment | Team performance assessment | Answer option c. | Answer option c. “Individual and team assessment” Answer option c. “Individual and team assessment”
Exam 3 | #108. Mark, as the Scrum Master, is chairing the Sprint Planning Session that includes five developers. They are playing planning poker and estimating story points on one of the backlog items that have been brought into the current Sprint. When the Fibonacci Sequence cards are revealed, the Developers have the following cards showing: 2, 13, 40, 40, and 100. To obtain consensus, Mark’s next step should be: |  | To encourage the Developers whose estimates were 40 to explain to the group their reasoning for their estimates. | To use the estimate of 40 as this represents the mode of the numbers. | To request that the Developers that estimated 2 and 100 explain their reasoning for their estimates. | To request that the team continue voting until they reach consensus. | Answer option c. | Answer option c. After the cards reveal the Story Point estimates, the Developers that vote the smallest and largest numbers use the “soap box” to explain why and how they came to their estimates. The Developers then vote again, but not until after they do the “soap box” process. Answer option c. After the cards reveal the Story Point estimates, the Developers that vote the smallest and largest numbers use the “soap box” to explain why and how they came to their estimates. The Developers then vote again, but not until after they do the “soap box” process.
Exam 3 | #109. The project team is using an automated resource assignment tool to reflect changes in resource assignments and also to notify project staff of the changes. The project manager makes sure that the team is up to date with the latest skills and work processes they need to employ in the project. What type of costs does this tool affect? |  | Internal Failure Costs | External Failure Costs | Prevention Costs | Appraisal Costs | Answer option c. | Answer option c. “Prevention Costs”. Costs related to the prevention of poor quality in the products, deliverables, or services of the specific project. Answer option c. “Prevention Costs”. Costs related to the prevention of poor quality in the products, deliverables, or services of the specific project.
Exam 3 | #110. Tom presented a new map to the Scrum Team. On the vertical axis, he draws the probability of a given risk occurring. On the horizontal axis, he draws the impact that the risk will have on the project or program should it materialize. What document did Tom present to his team? |  | Risk burndown chart | Story Map | Probability and impact matrix | Value stream map | Answer option c. | Answer option c. One of the best ways to visually display risks in a succinct manner is to use Probability and Impact Matrix. (changed from Risk map – in PMBoK there is no such term as Risk map) On the vertical axis, you have the probability of a given risk occurring, that is, the likelihood that the risk will materialize and become an Issue. On the horizontal axis we have the impact that the risk will have on the project or program should it materialize. Answer option c. One of the best ways to visually display risks in a succinct manner is to use Probability and Impact Matrix. (changed from Risk map – in PMBoK there is no such term as Risk map) On the vertical axis, you have the probability of a given risk occurring, that is, the likelihood that the risk will materialize and become an Issue. On the horizontal axis we have the impact that the risk will have on the project or program should it materialize.
Exam 3 | #111. When the team estimates the activity duration, this process results in documenting the basis of estimates. The supporting documentation should provide a clear and complete understanding of how the duration estimate was derived. Which of the following is not an example of this documentation? |  | Documentation of stakeholders contact details | Documentation of all assumptions made | Documentation of any known constraints | Documentation of individual project risks | Answer option a. | Answer option a. “Documentation of stakeholders contact details”. Stakeholder contact details are not related to activity duration estimates and can be found in the stakeholders register. Answer option a. “Documentation of stakeholders contact details”. Stakeholder contact details are not related to activity duration estimates and can be found in the stakeholders register.
Exam 3 | #112. Brian, a Project Manager, is assigned to a significant software development project for a large software development corporation XYZ. As the project manager, Brian must do most of the planning upfront and deliver the working software through a single pass from start to finish, as required by the Project Sponsor. After listening to the company's approach, Brian should provide the following advice: |  | He will be able to deliver on the project result using the approach recommended by the Project Sponsor on time and with no deviations from the stakeholders' expectations as he will be using an Agile approach. | He will be able to deliver on the project result using the approach recommended by the Project Sponsor on time and with no deviations from the stakeholders' expectations. He will be using an Iterative process. | He will be able to deliver on the project result using the approach recommended by the Project Sponsor on time and with no deviations from the stakeholders' expectations. He will be using a Predictive method. | He will need to modify the approach and build on product increments. To do so, he will use an Agile approach, and the customer will be providing constant feedback and approval to move forward with working software. | Answer option c. | Answer option c. Using a Predictive cycle in a sequential process of initiating, planning, executing, monitoring and controlling, and closing projects in a single pass will be the best approach for this project. Predictive approaches focus on upfront planning and executing project work to the plan. With a deliverable required to be completed in one single pass from end to end, Predictive approaches will be the best method for this example. Answer option c. Using a Predictive cycle in a sequential process of initiating, planning, executing, monitoring and controlling, and closing projects in a single pass will be the best approach for this project. Predictive approaches focus on upfront planning and executing project work to the plan. With a deliverable required to be completed in one single pass from end to end, Predictive approaches will be the best method for this example.
Exam 3 | #113. You are working on a traditional Waterfall project and your company wants to move to an Agile way of work. The VP of Information Technology wants to get the benefit of certain Agile tools that they have heard about that are used to uncover potential problems before they occur. What will you do next? |  | Create a product backlog, velocity chart, and Kanban board accessible to the executive and team members in an identified company repository | Begin iteration planning | Update the project management plan and distribute to key project stakeholders | Setup a recurring working session with project stakeholders to discuss the project | Answer option a. | Answer option a. One of the key benefits of Agile is providing visuals to manage the project. By making the Kanban visible to all, along with the backlog and velocity chart, all key stakeholders will have full visibility to project activities and progress. Answer option a. One of the key benefits of Agile is providing visuals to manage the project. By making the Kanban visible to all, along with the backlog and velocity chart, all key stakeholders will have full visibility to project activities and progress.
Exam 3 | #114. Abby is working with her team that is tasked with developing an internal web-based solution for the Inventory team’s need to workflow and track requests. The agile team is discussing how to conduct testing for one of the user stories and cannot come to an agreement. Abby’s best next course of action would be to: |  | Tell the team she will meet with the customer to get their input for their test preference. | Meet with the team, listen to the developer’s suggestions, and determine the most effective method. | Meet with the team and encourage and support them as they create a collective solution. | Schedule a meeting with the development team and the stakeholders to create a collective solution | Answer option c. | Answer option c. Agile teams are self-organizing and are responsible for the technical decisions of the project that are made. One of the project manager’s roles in an agile team is to provide support and guidance for the team. In this scenario, the best response is to use problem solving skills to assist the team in coming to consensus. Answer option c. Agile teams are self-organizing and are responsible for the technical decisions of the project that are made. One of the project manager’s roles in an agile team is to provide support and guidance for the team. In this scenario, the best response is to use problem solving skills to assist the team in coming to consensus.
Exam 3 | #115. Two of your team members are having an argument about the technical aspect of the project. Their opinions on how to resolve the problem are very different and it became a full-blown conflict. There is a lot of tension. What should you do next? |  | You should listen to both sides in order to understand their take on the issue, and then mediate the conflict and provide guidance to successfully resolve the conflict. | You should tell them right away who is right and who is wrong. | You should consult the team and ask for advice on the best course of action. | Size them up and see if one of them is flexible enough to concede their position. | Answer option a. | Answer option a. You should listen to both sides to understand their standing on the issue, and then mediate the conflict and provide guidance to successfully resolve the conflict. This is a collaborate/problem-solve conflict resolution technique. Answer option a. You should listen to both sides to understand their standing on the issue, and then mediate the conflict and provide guidance to successfully resolve the conflict. This is a collaborate/problem-solve conflict resolution technique .
Exam 3 | #116. Adam is using a technique that compares the performance measurement baseline to the actual schedule and cost performance, and also integrates the scope baseline with the cost baseline and with the schedule baseline to form the performance measurement baseline. Which technique is he using? |  | Earned value analysis | Trend analysis | Variance analysis | Reserve analysis | Answer option a. | Answer option a. “Earned value analysis”. Earned value analysis compares the performance measurement baseline to the actual schedule and cost performance. EVM integrates the scope baseline with the cost baseline and schedule baseline to form the performance measurement baseline. Answer option a. “Earned value analysis”. Earned value analysis compares the performance measurement baseline to the actual schedule and cost performance. EVM integrates the scope baseline with the cost baseline and schedule baseline to form the performance measurement baseline.
Exam 3 | #117. Sandra is a new Scrum Master in an IT software development team. She has been hearing of an impediment in every Daily Scrum this week. In today’s meeting, she asked the Developer who reported the impediment why he had not addressed the issue yet. The Development Team was quiet and did not offer any reasons. What Scrum process is being neglected? |  | The Sprint Planning Session at the beginning of the Sprint did not adequately address the risks that were potential threats to the work in this Sprint. | The Developer is responsible for removing obstacles that present an impediment to the progress of the Sprint. | One of the Scrum Master’s responsibilities to the Project Team is the removal of obstacles. | The Project Sponsor should be notified of the obstacle so that they can address the impediment. | Answer option c. | Answer option c. The removal of the impediment/obstacle is the job of the Scrum Master, not the Developer. Answer option c. The removal of the impediment/obstacle is the job of the Scrum Master, not the Developer.
Exam 3 | #118. Mark is leading an advertising project. He decided to use storyboarding to navigate through a series of images and illustrations. The customer welcomed his idea. Mark assured the customer that storyboarding is a common technique of _____ . |  | Prototyping | Facilitation | Mind Mapping | Context Diagramming | Answer option a. | Answer option a. “Prototype” Storyboarding and mock-ups are both prototyping tools. Answer option a. “Prototype” Storyboarding and mock-ups are both prototyping tools.
Exam 3 | #119. Darren is reviewing the quality control measurements to identify the lessons learned from the project. This is an example of _____ . |  | Document analysis | Regression analysis | Trend analysis | Variance analysis | Answer option a. | Answer option a. “Document analysis”. Assessing available documentation will allow identifying lessons learned and knowledge sharing for future projects and organizational assets improvement. Answer option a. “Document analysis”. Assessing available documentation will allow identifying lessons learned and knowledge sharing for future projects and organizational assets improvement.
Exam 3 | #120. You are the Scrum Master initiating a new iteration in your Agile project. New features have been added to the backlog, and the team is unsure of which features to work on next. How will you guide the Product Owner and team on priority? |  | Focus on the tasks created most recently so you can deliver value quickly | Ask the customer what they want delivered first | Analyze the value of each feature with the Product Owner, instead of determining effort & risks of each item with the Agile team. | Deliver the entire project at the end so the project sponsor can see all features together. | Answer option c. | Answer option c. Although value is determined by features that the customer wants, the priority is set by the Product Owner who represents the customer and continually grooms the Product Backlog. Answer option c. Although value is determined by features that the customer wants, the priority is set by the Product Owner who represents the customer and continually grooms the Product Backlog.
Exam 3 | #121. Sally is discussing with the project quality team about the Cost of non-conformance, which is the money spent during and after the project because of failures. Which of the following is an “internal failure cost”? |  | Rework | Warranty | Inspection | Equipment | Answer option a. | Answer option a. “Rework” is an internal failure cost. Answer option a. “Rework” is an internal failure cost.
Exam 3 | #122. During the first phase of your project, you have submitted a change request to the change control board. After a short deliberation, the change request was approved. You want to confirm that this change has been implemented correctly. Where do you confirm that the change request was implemented correctly? |  | Manage Quality | Control Quality | Direct and Manage Project Work | Monitor and Control Project Work | Answer option b. | Answer option b. “Control Quality”. Approved change requests are input to the Control Quality process. The implementation of approved changes should be verified, checked for completeness and correctness. Answer option b. “Control Quality”. Approved change requests are input to the Control Quality process. The implementation of approved changes should be verified, checked for completeness and correctness.
Exam 3 | #123. With the support of your product owner, the backlog is prioritized continuously, and the team picks to deliver the items that have the highest value. This means that at any point in time, the features or components that are deemed most valuable to the customer will be completed first. This effort from the team is derived by which of the following? |  | Team’s highest priority is to satisfy the customer through early and continuous delivery of valuable software. | Welcome changing requirements, even late in development. | Deliver working software frequently, from a couple of weeks to a couple of months, with a preference to the shorter iterations. | Business people and developers must work together daily throughout the project. | Answer option a . | Answer option a. Customers get valuable software delivery continuously when the team works on the most valuable Product Backlog Items. Answer option a . Customers get valuable software delivery continuously when the team works on the most valuable Product Backlog Items.
Exam 3 | #124. Kanban is a well-known methodology that is characterized by 3 S’s. Which of the following is not one of Kanban’s 3 S’s? |  | Scheduling | Scope | Selection | Sequencing | Answer option b | . Kanban’s 3 S’s are scheduling, selection, and sequencing. Scope is irrelevant as the purpose of Kanban is to identify and fix potential bottlenecks in the work progress and optimize the workflow.
Exam 3 | #125. Alex is managing a construction project. Currently, he is working on the “Estimate Costs” process. Which of the below answers is not an organizational process asset that can influence the process? |  | Cost estimating policies | Cost estimating templates | Exchange rates and inflation | Both A and B | Answer option c. | Answer option c. “Exchange rates and inflation” is not an organizational process, it is an enterprise environmental factor. Answer option c. “Exchange rates and inflation” is not an organizational process, it is an enterprise environmental factor.
Exam 3 | #126. Adam is working on implementation of the risk responses. He wants to review the nominated owners for each response plan. Which input contains these details? |  | Risk management plan | Risk report | Risk register | Risk breakdown structure | Answer option c. | Answer option c. “Risk register”. The risk register contains the identified risks of the project and usually links them to the specific stakeholders as either risk owners or as subject to risk impact. Answer option c. “Risk register”. The risk register contains the identified risks of the project and usually links them to the specific stakeholders as either risk owners or as subject to risk impact.
Exam 3 | #127. You are working on ensuring the information needs of the project and its stakeholders are met. Which of the following processes can help you to achieve this? |  | Manage communications | Manage stakeholder engagement | Monitor stakeholder engagement | Monitor communications | Answer option d. | Answer option d. “Monitor communications” is the process of ensuring the information needs of the project and its stakeholders are met. Answer option d. “Monitor communications” is the process of ensuring the information needs of the project and its stakeholders are met.
Exam 3 | #128. You are the project manager for an ISO project, which is intended to ensure that your organization meets the requirements of ISO 9001. You have decided to send several members of the team to an ISO 9001 training course. What do you do in order to make sure that effective training will be in place? |  | Use social media | The training should have been paid for | The reminders on the training should have been sent to make sure that the team members are aware of the training | The location should be confirmed | Answer option c. | Answer option c. In order to make sure that the team members are attending the training they should be reminded a few days earlier and they should be able to send a confirmation that they are going to attend the training. Answer option c. In order to make sure that the team members are attending the training they should be reminded a few days earlier and they should be able to send a confirmation that they are going to attend the training.
Exam 3 | #129. Juan wants to identify the working days, shifts, start, and end of normal business hours, weekends, and public holidays when each specific resource is available. He also wants to specify when and for how long the identified team and physical resources will be available during the project. Juan should refer to ______ . |  | Project Calendar | Resource Calendar | Risk Register | Stakeholder Register | Answer option b. | Answer option b. “Resource Calendar” contains information related to resource working hours and availability. Answer option b. “Resource Calendar” contains information related to resource working hours and availability.
Exam 3 | #130. The project team is excited that the major project deliverable has been developed. The project manager asked the team to validate the product before handing it over to the customer. Which of the following techniques can the team use for validation? |  | Inspection | Data Analysis | Decomposition | Expert Judgment | Answer option a. | Answer option a. “Inspection” helps the project team validate the deliverables’ conformance to the original requirements. Answer option a. “Inspection” helps the project team validate the deliverables’ conformance to the original requirements.
Exam 3 | #131. Paul is leading a new project, but he is not familiar with the technical aspects of the project. He just found that Anna led a similar project two months ago. As Paul tries to estimate the durations of activities in his project, Anna can help in providing _____ . |  | Analogous Estimating | Parametric Estimating | Three-Point Estimating | Bottom-Up Estimating | Answer option a. | Answer option a. “Analogous Estimating” is a technique for estimating the duration or cost of an activity or a project using historical data from a similar activity or project. Answer option a. “Analogous Estimating” is a technique for estimating the duration or cost of an activity or a project using historical data from a similar activity or project.
Exam 3 | #132. You are working on an Agile project where the customer is requesting additional features to be delivered in each iteration (Sprint). You know what they are asking for is not possible based on the team’s velocity. What is the BEST next step? |  | Add more members to the Development team to take on more work in each iteration. | Present the team velocity chart to the customer with the points allotted to each story in the backlog, and ask them to prioritize features in the backlog in coordination with the Product Owner in the next iteration. | Ask for additional feedback from different customers who will use the product being delivered. | Add additional stories in the iteration, as the development team will complete them in the current iteration. | Answer option b. | Answer option b. Show the customer the team velocity and how many points are allotted and ask them to assist in prioritizing the features they want next. This gives them control over the value delivered while not overburdening the team. Answer option b. Show the customer the team velocity and how many points are allotted and ask them to assist in prioritizing the features they want next. This gives them control over the value delivered while not overburdening the team.
Exam 3 | #133. The Development team is fairly new to Agile and has been given a highly complex project. The requirements need further elaboration and review, and after the first iteration (Sprint) the Product Owner rejects the work developed by the team. What should have been done by the development team to prevent this situation? |  | Confirmed Product Owner attendance during the daily standup meetings. | Cancel the sprint before the Product Owner can reject the work. | Document feedback of the Product Owner in the Sprint Retrospective. | Ensure the Product Owner works with their team daily by providing feedback on the product. | Answer option d. | Answer option d. The Product Owner should work with their team by providing product feedback and setting direction on the next piece of functionality to be developed and delivered. The Sprint Retrospective is not a place for the Product Owner to accept/reject work, and the team cannot cancel the sprint early for this reason. The Product Owner is not a mandatory member during the daily standup. Answer option d. The Product Owner should work with their team by providing product feedback and setting direction on the next piece of functionality to be developed and delivered. The Sprint Retrospective is not a place for the Product Owner to accept/reject work, and the team cannot cancel the sprint early for this reason. The Product Owner is not a mandatory member during the daily standup.
Exam 3 | #134. A project manager who works in an organization that uses traditional project management is assigned to an ongoing project. Recently, the organization has started using agile methodologies for projects. The project manager hears that some team members think the project is missing key subject matter expertise and that the team does NOT collaborate enough. How should the project manager respond to these team members' concerns? |  | Employ third-party specialists to fill the knowledge gap. | At the next stand-up meeting, emphasize the importance of collaboration to the entire team. | Add cross-functional internal resources and explain their value to the team. | Start using Kanban boards instead of Gantt charts so that work co-dependencies become obvious to everyone. | Answer option c | . Add cross-functional internal resources and explain their value to the team. Agile projects require “T” shaped team members. That is, individuals who are cross-functional and understand the importance and value of collaboration across functional areas. In this case, the team needs the addition of skilled resources and people who collaborate.
Exam 3 | #135. Kanban is an Agile methodology, where work items are represented visually to display various stages of the progress. From the selections below, which item is NOT one of the three principles of Kanban? |  | Daily standups for 15 minutes | Reduce the amount of work in progress | Enhance the workflow | Visualize the work items | Answer option a. | Kanban three principles are: Limit work in progress (WIP), visualize the workflow and enhance the workflow. Daily standups are a Scrum event and are not part of the Kanban method.
Exam 3 | #136. A project manager aims to represent the project risks and sources of uncertainty that might occur independently of any planned activity. Which model is the most useful for this representation? |  | Monte Carlo | Probabilistic branches | Expected monetary value | Tornado Diagram | Answer option b. | Answer option b. “Probabilistic Branches” are used to represent project risks and sources of uncertainty that might occur independently of any planned activity. Answer option b. “Probabilistic Branches” are used to represent project risks and sources of uncertainty that might occur independently of any planned activity.
Exam 3 | #137. Product Backlog prioritization is one of the most important features in agile software development. Projects are successful if the team effectively and consistently prioritizes the requirements (users stories). Backlog prioritization is required to organize the product backlog items to make the sequence of its development and deployment. When managing an agile software team, engaging the business in prioritizing the backlog is an example of: |  | Technical risk reduction | Incorporating stakeholder values | Vendor management | Stakeholder story mapping | Answer option b. | Answer option b. We engage the business in prioritizing the backlog to better understand and incorporate stakeholder values. Although such engagement will likely impact technical risk reduction, vendor management, or stakeholder story mapping, these are not the main reasons we engage the business. Answer option b. We engage the business in prioritizing the backlog to better understand and incorporate stakeholder values. Although such engagement will likely impact technical risk reduction, vendor management, or stakeholder story mapping, these are not the main reasons we engage the business.
Exam 3 | #138. The project team is not very confident that they would be able to deliver the project on time and would much rather discuss other details of the requirements that are expected by the customer. What can a Project manager do to make sure that the team is focused on creating immediate deliverables? |  | Create a sense of urgency | Ask the senior team member to be responsible for the deliverables | Group all deliverables together | Ask the customer to help define the new requirements | Answer option a. | Answer option a. “Create a sense of urgency” A project manager needs to establish a sense of urgency to the project team. The team needs to accomplish the ongoing tasks in the project thus delivering value to the customer quickly and efficiently. Answer option a. “Create a sense of urgency” A project manager needs to establish a sense of urgency to the project team. The team needs to accomplish the ongoing tasks in the project thus delivering value to the customer quickly and efficiently.
Exam 3 | #139. ____ requires disclosing the available budget to invited sellers in the RFP and selecting the highest-ranking technical proposal within the budget. |  | Qualifications document | Quality-based/highest technical proposal score | Quality and cost-based proposal | Fixed price contract | Answer option d. | Answer option d. “Fixed price contract”. The fixed price contract requires disclosing the available budget to invited sellers in the RFP and selecting the highest-ranking technical proposal within the budget. Because sellers are subject to a cost constraint, they will adapt the scope and quality of their offer to that budget. Answer option d. “Fixed price contract”. The fixed price contract requires disclosing the available budget to invited sellers in the RFP and selecting the highest-ranking technical proposal within the budget. Because sellers are subject to a cost constraint, they will adapt the scope and quality of their offer to that budget.
Exam 3 | #140. A project sponsor is developing a Project Benefits Management Plan. As he is identifying the tangible project benefits, which of the following would he include? |  | Brand recognition | Trademarks | Strategic alignment | Tools | Answer option d. | Answer option d. “Brand recognition” (Answer option a.), “Trademarks” (Answer option b.) and “Strategic alignment” (Answer option c.) are all examples of intangible elements. The best answer is “Tools” (option d.) Answer option d. “ Brand recognition ” (Answer option a.), “ Trademarks ” (Answer option b.) and “ Strategic alignment ” (Answer option c.) are all examples of intangible elements . The best answer is “Tools” (option d.)
Exam 3 | #141. A project team shows a high level of synergy and works together as a unit. The project team is at ______ stage. |  | Forming | Storming | Norming | Performing | Answer option d. | Answer option d. When the team is in the Performing stage, it shows a high level of synergy and work together as a unit. One of the models used to describe team development is the Tuckman ladder, which includes five stages of team development. Although it is common for these stages to occur in order, it is not uncommon for a team to get stuck in a particular stage or regress to an earlier stage. Projects with team members who worked together in the past might skip a stage. Answer option d. When the team is in the Performing stage, it shows a high level of synergy and work together as a unit. One of the models used to describe team development is the Tuckman ladder, which includes five stages of team development. Although it is common for these stages to occur in order, it is not uncommon for a team to get stuck in a particular stage or regress to an earlier stage. Projects with team members who worked together in the past might skip a stage. Forming. This phase is where the team members meet and learn about the project and their formal roles and responsibilities. Team members tend to be independent and not as open in this phase. Storming. During this phase, the team begins to address the project work, technical decisions, and the project management approach. If team members are not collaborative or open to differing ideas and perspectives, the environment can become counterproductive. Norming. In this phase, team members begin to work together and adjust their work habits and behaviors to support the team. The team members learn to trust each other. Performing. Teams that reach the performing stage function as a well-organized unit. They are interdependent and work through issues smoothly and effectively. Adjourning. In this phase, the team completes the work and moves on from the project. This typically occurs when staff is released from the project as deliverables are completed or as part of the Close Project or Phase process. Forming. This phase is where the team members meet and learn about the project and their formal roles and responsibilities. Team members tend to be independent and not as open in this phase. Forming. This phase is where the team members meet and learn about the project and their formal roles and responsibilities. Team members tend to be independent and not as open in this phase. Storming. During this phase, the team begins to address the project work, technical decisions, and the project management approach. If team members are not collaborative or open to differing ideas and perspectives, the environment can become counterproductive. Storming. During this phase, the team begins to address the project work, technical decisions, and the project management approach. If team members are not collaborative or open to differing ideas and perspectives, the environment can become counterproductive. Norming. In this phase, team members begin to work together and adjust their work habits and behaviors to support the team. The team members learn to trust each other. Norming. In this phase, team members begin to work together and adjust their work habits and behaviors to support the team. The team members learn to trust each other. Performing. Teams that reach the performing stage function as a well-organized unit. They are interdependent and work through issues smoothly and effectively. Performing. Teams that reach the performing stage function as a well-organized unit. They are interdependent and work through issues smoothly and effectively. Adjourning. In this phase, the team completes the work and moves on from the project. This typically occurs when staff is released from the project as deliverables are completed or as part of the Close Project or Phase process. Adjourning. In this phase, the team completes the work and moves on from the project. This typically occurs when staff is released from the project as deliverables are completed or as part of the Close Project or Phase process.
Exam 3 | #142. A project manager is conducting procurement on the project. He wants to review the standards and guidelines, which he will use to assess the received proposals. Which procurement documentation should he review? |  | Bid documents | Procurement statement of work | Independent cost estimates | Source selection criteria | Answer option d. | Answer option d. “Source selection criteria”. These criteria describe how bidder proposals will be evaluated, including evaluation criteria and weights. For risk mitigation, the buyer may decide to sign agreements with more than one seller to mitigate damage caused by a single seller having delivery problems that may impact the overall project. Answer option d. “Source selection criteria”. These criteria describe how bidder proposals will be evaluated, including evaluation criteria and weights. For risk mitigation, the buyer may decide to sign agreements with more than one seller to mitigate damage caused by a single seller having delivery problems that may impact the overall project.
Exam 3 | #143. Ashley decided to utilize a graphical planning tool, which makes key project elements visible to the entire team and provides a real-time overview of the project status. This is an example of_____. |  | Evolving trends in integration processes | Considerations for tailoring integration processes | Considerations for agile environments | Both B and C | Answer option a. | Answer option a. “Evolving trends in integration processes”. Evolving trends in integration processes include but are not limited to: Answer option a. “Evolving trends in integration processes”. Evolving trends in integration processes include but are not limited to: Use of automated tools. The volume of data and information that project managers need to integrate makes it necessary to use a project management information system (PMIS) and automated tools to collect, analyze, and use information to meet project objectives and realize project benefits. Use of visual management tools. Some project teams use visual management tools, rather than written plans and other documents, to capture and oversee critical project elements. Making key project elements visible to the entire team provides a real-time overview of the project status, facilitates knowledge transfer, and empowers team members and other stakeholders to help identify and solve issues. Project knowledge management. The increasingly mobile and transitory work force requires a more rigorous process of identifying knowledge throughout the project life cycle and transferring it to the target audience so that the knowledge is not lost. Expanding the project manager’s responsibilities. Project managers are being called on to initiate and finalize the project, such as project business case development and benefits management. Historically, these activities have been the responsibility of management and the project management office, but project managers are more frequently collaborating with them to better meet project objectives and deliver benefits. Project managers are also engaging in more comprehensive identification and engagement of stakeholders. This includes managing the interfaces with various functional and operational departments and senior management personnel. Hybrid methodologies. Some project management methodologies are evolving to incorporate successfully applied new practices. Examples include the use of agile and other iterative practices; business analysis techniques for requirements management; tools for identifying complex elements in projects; and organizational change management methods to prepare for transitioning the project outputs into the organization. Use of automated tools. The volume of data and information that project managers need to integrate makes it necessary to use a project management information system (PMIS) and automated tools to collect, analyze, and use information to meet project objectives and realize project benefits. Use of automated tools. The volume of data and information that project managers need to integrate makes it necessary to use a project management information system (PMIS) and automated tools to collect, analyze, and use information to meet project objectives and realize project benefits. Use of visual management tools. Some project teams use visual management tools, rather than written plans and other documents, to capture and oversee critical project elements. Making key project elements visible to the entire team provides a real-time overview of the project status, facilitates knowledge transfer, and empowers team members and other stakeholders to help identify and solve issues. Use of visual management tools. Some project teams use visual management tools, rather than written plans and other documents, to capture and oversee critical project elements. Making key project elements visible to the entire team provides a real-time overview of the project status, facilitates knowledge transfer, and empowers team members and other stakeholders to help identify and solve issues. Project knowledge management. The increasingly mobile and transitory work force requires a more rigorous process of identifying knowledge throughout the project life cycle and transferring it to the target audience so that the knowledge is not lost. Project knowledge management. The increasingly mobile and transitory work force requires a more rigorous process of identifying knowledge throughout the project life cycle and transferring it to the target audience so that the knowledge is not lost. Expanding the project manager’s responsibilities. Project managers are being called on to initiate and finalize the project, such as project business case development and benefits management. Historically, these activities have been the responsibility of management and the project management office, but project managers are more frequently collaborating with them to better meet project objectives and deliver benefits. Project managers are also engaging in more comprehensive identification and engagement of stakeholders. This includes managing the interfaces with various functional and operational departments and senior management personnel. Expanding the project manager’s responsibilities. Project managers are being called on to initiate and finalize the project, such as project business case development and benefits management. Historically, these activities have been the responsibility of management and the project management office, but project managers are more frequently collaborating with them to better meet project objectives and deliver benefits. Project managers are also engaging in more comprehensive identification and engagement of stakeholders. This includes managing the interfaces with various functional and operational departments and senior management personnel. Hybrid methodologies. Some project management methodologies are evolving to incorporate successfully applied new practices. Examples include the use of agile and other iterative practices; business analysis techniques for requirements management; tools for identifying complex elements in projects; and organizational change management methods to prepare for transitioning the project outputs into the organization. Hybrid methodologies. Some project management methodologies are evolving to incorporate successfully applied new practices. Examples include the use of agile and other iterative practices; business analysis techniques for requirements management; tools for identifying complex elements in projects; and organizational change management methods to prepare for transitioning the project outputs into the organization.
Exam 3 | #144. In _____ contracts, the price is set for the end product of the project and not subject to change unless the scope of work changes. |  | Time and material | Cost plus fixed fee | Firm fixed price | Fixed price incentive fee | Answer option c. | Answer option c. “Firm fixed price” sets the price for the end product of the project and not subject to change unless the scope of work changes Answer option c. “Firm fixed price” sets the price for the end product of the project and not subject to change unless the scope of work changes
Exam 3 | #145. Matt is collecting requirements for his project. This is his first project in the pharmaceutical field. As he is not familiar with many acronyms and deliverables, he decides to gather data by conducting interviews and focus group discussions. Which of the following is not a key characteristic of focus groups? |  | Face to face | Prepared questions | Target Subject Matter Experts | One-on-one interview | Answer option d. | Answer option d. “One-on-one interview”. Focus groups consist of multiple attendee discussions, not one-on-one. Answer option d. “One-on-one interview”. Focus groups consist of multiple attendee discussions, not one-on-one.
Exam 3 | #146. Some business documents are inputs when we are in the process of closing the project. Which of the following is a business document? |  | Project charter | Assumption log | Benefits management plan | None of the above | Answer option c. | Answer option c. Business documents include Business case and Benefits management plan. Answer option c. Business documents include Business case and Benefits management plan.
Exam 3 | #147. _____ can contain earned value graphs and information, trend lines and forecasts, reserve burndown charts, defect histograms, contract performance information, and risk summaries. |  | Quality report | Risk report | Work performance reports | Both A and C | Answer option c. | Answer option c. “Work performance reports” can contain earned value graphs and information, trend lines and forecasts, reserve burndown charts, defect histograms, contract performance information, and risk summaries Answer option c. “Work performance reports” can contain earned value graphs and information, trend lines and forecasts, reserve burndown charts, defect histograms, contract performance information, and risk summaries
Exam 3 | #148. A project manager is creating an agenda and presentation materials for a kick-off meeting that will involve stakeholders across the globe. How can the project manager facilitate and optimize stakeholder engagement? |  | Create slides for the kick-off meeting to address stakeholder involvement. | Survey stakeholders' preferred meeting dates and times to accommodate the teams in different time zones. | Verify that all required participants or their delegates will be available to attend. | Review the kick-off meeting agenda and materials for overall clarity and concision. | Answer option b | . Survey stakeholders’ preferred meeting dates and times to accommodate the teams in different time zones. Assuming a particular solution does NOT empower the team. Surveying the team and finding common consensus is a key part of servant leadership.
Exam 3 | #149. Jane wants to estimate project activity durations with a high degree of confidence. She decides to decompose the activity into more detail, estimate the duration of the details, and then aggregate these estimates into a total quantity for each of the activity’s duration. This technique is called as _____ . |  | Analogous Estimating | Parametric Estimating | Three-Point Estimating | Bottom-Up Estimating | Answer option d. | Answer option d. “Bottom-Up Estimating”. Bottom-up estimating is a method of estimating project duration or cost by aggregating the estimates of the lower level components of the WBS. When an activity’s duration cannot be estimated with a reasonable degree of confidence, the work within the activity is decomposed into more detail. The detail durations are estimated. These estimates are then aggregated into a total quantity for each of the activity’s duration. Answer option d. “Bottom-Up Estimating”. Bottom-up estimating is a method of estimating project duration or cost by aggregating the estimates of the lower level components of the WBS. When an activity’s duration cannot be estimated with a reasonable degree of confidence, the work within the activity is decomposed into more detail. The detail durations are estimated. These estimates are then aggregated into a total quantity for each of the activity’s duration.
Exam 3 | #150. The project team engages with the stakeholders through negotiation and communication during the project. This activity is done when the project team __________________ . |  | Identify Stakeholders | Plan Stakeholder Engagement | Manage Stakeholder Engagement | Monitor Stakeholder Engagement | Answer option c. | Answer option c. “Manage Stakeholder Engagement”. Negotiating, communicating is a way to engage stakeholders while managing their expectations. Answer option c. “Manage Stakeholder Engagement”. Negotiating, communicating is a way to engage stakeholders while managing their expectations.
Exam 3 | #151. You are managing a project that will create a set of online learning training classes. Your company has a copyright on all of them. You know exactly what to do because you have already done similar projects. You want to make sure that the training participants will be able to utilize the knowledge gained from the classes. How can you measure the effectiveness of the training on the team members’ performance? |  | Analyze the Return of Investment for the training | Test their knowledge frequently | Ask them to write a weekly report | Ask to give an individual assessment of the benefits from the training | Answer option a. | Answer option a. Analyzing the ROI for training is a way to measure the benefits gained from the training. It is calculated by subtracting the net profit from the training costs and then divided by the training costs. The result indicates the dollar amount returned as a benefit for every dollar spent on training. Answer option a. Analyzing the ROI for training is a way to measure the benefits gained from the training. It is calculated by subtracting the net profit from the training costs and then divided by the training costs. The result indicates the dollar amount returned as a benefit for every dollar spent on training.
Exam 3 | #152. An important stakeholder has submitted the requirements on the criteria that will be needed to validate the successful completion of a project deliverable. The Project Manager has directed you to add this requirement in the requirements documentation. Which category of requirements will this requirement be added to? |  | Business requirements | Stakeholder requirements | Solution requirements | Quality requirements | Answer option d. | Answer option d. Quality requirements capture any condition or criteria needed to validate the successful completion of a project deliverable or fulﬁllment of other project requirements. Answer option d. Quality requirements capture any condition or criteria needed to validate the successful completion of a project deliverable or fulﬁllment of other project requirements.
Exam 3 | #153. Project execution reports are a mess that you have been handed over. It is difficult for you to find a single document that shows the types and quantities of resources that will be needed for each activity or the related work package. You are looking for a document that can help you find out the estimated resources of each WBS branch and the project as a whole. Which of the following documents meets your demand? |  | Organizational Breakdown Structure | Work Breakdown Structure | Resource Requirements | Resource Calendars | Answer option c. | Answer option c. Resource requirements identify the types and quantities of resources required for each work package or activity in a work package and can be aggregated to determine the estimated resources for each work package, each WBS branch, and the project as a whole. Answer option c. Resource requirements identify the types and quantities of resources required for each work package or activity in a work package and can be aggregated to determine the estimated resources for each work package, each WBS branch, and the project as a whole.
Exam 3 | #154. The project sponsor is aware of the challenging situation surrounding the project, therefore he assigned some critical resources while developing the Project Charter. Which of the following is the right term for such resources? |  | Prescribed Budgeting | Incorporate Employees | Virtual Team Assignment | Pre-assignment | Answer option d. | Answer option d. “Pre-assignment”. When physical or team resources for a project are determined in advance, they are considered pre-assigned. This situation can occur if the project is the result of specific resources being identified as part of a competitive proposal or if the project is dependent on the expertise of a particular person(s). Pre-assignment might also include the team members who have already been assigned in Develop Project Charter Process or other processes before the initial Resource Management Plan has been completed. Answer option d. “Pre-assignment”. When physical or team resources for a project are determined in advance, they are considered pre-assigned. This situation can occur if the project is the result of specific resources being identified as part of a competitive proposal or if the project is dependent on the expertise of a particular person(s). Pre-assignment might also include the team members who have already been assigned in Develop Project Charter Process or other processes before the initial Resource Management Plan has been completed.
Exam 3 | #155. A recently formed agile team is exhausted after working twelve-hour days to fulfill their sprint commitments. Who has not properly performed their duties in this situation? |  | Project manager | Team members | Product owner | Scrum master | Answer option d. | The Scrum master has the role of ensuring that the team’s working conditions, including workload, are appropriate and sustainable.
Exam 3 | #156. You have been assigned to perform a major organizational change, where the focus will be on finding an Agile coach to train the development team to be Agile-focused. What kind of Agile coach would you choose? |  | Process Coach | Transformative Coach | Architectural Coach | Technical Coach | Answer option b. | Coaching Agile takes many forms depending on the organization’s needs. In this particular situation, the organization is looking to transform into Agile practices therefore the focus will be on a transformative Agile coach.
Exam 3 | #157. You are given the task to examine and report if the final work product conforms to the documented standards stated in the specification of the product. You will submit the report of the findings from the measurements of specifications. Which technique will you be applying in this case? |  | Inspections | Data representation | Cause-and-effect diagrams | Control charts | Answer option a. | Answer option a. An inspection is examination of a work product to determine if it conforms to documented standards. The results of inspections generally include measurements and may be conducted at any level. Answer option a. An inspection is examination of a work product to determine if it conforms to documented standards. The results of inspections generally include measurements and may be conducted at any level.
Exam 3 | #158. Fiona is new in Agile. She has worked with many teams in the past, and in recent years she specialized in system development and system upgrade projects. She understands that more and more projects are being managed and implemented using Scrum. She would like to get more information on how teams work in Agile in comparison with the Traditional projects. What is one of the main differences between teams in predictive approach projects and Agile projects? |  | A strong sense of team spirit in Agile teams. | Reduced conflicts in Agile teams. | Better product management in Agile teams. | Self-organizing teams in Agile teams | Answer option d. | Answer option d. Agile teams are supposed to be self-organizing and empowered when compared to non-Agile teams. Answer option d. Agile teams are supposed to be self-organizing and empowered when compared to non-Agile teams.
Exam 3 | #159. The project team identified a high-priority opportunity, and the project manager wants to make sure that this opportunity is realized. Which of the following risk strategies should he plan? |  | Escalate | Share | Exploit | Accept | Answer option c. | Answer option c. “Exploit” The exploit strategy is used for high-priority opportunities where the organization wants to ensure that the opportunity is realized. Answer option c. “Exploit” The exploit strategy is used for high-priority opportunities where the organization wants to ensure that the opportunity is realized.
Exam 3 | #160. Alex is a project manager managing a small internal project. To reduce misunderstandings and miscommunication, which interpersonal and team skills should he use? |  | Active listening | Political awareness | Networking | Cultural awareness | Answer option a. | Answer option a. “Active listening” is used to reduce misunderstandings and other miscommunication. Answer option a. “Active listening” is used to reduce misunderstandings and other miscommunication.
Exam 3 | #161. Agile teams practice frequent verification and validation during and at the end of each iteration through demonstrations (demo’s) and Sprint Reviews. Which one of the following is NOT a benefit of this method? |  | It reduces risks to project costs as mistakes are found early in development prior to additional tasks being done on a faulty foundation. | It is easier to manage since there are multiple feedback loops. | It gives the development team something to do towards the end of each sprint. | It enables the team to identify mistakes and align with customer expectations early. | Answer option c. | Answer option c. Busy work does not add value to the project, and it is not a benefit of Agile. Answer option c. Busy work does not add value to the project, and it is not a benefit of Agile.
Exam 3 | #162. Monitor Risks is a key process for all project managers. Which of the following is not one of the process tools and techniques used in this process? |  | Data Analysis | Audits | Meetings | Questionnaires | Answer option d. | Answer option d. The best answer is “Questionnaires” (Answer option d.) it is not commonly used for the process, because questionnaires are used for data gathering. “Data Analysis” (Answer option a.), “Audits” (Answer option b.) and “Meetings” (Answer option c.) are tools and techniques that can be used within the process. Answer option d. The best answer is “Questionnaires” (Answer option d.) it is not commonly used for the process, because questionnaires are used for data gathering. “Data Analysis” (Answer option a.), “Audits” (Answer option b.) and “Meetings” (Answer option c.) are tools and techniques that can be used within the process.
Exam 3 | #163. You have been managing Agile projects for the past few years. Based on your experience, personal interaction and interpersonal skills are the most important in building your team. You know that coaching and mentoring is one of the best ways to improve your team member’s skills. As a team coach, what should be your attitude toward your team members’ individual goals and personal motivations? |  | Ignore them; personal issues have no bearing on reaching the project goals. | Cultivate them; personal goals are an important reason why people want to be successful at work. | Understand them; try to align personal motivations with the team’s progress toward the project goals. | Leverage them; use individual goals to persuade team members to raise their performance level | Answer option c . | Answer option c. Agile leaders try to align their team members’ individual goals and personal motivations with the team’s progress toward the project goals. To do this, it is necessary to learn to understand those motivators first. It isn’t effective leadership to ignore, dwell on, or use personal goals to manipulate people. The goal of agile leaders is to look at alignment. Answer option c . Agile leaders try to align their team members’ individual goals and personal motivations with the team’s progress toward the project goals. To do this, it is necessary to learn to understand those motivators first. It isn’t effective leadership to ignore, dwell on, or use personal goals to manipulate people. The goal of agile leaders is to look at alignment.
Exam 3 | #164. A project team is still at the “storming” stage. Which of the following characteristics would the team exhibit? |  | Members are interdependent and work through issues smoothly | Members are not open to differing ideas and perspectives | Members see each other as trustworthy but don’t know how to work together | Members tend to be independent | Answer option b. | Answer option b. “Members are not open to differing ideas and perspectives”. During this phase, the team begins to address the project work, technical decisions, and the project management approach. If team members are not collaborative or open to differing ideas and perspectives, the environment can become counterproductive. Answer option b. “Members are not open to differing ideas and perspectives”. During this phase, the team begins to address the project work, technical decisions, and the project management approach. If team members are not collaborative or open to differing ideas and perspectives, the environment can become counterproductive.
Exam 3 | #165. A bridge has fallen in Brampton, Ontario, Canada. Brian, a Project Manager, works for a civil construction company, and he needs to evaluate the complexity of restoring the bridge. What is the most likely scenario according to the Stacey Complexity Model? |  | The solution is straightforward because the bridge can be taken down and rebuilt. | The solution is complicated because some of the bridge is recovered, and the rest is to be rebuilt. | The solution is complex because even though some parts can be recovered and others rebuilt, the project will be costly and take a long time. | Both b and c | Answer option d . | Answer option d. As uncertainty increases, the probability of change, waste, and rework increases. So, the project will cost more, and it will take more time. Therefore, agile approaches are best suited for complicated and complex projects. Answer option d . As uncertainty increases, the probability of change, waste, and rework increases. So, the project will cost more, and it will take more time. Therefore, agile approaches are best suited for complicated and complex projects.
Exam 3 | #166. Dan is working on the closure of a server migration project. He is investigating the project risks to confirm that there are no open risks left. Which document can assist him in achieving this objective? |  | Risk register | Risk report | Change log | Issue log | Answer option b. | Answer option b. “Risk report” The risk report provides information on the risk status and is used to check that there are no open risks at the end of the project. Answer option b. “Risk report” The risk report provides information on the risk status and is used to check that there are no open risks at the end of the project.
Exam 3 | #167. To tackle the communication issues within the project team, Dan arranged a focus group to discuss these issues. Which communication method is he using? |  | Interactive communication | Push communication | Pull communication | Public communication | Answer option a. | Answer option a. “Interactive communication” focus groups are two directions communication. Between two or more parties performing a multidirectional exchange of information in real-time. Interactive communication is done through meetings, phone calls, instant messaging, some forms of social media, and videoconferencing. Answer option a. “Interactive communication” focus groups are two directions communication. Between two or more parties performing a multidirectional exchange of information in real-time. Interactive communication is done through meetings, phone calls, instant messaging, some forms of social media, and videoconferencing.
Exam 3 | #168. After performing the stakeholders’ assessment, the project team classified the stakeholders based on the assessments of their power, urgency, and legitimacy. Which data representation technique did the project manager use? |  | Power/interest grid | Impact/influence grid | Stakeholder cube | Salience model | Answer option d. | Answer option d. “Salience model”. Describes classes of stakeholders based on assessments of their power (level of authority or ability to influence the outcomes of the project), urgency (need for immediate attention, either time-constrained or relating to the stakeholders’ high stake in the outcome), and legitimacy (their involvement is appropriate). Answer option d. “Salience model”. Describes classes of stakeholders based on assessments of their power (level of authority or ability to influence the outcomes of the project), urgency (need for immediate attention, either time-constrained or relating to the stakeholders’ high stake in the outcome), and legitimacy (their involvement is appropriate).
Exam 3 | #169. Gary is in the middle of translating the quality management plan into executable quality activities that incorporate the organization’s quality policies into the project. Which process is Gary performing? |  | Plan Quality | Control Quality | Manage Quality | Develop Quality | Answer option c. | Answer option c. “Manage Quality”. The process of translating the quality management plan into executable quality activities that incorporate the organization’s quality policies into the project. Answer option c. “Manage Quality”. The process of translating the quality management plan into executable quality activities that incorporate the organization’s quality policies into the project.
Exam 3 | #170. You are an expert developer in an organization that is new to Scrum and Agile. The development team, which was recently formed is fresh and well-motivated yet lacks experience in Agile applications and is more trained in the traditional approach. Kyle, who is a team member, reaches you and asks, who will be the project estimator, setting up points for stories on the current Sprint. How would you answer Kyle: |  | The Product Owner is going to be the estimator since he owns the Product Backlog and is well aware of the log items and what needs to be delivered first. | The Scrum Master is going to be the estimator since he articulates the process and ensures the team is not exceeding the time on each Sprint. | The entire team including the Product Owner and the Scrum Master will be responsible to contribute in providing estimates. | You, the experienced developer, will be in charge to provide estimates until other team members get enough experience to be in charge of this role. | Answer option c. | Answer option c. Per Scrum framework, the entire team during the Sprint planning meeting is responsible for providing estimates. The objective of estimation is to consider User Stories for the Sprint by priority and ensure delivery within the set period. Answer option c. Per Scrum framework, the entire team during the Sprint planning meeting is responsible for providing estimates. The objective of estimation is to consider User Stories for the Sprint by priority and ensure delivery within the set period.
Exam 3 | #171. While initiating an internal project, the project sponsor plans for a review at the end of each phase to decide whether to continue to the next phase or not. This is a reference to _____ . |  | Milestones | Phase gates | Closure points | All of the above | Answer option b. | Answer option b. “Phase gates”. A review at the end of a phase in which a decision is made to continue to the next phase, to continue with modification, or to end a project or program. Answer option b. “Phase gates”. A review at the end of a phase in which a decision is made to continue to the next phase, to continue with modification, or to end a project or program.
Exam 3 | #172. You are a Scrum master working on an agile project. While working on the third Sprint the project stakeholders ask you to report why you removed some of the features from the Sprint and what are the expected features to be seen in the next Sprint? What will you do as a Scrum Master to handle this situation? |  | Request the project stakeholders to get information from the product owner | Request the project stakeholders to check the project breakdown chart | Request the project stakeholders to get information from the team members | Submit the requested report in the next iteration review meeting | Answer option a. | Answer option a. In agile roles and responsibilities are clearly defined. It is the product owner who is responsible to deal with the customers, stakeholders, and the teams for deciding and defining the product direction. The product owner has deep knowledge in the business area and is responsible to take business-related decisions. Answer option a. In agile roles and responsibilities are clearly defined. It is the product owner who is responsible to deal with the customers, stakeholders, and the teams for deciding and defining the product direction. The product owner has deep knowledge in the business area and is responsible to take business-related decisions.
Exam 3 | #173. A project manager is managing a software development project. Early on, the project manager asks the Scrum Master how many story points can be completed in each iteration (Sprint). What should the Scrum Master do? |  | Ask the customer to provide the velocity. | Establish average velocity based on input from the Development team. | Run multiple sprints before determining the team velocity. | Hold a working session with the Project Manager to determine velocity. | Answer option b. | Answer option b. Activity durations can be calculated by using average velocity to determine how many story points can be completed in each iteration (Sprint). When teams provide their own measurements, teams are better able to assess, estimate, and deliver their work. Answer option b. Activity durations can be calculated by using average velocity to determine how many story points can be completed in each iteration (Sprint). When teams provide their own measurements, teams are better able to assess, estimate, and deliver their work.
Exam 3 | #174. A contract is a mutually binding agreement that obligates the seller to provide the specified products, services, or results; obligates the buyer to compensate the seller; and represents a legal relationship that is subject to remedy in the courts. The major components in an agreement document will vary. Which of the following is an example of a component in an agreement ? |  | Performance Reporting | Stakeholder engagement assessment | Project Size | Prompt Lists | Answer option a. | Answer option a. “Performance Reporting”. The procurement SOW should be clear, complete, and concise. It includes a description of any collateral services required, such as performance reporting or post-project operational support for the procured item. Answer option a. “Performance Reporting”. The procurement SOW should be clear, complete, and concise. It includes a description of any collateral services required, such as performance reporting or post-project operational support for the procured item.
Exam 3 | #175. Develop Project Charter is the process of developing a document that formally authorizes the existence of a project and provides the project manager the authority to apply organizational resources to project activities. Which of the following is not a data-gathering tool Darren can use while he is developing his project charter? |  | Brainstorming | Focus Groups | Interviews | Assumption Log | Answer option d. | Answer option d. “Brainstorming” (Answer option a.), “Focus Groups” (Answer option b.) and “Interviews” (Answer option c.) are all data-gathering tools he can use while developing the project charter. The best answer is “Assumption Log” (option d) is a project document. Answer option d. “Brainstorming” (Answer option a.), “Focus Groups” (Answer option b.) and “Interviews” (Answer option c.) are all data-gathering tools he can use while developing the project charter . The best answer is “Assumption Log” (option d) is a project document.
Exam 3 | #176. A product owner repeatedly complains, saying that a function developed by the development team does NOT seem to align with the original design. What will help to solve this issue? |  | Ask the product owner to explain his point of view clearly to the team. | Ask the quality assurance team to identify any mismatches in functionality compared to the initial design. | Ask the development team to rewrite the function so that it matches with the project scope. | Update the product owner twice per week on product development. | Answer option d. | The product owner has already explained the requirements in the original design. The solution here is to keep the product owner updated on development so that the team can adjust their work if it goes out of scope.
Exam 3 | #177. Monitor Risks is the process of monitoring the implementation of the agreed-upon risk response plans, tracking identified risks, identifying, and analyzing new risks, and evaluating risk process effectiveness throughout the project. Suzan knows that she needs to update the process inputs on a regular basis. Which of the following is one of the process inputs? |  | Lessons Learned Register | Stakeholders Register | Bid Documents Register | Assignment Register | Answer option a. | Answer option a. “Lessons Learned Register”. Monitor Risks process inputs are: Answer option a. “Lessons Learned Register”. Monitor Risks process inputs are: 1 Project management plan 1 Project management plan Risk management plan Risk management plan Risk management plan 2 Project documents 2 Project documents Issue log Lessons learned register Risk register Risk report Issue log Issue log Lessons learned register Lessons learned register Risk register Risk register Risk report Risk report 3 Work performance data 3 Work performance data 4 Work performance reports 4 Work performance reports
Exam 3 | #178. Richard, an Agile Project Manager, is scheduled to deliver a new accounting software for a reputable audit company Veritech. However, he just found out that there has been an update in the General Accepted Accounting Principles. What can Richard do to deliver the accounting software and comply with the new requirements? |  | Evaluate if the work can be delivered in small increments. | Develop a predictive schedule for the software to be developed. | Divide the project into phases. | Outsource the work that cannot be done by the team. | Answer option a. | By delivering small increments of work, the team will be able to understand the customer requirements better. Also, the team will be able to make corrections faster by working closely with the customer.
Exam 3 | #179. An Agile team is working on a software development project. The team planned to complete 25 story points in an iteration (Sprint), but only completed 17. What is the current status of the project? |  | Project is behind schedule. | Project is ahead of schedule. | Project is on schedule. | This cannot be determined with the given information. | Answer option a. | Answer option a. 17 of 20 story points were completed, so the project is behind schedule. Answer option a. 17 of 20 story points were completed, so the project is behind schedule.
Exam 3 | #180. Project managers directly interact with a lot of internal and external stakeholders in assessing the compliance goals, integrating stakeholder’s requirements, understanding project risks, and coordinating resources. What skills are the most important for the Project Manager to effectively engage with the stakeholders and manage their expectations? |  | Risk management skills—the PM needs to understand stakeholder risk and develop successful mitigation strategies. | Project integration skills—the PM needs to be able to integrate many complex aspects of the project. | Communication skills—the PM needs to be able to engage with and manage the expectations of stakeholders. | Resource management skills—the PM needs to coordinate with stakeholders to obtain needed resources. | Answer option c. | Answer option c. Communications and interpersonal skills are some of the key skills for stakeholder engagement success. Answer option c. Communications and interpersonal skills are some of the key skills for stakeholder engagement success.

## exam4
Exam Name | Question | quesimgsrc | Answer1 | Answer2 | Answer3 | Answer4 | Correct-Answer | Explanation | answerimgsrc
Exam 4 | #1. You are about to start a new project and need to hire some human resources to complete a highly specialized deliverable for the project. During this process, you should begin by: |  | Reviewing the vision, mission, and objectives of the organization. | Conducting an interview with all prospective team members. | Reviewing the Project management plan. | Finding out about all enterprise environmental factors and organizational process assets pertaining to the process. | Answer option a. | Answer option a. The PM should start the process with a review of the vision, mission, and objectives of the organization. Then the PM should check the EEF/OPA, then review the PM Plans and finally interview prospective members. Answer option a. The PM should start the process with a review of the vision, mission, and objectives of the organization. Then the PM should check the EEF/OPA, then review the PM Plans and finally interview prospective members .
Exam 4 | #2. While monitoring communications, Alex is seeking information about the team members, stakeholders, and the work involved in the communication process. Alex can look into the _____ . |  | Resource management plan | Communications management plan | Stakeholder engagement plan | Project communications | Answer option b. | Answer option b. “Communications management plan” Answer option b. “Communications management plan”
Exam 4 | #3. You are planning to tailor (adjust) an organizational project management approach to fit your project. However, your organization has established an approach based on a certain proven standard for your industry. Which of the following statements is correct? |  | You should tailor the approach in consultation with your team and other PMs. | You will be able to tailor the project management approach for your project only if tailoring guidelines are provided by your organization. | You should consider another approach if the organizational approach does not support your project. | Tailoring cannot be done, as the organizational approach should be used across the board for all projects within the organization. | Answer option b. | Answer option b. You will be able to tailor the project management approach for your project only if tailoring guidelines are provided by your organization. If there are no tailoring guidelines, the Project Manager needs to consult with the management. Answer option b. You will be able to tailor the project management approach for your project only if tailoring guidelines are provided by your organization. If there are no tailoring guidelines, the Project Manager needs to consult with the management.
Exam 4 | #4. Alex asked his project team to rank the project stakeholders. He expects to see the stakeholder who is most interested and who has the highest influence at the top of the list. _____ must be used for this purpose. |  | Power/interest grid | Directions of influence | Stakeholder engagement assessment matrix | Prioritization | Answer option d. | Answer option d. “Prioritization” Answer option d. “Prioritization”
Exam 4 | #5. A project manager is working on a large IT project. She needs to ensure that all data security requirements are covered during the project’s execution phase. Each of the databases created during different project phases will have a specific data security policy to comply with governmental data security laws. How should the project manager plan to meet these requirements? |  | Plan a database development specification, then regularly check to ensure the work aligns with the specification. | Arrange for review of the data security status on a quarterly basis, and recommend remedial steps if noncompliance is found. | Tell the database developer to submit documentation of data security items and the steps they need to take to correct items that do NOT meet specifications. | Add a quality assurance specialist resource to the project team, who will be responsible for monitoring the data security quality of the project. | Answer option b . | Answer option b. Clearly documenting how key requirements have been met is a great way to ensure quality and identify any gaps that need to be addressed. Answer option b . Clearly documenting how key requirements have been met is a great way to ensure quality and identify any gaps that need to be addressed.
Exam 4 | #6. A project team collected sensitive client data during the early stages of a project to help develop the project management plan. The team is now working on deliverables for the project when the compliance manager discovers a data breach and alerts the team to a compliance issue. Which document should the project manager review first? |  | Statement of work (SOW) | Issue log | Business case | Risk register | Answer option b . | Answer option b. After a new compliance issue is raised, the issue log should be reviewed and updated, as needed, prior taking action to resolve. Answer option b . After a new compliance issue is raised, the issue log should be reviewed and updated, as needed, prior taking action to resolve.
Exam 4 | #7. Sam is leading an initiative where the focus is to ensure to deliver benefits as expected, by coordinating the activities and components of the initiative. This is an example of _____ . |  | Projects | Programs | Portfolios | Business as usual | Answer option b. | Answer option b. “Programs” Answer option b. “Programs”
Exam 4 | #8. The project manager assigned Peter to collect and record the project’s knowledge. To share and record the knowledge based on experience and insights, which technique should he use? |  | Networking | Knowledgebase | Databases | All of the above | Answer option a. | Answer option a. ”Networking” experience and insights are tacit knowledge, tacit knowledge is shared through interactive sessions. Answer option a. ”Networking” experience and insights are tacit knowledge, tacit knowledge is shared through interactive sessions.
Exam 4 | #9. Juan is replacing Bridget as a project manager since Bridget will go on maternity leave next week. He received the project WBS. but he has difficulties understanding all the WBS components. Which of the following is the best option that Juan can refer to? |  | Project Charter | WBS Dictionary | Previous Project Manager | Requirements Documentation | Answer option b. | Answer option b. ”WBS Dictionary” contains the description of the work packages. Answer option b. ”WBS Dictionary” contains the description of the work packages.
Exam 4 | #10. One of the project team members has problems with writing reports, which caused communication issues in the project. As a project manager, what would you advise him to do? |  | Use active listening | Use the 5Cs of written communications | Use cultural awareness | Use political awareness | Answer option b. | Answer option b. “Use the 5Cs of written communications” Misunderstandings can be reduced but not eliminated through using the 5Cs of written communications in composing a traditional (non-social media) written or spoken message. Answer option b. “Use the 5Cs of written communications” Misunderstandings can be reduced but not eliminated through using the 5Cs of written communications in composing a traditional (non-social media) written or spoken message. Correct grammar and spelling. Poor use of grammar or inaccurate spelling can be distracting and can also introduce distortions in the message, diminishing credibility. Concise expression and elimination of excess words. A concise, well-crafted message reduces the opportunities for misunderstanding the intent of the message. Clear purpose and expression directed to the needs of the reader. Ensure that the needs and interests of the audience are factored into the message. Coherent logical flow of ideas. A coherent logical flow of ideas and using “markers” such as introduction and summaries of the ideas throughout the writing. Controlling the flow of words and ideas. Controlling the flow of words and ideas may involve graphics or just summaries. Correct grammar and spelling. Poor use of grammar or inaccurate spelling can be distracting and can also introduce distortions in the message, diminishing credibility. Correct grammar and spelling. Poor use of grammar or inaccurate spelling can be distracting and can also introduce distortions in the message, diminishing credibility. Concise expression and elimination of excess words. A concise, well-crafted message reduces the opportunities for misunderstanding the intent of the message. Concise expression and elimination of excess words. A concise, well-crafted message reduces the opportunities for misunderstanding the intent of the message. Clear purpose and expression directed to the needs of the reader. Ensure that the needs and interests of the audience are factored into the message. Clear purpose and expression directed to the needs of the reader. Ensure that the needs and interests of the audience are factored into the message. Coherent logical flow of ideas. A coherent logical flow of ideas and using “markers” such as introduction and summaries of the ideas throughout the writing. Coherent logical flow of ideas. A coherent logical flow of ideas and using “markers” such as introduction and summaries of the ideas throughout the writing. Controlling the flow of words and ideas. Controlling the flow of words and ideas may involve graphics or just summaries. Controlling the flow of words and ideas. Controlling the flow of words and ideas may involve graphics or just summaries.
Exam 4 | #11. Alex is leading an initiative with an organizational scope that changes with the strategic objectives of the organization. This is an example of _____ . |  | Projects | Programs | Portfolios | Business as usual | Answer option c. | Answer option c. ”Portfolios” Answer option c. ”Portfolios”
Exam 4 | #12. During a focus group meeting, Melissa has identified a high-priority threat with a high probability of occurrence and a high negative impact. Her objective is to eliminate the threat and reduce its probability of occurrence to zero. This is an example of _____ . |  | Workaround | Risk Transfer | Risk Avoidance | Risk Acceptance | Answer option c. | Answer option c. “Risk Avoidance” A risk response strategy whereby the project team acts to eliminate the threat or protect the project from its impact. Answer option c. “Risk Avoidance” A risk response strategy whereby the project team acts to eliminate the threat or protect the project from its impact.
Exam 4 | #13. You are the Agile project manager working on a hybrid project. You and the Product Owner are working through the product requirements for the Sponsor. The Sponsor raises concerns that the Development team does not fully understand the requirements. What will you do next? |  | Ask the team to create a high-level prototype of the requirements to review with all related stakeholders. | Provide the Scope Statement to the sponsor for clarification. | Hold a Backlog Grooming session with the Product Owner to clarify requirements. | Show the team the project schedule to align on features and delivery dates. | Answer option a. | Answer option a. Agile uses visual prototypes (i.e. storyboards, wireframes, models, etc.) to get a quick understanding of the requirements from all impacted stakeholders. Answer option a. Agile uses visual prototypes (i.e. storyboards, wireframes, models, etc.) to get a quick understanding of the requirements from all impacted stakeholders.
Exam 4 | #14. Allan is a project manager who is in the process of closing the project. Allan can use ____ as an input for this process. |  | Final report | Final project audits | Operational and support documents | Project or phase closure documents | Answer option b. | Answer option b. “Final project audits” is one of the organizational process assets that can influence the Close Project or Phase process. The other documents listed as answers are outputs of the closing process. Answer option b. “Final project audits” is one of the organizational process assets that can influence the Close Project or Phase process. The other documents listed as answers are outputs of the closing process.
Exam 4 | #15. Steve is a project manager who is currently defining how to estimate, acquire, manage, and use human and physical resources. What is he currently involved in? |  | Plan Resource Management | Estimate Activity Resources | Acquire Resources | Control Resources | Answer option a. | Answer option a. “Plan Resource Management”. The process of defining how to estimate, acquire, manage, and utilize physical and team resources. Answer option a. “Plan Resource Management”. The process of defining how to estimate, acquire, manage, and utilize physical and team resources.
Exam 4 | #16. You are an expert developer in an organization that is new to Scrum and Agile. In analyzing a new application feature, each team member is providing estimates, but the estimates provided are significantly different from each other; the story points are not consistent. As a way to provide more realistic estimates and to speed up the estimation process, you recommend a certain technique to optimize the process. From the selections below, which one would it be: |  | Planning Poker | The Fibonacci Sequence | Shirt Sizing | Bottom-up estimating | Answer option a . | Answer option a. Per Scrum framework, planning poker (a.k.a Scrum Poker) is a consensus-based technique used to estimate efforts needed to complete a story. It works by handing each member an index card with a range of Fibonacci sequence numbers. After presenting user stories to the team, each member holds the numbers they have chosen for their estimate. With the size of stories being represented by Fibonacci numbers and with some back-and-forth, consensus is quickly achieved on each story’s estimate. Answer option a . Per Scrum framework, planning poker (a.k.a Scrum Poker) is a consensus-based technique used to estimate efforts needed to complete a story. It works by handing each member an index card with a range of Fibonacci sequence numbers. After presenting user stories to the team, each member holds the numbers they have chosen for their estimate. With the size of stories being represented by Fibonacci numbers and with some back-and-forth, consensus is quickly achieved on each story’s estimate.
Exam 4 | #17. While conducting the procurements, which document can be used to check the technical requirements the seller needs to satisfy? |  | Communications management plan | Project communications | Procurement management plan | Requirements documentation | Answer option d. | Answer option d. “Requirements documentation”. Requirements documentation may include: Answer option d. “Requirements documentation”. Requirements documentation may include: Technical requirements that the seller is required to satisfy, and Requirements with contractual and legal implications that may include health, safety, security, performance, environmental, insurance, intellectual property rights, equal employment opportunity, licenses, permits, and other non-technical requirements. Technical requirements that the seller is required to satisfy, and Technical requirements that the seller is required to satisfy, and Requirements with contractual and legal implications that may include health, safety, security, performance, environmental, insurance, intellectual property rights, equal employment opportunity, licenses, permits, and other non-technical requirements. Requirements with contractual and legal implications that may include health, safety, security, performance, environmental, insurance, intellectual property rights, equal employment opportunity, licenses, permits, and other non-technical requirements.
Exam 4 | #18. On an Agile project, demonstrations are conducted towards the end of the iteration (Sprint). What is the benefit of a demonstration (Demo)? |  | Allows the team to get together in a meeting. | Saves the Development Team time from creating a real product. | Allows the Product Owner to discuss and agree on requirements with their stakeholders. | Allows users to create new features with the help of the Development Team. | Answer option c . | Answer option c. Demonstrations are a key item to gather feedback from stakeholders and allow them to agree on requirements and product features before costs are incurred on actual development. Answer option c . Demonstrations are a key item to gather feedback from stakeholders and allow them to agree on requirements and product features before costs are incurred on actual development.
Exam 4 | #19. You are procuring the services of a company to migrate your company’s software systems to the cloud. Your company has no expertise in this area—in fact, you don’t even understand what some of these terms mean, so you add a clause to the contract that the seller must be responsible for managing all major risks of the project. Which of the following is correct about contract risk management? |  | This is sensible because your company doesn’t have the expertise to understand the major risks or how to manage them. | The seller can't manage all major risks, as they don’t have control over all of them. | Risk management can't be included in a contract. | Risk management will be included in the contract. | Answer option b . | Answer option b. The seller can’t manage all major risks, as they don’t have control over all of them, particularly when your company’s software systems are being transferred to the cloud. No contractor is capable of managing all the possible major risks on a project. Answer option b . The seller can’t manage all major risks, as they don’t have control over all of them, particularly when your company’s software systems are being transferred to the cloud. No contractor is capable of managing all the possible major risks on a project.
Exam 4 | #20. Dev is working in the PMO of Water-X Company. PMO Manager Brittany asked Dev to review and report the performance of the “Water Brick” project. While Dev is reviewing the performance of the project, he found the following performance data; AC=$150K, EV=$140K, PV=$130K. Dev should report that ______ . |  | Project is behind schedule | Project is ahead of schedule | Project is on schedule | Cannot say | Answer option b. | Answer option b. “Project is ahead of schedule” to assess the project schedule performance you can either calculate SV or SPI, SV= EV-PV=$140K-$130K=$10K. Positive SV means the project is ahead of schedule. Answer option b. “Project is ahead of schedule” to assess the project schedule performance you can either calculate SV or SPI, SV= EV-PV=$140K-$130K=$10K. Positive SV means the project is ahead of schedule.
Exam 4 | #21. _____ provide(s) control actions for assessing the effectiveness of response plans, symptoms and warning signs of risk, residual and secondary risks, and a watch list of low-priority risks. |  | Issue log | Risk reviews | Risk register | Risk report | Answer option c. | Answer option c. “Risk register” Answer option c. “Risk register”
Exam 4 | #22. Thomas is developing a set of logically related project activities that culminates in completion of one or more deliverables. What is he developing? |  | Project phase | Phase gate | Project life cycle | Project Management Process Group | Answer option a. | Answer option a. ”Project phase”. A project life cycle is a series of phases that a project passes through from its start to its completion. A project phase is a collection of logically related project activities that culminates in completion of one or more deliverables. Answer option a. ”Project phase”. A project life cycle is a series of phases that a project passes through from its start to its completion. A project phase is a collection of logically related project activities that culminates in completion of one or more deliverables.
Exam 4 | #23. Allan is developing options, selecting strategies, and agreeing on actions to address overall project risk exposure, as well as to treat individual project risks. Which process is he performing? |  | Plan Risk Management | Identify Risks | Perform Qualitative Risk Analysis | Plan Risk Responses | Answer option d. | Answer option d. “Plan Risk Responses”. Plan Risk Responses is the process of developing options, selecting strategies, and agreeing on actions to address overall project risk exposure as well as to treat individual project risks. Answer option d. “Plan Risk Responses”. Plan Risk Responses is the process of developing options, selecting strategies, and agreeing on actions to address overall project risk exposure as well as to treat individual project risks.
Exam 4 | #24. George is attending a Scrum Master training and is reviewing the information prior to taking the course final exam. As he is studying the Sprint Retrospective material, he is NOT likely to read the following: |  | The Sprint Retrospective is an opportunity for the Scrum Team to inspect itself and create a plan for improvements for the next Sprint. | It occurs before the Sprint Review. | It is time-boxed to no more than 3-hours. | The goal of the Sprint Retrospective is to inspect-and-adapt the process. | Answer option b. | Answer option b. The Sprint Retrospective occurs AFTER the Sprint Review. Without the feedback stakeholders provide in the Sprint Review, the team will not have all the necessary information for them to inspect itself and create improvement plans. Answer option b. The Sprint Retrospective occurs AFTER the Sprint Review. Without the feedback stakeholders provide in the Sprint Review, the team will not have all the necessary information for them to inspect itself and create improvement plans.
Exam 4 | #25. During the team meeting, two team members had a conflict about how to perform a certain activity. The project manager assigned a third expert team member to investigate the best way to perform the activity. Which conflict resolution technique did he use? |  | Accommodate | Compromise | Force | Collaborate | Answer option d. | Answer option d. “Collaborate”. Collaborate/problem-solve. Incorporating multiple viewpoints and insights from differing perspectives; requires a cooperative attitude and open dialogue that typically leads to consensus and commitment. This approach can result in a win-win situation. Answer option d. “Collaborate”. Collaborate/problem-solve. Incorporating multiple viewpoints and insights from differing perspectives; requires a cooperative attitude and open dialogue that typically leads to consensus and commitment. This approach can result in a win-win situation.
Exam 4 | #26. In business, it is important to measure success. In order to do this, you need to know what success looks like. Which of the following is the best statement related to success? |  | Project success is measured by product and project quality, timeliness, budget compliance, and the degree of customer satisfaction. | Portfolio success is measured in terms of the aggregate investment performance and benefit realization of the portfolio. | Program success is measured by the program’s ability to deliver its intended benefits to an organization and by the program’s efficiency and effectiveness in delivering those benefits. | All the above are correct. | Answer option d. | Answer option d. All the above are correct. All statements define the success in projects, programs, and portfolio management. Answer option d. All the above are correct. All statements define the success in projects, programs, and portfolio management.
Exam 4 | #27. The Project Manager has assigned you the task to identify the availability of each specific resource on the project. He has directed you to make a document that shows the resource availability across the working days, shifts, start and end of normal business hours, weekends, and public holidays occurring throughout the phases of the project. Which document contains all this detail? |  | Organizational Breakdown Structure | Work Breakdown Structure | Resource Requirements | Resource Calendar | Answer option d . | Answer option d. “Resource Calendar” identiﬁes the working days, shifts, start and end of normal business hours, weekends, and public holidays when each speciﬁc resource is available. Answer option d . “Resource Calendar” identiﬁes the working days, shifts, start and end of normal business hours, weekends, and public holidays when each speciﬁc resource is available.
Exam 4 | #28. You were managing a project to update the HR system for your company. The old system is functional, apart from a few bottlenecks. All is going great, but due to some family issues, you need to step away from the project for a few weeks. Your company is concerned as they don’t believe they can find a replacement at such short notice. Your manager allows you to phone a friend, a retired project manager, and he agrees to cover for you. Upon your return, you are pleased to find he has solved all the problems with the bottlenecks, as he has a lot of expertise in this area. When the system goes live, you are informed that you will get a bonus for the successful completion of the project. What action should you take? |  | Say nothing. Your company will not find out who actually did the majority of the work. | Say nothing, give the bonus to your friend, and accept the promotion. That way everyone wins. | Tell your manager that it was your friend who sorted out the payroll. You may lose the bonus and promotion. | Refuse the bonus and promotion because you don’t deserve them. | Answer option c. | Answer option c. “Tell your manager that it was your friend who sorted out the payroll. You may lose the bonus and promotion.”. Avoid taking credit for the achievements of others. Answer option c. “Tell your manager that it was your friend who sorted out the payroll. You may lose the bonus and promotion.”. Avoid taking credit for the achievements of others .
Exam 4 | #29. Michael intends to procure a part of his project work with well-defined requirements with no expected significant changes to the scope. Which contract type best matches Michael’s project? |  | Fixed-Price Contracts | Cost-Reimbursable Contracts | Time and Material Contracts | None of the Above | Answer option a. | Answer option a. “Fixed-Price Contracts”. This category of contracts involves setting a fixed total price for a defined product, service, or result to be provided. These contracts should be used when the requirements are well defined and no significant changes to the scope are expected. Answer option a. “Fixed-Price Contracts”. This category of contracts involves setting a fixed total price for a defined product, service, or result to be provided. These contracts should be used when the requirements are well defined and no significant changes to the scope are expected.
Exam 4 | #30. A project manager implements the Risk Responses. He wants to review the listed roles and responsibilities of the project team members and other stakeholders for risk management. Which input provides this information? |  | Risk register | Risk management plan | Risk report | Issue log | Answer option b. | Answer option b. “Risk management plan” Answer option b. “Risk management plan”
Exam 4 | #31. Billy is working on estimating team resources and the type and quantities of material, equipment, and supplies necessary to perform project work. What is he involved in? |  | Plan Resource Management | Estimate Activity Resources | Manage team | Control Resources | Answer option b. | Answer option b. “Estimate Activity Resources” is the process of estimating team resources and the type and quantities of material, equipment, and supplies necessary to perform project work. Answer option b. “Estimate Activity Resources” is t he process of estimating team resources and the type and quantities of material, equipment, and supplies necessary to perform project work.
Exam 4 | #32. A project manager is performing the control costs process. He intends to measure the amount of budget deficit or surplus at the current point in time. Which measure is he using? |  | Schedule performance index (SPI) | Cost performance index (CPI) | Cost variance (CV) | Schedule variance (SV) | Answer option c. | Answer option c. “Cost variance (CV)” is the amount of budget deficit or surplus at a given point in time expressed as the difference between the earned value and the actual cost. Answer option c. “Cost variance (CV)” is t he amount of budget deficit or surplus at a given point in time expressed as the difference between the earned value and the actual cost.
Exam 4 | #33. Alex is a project manager managing an internal project. He is currently directing and managing the project. Which of the following organizational process assets can influence his project work? |  | Organizational structure | Management practices | Organizational standard policies | Stakeholder risk thresholds | Answer option c. | Answer option c. The best answer is “Organizational standard policies” (Answer option c.) is the only OPA.” Organizational structure” (Answer option a), “Management practices” (Answer option b.) and “Stakeholder risk thresholds” (Answer option d.) are all enterprise environmental factors. Answer option c. The best answer is “ Organizational standard policies ” (Answer option c.) is the only OPA.” Organizational structure ” (Answer option a), “ Management practices ” (Answer option b.) and “ Stakeholder risk thresholds ” (Answer option d.) are all enterprise environmental factors.
Exam 4 | #34. Alex is comparing the processes used to create quality measurements and validates actual measurements to determine their level of correctness. Which document (input) is he reviewing? |  | Quality metrics | Quality control measurements | Quality reports | Quality management plan | Answer option b. | Answer option b. ”Quality control measurements”. Quality control measurements are used to analyze and evaluate the quality of the processes and deliverables of the project against the standards of the performing organization, or the requirements specified. Answer option b. ”Quality control measurements”. Quality control measurements are used to analyze and evaluate the quality of the processes and deliverables of the project against the standards of the performing organization, or the requirements specified.
Exam 4 | #35. While performing the validate scope process, Alex is wondering which document to review to find out how to obtain formal acceptance of the completed project deliverables. Which document should he review? |  | Requirements management plan | Scope baseline | Scope management plan | Requirements documentation | Answer option c. | Answer option c. Scope Management Plan. The scope management plan is a component of the project management plan that describes how the scope will be defined, developed, monitored, controlled, and validated. The components of a scope management plan include: Process for preparing a project scope statement; Process that enables the creation of the WBS from the detailed project scope statement; Process that establishes how the scope baseline will be approved and maintained; and Process that specifies how formal acceptance of the completed project deliverables will be obtained. Answer option c. Scope Management Plan. The scope management plan is a component of the project management plan that describes how the scope will be defined, developed, monitored, controlled, and validated. The components of a scope management plan include: Process for preparing a project scope statement; Process that enables the creation of the WBS from the detailed project scope statement; Process that establishes how the scope baseline will be approved and maintained; and Process that specifies how formal acceptance of the completed project deliverables will be obtained.
Exam 4 | #36. _____ measure, compare, and analyze quality, resource, schedule, and cost performance against the agreement. This includes identifying work packages that are ahead or behind schedule, over or under budget, or have resource or quality issues. |  | Performance reviews | Earned value analysis | Inspection | Audits | Answer option a. | Answer option a. ”Performance reviews” Answer option a. ”Performance reviews”
Exam 4 | #37. _____ is a structured review of the work being performed by the contractor. This may involve a simple review of the deliverables or an actual physical review of the work itself. |  | Performance reviews | Earned value analysis | Inspection | Audits | Answer option c. | Answer option c. “Inspection”. Inspection is a structured review of the work being performed by the contractor. This may involve a simple review of the deliverables or an actual physical review of the work itself. On a construction/engineering/infrastructure project, inspections involve walkthroughs of the site by both the buyer and the contractor to ensure a mutual understanding of the work in progress. Answer option c. “Inspection”. I nspection is a structured review of the work being performed by the contractor. This may involve a simple review of the deliverables or an actual physical review of the work itself. On a construction/engineering/infrastructure project, inspections involve walkthroughs of the site by both the buyer and the contractor to ensure a mutual understanding of the work in progress.
Exam 4 | #38. During the project execution, the team reported an issue related to a previously identified risk. The risk owner did not implement the agreed response for that risk, therefore it became an issue. The project manager needs to check who is the owner of this particular risk. He should look into ____ . |  | Risk register | Risk management plan | Risk report | Issue log | Answer option a. | Answer option a. “Risk register” Answer a. Risk register contains information about risk owners. Answer option a. “Risk register” Answer a. Risk register contains information about risk owners.
Exam 4 | #39. Which of the below is a correct clarifying principle within the Agile manifesto? |  | Find risk early and upfront to create a valuable product. | Working software is the primary measure of progress. | Constant recurring meetings guarantee work for the Development team. | Morale and team happiness is measured by monthly surveys. | Answer option b . | Answer option b. Working software is the primary measure of progress. Answer option b . Working software is the primary measure of progress.
Exam 4 | #40. You are managing a project to create a new online newsletter. The security manager alerts you that a quality control check shows that the website is insecure, as it is open to malicious viruses and spam-ware. You ask the security manager to raise a change request, as this needs to be fixed urgently. What should the change request have in addition to everything else? |  | Approval from the security manager | Supporting detail | To be copied to all programmers | A User Acceptance Test review | Answer option b. | Answer option b. “Supporting detail” is needed to review and process the change request. Once the change request is processed, it will be approved by the CCB (Security manager might be a part of the CCB) Answer option b. “Supporting detail” is needed to review and process the change request. Once the change request is processed, it will be approved by the CCB (Security manager might be a part of the CCB)
Exam 4 | #41. In a project designed to deliver a new internal website. The IT Manager who will be supporting the website after it is delivered comes to the Scrum Master, Moshami, to discuss the project objectives. After seeing the Product Backlog in Moshami’s office, many of his team has come to him to discuss the project. He requests that Moshami not share the Product Backlog so freely as it is creating distractions amongst his team. Which of the following BEST represents what Moshami should share with the IT Manager? |  | One of the core pillars of Scrum Theory is Adaptation and, thus, adjustments should be made to the processes and artifacts to minimize deviation. | One of the core pillars of Scrum Theory is Inspection and, thus, The Scrum process promotes frequent Inspection of the Artifacts and progress to identify undesirable variances. | One of the core pillars of Scrum Theory is Transparency and, thus, the significant aspects of the process must be visible to those responsible for the outcome. | All of the above. | Answer option c. | Answer option c. The three pillars of Scrum Theory are Adaptation, Inspection and Transparency. While A, B and C answers are pillars of Scrum Theory, the most appropriate response for Moshami to choose at this point is C. The IT Manager’s concerns are related to sharing knowledge about the project scope and deliverables, and because of this, Moshami’s answer would best be related to the Transparency pillar. Answer option c. The three pillars of Scrum Theory are Adaptation, Inspection and Transparency. While A, B and C answers are pillars of Scrum Theory, the most appropriate response for Moshami to choose at this point is C. The IT Manager’s concerns are related to sharing knowledge about the project scope and deliverables, and because of this, Moshami’s answer would best be related to the Transparency pillar.
Exam 4 | #42. A project manager is aiming to improve teamwork, enhance interpersonal skills and competencies, motivate employees, reduce attrition, and improve overall project performance. Which process is he performing? |  | Acquire Resources | Develop Team | Manage Team | Control Resources | Answer option b. | Answer option b. “Develop Team”. The develop project team process is the second HR process in the executing process group and the intent is to improve the competencies of team members through training and enhance the interactions of team members through team-building. There are a number of techniques used to develop the project team such as: improving interpersonal or “soft” skills, Training team members to enhance their competencies, Team-building activities to progress them through the stages of team development (forming, storming, norming, and performing) Answer option b. “Develop Team”. The develop project team process is the second HR process in the executing process group and the intent is to improve the competencies of team members through training and enhance the interactions of team members through team-building. There are a number of techniques used to develop the project team such as: improving interpersonal or “soft” skills, Training team members to enhance their competencies, Team-building activities to progress them through the stages of team development (forming, storming, norming, and performing)
Exam 4 | #43. Ruby is a project manager managing a hybrid enterprise software development project. The product development will be done using agile principles. During the daily standup, a team member reports an issue shared by a stakeholder. What should Ruby do next? |  | Add the issue to the parking lot, and then conduct another meeting after the standup to address the issue. | Add this risk to the risk register, to discuss during the standup. | Advise the Development Team to immediately address the issue in the meeting. | Review the Stakeholder Register. | Answer option a . | Answer option a. Standups are for identifying problems but not for solutioning them. The project manager should add the issue to a parking lot, and then create another meeting to solve the issue there. Answer option a . Standups are for identifying problems but not for solutioning them. The project manager should add the issue to a parking lot, and then create another meeting to solve the issue there.
Exam 4 | #44. According to the Tuckman ladder model, the project team moved to the performing stage. Before moving to performing, what stage was the team in? |  | Performing | Forming | Norming | Storming | Answer option c. | Answer option c. “Norming” Answer option c. “Norming”
Exam 4 | #45. Kareem is handing over a project to his colleague Vanessa. Vanessa wanted to see the projected expenditures and anticipated liabilities in the project. Kareem should provide Vanessa _____ . |  | Project funding requirements | Financing | Funding limits reconciliation | Project budget | Answer option a. | Answer option a. “Project funding requirements” include total funding requirements and periodic funding requirements (e.g., quarterly, annually) are derived from the cost baseline. The cost baseline will include projected expenditures plus anticipated liabilities. Answer option a. “Project funding requirements” include t otal funding requirements and periodic funding requirements (e.g., quarterly, annually) are derived from the cost baseline. The cost baseline will include projected expenditures plus anticipated liabilities.
Exam 4 | #46. While performing monitoring and communication activities, Paul is seeking to obtain records of conflicts during stakeholder engagement in order to determine how to resolve them. Which document would have those details? |  | Issue log | Lessons learned register | Project communications | Communications management plan | Answer option a. | Answer option a. “Issue log” contains all of the project’s issues including communications and stakeholders’ conflicts Answer option a. “Issue log” contains all of the project’s issues including communications and stakeholders’ conflicts
Exam 4 | #47. Alan is a Project Manager managing a software development project for Company InfoTech using a hybrid approach. The product development will be done using Agile principles. The project has high risk and a high degree of uncertainty. The sponsor has requested Alan develop a cost estimate in a short period of time. How can he accomplish this? |  | Ask the customer to provide a cost estimate. | Involve the sponsor in daily standup meetings. | Define the statement of work and ensure cost estimates are performed. | Provide a lightweight cost estimate, which can be adjusted as changes arise. | Answer option d . | Answer option d. According to the PMBOK, projects with high levels of uncertainty or those where the scope is not yet fully defined may not benefit from detailed cost calculations due to frequent changes. Instead, lightweight estimation tactics can be used to generate fast, high-level forecasts of project labor costs, which can be easily adjusted as changes arise. Agile methods make it difficult to provide a fully refined, definite estimate, and lightweight estimates can enable the Agile project to be sanctioned and approved. Answer option d . According to the PMBOK, projects with high levels of uncertainty or those where the scope is not yet fully defined may not benefit from detailed cost calculations due to frequent changes. Instead, lightweight estimation tactics can be used to generate fast, high-level forecasts of project labor costs, which can be easily adjusted as changes arise. Agile methods make it difficult to provide a fully refined, definite estimate, and lightweight estimates can enable the Agile project to be sanctioned and approved.
Exam 4 | #48. Recently you have been assigned as a Product Owner to the Scrum team that you had never worked with before. One week later one of your company's managers approaches you and asks to confirm that the project will be finished by the 6th of March. He says that he reviewed estimates given by your team and needs a commitment to guarantee it will be finished to the exact date. What is the most likely problem in this situation? |  | The Manager should approach a Scrum Master, not you. | Many managers confuse estimates with commitments. As soon as a team comes up with an estimate, they are forced to commit to it. | You have been assigned to the project recently therefore you are not able to make any commitments yet. | Agile teams don't make any commitments to specific dates. | Answer option b. | Answer option b. An estimate is a probability, and a commitment cannot be made to a probability. Commitments are made to dates. Normally the date that a team is asked (or told) to commit to is one to which they would assign a less than 100% probability. Answer option b. An estimate is a probability, and a commitment cannot be made to a probability. Commitments are made to dates. Normally the date that a team is asked (or told) to commit to is one to which they would assign a less than 100% probability .
Exam 4 | #49. A project manager is controlling the project resources. He wants to review the external resources to the organization and the procedures to follow when there is an unplanned need for resources. Which document should he review? |  | Physical resource assignments | Agreements | Resource breakdown structure | Resource requirements | Answer option b. | Answer option b. “Agreements” Answer option b. “Agreements”
Exam 4 | #50. You are an expert developer in an organization that is new to Scrum and Agile. The Product Owner approaches you and the team and requests a Sprint planning session to talk about the new deliverable, which is a set of software suites including a collection of several applications. He mentions using affinity estimation as a technique to estimate user stories in points. Stephen is a new developer in Agile reaches you and asks; what exactly is affinity estimation? How would you answer: |  | Affinity estimation is a group activity estimation technique in which the entire teams work in parallel to estimate user stories. | Affinity estimation is an estimation technique where the team outsources estimating to specialty-based experts. | Affinity estimation is an estimation technique that is derived from a parametric approach where published figures can be used as the basis for the estimate. | Affinity estimation is a group activity estimation technique in which the user stories are grouped together in size order. | Answer option d. | Answer option d. Per Scrum framework, affinity estimation is a popular alternative to Planning Poker. It is used when the deliverable is large enough that the stories are grouped together on a size basis. Stories that look very small are put in one category, while very large stories are placed in another. This approach is often led by a Scrum Master and performed by the entire team. Answer option d. Per Scrum framework, affinity estimation is a popular alternative to Planning Poker. It is used when the deliverable is large enough that the stories are grouped together on a size basis. Stories that look very small are put in one category, while very large stories are placed in another. This approach is often led by a Scrum Master and performed by the entire team.
Exam 4 | #51. Wilson is invited to meet the project sponsor and portfolio manager. They asked him for a fifteen minutes standup meeting where he can share all the significant points and events of the project. Which document should Wilson present? |  | Activity List | Milestone List | Requirements List | Measurements List | Answer option b. | Answer option b. “Milestone List”. Since there is a limited time to present information about the project, the milestone list will give a high-level overview of the project. Answer option b. “Milestone List”. Since there is a limited time to present information about the project, the milestone list will give a high-level overview of the project.
Exam 4 | #52. During the project execution, the project team needs to reassess and classify the project stakeholders according to their level of authority and level of concern about the project’s outcomes. Which data representation technique should they use? |  | Power/interest grid | Power/influence grid | Stakeholder cube | Salience model | Answer option a. | Answer option a. “Power/interest grid” is the right answer. Power/interest grid, power/influence grid, or impact/influence grid are techniques that group stakeholders according to their level of authority (power), level of concern about the project’s outcomes (interest), ability to influence the outcomes of the project (influence), or ability to cause changes to the project’s planning or execution. These classification models are useful for small projects or for projects with simple relationships between stakeholders and the project, or within the stakeholder community itself. Answer option a. “Power/interest grid” is the right answer. Power/interest grid, power/influence grid, or impact/influence grid are techniques that group stakeholders according to their level of authority (power), level of concern about the project’s outcomes (interest), ability to influence the outcomes of the project (influence), or ability to cause changes to the project’s planning or execution. These classification models are useful for small projects or for projects with simple relationships between stakeholders and the project, or within the stakeholder community itself.
Exam 4 | #53. A project manager is working on ensuring the timely and appropriate collection, creation, distribution, storage, retrieval, management, monitoring, and the ultimate disposition of the project information. Which process is he performing? |  | Plan Knowledge | Manage Knowledge | Manage Communications | Monitor Communications | Answer option c. | Answer option c. “Manage Communications” is the process of ensuring timely and appropriate collection, creation, distribution, storage, retrieval, management, monitoring, and the ultimate disposition of project information. The key benefit of this process is that it enables efficient and effective information flow between the project team and the stakeholders. This process is performed throughout the project. Answer option c. “Manage Communications” i s the process of ensuring timely and appropriate collection, creation, distribution, storage, retrieval, management, monitoring, and the ultimate disposition of project information. The key benefit of this process is that it enables efficient and effective information flow between the project team and the stakeholders. This process is performed throughout the project.
Exam 4 | #54. _____ is used to assess the various scenarios guided by the output from the Project Risk Management processes to bring the schedule model into alignment with the project management plan and approved baseline. |  | Performance reviews | What-if scenario analysis | Trend analysis | Variance analysis | Answer option b. | Answer option b. “What-if scenario analysis” Answer option b. “What-if scenario analysis”
Exam 4 | #55. Lee has been hired to serve as Scrum Master with a team that is new to agile methodology. In his conversations with his new team and other stakeholders, which of the following is a misconception he is likely to hear? |  | Agile methodology is unstructured. | Agile methodology is an excuse for poor design and reduced quality. | Agile methodology is designed to do more with fewer resources. | All of the above. | Answer option d. | Answer option d. There are many misconceptions about agile methodology, including A, B, and C. Answer option d. There are many misconceptions about agile methodology, including A, B, and C.
Exam 4 | #56. _____ specifies the acceptable range used to determine realistic activity duration estimates and may include a specified amount for contingencies. |  | Units of measure | Control thresholds | Level of accuracy | Level of precision | Answer option c. | Answer option c. “Level of accuracy”. The level of accuracy specifies the acceptable range used in determining realistic activity duration estimates and may include an amount for contingencies. Answer option c. “Level of accuracy”. The level of accuracy specifies the acceptable range used in determining realistic activity duration estimates and may include an amount for contingencies.
Exam 4 | #57. You’re working on a support project for a software product with high levels of technical debt. Due to this issue, your organization has stopped adding any new features or fixing defects. As a result, the product becomes less and less appealing to current and potential customers. How can you resolve this issue going forward? |  | Establish refactoring, agile modeling, pervasive testing, and automated Code Quality Analysis. | Create a definition of ready for the testing stories. Consider splitting testing stories to use smaller stories. | Help sponsors and stakeholders craft a product vision. Consider building a product roadmap using specification by example. | As a servant leader help clear these obstacles for the team through escalation | Answer option a. | Answer option a. Technical debt (degraded code quality) is solved through refactoring, agile modeling, pervasive testing, automated code quality analysis, the definition of done. Answer option a. Technical debt (degraded code quality) is solved through refactoring, agile modeling, pervasive testing, automated code quality analysis, the definition of done.
Exam 4 | #58. Adam is prioritizing the individual project risks for further analysis or action by assessing their probability of occurrence and impact as well as other characteristics. Which process is he performing? |  | Perform Qualitative Risk Analysis | Perform Quantitative Risk Analysis | Plan Risk Management | Identify Risks | Answer option a. | Answer option a. “Perform Qualitative Risk Analysis”. The process of prioritizing individual project risks for further analysis or action by assessing their probability of occurrence and impact as well as other characteristics. Answer option a. “Perform Qualitative Risk Analysis”. The process of prioritizing individual project risks for further analysis or action by assessing their probability of occurrence and impact as well as other characteristics.
Exam 4 | #59. The Scrum Master on an Agile team has asked the team to do a self-assessment on their performance. What is the purpose of this self-assessment? |  | Determine project cost of resources. | Determine team performance and effectiveness on delivering product increments. | Determine the number of stories the team should have completed in the previous iteration (Sprint). | Review the performance of a second Agile team in the company. | Answer option b . | Answer option b. The self-assessment is used to gauge team members’ performance, determine team strengths, and areas to improve. Answer option b . The self-assessment is used to gauge team members’ performance, determine team strengths, and areas to improve.
Exam 4 | #60. The Project Manager has just handed over the final requirements documentation to you. He has asked you to make a document for him which creates a grid that links each of these requirements to Business needs and objectives. He has also asked you to link each requirement to Project scope and WBS deliverables. Which of the following documents fulfills his demand? |  | Project Scope Statement | Scope Baseline | Requirements Traceability Matrix | Scope Management Plan | Answer option c. | Answer option c. “Requirements Traceability Matrix”. The requirements traceability matrix is a grid that links product requirements from their origin to the deliverables that satisfy them. The implementation of a requirements traceability matrix helps ensure that each requirement adds business value by linking it to the business and project objectives. Answer option c. “Requirements Traceability Matrix”. The requirements traceability matrix is a grid that links product requirements from their origin to the deliverables that satisfy them. The implementation of a requirements traceability matrix helps ensure that each requirement adds business value by linking it to the business and project objectives.
Exam 4 | #61. April has been contracted to work with ABC Corporation as their PMO introduces agile methodologies to their project managers. The PMO has been in operation for many years and has project managers who have exclusively used predictive methodologies. In the initial meeting with the project manager, April discovers there are two project managers who are resistant to the change to agile. A chief complaint is that the team does not have the bandwidth for additional processes and the addition of a new methodology will create too great of a burden on the project managers. In April’s conversations with the team, she may explain all of the following, EXCEPT: |  | These new methods attempt a useful compromise between no process and too much process, providing just enough process to gain a reasonable payoff. | Agile teams often have fewer processes to follow because they build projects around motivated individuals who are given the environment and support they need to get the job done. | As the team will shift from prioritizing planning to responding to change, there will likely be fewer stringent processes to follow. | The leadership team has decided that agile practices best align with the company’s strategic goals, so the project management team is expected to learn and practice the new methods. | Answer option d. | A, B, and C are all principles and benefits of agile project management. While D is a true statement, it is not helpful in April’s attempt to gain the team’s buy-in as she introduces agile project management.
Exam 4 | #62. A project manager is working on influencing team behavior, managing conflict, and resolving its issues. Which process is he performing? |  | Acquire Resources | Develop Team | Manage Team | Control Resources | Answer option c. | Answer option c. “Manage Team”. The process of tracking team member performance, providing feedback, resolving issues, and managing team changes to optimize project performance. Answer option c. “Manage Team”. The process of tracking team member performance, providing feedback, resolving issues, and managing team changes to optimize project performance.
Exam 4 | #63. Jack just completed his project’s 1st phase gate review. Which of the following actions is a possible result? |  | Repeat the phase | Remain in the phase | End the project | All of the above | Answer option d. | Answer option d. ”All of the above” all provided actions are possible results. Answer option d. ”All of the above” all provided actions are possible results.
Exam 4 | #64. You are working on an Agile team charter. The team charter should NOT answer this question: |  | Why are we doing this project? | Who benefits from executing this project? | How many defects are allowed on the project? | What is the “definition of done” for the project? | Answer option c . | Answer option c. The charter covers why the project is being done, who benefits, and the “definition of done”. Additionally, it covers how the team will work together in order to create the product. Answer option c . The charter covers why the project is being done, who benefits, and the “definition of done”. Additionally, it covers how the team will work together in order to create the product.
Exam 4 | #65. Company XYZ assigned Alex to lead the merger of the company with Sid Corporation. Accordingly, Alex will be responsible for the execution of all activities related to legalization, organizational restructuring, and financial merger. How would you classify Alex’s work? |  | Business as usual | Project | Operational work | Portfolio | Answer option b. | Answer option b. “Project” the work carried out by Alex is temporary, unique drives change, and brings value to the organization. Answer option b. “Project” the work carried out by Alex is temporary, unique drives change, and brings value to the organization.
Exam 4 | #66. Steve is making a numerical analysis of the combined effect of identified individual project risks and other sources of uncertainty on the overall project objectives. Which process is he performing? |  | Plan Risk Management | Identify Risks | Perform Qualitative Risk Analysis | Perform Quantitative Risk Analysis | Answer option d. | Answer option d. “Perform Quantitative Risk Analysis”. Perform Quantitative Risk Analysis is the process of numerically analyzing the combined effect of identified individual project risks and other sources of uncertainty on overall project objectives. Answer option d. “Perform Quantitative Risk Analysis”. Perform Quantitative Risk Analysis is the process of numerically analyzing the combined effect of identified individual project risks and other sources of uncertainty on overall project objectives.
Exam 4 | #67. You are classifying your project stakeholders using a data-representation technique where you place the stakeholders based on their directions of influence. You are about to classify the project team. How would you classify them? |  | Upward | Downward | Outward | Sideward | Answer option b. | Answer option b. “Downward” the project team includes those who will perform the project work and they are classified as downward stakeholders. Answer option b. “Downward” the project team includes those who will perform the project work and they are classified as downward stakeholders.
Exam 4 | #68. While managing the Stakeholder engagement process, the project manager is reviewing the process for submitting, evaluating, and implementing changes to the project. Which document or plan contains these details? |  | Change management plan | Change log | Configuration management plan | Issue log | Answer option a. | Answer option a. “Change management plan” Answer option a. “Change management plan”
Exam 4 | #69. Iterative scheduling with backlog and on-demand scheduling are examples of _____ . |  | Emerging practices for project schedule management | Considerations for tailoring Project Schedule Management | Organizational process assets | Enterprise environmental factors | Answer option a. | Answer option a. “Emerging practices for project schedule management”. They are used in agile projects. Answer option a. “Emerging practices for project schedule management”. They are used in agile projects.
Exam 4 | #70. While performing the close project process, the project manager wants to review the lessons learned, final project audits, and project evaluations. Which input should he review? |  | Project management plan | Project documents | Organizational process assets | Business documents | Answer option b. | “Project documents” include Risk register and risk report which contains project risks and their status, change log which contains changes and their status and Issue log which contains Issues and their status.
Exam 4 | #71. A Project Manager is working on a hybrid project utilizing both Waterfall and Agile project management processes. At the end of the fourth iteration (Sprint), the sponsor informs the Project Manager that the project is not performing as planned. What should the Project Manager do to improve performance for the next iterations? |  | Discuss solutions with senior management. | Conduct a Backlog grooming session with the Product Owner. | Host an ad-hoc standup session with the Scrum Master to discuss the issue. | Hold a Retrospective session with all stakeholders. | Answer option d. | Answer option d. Retrospectives are held to correct processes and determine areas of improvement if needed. Answer option d. Retrospectives are held to correct processes and determine areas of improvement if needed.
Exam 4 | #72. John is reviewing the guidance on providing project team member rewards, feedback, additional training, and disciplinary actions because of team performance assessments. Which input can provide these details? |  | Resource calendars | Resource assignments | Resource management plan | Team charter | Answer option c. | Answer option c. “Resource management plan”. The resource management plan provides information about team member rewards, feedback, additional training, and disciplinary actions as a result of team performance assessments and other forms of project team management. The resource management plan may also include the team performance assessment criteria. Answer option c. “Resource management plan”. T he resource management plan provides information about team member rewards, feedback, additional training, and disciplinary actions as a result of team performance assessments and other forms of project team management. The resource management plan may also include the team performance assessment criteria.
Exam 4 | #73. _____ defines whether waterfall, iterative, adaptive, agile, or a hybrid development approach to be used. |  | The quality management plan | The project life cycle description | The development approach | The enterprise environmental factors | Answer option c. | Answer option c. ”The development approach” Describes the product, service, or results in a development approach, such as predictive, iterative, agile, or a hybrid model. Answer option c. ”The development approach” Describes the product, service, or results in a development approach, such as predictive, iterative, agile, or a hybrid model.
Exam 4 | #74. Chris just completed monitoring the status of the project, product scope, and managing changes to the scope baseline. Which process should he perform next? |  | Define Scope | Create WBS | Validate Scope | Control Scope | Answer option c. | Answer option c. “Validate Scope”. The question refers that he just completed the “control scope” process. Validate scope usually is the following process. Answer option c. “Validate Scope”. The question refers that he just completed the “control scope” process. Validate scope usually is the following process.
Exam 4 | #75. Build & Cheers Company assigned Keith to manage a construction project. This is Keith’s first project in this field. While he tries to sequence the project activities, he seeks advice on the preferred logic of some project activities from a colleague. Which of the following is Keith trying to identify? |  | Internal Dependencies | External Dependencies | Mandatory Dependencies | Discretionary Dependencies | Answer option d. | Answer option d. “Discretionary Dependencies”. Discretionary dependencies are sometimes referred to as preferred logic, preferential logic, or soft logic. Discretionary dependencies are established based on knowledge of best practices within a particular application area or some unusual aspect of the project where a specific sequence is desired, even though there may be other acceptable sequences. Answer option d. “Discretionary Dependencies”. Discretionary dependencies are sometimes referred to as preferred logic, preferential logic, or soft logic. Discretionary dependencies are established based on knowledge of best practices within a particular application area or some unusual aspect of the project where a specific sequence is desired, even though there may be other acceptable sequences.
Exam 4 | #76. The customer is asking for a visual display that presents up-to-date, sufficiently detailed information about the incremental nature of the product, how it will be built and delivered over time, along with the crucial factors that affect each release. What is the best information radiator to use here? |  | Product backlog | Product roadmap | Release plan | Sprint backlog | Answer option b. | Answer option b. “Product roadmap”. A product roadmap to show the anticipated sequence of deliverables over time. The product owner re-plans the roadmap based on what the team produces. Answer option b. “Product roadmap”. A product roadmap to show the anticipated sequence of deliverables over time. The product owner re-plans the roadmap based on what the team produces.
Exam 4 | #77. _____ is the effect of uncertainty on the project as a whole, arising from all sources of uncertainty including individual risks, representing the exposure of stakeholders to the implications of variations in project outcome, both positive and negative. |  | Individual project risk | Overall project risk | Variability risk | Ambiguity risk | Answer option b. | Answer option b. “Overall project risk”. Overall project risk is the effect of uncertainty on the project as a whole, arising from all sources of uncertainty including individual risks, representing the exposure of stakeholders to the implications of variations in project outcome, both positive and negative. Project Risk Management processes address both levels of risk in projects. Answer option b. “Overall project risk”. Overall project risk is the effect of uncertainty on the project as a whole, arising from all sources of uncertainty including individual risks, representing the exposure of stakeholders to the implications of variations in project outcome, both positive and negative. Project Risk Management processes address both levels of risk in projects.
Exam 4 | #78. You are reviewing a document that details the method of measuring project benefits including post-project benefits. Benefit owners are also listed. What document are we talking about? |  | Project charter | Business case | Cost management plan | Benefits management plan | Answer option d. | “Benefits management plan” is the only document that describes each benefit with the owner of that benefit, targets timelines for each benefit, and how the benefits will be measured.
Exam 4 | #79. Sam is reviewing the raw observations and measurements identified during direct and manage project work. This is an example of _____ . |  | Work performance data | Work performance information | Work performance reports | Project management information system | Answer option a. | Answer option a. “Work performance data” is the raw observations and measurements identified during activities being performed to carry out the project work. Answer option a. “Work performance data” is t he raw observations and measurements identified during activities being performed to carry out the project work.
Exam 4 | #80. The project manager is reviewing the quality control chart with the project team and the product owner. The response times have been going down but are still above the upper control limit. What does that mean? |  | The project standards are in line with the plan. | The project's quality is above expectations. | The project's burndown rate is above normal. | The project's quality is outside the quality standards set for the project. | Answer option d. | Answer option d. “The project’s quality is outside the quality standards set for the project”. The only correct answer is that the project quality is outside the quality standards set for the project. The response times are above the upper control limit which means the data is out of control. Answer option d. “The project’s quality is outside the quality standards set for the project”. The only correct answer is that the project quality is outside the quality standards set for the project. The response times are above the upper control limit which means the data is out of control.
Exam 4 | #81. Jack is developing his project team, and he needs to identify the team and members’ roles and responsibilities. Which input should he review? |  | Team charter | Resource management plan | Project team assignments | Resource calendars | Answer option c. | Answer option c. “Project team assignments”. Documentation of team assignments records the team members and their roles and responsibilities for the project. Documentation can include a project team directory and names inserted into the project management plan, such as the project organization charts and schedules. Answer option c. “Project team assignments”. Documentation of team assignments records the team members and their roles and responsibilities for the project. Documentation can include a project team directory and names inserted into the project management plan, such as the project organization charts and schedules.
Exam 4 | #82. Kelly is working as a project manager in a non-profit organization’s project. She is working on improving competencies, team members’ interactions, and the overall team environment to enhance project performance. Which process is she performing? |  | Acquire Resources | Develop Team | Manage Team | Control Resources | Answer option b. | Answer option b. ”Develop Team” is the process of improving competencies, team member interaction, and the overall team environment to enhance project performance. Answer option b. ”Develop Team” is t he process of improving competencies, team member interaction, and the overall team environment to enhance project performance.
Exam 4 | #83. _____ is the expected total cost of completing all work expressed as the sum of the actual cost to date and the estimate to complete. |  | EAC | ETC | VAC | BAC | Answer option a. | Answer option a. “EAC”. Estimate at Completion (EAC) is the expected total cost of completing all work expressed as the sum of the actual cost to date and the estimate to complete. Answer option a. “EAC”. Estimate at Completion (EAC) is the expected total cost of completing all work expressed as the sum of the actual cost to date and the estimate to complete.
Exam 4 | #84. Larry is assigned to a new application development project for food delivery company Foody. The customer has described the minimum requirements needed quickly to serve their market. Some features may add more comfort to the app, but the customer's priority is to be able to deliver and collect money. What approach should Larry use if he is asked to have an initial version that functions in the next four weeks? |  | Kanban approach. | Incremental approach. | Predictive approach. | Iterative approach. | Answer option b . | Answer option b. Incremental life cycles optimize work to deliver customer value more frequently. The deviations from the project can be managed more precisely because the value is provided sooner. Answer option b . Incremental life cycles optimize work to deliver customer value more frequently. The deviations from the project can be managed more precisely because the value is provided sooner.
Exam 4 | #85. The seller might be referred to by a variety of names during the contract life cycle. Which of the following is one of these names? |  | Bidder | Contracted Supplier | Selected Source | All of the Above | Answer option d. | Answer option d. The best answer is “All of the Above” (Answer option d). A seller can be referred to as “Bidder” (Answer option a), “Contracted Supplier” (Answer option b), and “Selected Source” (Answer option c). Answer option d. The best answer is “All of the Above” (Answer option d). A seller can be referred to as “Bidder” (Answer option a), “Contracted Supplier” (Answer option b), and “Selected Source” (Answer option c).
Exam 4 | #86. The Project Manager of a current project has been urgently called back to the performing organization’s PMO in Washington DC. The Senior Portfolio Manager told him that he is very concerned about Mr. Smith, who is a very important stakeholder. Mr. Smith has a lot of experience and strong influence; therefore he might have a potential impact on the current performance of the project. Unfortunately, Mr. Smith is not showing any support or any positive input at the moment, which is urgently needed. What is the current stakeholder engagement level of Mr. Smith? |  | Unaware | Neutral | Resistant | Supportive | Answer option c. | “Resistant”. Because such a stakeholder is aware of the project and potential impacts but resistant to any changes that may occur as a result of the work or outcomes of the project. These stakeholders will be unsupportive of the work or outcomes of the project.
Exam 4 | #87. What is the best approach in handling the Product Backlog if you are working on the project with multiple Scrum teams? |  | Create component-specific Product Backlogs for each team | Employ one Product Backlog, extend the grooming horizon, and consider providing team-specific views into the backlog | Prefer component teams to feature teams and empty separate Product Backlog for each team | There is no best approach, it is possible to go with any of them. | Answer option b. | Answer option b. Whenever you work on a large Scrum project, ensure that there is one product backlog that contains the work necessary to bring the product to life. Avoid team- or component-specific backlogs that translate product requirements into subsystem or component requirements. Employ one product backlog, extend the grooming horizon, and consider providing team-specific views into the backlog. Answer option b. Whenever you work on a large Scrum project, ensure that there is one product backlog that contains the work necessary to bring the product to life. Avoid team- or component-specific backlogs that translate product requirements into subsystem or component requirements. Employ one product backlog, extend the grooming horizon, and consider providing team-specific views into the backlog.
Exam 4 | #88. A project manager is working with a customer who repeatedly submits requests for new requirements for an existing software product. The project manager has already provided the completed scope definition for the product's next version release to stakeholders. Which step is appropriate for the project manager to take next? |  | Hold a meeting with the product manager to request that the number of new requests be reduced. | Define project boundaries immediately with the sponsor. | Organize a meeting with the stakeholders to set expectations. | Analyze the scope management plan to see how changes in scope are handled. | Answer option d . | Answer option d. Analyze the scope management plan to see how changes in scope are handled. Answer option d . Analyze the scope management plan to see how changes in scope are handled.
Exam 4 | #89. Your team is working on creating a blood pressure monitoring app that will be a breakthrough in the market. The customer is closely involved in the overall project and is present daily during the project. Yesterday, your team completed their last iteration, but the demo hasn't been approved yet. What does this mean? |  | The team still needs to do refactoring and user testing. | In trying out the product increment, the customer thought of another feature to add to the backlog. | In the demo, the customer decided that the team hadn't completed one of the items selected from the backlog for that iteration. | The product increment hasn't passed QA testing. | Answer option c. | Answer option c. An iteration is “approved” when the product owner is satisfied that the product increment meets the iteration goal–the items selected from the backlog for that iteration. Although the customer might also think of another feature to add to the backlog, they would still approve the iteration if the work that was done meets the goal that was set. The other two options (missing refactoring, QA testing) are activities that should have been done during the iteration. If the team hasn’t done them, that might be a reason for not approving the iteration. But they aren’t the best answer to this scenario, since we don’t have enough information to pick one of them. Answer option c. An iteration is “approved” when the product owner is satisfied that the product increment meets the iteration goal–the items selected from the backlog for that iteration. Although the customer might also think of another feature to add to the backlog, they would still approve the iteration if the work that was done meets the goal that was set. The other two options (missing refactoring, QA testing) are activities that should have been done during the iteration. If the team hasn’t done them, that might be a reason for not approving the iteration. But they aren’t the best answer to this scenario, since we don’t have enough information to pick one of them.
Exam 4 | #90. A project manager is working on a project where he needs to produce the deliverable through a series of iterations that successively add functionality within a predetermined period. Which project lifecycle should he use for this project? |  | Predictive | Iterative | Incremental | Hybrid | Answer option c. | Answer option c. “Incremental”. Incremental Life Cycle is an adaptive project life cycle where the deliverable is produced through a series of iterations that successively add functionality within a predetermined time frame. The deliverable contains the necessary and sufficient capability to be considered complete only after the final iteration. Answer option c. “Incremental”. Incremental Life Cycle is an adaptive project life cycle where the deliverable is produced through a series of iterations that successively add functionality within a predetermined time frame. The deliverable contains the necessary and sufficient capability to be considered complete only after the final iteration.
Exam 4 | #91. _____ describes how to conduct communications between buyers and sellers. |  | Communications management plan | Project communications | Procurement management plan | Requirements documentation | Answer option a. | Answer option a. “Communications management plan” describes how to conduct communications with all project stakeholders. Answer option a. “Communications management plan” describes how to conduct communications with all project stakeholders.
Exam 4 | #92. The project manager is managing the engagement with the Stakeholders. She wants to obtain the methods, formats, and technologies used for stakeholder communication. ____ contains these details. |  | Communications management plan | Stakeholder engagement plan | Stakeholder register | Both A and B | Answer option a. | Answer option a. “Communications management plan”. The communications management plan describes the methods, formats, and technologies used for stakeholder communication. Answer option a. “Communications management plan”. The communications management plan describes the methods, formats, and technologies used for stakeholder communication.
Exam 4 | #93. As a project manager, you need to use your interpersonal skills to manage different stakeholders throughout the project. The skills are also on display while planning the project communication strategy. At the same time, you need to be politically aware of the powers to be in and out of the organization. How will political awareness really help the project manager? |  | It helps the project manager to understand politics. | It helps to understand the power/interest/influence grids. | It enables the project manager to understand the powers within the organization. | It helps make stakeholder assessment. | Answer option c. | Answer option c. Political awareness is important during communications planning to understand power relationships and realize who you need to work with and at what level. Answer option c. Political awareness is important during communications planning to understand power relationships and realize who you need to work with and at what level .
Exam 4 | #94. Mark is working on finalizing open claims, updating records to reflect results, and archiving information for future use. These activities are performed during _____ . |  | Close procurement process | Close project process | Control procurement process | Conduct procurement process | Answer option b. | Answer option b. ”Close project process” Answer option b. ”Close project process”
Exam 4 | #95. A project manager observes that team members are in a low mood after demos. Feedback from stakeholders is constantly causing concern for the team. As a result, the team rushes through product demos, and the interaction between the team and stakeholders is minimal. Which action should the project manager take? |  | Meet with the stakeholders and find out the root cause of their feedback. Work with the stakeholders to rectify the problems. | Verify that the project requirements are suitable and that the team members can do the work. | Coach the team to be more confident in their work and communicate properly with the stakeholders. | Consult the stakeholder matrix and identify whether any of these people are known to be difficult. | Answer option c . | Answer option c. Leading the team means understanding how the team can work together to bring a successful project. In this case, they are NOT communicating well with project stakeholders and risk becoming demoralized. You should perceive this behavior as a risk to the project, caused by poor communication. You will already have verified the requirements and determined that your resources are adequate. Whether or not a stakeholder is difficult, your team needs to be able to perform. If you choose to work directly with the stakeholders, then you are undermining your team. Coach the team members on how to work better with the stakeholders. Answer option c . Leading the team means understanding how the team can work together to bring a successful project. In this case, they are NOT communicating well with project stakeholders and risk becoming demoralized. You should perceive this behavior as a risk to the project, caused by poor communication. You will already have verified the requirements and determined that your resources are adequate. Whether or not a stakeholder is difficult, your team needs to be able to perform. If you choose to work directly with the stakeholders, then you are undermining your team. Coach the team members on how to work better with the stakeholders.
Exam 4 | #96. Edward is working on defining how to conduct risk management activities for a project. Which process is he performing? |  | Plan Risk Management | Identify Risks | Perform Qualitative Risk Analysis | Perform Quantitative Risk Analysis | Answer option a. | Answer option a. “Plan Risk Management”. Plan Risk Management is the process of defining how to conduct risk management activities for a project. Answer option a. “Plan Risk Management”. Plan Risk Management is the process of defining how to conduct risk management activities for a project.
Exam 4 | #97. During the Communications Management planning of the project, Sam has planned a series of project review sessions for the stakeholder community to update the stakeholder engagement approach. Which emerging practice is he using? |  | Inclusion of stakeholders in project reviews | Inclusion of stakeholders in project meetings | Increased use of social computing | Multifaceted approaches to communication | Answer option a. | Answer option a. ”Inclusion of stakeholders in project reviews”. The project stakeholders can be individuals, groups, and organizations that the project team has identified as essential to the successful delivery of project objectives and organizational outcomes. An effective communication strategy requires regular and timely reviews of the stakeholder community and updates to manage changes in its membership and attitudes. Answer option a. ”Inclusion of stakeholders in project reviews”. The project stakeholders can be individuals, groups, and organizations that the project team has identified as essential to the successful delivery of project objectives and organizational outcomes. An effective communication strategy requires regular and timely reviews of the stakeholder community and updates to manage changes in its membership and attitudes.
Exam 4 | #98. Paula is taking a Scrum Master course to enhance her PMP certification she received 5 years ago. She is reviewing the materials about Sprint Artifacts. Which of the following would NOT be one of the descriptions of the Sprint Backlog in the course materials? |  | The Scrum team estimates the effort needed to complete each task in the Sprint backlog. | Each item can be completed within the 2-week Sprint. | During Sprint execution, a point person may volunteer to be primarily responsible for a task. | Sprint Backlog items are owned by the entire team. | Answer option b . | Answer option b. Each item requires a maximum of one day’s work. The other items are correct and are correct descriptions of Sprint Backlogs. Answer option b . Each item requires a maximum of one day’s work. The other items are correct and are correct descriptions of Sprint Backlogs.
Exam 4 | #99. _____ measure the completeness, compliance, and fitness for use of a product or service prior to user acceptance and final delivery. |  | Manage Quality | Audit Quality | Validate Scope | Control Quality | Answer option d. | Answer option d. “Control Quality”. Answer option d. “Control Quality”.
Exam 4 | #100. Darren is directing and managing the work on the project for a customer. Which of the following is an expected output from this process? |  | Deliverables | Accepted deliverables | Verified deliverables | None of the above | Answer option a. | Answer option a. “Deliverables”. Completed deliverables are an output of this process. These deliverables will need to be verified by the quality control team and then accepted by the customer. Answer option a. “Deliverables”. Completed deliverables are an output of this process. These deliverables will need to be verified by the quality control team and then accepted by the customer.
Exam 4 | #101. You are an expert developer in an organization that is new to Scrum and Agile. The development team, which was recently formed is fresh and well-motivated yet lacks experience in Agile applications and is more trained in the traditional approach. The team is about to get its first official Sprint Planning session and the Product Owner mentions using “Story points” as basis for estimate? Rebecca, who is a team member, asks what is a Story Point. How would you answer her: |  | Story point is a unit of measure where the stories are measured in hours. | Story point is a unit of measure where the stories are measured in Sprints. | Story point is a unit of measure that measures how much effort is required to complete user stories. | Story point is a unit of measure that defines how many developers needed per Sprint. | Answer option c . | Answer option c. Per Agile, Story points are abstract measurements that the developers use to estimate the overall effort required to complete user stories on Sprints. Those points are usually represented using the Fibonacci Sequence. Answer option c . Per Agile, Story points are abstract measurements that the developers use to estimate the overall effort required to complete user stories on Sprints. Those points are usually represented using the Fibonacci Sequence.
Exam 4 | #102. Darren is working on development of a series of stages that his project will pass through from its start to its completion. This is called as _____ . |  | Project phase | Phase gate | Project life cycle | Project Management Process Group | Answer option c. | Answer option c. “Project lifecycle” Answer option c. “Project lifecycle”
Exam 4 | #103. Anastasia is monitoring the implementation of agreed-upon risk response plans, tracking identified risks, identifying and analyzing new risks, and evaluating risk process effectiveness throughout the project. Which process is she performing? |  | Plan Risk Management | Identify Risks | Implement Risk Responses | Monitor Risks | Answer option d. | Answer option d. “Monitor Risks”. Answer option d. “Monitor Risks”.
Exam 4 | #104. Gary understands the importance of controlling the project’s scope. He used to compare the baseline to the actual results and determine the variance. The project sponsor advised him to check the performance over time. What should Gary do? |  | Trend Analysis | Reserve Analysis | Alternative Analysis | Schedule Network Analysis | Answer option a. | Answer option a. “Trend Analysis”. Trend analysis examines project performance over time to determine if performance is improving or deteriorating. Answer option a. “Trend Analysis”. Trend analysis examines project performance over time to determine if performance is improving or deteriorating.
Exam 4 | #105. An Agile team is working on a Software project. The team planned to complete 40 story points in an iteration, but only completed 32 story points. What is the current team performance? |  | The team is working at 28% of the rate planned. | The team is working at only 80% of the rate planned. | The team is working at only 20% of the rate planned. | The team is working at only 72% of the rate planned. | Answer option b . | Answer option b. Using traditional EVM metrics such as Schedule Performance Index (SPI), we can calculate this value in this Agile scenario. Using SPI = EV/PV, 40/32 = 0.80 (The team is only working 80% of the rate planned). Answer option b . Using traditional EVM metrics such as Schedule Performance Index (SPI), we can calculate this value in this Agile scenario. Using SPI = EV/PV, 40/32 = 0.80 (The team is only working 80% of the rate planned).
Exam 4 | #106. Graham is the marketing manager of a vast soft-drink corporation PopUp. The company wants to develop a new kind of drink and each element of the marketing campaign will require different timeboxes. For example, creating a budget, researching the market, developing the brand image, creating the social media campaign, etc., require multiple timeboxes depending on the product type and market positions. Which life cycle approach will be suitable in this case? |  | Flow-based Agile life cycle | Iteration-based Agile life cycle | Predictive life cycle | Incremental life cycle | Answer option a . | Answer option a. Agile is a life cycle approach that includes iterative and incremental methods to deliver value for the customer. However, in this case, because the features cannot be developed in similar timeboxes, a flow-based agile life cycle is recommended. Answer option a . Agile is a life cycle approach that includes iterative and incremental methods to deliver value for the customer. However, in this case, because the features cannot be developed in similar timeboxes, a flow-based agile life cycle is recommended.
Exam 4 | #107. _____ can establish release and iteration length, rules of performance measurement, schedule model development, and schedule model maintenance. |  | Project schedule | Schedule management plan | Schedule baseline | Agile release planning | Answer option b. | Answer option b. “Schedule management plan”. The mentioned information is part of the data that a schedule management plan can establish and contain. Answer option b. “Schedule management plan”. The mentioned information is part of the data that a schedule management plan can establish and contain.
Exam 4 | #108. You are managing a small project to upgrade your company’s communications system. The risk is very low because you are very experienced in this area. The system is delivered in advance and just needs to be installed and your team needs to perform a series of diagnostics tests. The old communications system will be working in parallel with the new one until you are sure it is safe to de-install it. You have completed a qualitative risk analysis for the project and are about to execute work, but the project management office informs you that you cannot proceed until you have also completed detailed quantitative risk analysis. Is the PMO making a reasonable request? |  | Yes, because a project manager must never question advice from the PMO. | No, because you are an experienced project manager in this area and the project is small, and so a quantitative risk analysis is not essential. | Yes, because you must always perform a quantitative risk analysis after a qualitative risk analysis. | No, because you must always perform a quantitative risk analysis before a qualitative risk analysis. | Answer option b. “ | Answer option b. “No, because you are an experienced project manager in this area and the project is small, and so a quantitative risk analysis is not essential.” It is most likely appropriate for large or complex projects, strategically important projects, projects for which it is a contractual requirement or projects in which a key stakeholder requires it. Answer option b. “ No, because you are an experienced project manager in this area and the project is small, and so a quantitative risk analysis is not essential.” It is most likely appropriate for large or complex projects, strategically important projects, projects for which it is a contractual requirement or projects in which a key stakeholder requires it.
Exam 4 | #109. Which of the following processes uses the data and results from the control quality process to reflect the overall quality status of the project to the stakeholders? |  | Validate scope | Control scope | Plan Quality | Manage Quality | Answer option d. | Answer option d. “Manage Quality” Answer option d. “Manage Quality”
Exam 4 | #110. The Project Manager requested that you estimate the duration of different activities involved in the construction phase. You are sitting with your team and you are giving them examples of how you did these activities on a previous project. Based on those examples, you are giving them estimates for each of the activities which are being discussed. Which technique did you use while estimating the duration of these activities? |  | Parametric Estimation | Analogous Estimation | Three-point Estimation | Bottom-up Estimation | Answer option b. | Answer option b. “Analogous Estimation”. Analogous estimating uses parameters from a previous, similar project, such as duration, budget, size, weight, and complexity, as the basis for estimating the same parameter or measure for future projects. Answer option b. “Analogous Estimation”. Analogous estimating uses parameters from a previous, similar project, such as duration, budget, size, weight, and complexity, as the basis for estimating the same parameter or measure for future projects.
Exam 4 | #111. You are an expert developer in an organization that is new to Scrum and Agile. The development team, which was recently formed, is still learning the basics of estimation in Scrum. There is confusion among the Scrum team about which estimation technique is based on the sum of the preceding two numbers. From the selection below, which one would this technique be: |  | The Fibonacci Sequence | Planning Poker | T-Shirt Sizing | Unit Price Estimate | Answer option a. | Answer option a. Per Scrum framework, The Fibonacci Sequence is used by Scrum teams to estimate the effort required to complete a task; it works by a series of steadily increasing numbers. The sequence follows the rule that each number is equal to the sum of the preceding two numbers. Answer option a. Per Scrum framework, The Fibonacci Sequence is used by Scrum teams to estimate the effort required to complete a task; it works by a series of steadily increasing numbers. The sequence follows the rule that each number is equal to the sum of the preceding two numbers.
Exam 4 | #112. You’ve moved to a new software company as a lead software engineer. Your new employer's highest priority is customer satisfaction through early and continuous delivery of valuable software. What else should be part of this business mindset? |  | Welcome changing requirements and working software is the primary measure of progress and building projects around motivated individuals. | Measure and optimize the flow of the work through the system using earned value management, limit scope creeps, and avoid gold plating. | Use of velocity as a performance metric to determine team productivity. | Delay changes in requirements as much as possible. The economic consequences of the change are always higher than the financial consequences of deferring the change | Answer option a. | Answer option a. The Agile Mindset is a way of thinking and behaving underpinned by the four values and twelve principles of the Agile Manifesto. Answer option a. The Agile Mindset is a way of thinking and behaving underpinned by the four values and twelve principles of the Agile Manifesto.
Exam 4 | #113. During the execution of an IT project, the project manager needed to revise the stakeholders’ positions in the organization, roles on the project, and their levels of support for the project. Which technique should he use? |  | Power/influence grid | Prioritization | Stakeholder analysis | Document analysis | Answer option c. | Answer option c. “Stakeholder analysis” Answer option c. “Stakeholder analysis”
Exam 4 | #114. _____ is used to monitor the status of contingency and management reserves for the project to determine if these reserves are still needed or if additional reserves should be requested. |  | Trend analysis | Variance analysis | Forecasting | Reserve analysis | Answer option d. | Answer option d. “Reserve analysis”. During cost control, reserve analysis is used to monitor the status of contingency and management reserves for the project to determine if these reserves are still needed or if additional reserves need to be requested. Answer option d. “Reserve analysis”. During cost control, reserve analysis is used to monitor the status of contingency and management reserves for the project to determine if these reserves are still needed or if additional reserves need to be requested.
Exam 4 | #115. Christina is in charge of managing a refurbishing project for an old building. Because the project incurs infrequent changes, and the goal is to deliver a solution that is appropriate for the expectations of the stakeholders, what approach will be best to use? |  | An iterative life cycle to help her improve the product or result through successive prototypes. | A predictive life cycle because she needs to deliver on a standard project management process. | An incremental life cycle because she needs to build on the product's functionality. | An agile life cycle because she needs to review work and deliver value frequently. | Answer option a . | Answer option a. Iterative life cycles facilitate the learning process rather than looking for speed. Therefore, the product or result will be improved by developing new prototypes based on experience. Answer option a . Iterative life cycles facilitate the learning process rather than looking for speed. Therefore, the product or result will be improved by developing new prototypes based on experience.
Exam 4 | #116. Company XYZ decided to launch a project that aims to improve employee satisfaction. What type of factors lead to the initiation of this project? |  | Meet regulatory, legal, or social requirements | Satisfy stakeholder requests or needs | Implement or change business or technological strategies | Create, improve, or fix products, processes, or services | Answer option b. | Answer option b. “Satisfy stakeholder requests or needs”. Employees and company management are stakeholders. Answer option b. “Satisfy stakeholder requests or needs”. Employees and company management are stakeholders.
Exam 4 | #117. A project manager is leading and performing the work defined in the project management plan and implementing the approved changes to achieve the project’s objectives. Which process is he performing? |  | Monitor and Control Project Work | Direct and Manage Project Work | Perform Integrated Change Control | Validate Scope | Answer option b. | Answer option b. “Direct and Manage Project Work”. Direct and Manage Project Work is the process of leading and performing the work defined in the project management plan and implementing approved changes to achieve the project’s objectives. Answer option b. “Direct and Manage Project Work”. Direct and Manage Project Work is the process of leading and performing the work defined in the project management plan and implementing approved changes to achieve the project’s objectives.
Exam 4 | #118. David is developing an approximation of the monetary resources needed to complete the project work. Which process is he performing? |  | Plan Cost Management | Estimate Costs | Determine Budget | Control Costs | Answer option b. | Answer option b. “Estimate Costs”. The process of developing an approximation of the monetary resources needed to complete project work. Answer option b. “Estimate Costs”. T he process of developing an approximation of the monetary resources needed to complete project work.
Exam 4 | #119. _____ involve a precedence relationship between project activities and are generally under the project team’s control. |  | External dependencies | Internal dependencies | Mandatory dependencies | Discretionary dependencies | Answer option b. | Answer option b. “Internal dependencies”. Internal dependencies involve a precedence relationship between project activities and are generally under the project team’s control. For example, if the team cannot test a machine until they assemble it, there is an internal mandatory dependency. The project management team determines which dependencies are internal during the process of sequencing the activities. Answer option b. “Internal dependencies”. Internal dependencies involve a precedence relationship between project activities and are generally under the project team’s control. For example, if the team cannot test a machine until they assemble it, there is an internal mandatory dependency. The project management team determines which dependencies are internal during the process of sequencing the activities.
Exam 4 | #120. The developers have just finished building a product increment and will present it to Sara in a demonstration tomorrow. Sara may either accept the increment or request changes to it. What is Sara’s most likely role on the project? |  | Product owner | Sponsor | Scrum Master | Project manager | Answer option a. | Answer option a. “Product Owner”. The description in the question defines the product owner’s role on a project. The other options are incorrect. Answer option a. “Product Owner”. The description in the question defines the product owner’s role on a project. The other options are incorrect.
Exam 4 | #121. Bob is working as a project manager at Space King Company. He is working on an unmanned air vehicle project. The software part of the project work has been procured and assigned to a software vendor. Bob wants to see how the seller is performing by comparing the deliverables received, the technical performance achieved and the costs incurred and accepted against the SOW budget for the work performed. He can check ____ . |  | Work performance data | Work performance information | Work performance reports | None of the above | Answer option b. “ | Answer option b. “Work performance information” includes information on how a seller is performing by comparing the deliverables received, the technical performance achieved, and the costs incurred and accepted against the SOW budget for the work performed. Answer option b. “ Work performance information” includes information on how a seller is performing by comparing the deliverables received, the technical performance achieved, and the costs incurred and accepted against the SOW budget for the work performed.
Exam 4 | #122. While performing the close project process, the project manager wants to ensure there are no risks, changes or issues are open. Which input should he review? |  | Project management plan | Project documents | Business documents | Organizational process assets | Answer option b. | Answer option b. “Project documents” include risk register and risk report which contains project risks and their status, change log which contains changes and their status and issue log which contains issues and their status. Answer option b. “Project documents” include risk register and risk report which contains project risks and their status, change log which contains changes and their status and issue log which contains issues and their status.
Exam 4 | #123. Rebecca is studying for her PMP exam and is reviewing the course material on Agile Project Management. Which of the following practices is Rebecca NOT to see in the section detailing Kanban? |  | Technical practice emphasis: as it is an agile engineering methodology, technical practices are prioritized. | Visualize what you do today (workflow): seeing all the items in context of each other can be very informative. | Limit the amount of work in progress (WIP): this helps balance the flow-based approach. | Enhance flow: when something is finished, the next highest thing from the backlog is pulled into play. | Answer option a. | Answer option a. A is a practice of XP Programming, while B, C, and D are practices of Kanban. Answer option a. A is a practice of XP Programming, while B, C, and D are practices of Kanban.
Exam 4 | #124. Brandon, an Agile Project Manager, has been leading an agile software development project for Company BioDev. In the beginning, the team was excited to work on the project, but now team members are not collaborating and there are recurring conflicts between them. Brandon, in an effort to resolve conflicts, begins to engage with the team and discovers that each team has different approaches for completing the project. He then begins to facilitate open dialogue between each team member to gain consensus and commitment. What conflict resolution style is Brandon using? |  | Withdraw/Avoid | Collaborate/Problem Solve | Force/Direct | Manage/Protect | Answer option b . | Answer option b. Collaborate/Problem Solve allows the Project Manager to have open dialogue with all team members, leading to consensus, alignment, and commitment from the team. Answer option b . Collaborate/Problem Solve allows the Project Manager to have open dialogue with all team members, leading to consensus, alignment, and commitment from the team.
Exam 4 | #125. In _____ projects, the Control Quality activities may be performed by all team members throughout the project life cycle. |  | Waterfall | Predictive | Agile | All of the above | Answer option c. | Answer option c. “Agile”. In agile projects, the Control Quality activities may be performed by all team members throughout the project life cycle. In waterfall model-based projects, the quality control activities are performed at specific times, toward the end of the project or phase, by specified team members. Answer option c. “Agile”. I n agile projects, the Control Quality activities may be performed by all team members throughout the project life cycle. In waterfall model-based projects, the quality control activities are performed at specific times, toward the end of the project or phase, by specified team members.
Exam 4 | #126. A project manager needs to ensure that the team delivers business value within the required timelines. The project manager recently learned that key stakeholders are worried that the current release plan will NOT meet urgent business needs. How can the project manager effectively respond to stakeholder concerns? |  | Renegotiate scope with the project sponsor after examining the work breakdown structure (WBS). | Consult with the stakeholders and team members to identify the minimum viable product (MVP) needed for launch. | Determine the schedule performance index (SPI), then escalate the schedule risk to the project sponsor. | Monitor progress using a burndown chart after modifying the schedule baseline to meet stakeholder requirements. | Answer option b . | Answer option b. Defining the minimum viable product would allow the team to release business value within timelines by focusing only on the must-have items that the business stakeholders need. Answer option b . Defining the minimum viable product would allow the team to release business value within timelines by focusing only on the must-have items that the business stakeholders need.
Exam 4 | #127. A project manager is performing the Direct and Manage Project Work process, where he needs to review the performance reports, deliverable status, and other information generated by the project. Which input does he need to go through? |  | Project management plan | Project communications | Project schedule | Risk report | Answer option b. “ | Answer option b. “Project communications” contains the details mentioned in the case. Answer option b. “ Project communications” contains the details mentioned in the case.
Exam 4 | #128. Company XYZ assigned Adam to a project, which focuses on moving the company databases to an external cloud-based server. The project is complex because one of the components of the project is to remove hardware, which has a very clear and defined scope. The software part of the project only has a high-level scope. What evolving trend in the project integration process should Adam adopt in this case? |  | Use of automated tools | Expanding the project manager’s responsibilities | Hybrid methodologies | Project knowledge management | Answer option c. | Answer option c. “Hybrid methodologies”. Some project management methodologies are evolving to incorporate successfully applied new practices. Examples include the use of agile and other iterative practices; business analysis techniques for requirements management; tools for identifying complex elements in projects; and organizational change management methods to prepare for transitioning the project outputs into the organization. Answer option c. “Hybrid methodologies”. Some project management methodologies are evolving to incorporate successfully applied new practices. Examples include the use of agile and other iterative practices; business analysis techniques for requirements management; tools for identifying complex elements in projects; and organizational change management methods to prepare for transitioning the project outputs into the organization.
Exam 4 | #129. The project team scheduled a weekly meeting to discuss the events they went through during the week to identify the lessons learned and share insights. What type of knowledge could the team share in this meeting? |  | Explicit knowledge | Tacit knowledge | Direct knowledge | Both A and B | Answer option d. | Answer option d. The best answer is “Both A and B” (Answer option d). “Explicit knowledge” (Answer option a) knowledge that can be easily codified with words and images which can be documented as lessons learned. “Tacit knowledge” (Answer option b) the experience and insights the team will share together and cannot be easily codified into words. Answer option d. The best answer is “Both A and B” (Answer option d). “Explicit knowledge” (Answer option a) knowledge that can be easily codified with words and images which can be documented as lessons learned. “Tacit knowledge” (Answer option b) the experience and insights the team will share together and cannot be easily codified into words.
Exam 4 | #130. _____ is a financial analysis tool used to estimate the strengths and weaknesses of alternatives in order to determine the best option in terms of benefits provided. |  | Trend analysis | Earned value analysis | Cost-benefit analysis | Cost of quality (COQ) | Answer option c. | Answer option c. “Cost-benefit analysis”. A cost-benefit analysis is a financial analysis tool used to estimate the strengths and weaknesses of alternatives in order to determine the best option in terms of benefits provided. Answer option c. “Cost-benefit analysis”. A cost-benefit analysis is a financial analysis tool used to estimate the strengths and weaknesses of alternatives in order to determine the best option in terms of benefits provided.
Exam 4 | #131. A project manager is communicating and working with stakeholders to meet their needs & expectations, address issues, and foster appropriate stakeholder involvement. Which process is he performing? |  | Plan Stakeholder Engagement | Manage Stakeholder Engagement | Manage communication | Monitor Stakeholder Engagement | Answer option b. | Answer option b. ”Manage Stakeholder Engagement”. The process of communicating and working with stakeholders to meet their needs and expectations, address issues, and foster appropriate stakeholder engagement involvement. Answer option b. ”Manage Stakeholder Engagement”. The process of communicating and working with stakeholders to meet their needs and expectations, address issues, and foster appropriate stakeholder engagement involvement.
Exam 4 | #132. Mabel will be the project manager for a renowned software company. She is collecting requirements to understand the stakeholder's needs. Suddenly, Mabel finds herself in a situation of uncovering hidden or misunderstood conditions. She is trying to plan for the project, but she realizes that the problem is becoming unbearable. What approach should Mabel use to manage these hidden and misunderstood requirements? |  | Agile approach. | Incremental approach. | Predictive approach. | Iterative approach. | Answer option a . | Answer option a. In an agile environment, requirements change all the time. So, it becomes necessary to use an approach where we can uncover any hidden or misunderstood needs. We do so by using the incremental and iterative elements of the agile process. Answer option a . In an agile environment, requirements change all the time. So, it becomes necessary to use an approach where we can uncover any hidden or misunderstood needs. We do so by using the incremental and iterative elements of the agile process.
Exam 4 | #133. You are the Scrum Master in an Agile organization. You keep reminding the upper management that your Scrum team needs to be optimal in size in order to follow the Scrum model and deliver significant work efficiently. From the selections below, what is the optimal team size per Scrum? |  | The optimal Scrum team is between 3 and 9 per the methodology. | The optimal Scrum team is between 4 and 8 per the methodology. | The optimal Scrum team is between 5 and 15 per the methodology. | Scrum does not define a specific team size because each job is different. | Answer option a . | Answer option a. Per Scrum framework, the optimal size is between 3-9; fewer than 3 members will decrease interaction and result in smaller productivity rates while more than 9 members will require further coordination and result in complexity for the empirical process to manage. Answer option a . Per Scrum framework, the optimal size is between 3-9; fewer than 3 members will decrease interaction and result in smaller productivity rates while more than 9 members will require further coordination and result in complexity for the empirical process to manage.
Exam 4 | #134. A project manager is working on obtaining team members, facilities, equipment, materials, supplies, and other resources necessary to complete project work. Which process is he performing? |  | Acquire Resources | Develop Team | Manage Team | Control Resources | Answer option a. | Answer option a. “Acquire Resources”. Acquire Resources is the process of obtaining team members, facilities, equipment, materials, supplies, and other resources necessary to complete project work. Answer option a. “Acquire Resources”. Acquire Resources is the process of obtaining team members, facilities, equipment, materials, supplies, and other resources necessary to complete project work.
Exam 4 | #135. You’re hiring for a new project, and you’re looking for someone who is an expert in identifying business needs, can prioritize, and can work well with the rest of the scrum team. All changes to the product backlog should be done by him/her. What role are you looking for? |  | An experienced scrum-master | Software project manager | Software technical lead | Product owner | Answer option d. | Answer option d. “Product Owner”. The Product Owner is a person responsible for maximizing the value of the product and who is ultimately responsible and accountable for the end product that is built. See also Service Request Manager. Answer option d. “Product Owner”. The Product Owner is a person responsible for maximizing the value of the product and who is ultimately responsible and accountable for the end product that is built. See also Service Request Manager.
Exam 4 | #136. Sam is a project manager who is currently validating the scope of the deliverables. Sam will be reviewing the ______ document to compare the actual results to determine if a change, corrective action, or preventive action is necessary. |  | Requirements management plan | Scope management plan | Requirements documentation | Scope baseline | Answer option c. | Answer option c. “Requirements documentation” Although “Scope baseline” (Answer option d.) can be used for the same objective it is not a valid option as it’s a plan not a document. Answer option c. “Requirements documentation” Although “Scope baseline” (Answer option d.) can be used for the same objective it is not a valid option as it’s a plan not a document.
Exam 4 | #137. The project team identified one of the key stakeholders as neutral while the team wanted him to be supportive. Which technique are they using? |  | Directions of influence | Salience model | Stakeholder engagement assessment matrix | Stakeholder cube | Answer option c. | Answer option c. “Stakeholder engagement assessment matrix”. A stakeholder engagement assessment matrix supports a comparison between the current engagement levels of stakeholders and the desired engagement levels required for successful project delivery. Answer option c. “Stakeholder engagement assessment matrix”. A stakeholder engagement assessment matrix supports a comparison between the current engagement levels of stakeholders and the desired engagement levels required for successful project delivery.
Exam 4 | #138. Claire was assigned to a new project which has been ongoing for three months. She wanted to check the project performance data of the project. She received the following data: AC=$200K, EV=$210K, and PV=$200K. How is the project performing? |  | Project is under budget | Project is over budget | Project is on budget | Cannot say | Answer option a. | Answer option a. to decide the project cost performance you can either calculate CV or CPI, CV=EV-AC=210-200=10, as the result is positive then “Project is under budget” Answer option a. to decide the project cost performance you can either calculate CV or CPI, CV=EV-AC=210-200=10, as the result is positive then “Project is under budget”
Exam 4 | #139. A project team is showing a high level of trust but not showing the same level of productivity. The project team is in _____ Tuckman ladder stage. |  | Storming | Forming | Performing | Norming | Answer option d. “ | Answer option d. “Norming”. In this phase, team members begin to work together and adjust their work habits and behaviors to support the team. The team members learn to trust each other. Answer option d. “ Norming”. In this phase, team members begin to work together and adjust their work habits and behaviors to support the team. The team members learn to trust each other.
Exam 4 | #140. Chris is a project manager assigned to develop the charter of an Agile Project for a Software development company and realizes the financial analysis in the business case is inaccurate. What should he do next? |  | Update the Product Backlog with an additional risk. | Submit a change request to the Change Control Board (CCB). | Notify the project sponsor and stakeholders as soon as possible. | Consult the Development Team SME’s. | Answer option c . | Answer option c. Notify the sponsor and stakeholders as soon as possible that there has been an oversight in the business case. If the financial analysis is inaccurate, this can have a negative effect on the valuation of the organization. The sponsor is accountable for the development and maintenance of the business case. Answer option c . Notify the sponsor and stakeholders as soon as possible that there has been an oversight in the business case. If the financial analysis is inaccurate, this can have a negative effect on the valuation of the organization. The sponsor is accountable for the development and maintenance of the business case.
Exam 4 | #141. A project manager is working on a project where he can determine project scope, time, and cost in the early phases of the life cycle. Which project lifecycle should he use for this project? |  | Predictive | Iterative | Incremental | Hybrid | Answer option a. | Answer option a. ”Predictive” since the project scope is clear, he can provide a realistic plan for it. Answer option a. ”Predictive” since the project scope is clear, he can provide a realistic plan for it.
Exam 4 | #142. Lucas is managing a media project for a TV channel. The project has a very clear scope, and the project is going very well as planned. One of the key persons who will accept the project from the customer asked for a one-on-one meeting with Lucas. During the meeting, the customer asked for a change to the project scope that will affect the schedule and cost of the project. Lucas should bring this change request to ____________ . |  | Customer | Service Provider | Third Party Vendor | Change Control Board | Answer option d. | Answer option d. ”Change Control Board” decides the impacts of a change, and decides whether to approve a change request. Answer option d. ”Change Control Board” decides the impacts of a change, and decides whether to approve a change request.
Exam 4 | #143. You are the Scrum Master in an Agile organization. You like to plan all Scrum events according to the framework. Every time a new Sprint is complete (Typically a 1-month Sprint), you schedule a sprint review meeting with the Product Owner, the development team, and all key stakeholders to discuss what has been achieved on the Sprint so far. Sprint review meeting is time-boxed for: |  | Four (4) hours | Three (3) hours | One (1) hour | It is open ended, depending on the deliverable. | Answer option a . | Answer option a. Per Scrum framework, at the end of each Sprint, a sprint review meeting must be held to inspect and adapt the deliverables. This meeting should not exceed 4 hours for a 1-month Sprint. Answer option a . Per Scrum framework, at the end of each Sprint, a sprint review meeting must be held to inspect and adapt the deliverables. This meeting should not exceed 4 hours for a 1-month Sprint.
Exam 4 | #144. In the Tuckman ladder model, it is common for these stages to occur in order at the same time. It is not odd for a team to get stuck in a particular stage or revert to an earlier stage. If team XYZ just passed the forming stage, they will most probably go into the ____ stage. |  | Performing | Forming | Norming | Storming | Answer option d. | Answer option d. “Storming”. The order of Tuckman ladder stages is as following: Forming -> Storming -> Norming -> Performing -> Adjourning. Answer option d. “Storming”. The order of Tuckman ladder stages is as following: Forming -> Storming -> Norming -> Performing -> Adjourning.
Exam 4 | #145. A project manager is visiting a software supplier's office. Some of the sights are surprising: two people per workstation, estimations based on a deck of cards, developers forcing their tests to fail, and routines with names that do not relate to project management. What could explain these practices? |  | The servant leader has granted the team a bit too much freedom. | The supplier has adopted extreme Programming methods. | The supplier appears to be conducting “gaming” training sessions. | The project manager happened to visit during a team building exercise. | Answer option b . | Answer option b. Extreme Programming practices include pair programming (2 per workstation), planning poker, test-first programming, and metaphor naming of processes. Answer option b . Extreme Programming practices include pair programming (2 per workstation), planning poker, test-first programming, and metaphor naming of processes.
Exam 4 | #146. Kerry is a software developer for multinational AI company IntelTech based in Singapore. A new customer has made a requirement for an innovative system based on artificial intelligence. After meeting with the customer, Kerry has determined that the project will have fixed requirements. Activities will be performed only once for a given increment, including frequent smaller deliveries. Most of all, the customer wants the software to be working in about three months. What type of life cycle should Kerry choose to work on this project? |  | Predictive | Iterative | Incremental | It is impossible to have fixed requirements and frequent smaller deliveries and speed. | Answer option d . | Answer option d. Predictive life cycle is used when requirements are fixed, activities are performed only once for the entire project, deliveries are performed once, and the goal is to control cost. In an incremental life cycle approach, requirements should be dynamic, and other conditions could be maintained. Answer option d . Predictive life cycle is used when requirements are fixed, activities are performed only once for the entire project, deliveries are performed once, and the goal is to control cost. In an incremental life cycle approach, requirements should be dynamic, and other conditions could be maintained.
Exam 4 | #147. Thomas is monitoring the status of the project to update the project costs and manage changes to the cost baseline. Which process is he performing? |  | Plan Cost Management | Estimate Costs | Determine Budget | Control Costs | Answer option d. | Answer option d. “Control Costs”. The process of monitoring the status of the project to update the project costs and manage changes to the cost baseline. Answer option d. “Control Costs”. The process of monitoring the status of the project to update the project costs and manage changes to the cost baseline.
Exam 4 | #148. Tobey is defining how the project’s costs will be estimated, budgeted, managed, monitored, and controlled. Which process is he performing? |  | Plan Cost Management | Estimate Costs | Determine Budget | Control Costs | Answer option a. | Answer option a. “Plan Cost Management” Answer option a. “Plan Cost Management”
Exam 4 | #149. A product owner has set up a room with five laptops and invited four different end-users to test the capabilities of a new system. The developers from the project team have been invited in the room to observe the users take notes and answer the basic questions. Which of the following agile techniques and tools has been described in the scenario? |  | Usability testing | Automated testing | Scripted tests | Exploratory testing | Answer option a. | Answer option a. “Usability testing” is a type of testing that involves end-users to check their response to the system. The main goal of this testing is to identify how easy it is for end-users to use the system and to reveal the usability issues or defects that would lead to redesign. In the above scenario, end-users are invited to test the capabilities of the new system and developers observe the users while they interact with the system, take notes and answer the basic questions. Answer option a. “Usability testing” is a type of testing that involves end-users to check their response to the system. The main goal of this testing is to identify how easy it is for end-users to use the system and to reveal the usability issues or defects that would lead to redesign. In the above scenario, end-users are invited to test the capabilities of the new system and developers observe the users while they interact with the system, take notes and answer the basic questions.
Exam 4 | #150. Aisha is documenting how the project and product scope will be defined, validated, and controlled. Which process is she performing? |  | Plan Scope Management | Collect Requirements | Define Scope | Create WBS | Answer option a. | Answer option a. “Plan Scope Management”. The process of creating a scope management plan that documents how the project and product scope will be defined, validated, and controlled. Answer option a. “Plan Scope Management”. The process of creating a scope management plan that documents how the project and product scope will be defined, validated, and controlled.
Exam 4 | #151. While studying for his PMP exam, James is studying the Definition of Done and how it is determined in a Sprint. Which of the following is NOT one of the explanations in his course material? |  | All the features on the Product Backlog are implemented. | Code meets general Coding Standard. | Functional tests are performed by the team. | All Acceptance and Integrations tests are Green (passed). | Answer option a. | Answer option a. The features of the Sprint Backlog are implemented, not the Product Backlog. B, C and D are all true features of the Definition of Done. Answer option a. The features of the Sprint Backlog are implemented, not the Product Backlog. B, C and D are all true features of the Definition of Done.
Exam 4 | #152. You are an expert developer in an organization that is new to Scrum and Agile. The organization is committed to rolling out a new cell phone feature that is due in one week. The timeline is tight. The Sprint has been determined and the estimates were performed using story points and hours by the team; you walk up to the Scrum Master and recommend using “pair-programming” technique to deliver this task. What is the pair-programming” in Agile: |  | It is a technique where two developers work together to write the lines of code faster. | It is a technique where one developer writes the code and another reports the progress to the Product Owner subsequently. | It is a technique where two developers work in tandem at one station and take turns between two roles. | It is a technique where one developer codes and the other meets constantly with the client for early feedback on what has been completed. | Answer option c. | Answer option c. Per Agile, Pair Programming is a software development technique, in which two developers work in tandem at one station. It is very popular in Scrum and other Agile frameworks as well. The two developers take turns between two main roles: Coder (a.k.a driver) writes the lines of code and Observer (a.k.a navigator) reviews each line as it is written. The collaborative approach keeps both developers highly engaged and usually yields high quality results faster. Answer option c. Per Agile, Pair Programming is a software development technique, in which two developers work in tandem at one station. It is very popular in Scrum and other Agile frameworks as well. The two developers take turns between two main roles: Coder (a.k.a driver) writes the lines of code and Observer (a.k.a navigator) reviews each line as it is written. The collaborative approach keeps both developers highly engaged and usually yields high quality results faster.
Exam 4 | #153. The goal of each iteration is to produce a working increment of the product which can be demonstrated to stakeholders. Therefore, one of the key meetings in a Sprint is the sprint demo (also known as the Sprint Review Meeting). The Scrum team completes the sprint and the progress of the team is assessed against the sprint goal. Who conducts the iteration demo in Scrum? |  | Product Manager | Scrum Master | Product Owner | Team | Answer option c. | Answer option c. “Product Owner” conducts the Sprint Review (Demo) meeting. Answer option c. “Product Owner” conducts the Sprint Review (Demo) meeting.
Exam 4 | #154. Which of the following are components of the scope baseline in agile projects? |  | Scope Statement and project schedule | Product requirements and user stories | Product Scope Statement and Work Breakdown Structure (WBS) | WBS Dictionary and Work Breakdown Structure (WBS) | Answer option b . | Answer option b. Projects with Agile lifecycles, unlike the Waterfall method, use backlogs as the scope baseline to reflect the needs of the project. The WBS, WBS Dictionaries, and Scope Statement are used in Waterfall lifecycles. Answer option b . Projects with Agile lifecycles, unlike the Waterfall method, use backlogs as the scope baseline to reflect the needs of the project. The WBS, WBS Dictionaries, and Scope Statement are used in Waterfall lifecycles .
Exam 4 | #155. A project manager is in the process of closing the project. He needs to review the versions and baselines of all official organizational standards, policies, procedures, and other project documents. Which of the following should he review first? |  | Business documents | Procurement documentation | Configuration management knowledge base | Project documents | Answer option c. | Answer option c. ”Configuration management knowledge base” contains the versions and baselines of all official organizational standards, policies, procedures, and any project documents. Answer option c. ”Configuration management knowledge base” contains the versions and baselines of all official organizational standards, policies, procedures, and any project documents.
Exam 4 | #156. You are an agile coach and want to confirm that the development team has an easy method to organize the work and visualize the remaining work in the iteration. Which of the following is the best approach you will use to complete the goals? |  | Use information radiator | Use burndown chart | Use burnup chart | Use the task board | Answer option d . | Answer option d. “Use the task board”. Task board is a diagrammatic tool that basically helps the teams in organizing and analyzing the progress of their work. In the task board the tasks considered in the Sprint are divided into 3 main categories: 1. tasks to be started, 2. tasks in progress, and 3. tasks completed. It makes it easy for everyone to see the tasks the team is currently working on and to select the next ones. Answer option d . “Use the task board”. Task board is a diagrammatic tool that basically helps the teams in organizing and analyzing the progress of their work. In the task board the tasks considered in the Sprint are divided into 3 main categories: 1. tasks to be started, 2. tasks in progress, and 3. tasks completed. It makes it easy for everyone to see the tasks the team is currently working on and to select the next ones.
Exam 4 | #157. A project manager is creating an agenda and presentation materials for a kick-off meeting that will involve stakeholders across the globe. How can the project manager facilitate and optimize stakeholder engagement? |  | Create slides for the kick-off meeting to address stakeholder involvement. | Survey stakeholders' preferred meeting dates and times to accommodate the teams in different time zones. | Verify that all required participants or their delegates will be available to attend. | Review the kick-off meeting agenda and materials for overall clarity and concision. | Answer option b . | Answer option b. Survey stakeholders’ preferred meeting dates and times to accommodate the teams in different time zones. Assuming a particular solution does NOT empower the team. Surveying the team and finding common consensus is a key part of servant leadership. Answer option b . Survey stakeholders’ preferred meeting dates and times to accommodate the teams in different time zones. Assuming a particular solution does NOT empower the team. Surveying the team and finding common consensus is a key part of servant leadership.
Exam 4 | #158. Adam is a project manager assigned to an internal project. The project team is working as one unit and complies with the team guidelines and values. Adam wanted to replicate this successful team model for his future projects. Which document that assists in developing the team should he review? |  | Lessons learned register | Project team assignments | Lessons learned repository | Team charter | Answer option d. | Answer option d. “Team charter” contains team guidelines and values. The team charter is a document that establishes the team values, agreements, and operating guidelines for the team. Answer option d. “Team charter” contains team guidelines and values. The team charter is a document that establishes the team values, agreements, and operating guidelines for the team.
Exam 4 | #159. Max is leading an internal project that aims to improve employees’ work conditions. What type of benefit does this project generate? |  | Tangible | Intangible | Elemental | Both A and B | Answer option b. | Answer option b. “Intangible”. Improvement of the working conditions are intangible (cannot be measured in monetary value) benefits. Answer option b. “Intangible”. Improvement of the working conditions are intangible (cannot be measured in monetary value) benefits.
Exam 4 | #160. While initiating a project, you just completed identifying the project’s stakeholders. Which outputs would you expect? |  | Stakeholder register | Project management plan updates | Change requests | Stakeholder engagement plan | Answer option a. | Answer option a. The best answer is “Stakeholder register” (Answer option a.).” Project management plan updates” (Answer option b), “Change requests” (Answer option c.) are expected outputs in the later iterations of the process but not during initiation. “Stakeholder engagement plan” (Answer option d.) is an output of later process “Plan Stakeholder engagement”. Answer option a. The best answer is “ Stakeholder register ” (Answer option a.).” Project management plan updates ” (Answer option b), “ Change requests ” (Answer option c.) are expected outputs in the later iterations of the process but not during initiation. “ Stakeholder engagement plan ” (Answer option d.) is an output of later process “Plan Stakeholder engagement” .
Exam 4 | #161. Mike has listed the project deliverables that are completed and checked for their correctness through the Control Quality process. What is Mike looking for? |  | Verified Deliverables | Scope Management Plan | Requirements Documentation | Requirements Traceability Matrix | Answer option a. | Answer option a. “Verified Deliverables” are completed project deliverables that have been checked and confirmed for correctness through the Control Quality process. Answer option a. “Verified Deliverables” are c ompleted project deliverables that have been checked and confirmed for correctness through the Control Quality process.
Exam 4 | #162. Despite the use of advanced communication technologies, Alex is facing multiple communication problems within the team since the team members are located across different company facilities within the same city. To resolve these issues, which technique should he use? |  | Virtual teams | Colocation | Communication technology | Conflict management | Answer option b. | Answer option b. “Colocation” since the offices are near colocation would be the best solution since the virtual teams concept is not working – the team is already using advanced communication technologies. Answer option b. “Colocation” since the offices are near colocation would be the best solution since the virtual teams concept is not working – the team is already using advanced communication technologies.
Exam 4 | #163. Alex is working on increasing support and minimizing resistance from the stakeholders. Which process is he performing? |  | Identify Stakeholders | Plan Stakeholder Engagement | Manage Stakeholder Engagement | Monitor Stakeholder Engagement | Answer option c. | Answer option c. ”Manage Stakeholder Engagement”. Manage Stakeholder Engagement is the process of communicating and working with stakeholders to meet their needs and expectations, address issues, and foster appropriate stakeholder involvement. The key benefit of this process is that it allows the project manager to increase support and minimize resistance from stakeholders. Answer option c. ”Manage Stakeholder Engagement”. Manage Stakeholder Engagement is the process of communicating and working with stakeholders to meet their needs and expectations, address issues, and foster appropriate stakeholder involvement. The key benefit of this process is that it allows the project manager to increase support and minimize resistance from stakeholders.
Exam 4 | #164. Organizational culture and structure, team resource availability and skills, physical resource availability, and scheduling software are examples of _______ . |  | Emerging practices for project schedule management | Considerations for tailoring Project Schedule Management | Organizational process assets | Enterprise environmental factors | Answer option d. | Answer option d. “Enterprise environmental factors”. In this case all of them are internal EEF. Answer option d. “Enterprise environmental factors”. In this case all of them are internal EEF.
Exam 4 | #165. Sam is doing a set of activities that have some repetitive elements to its deliverables. However, his work will end up with a unique result. Accordingly, how should Sam classify the work he is doing? |  | A project | A Program | Operational work | A portfolio | Answer option a. | Answer option a. ”A project” Repetitive elements may be present in some project deliverables and activities. This repetition does not change the fundamental and unique characteristics of the project work. Since the output is a unique product, this is considered a project. Answer option a. ”A project” Repetitive elements may be present in some project deliverables and activities. This repetition does not change the fundamental and unique characteristics of the project work. Since the output is a unique product, this is considered a project.
Exam 4 | #166. The customer requested Henry to meet high-quality standards for the project deliverables. Henry decides to set aside a budget for activities that would minimize the poor quality in the project deliverables. Which type of CoQ did he use? |  | Prevention Cost | Appraisal Cost | Failure Cost | Liability Cost | Answer option a. | Answer option a. “Prevention Cost”. Costs related to the prevention of poor quality in the products, deliverables, or services of the specific project. Answer option a. “Prevention Cost”. Costs related to the prevention of poor quality in the products, deliverables, or services of the specific project.
Exam 4 | #167. Alex aims for outlining and guiding the selection of resources and assigning them to their respective activities. Which process is he performing? |  | Acquire Resources | Develop Team | Manage Team | Control Resources | Answer option a. | Answer option a. “Acquire Resources” is the process of obtaining team members, facilities, equipment, materials, supplies, and other resources necessary to complete project work. Answer option a. “Acquire Resources” is t he process of obtaining team members, facilities, equipment, materials, supplies, and other resources necessary to complete project work.
Exam 4 | #168. _____ is a projection of the amount of budget deficit or surplus, expressed as the difference between the budget at completion and the estimate at completion. |  | EAC | ETC | VAC | BAC | Answer option c. | Answer option c. ”VAC”. Variance at Completion. Answer option c. ”VAC”. Variance at Completion.
Exam 4 | #169. _____ is used to determine whether it is better to accomplish work or deliverables by the project team or purchase it from outside sources. |  | Make-or-buy analysis | Conduct procurement | Source selection analysis | Source selection criteria | Answer option a. | Answer option a. “Make-or-buy analysis”. A make-or-buy analysis is used to determine whether work or deliverables can best be accomplished by the project team or should be purchased from outside sources. Answer option a. “Make-or-buy analysis”. A make-or-buy analysis is used to determine whether work or deliverables can best be accomplished by the project team or should be purchased from outside sources.
Exam 4 | #170. Graeme has identified a threat to his project. He decided to make a premium payment and asked another company to deal with the project work that carries the risk component. This is an example of _____ . |  | Workaround | Risk Transfer | Risk Avoidance | Risk Acceptance | Answer option b. | Answer option b. “Risk Transfer” involves shifting ownership of a threat to a third party that would manage the risk and to bear the impact, if the threat occurs. Answer option b. “Risk Transfer” involves shifting ownership of a threat to a third party that would manage the risk and to bear the impact, if the threat occurs.
Exam 4 | #171. Sam is developing a diagram to present information visually. It is created around a single quality concept, drawn as an image in the center of a blank landscape page, to which associated representations of ideas such as images, words, and parts of words are added. Which data representation technique did he use? |  | Flowcharts | Logical data model | Matrix diagrams | Mind mapping | Answer option d. | Answer option d. “Mind mapping”. A technique used to consolidate ideas created through individual brainstorming sessions into a single map to reflect commonality and differences in understanding and to generate new ideas. Answer option d. “Mind mapping”. A technique used to consolidate ideas created through individual brainstorming sessions into a single map to reflect commonality and differences in understanding and to generate new ideas.
Exam 4 | #172. Which of the following is not a benefit associated with product demonstrations during sprint review sessions? |  | Learn about feature suitability | Learn about feature usability | Learn about feature estimates | Learn about new requirements | Answer option c . | Answer option c. “Learn about feature estimates”. Product demonstrations provide the benefits of learning about feature suitability and usability, and they can prompt discussions of new requirements. They are not typically used to learn about feature estimates since estimating is done during estimation sessions, rather than during demonstrations. Answer option c . “Learn about feature estimates”. Product demonstrations provide the benefits of learning about feature suitability and usability, and they can prompt discussions of new requirements. They are not typically used to learn about feature estimates since estimating is done during estimation sessions, rather than during demonstrations .
Exam 4 | #173. A project manager is controlling the project resources. Which organizational process assets can affect the process? |  | Policies regarding resource control and assignment | Escalation procedures for handling issues within the performing organization | Lessons learned repository from previous similar projects | All of the above | Answer option d. | Answer option d. The best answer is “All of the above” (Answer option d.). “ Policies regarding resource control and assignment” (Answer option a), “Escalation procedures for handling issues within the performing organization” (Answer option b.) and “Lessons learned repository from previous similar projects” (Answer option c.) are all organizational process assets that can influence the process. Answer option d. The best answer is “All of the above” (Answer option d.). “ Policies regarding resource control and assignment” (Answer option a), “Escalation procedures for handling issues within the performing organization” (Answer option b.) and “Lessons learned repository from previous similar projects” (Answer option c.) are all organizational process assets that can influence the process.
Exam 4 | #174. A project manager is working on tracking team member performance, providing feedback, resolving issues, and managing team changes to optimize the project performance. Which process is he performing? |  | Acquire Resources | Develop Team | Manage Team | Control Resources | Answer option c. | Answer option c. “Manage Team”. The process of tracking team member performance, providing feedback, resolving issues, and managing team changes to optimize project performance. Answer option c. “Manage Team”. The process of tracking team member performance, providing feedback, resolving issues, and managing team changes to optimize project performance.
Exam 4 | #175. Reassigning personnel, dealing with excess project material, and reallocating project facilities, equipment, and other resources are examples of the tasks that are performed during ____ . |  | Planning | Executing | Monitoring and controlling | Closing | Answer option d. | Answer option d. ”Closing”. Actions and activities necessary to satisfy completion or exit criteria for the phase or project such as: Answer option d. ”Closing”. Actions and activities necessary to satisfy completion or exit criteria for the phase or project such as: Making certain that all documents and deliverables are up-to-date and that all issues are resolved; Confirming the delivery and formal acceptance of deliverables by the customer; Ensuring that all costs are charged to the project; Closing project accounts; Reassigning personnel; Dealing with excess project material; Reallocating project facilities, equipment, and other resources; and Elaborating the final project reports as required by organizational policies. Making certain that all documents and deliverables are up-to-date and that all issues are resolved; Making certain that all documents and deliverables are up-to-date and that all issues are resolved; Confirming the delivery and formal acceptance of deliverables by the customer; Confirming the delivery and formal acceptance of deliverables by the customer; Ensuring that all costs are charged to the project; Ensuring that all costs are charged to the project; Closing project accounts; Closing project accounts; Reassigning personnel; Reassigning personnel; Dealing with excess project material; Dealing with excess project material; Reallocating project facilities, equipment, and other resources; and Reallocating project facilities, equipment, and other resources; and Elaborating the final project reports as required by organizational policies. Elaborating the final project reports as required by organizational policies.
Exam 4 | #176. During the project closure, Abigail is preparing a presentation to justify the project and explain the benefits the project will generate compared to the costs of investment in the project. Which document should she review? |  | Project charter | Project management plan | Business documents | All of the above | Answer option c. | Answer option c. “Business documents” the data required for the presentation provided in the business case which is one of the Business documents. Answer option c. “Business documents” the data required for the presentation provided in the business case which is one of the Business documents.
Exam 4 | #177. You’re working on a new IoT vending machine prototype that utilizes artificial intelligence and machine learning to predict what people would like to eat. There is no complete requirements specification, the idea is new, and no one has ever built a product like that before. The path to get this product to the market is not clear. However, your organization decided that the best approach to move forward is to embrace continuous learning, inspecting, and adapting as core values for this project. What framework or methodology should you be using in this project? |  | Scrum | Requirements Engineering | Prince2 | Praxis | Answer option a. | Answer option a. Continuous learning, inspecting, and adapting are core Agile values, and Scrum is the only given Agile practice in the answer choices. Answer option a. Continuous learning, inspecting, and adapting are core Agile values, and Scrum is the only given Agile practice in the answer choices.
Exam 4 | #178. An agile team is beginning a new release. Things are progressing a little slower than initially estimated. The team is not sure why the project manager is not leading the work performance and checking progress. They are confused by the lack of hands-on guidance. The project manager is taking a servant leadership approach. Which of the following actions is the project manager most likely to do? |  | Create a high-level scope statement and estimates | Intervene in unproductive team arguments | Do administrative activities for the team | Demonstrate the system to senior executives | Answer option c . | Answer option c. “Do administrative activities for the team”. In taking a servant leadership approach, the project manager is most likely to do administrative activities for the team. As implied by the term, the role of a servant leader is focused on serving the team. A servant leader recognizes that the team members create the business value and does what is necessary to help the team be successful. Answer option c . “Do administrative activities for the team”. In taking a servant leadership approach, the project manager is most likely to do administrative activities for the team. As implied by the term, the role of a servant leader is focused on serving the team. A servant leader recognizes that the team members create the business value and does what is necessary to help the team be successful.
Exam 4 | #179. Your organization has launched a strategic technology project which might be highly competitive. You already recognize that there are similar products on the market, therefore your organization is pushing to have as unique and innovative products as possible. For that reason, you and your team need to first identify the critical features of the product. What type of meeting will you organize? |  | User stories workshop | Product design meeting | Joint application development workshop | Quality function deployment workshop | Answer option d . | Answer option d. “Quality Function Deployment workshop”. QFD (Quality function deployment) focuses on critical and innovative product characteristics, and it is traditionally used in the manufacturing industry. Answer option d . “Quality Function Deployment workshop”. QFD (Quality function deployment) focuses on critical and innovative product characteristics, and it is traditionally used in the manufacturing industry.
Exam 4 | #180. Godwin finished identifying all project activities. He wants to start identifying the relationships among the project activities. Godwin will be performing the _____ process next. |  | Define Activities | Develop Schedule | Sequence Activities | Plan Schedule Management | Answer option c. | Answer option c. ”Sequence Activities” comes after the “define activities” process. Answer option c. ”Sequence Activities” comes after the “define activities” process.

## exam5
Exam Name | Question | quesimgsrc | Answer1 | Answer2 | Answer3 | Answer4 | Correct-Answer | Explanation | answerimgsrc
Exam 5 | #1. A large development team of 100 members is working on a large and complex system with multiple sub-systems. They would like to start using the Agile Scrum Methodology. Venna is the dedicated Scrum Master of the team; what should she do? |  | Establish day and night shifts best suited for large and complex projects. | Ask all team members to have a meeting first and decide if they agree to use Scrum. | Scrum is not suited for large projects. The team should use the Waterfall approach. | Establish a Scrum of Scrums system so that small Scrum teams can work on related sub-systems, adding value to the project execution. | Answer option d. | Answer option d. Scrum of Scrums allows larger projects to be divided into specialized Scrum teams, responsible for completing the assigned sub-system of the overall project. Answer option d. Scrum of Scrums allows larger projects to be divided into specialized Scrum teams, responsible for completing the assigned sub-system of the overall project.
Exam 5 | #2. Glyn has taken over a project. He finds many conflicts are ongoing among the project team. Which of the following is a valid technique for resolving conflicts? |  | Exploit | Accept | Force | None of the Above | Answer option c. | Answer option c. The best answer is “Force” (Answer option c.) as it is a conflict resolution technique. “Exploit” (Answer option a.) and “Accept” (Answer option b.) are both risk response strategies, not conflict resolution techniques. Answer option c. The best answer is “ Force ” (Answer option c.) as it is a conflict resolution technique. “ Exploit ” (Answer option a.) and “ Accept ” (Answer option b.) are both risk response strategies, not conflict resolution techniques .
Exam 5 | #3. According to the stakeholder engagement-assessment matrix, if a stakeholder is aware of the project and its potential impacts and is actively engaged in ensuring that the project is a success, he is classified as _____ . |  | Resistant | Neutral | Supportive | Leading | Answer option d. | Answer option d. “Leading”. Resistant: The stakeholder is aware of the project but does not support it. Neutral: The stakeholder is ambivalent about the project and its outcomes. Supportive: The stakeholder feels favorably about the project and its outcomes. Leading: The stakeholder is actively engaged in promoting the project. Answer option d. “Leading”. Resistant: The stakeholder is aware of the project but does not support it. Neutral: The stakeholder is ambivalent about the project and its outcomes. Supportive: The stakeholder feels favorably about the project and its outcomes. Leading: The stakeholder is actively engaged in promoting the project.
Exam 5 | #4. You are the Scrum Master of a well performing Scrum team. You work in an organization where projects are frequently carried out in a fast-paced environment. You have noticed that the user story requirements during the last few Sprints are not well defined. What could have been the reason? |  | The Product Owner has not been attending the Sprint Review sessions. | You have increased the sprints duration from two weeks to four weeks. | The user stories are different in scope and functionality. | The Product Owner has not been attending the last few backlog grooming sessions. | Answer option d. | Answer option d. In Scrum framework, the Product Owner is in charge of the Product Backlog and the user stories in the backlog. Backlog grooming is a recurring event in which the Product Owner along with the development team prepare for the upcoming sprints and ensure the user stories on the sprints are well defined and understood by the development team. Answer option d. In Scrum framework, the Product Owner is in charge of the Product Backlog and the user stories in the backlog. Backlog grooming is a recurring event in which the Product Owner along with the development team prepare for the upcoming sprints and ensure the user stories on the sprints are well defined and understood by the development team.
Exam 5 | #5. You are working on a project in a war-stricken country. The project is very complex, and the political and economic situation on the ground is making the implementation of your project even more difficult. In order to continue with the work on your project, you are required to make a payment to the authorities. What should you do? |  | Do not pay | Make the payment | Ask the authorities for proof of payment | Ask the legal counselor if such a payment is considered a bribe | Answer option b. | Answer option b. “Make the payment”. You may suspect it is a violation of the ethical codex. However, a bribe is not mentioned here. As the payment is required, it must be made. Answer option b. “Make the payment”. You may suspect it is a violation of the ethical codex. However, a bribe is not mentioned here. As the payment is required, it must be made.
Exam 5 | #6. This is your first Agile software project. You are working with an experienced team and you are trying to make a parallel between many of the terms used in Agile and in the Traditional project approach, which you are very familiar with. You have managed over 10 waterfall projects with success. Which type of meetings is unique for your current project compared to your earlier projects? |  | Stakeholder meetings | Retrospective meetings | Quality review meetings | Team performance review meetings | Answer option b. | “Retrospective meetings” are unique to Agile projects. It is a meeting after each sprint (iteration) where the development team talks about the work that was done, the successes and challenges, and together the team agrees on a few improvements they will make in the next sprint.
Exam 5 | #7. Garry is performing the earned value analysis. The project earned value is $30,000, planned value is $20,000 and the actual cost is $25,000. The project cost performance index is _____ . |  | 0.8 | 1.2 | 1.25 | 1.5 | Answer option b. | Answer option b. “1.20” cost performance index=EV/AC= 30/25=1.2 Answer option b. “1.20” cost performance index=EV/AC= 30/25=1.2
Exam 5 | #8. A Scrum Master is working on an Agile Project. Recently the project team has completed a Sprint (iteration). However, significant defects have been discovered prior to the commencement of the next Sprint. During the next retrospective, what should the Scrum Master, Rachel, recommend to avoid the reoccurrence of a consistent issue? |  | Escalating to Senior Management. | Updating the risk register. | Performing a root cause analysis. | Delaying the next Sprint (iteration) until all defects have been fixed. | Answer option c . | Answer option c. Perform root cause analysis, which allows the team to trace back the problem to the root cause. When all root problems are removed, the problem no longer occurs. Answer option c . Perform root cause analysis, which allows the team to trace back the problem to the root cause. When all root problems are removed, the problem no longer occurs.
Exam 5 | #9. A few months ago the members of the delivery team seemed to be arguing constantly, and they needed a lot of guidance from their team leader. But now they seem to have worked through their issues and their team leader isn't as involved on a daily basis. What has changed? |  | The team moved from the Storming stage to the Norming stage. | The team moved from the Storming stage to the Performing stage. | The team leader moved from the Supporting style to the Coaching style. | The team leader moved from the Directing style to the Coaching style | Answer option a. | Answer option a. This scenario describes a team that is moving from the Storming stage to the Norming stage. (A team typically needs to complete the Norming stage before it can reach the Performing stage.) The leadership styles that correspond to Storming and Norming are Coaching and Supporting, respectively. So here the team leader would have changed her style from Coaching to Supporting, rather than vice versa–but that switch would have been in response to the team, not the cause of the change. Answer option a. This scenario describes a team that is moving from the Storming stage to the Norming stage. (A team typically needs to complete the Norming stage before it can reach the Performing stage.) The leadership styles that correspond to Storming and Norming are Coaching and Supporting, respectively. So here the team leader would have changed her style from Coaching to Supporting, rather than vice versa–but that switch would have been in response to the team, not the cause of the change .
Exam 5 | #10. _____ may reveal stakeholders’ needs or expectations for specific resources to be used on the project. This document should be considered in the process of acquiring the Resources |  | Resource calendar | Resource requirement | Resource management plan | Stakeholder register | Answer option d. | Answer option d. “Stakeholder register” Answer option d. “Stakeholder register”
Exam 5 | #11. _____ includes information on how a seller is performing by comparing the deliverables received, the technical performance achieved, and the costs incurred and accepted against the SOW budget for the work performed. |  | Closed procurements | Procurement documentation updates | Work performance information | Change requests | Answer option c. | Answer option c. “Work performance information” Answer option c. “Work performance information”
Exam 5 | #12. At the start of release planning, the team and product owner collaboratively explored the conditions of satisfaction. Common factors in product owner’s conditions of satisfaction included scope, schedule, and budget. Why was quality not included in this list? |  | Quality is not considered as one of the common factors in the product owner's conditions of satisfaction. | Quality is usually negotiated during iteration planning. | Quality is usually negotiated between the Scrum Master and the Product Owner, not the Team. | Agile teams typically prefer to treat quality as non-negotiable. | Answer option d. | Answer option d. ” Agile treats quality as non-negotiable”. In traditional project management quality is a negotiable factor, and the Project Manager is allowed to negotiate required quality when needed. Answer option d. ” Agile treats quality as non-negotiable”. In traditional project management quality is a negotiable factor, and the Project Manager is allowed to negotiate required quality when needed.
Exam 5 | #13. Your project is behind schedule. You decided to start some planned activities in parallel to compensate for the delay. This is an example of _____ . |  | Rework | Crashing | Overtime | Fast Tracking | Answer option d. | Answer option d. “Fast Tracking”. A schedule compression technique in which activities or phases are normally done in a sequence is performed in parallel for at least a portion of their duration. Answer option d. “Fast Tracking”. A schedule compression technique in which activities or phases are normally done in a sequence is performed in parallel for at least a portion of their duration.
Exam 5 | #14. Elements of the organizational process assets that can be updated as a result of the Conduct Procurements process include _____ . |  | Financial policies and procedures regarding invoicing and payment processes | Listings of prospective and prequalified sellers | Contract management systems | Local laws and regulations regarding procurements | Answer option b. | Answer option b. “Listings of prospective and prequalified sellers” Answer option b. “Listings of prospective and prequalified sellers”
Exam 5 | #15. Harold is working in a multinational organization. There are several departments and each department has specialized resources. Project managers are under PMO. Software developers are in the software development department, test engineers belong to the test department and analysts are in the analysis department. Harold has been assigned to a new project and he needs to acquire internal resources through _____ . |  | Procurement processes | Functional managers | Subcontractors | PMO | Answer option b. | Answer option b. ”Functional managers”. Internal resources are under the control of functional and resource managers. Answer option b. ”Functional managers”. Internal resources are under the control of functional and resource managers.
Exam 5 | #16. Alex is working on a project that aims to increase stockholders’ equity. Which type of benefits is this for the organization? |  | Direct | Tangible | Intangible | Indirect | Answer option b. | Answer option b. “Tangible”. Because it will increase the equity value, which is monetary & tangible. Answer option b. “Tangible”. Because it will increase the equity value, which is monetary & tangible.
Exam 5 | #17. A project manager uses a project team composed of various team members from different departments within the organization. His authority is, however, limited. Which type of project organization is this? |  | Departmental | Functional | Interrelated | Organic or flexible | Answer option b. | Answer option b. “Functional” organization is an organization where the Project Manager has team members from different departments but has only limited authority. Answer option b. “Functional” organization is an organization where the Project Manager has team members from different departments but has only limited authority.
Exam 5 | #18. As the project team studied the current engagement level of the customer’s service manager, they found that his knowledge about the project and its objectives are unclear, which led him to believe that the project represents a challenge to his department. At which engagement level does he stand? |  | Unaware | Resistant | Neutral | Cannot say | Answer option b. | Answer option b. ” Resistant” since he is aware but sees the project as a threat (challenge). Answer option b. ” Resistant” since he is aware but sees the project as a threat (challenge).
Exam 5 | #19. Chris is leading a project team where its members are interdependent and work through issues smoothly and effectively. At which stage does this team stand? |  | Forming | Storming | Norming | Performing | Answer option d. | Answer option d. “Performing”. Teams that reach the performing stage function as a well-organized unit. They are interdependent and work through issues smoothly and effectively. Answer option d. “Performing”. Teams that reach the performing stage function as a well-organized unit. They are interdependent and work through issues smoothly and effectively.
Exam 5 | #20. Brenda is Sugar Soda Corp’s PMO Director and is meeting with the IT Steering Committee team to discuss a new project approach that her team is using. She explains that “This approach requires the project teams to iterate repeatedly to create deliverables. The benefits include the receiving of early feedback, customer confidence, and customer visibility. In addition, the company often receives an early ROI because work is delivered early, and the highest value work is delivered first.” The CEO asks Brenda to explain which approach she is describing. Brenda’s answer is: |  | Predictive | Iterative | Incremental | Agile | Answer option d. | Answer option d. Because her approach includes both iterative and incremental deliveries, it is considered an agile approach. Answer option d. Because her approach includes both iterative and incremental deliveries, it is considered an agile approach.
Exam 5 | #21. You are the Scrum Master in an Agile organization and a team member who recently joined reaches out to you during the Sprint and says, “I want to pull more work from the queue because I think I will be done with my current story very soon.” You tell her our schedule approach does not work this way because we use: |  | On-demand scheduling as an approach to schedule the work as we split the stories equally among the team members. | Iterative Scheduling as in rolling wave format, where stories with the highest priority get completed first. | Kanban boards because we like to visualize all the tasks then split the work based on everyone’s level of expertise. | Critical Path Method because some user stories are linear in structure and thus pulling from the queue is not available. | Answer option b. | Answer option b. Iterative scheduling is characterized by progressive elaboration where the user stories are planned in rolling wave technique. Unlike On-demand scheduling where team members can pull work from the queue based on their availability. Kanban and Critical Path Method are not associated with scheduling in Agile or Scrum. Answer option b. Iterative scheduling is characterized by progressive elaboration where the user stories are planned in rolling wave technique. Unlike On-demand scheduling where team members can pull work from the queue based on their availability. Kanban and Critical Path Method are not associated with scheduling in Agile or Scrum.
Exam 5 | #22. Jack is developing the project charter. He wants to understand the necessary information from a business standpoint of how the expected outcomes of the project justify the required investment. Which document should he review? |  | Project Milestones | Business case | Agreements | Organizational process assets | Answer option b. | Answer option b. ”Business case” describes the necessary information from a business standpoint to determine whether the expected outcomes of the project justify the required investment. Answer option b. ”Business case” describes the necessary information from a business standpoint to determine whether the expected outcomes of the project justify the required investment.
Exam 5 | #23. Sugar & Pepper Co. is an international company with several offices around the world. They acquired a new company in Brazil to enter this new market. Sugar & Pepper Co. initiated a new project to adapt the company's culture to the local norms. This is an example of _____ . |  | Meet regulatory, legal, or social requirements | Satisfy stakeholder requests or needs | Implement or change business or technological strategies | Create, improve, or fix products, processes, or services | Answer option a. | Answer option a. ”Meet regulatory, legal or social requirements” the case describes a social requirement. Answer option a. ”Meet regulatory, legal or social requirements” the case describes a social requirement.
Exam 5 | #24. A software development company is expanding its operations to meet increasing market demand. The employees are working on two or three agile teams, each working on different new software products. Work is declining and defects are increasing. In which two ways can the project manager help the agile teams improve their work? |  | Perform root-cause analysis in the next retrospectives. | Influence the product owners to right-size their portfolios. | Organize dedicated teams to monitor the work. | Appoint dedicated test teams to offload the agile teams. | Answer option a. | Answer option a. Perform root-cause analysis in the next retrospectives. Answer option a. Perform root-cause analysis in the next retrospectives.
Exam 5 | #25. A project manager is analyzing the influence of the results from the previous audits on the management quality process. Under which category do these elements fall? |  | Emerging practices | Enterprise environmental factors | Organizational process assets | Expert judgment | Answer option c. | Answer option c. “Organizational process assets”. OPA =The plans, processes, policies, procedures and knowledge base specific to, developed by, and used by, the organization – and which you actually use in the management of the project. Most organizations have developed a range of templates, proforma contracts, plans, procedures, registers and assessment tools to assist in the management of the project. Organizations have also acquired knowledge in the form of lessons learned and the organization’s knowledge base that can be very useful. Answer option c. “Organizational process assets”. OPA =The plans, processes, policies, procedures and knowledge base specific to, developed by, and used by, the organization – and which you actually use in the management of the project. Most organizations have developed a range of templates, proforma contracts, plans, procedures, registers and assessment tools to assist in the management of the project. Organizations have also acquired knowledge in the form of lessons learned and the organization’s knowledge base that can be very useful.
Exam 5 | #26. A project manager in the process of implementing the Risk Responses. He is reviewing the specified risk thresholds for the project based on the risk appetite of the key stakeholders. Which input is he reviewing? |  | Risk management plan | Risk register | Risk report | Issue log | Answer option a. | Answer option a. “Risk management plan”. Answer option a. “Risk management plan”.
Exam 5 | #27. Dan is managing the Stakeholder engagement. Which of the following documents should he include as input? |  | Project charter | Change log | Business case | Assumptions log | Answer option b. | Answer option b. “Change log” Answer option b. “Change log”
Exam 5 | #28. Jack is designing his project phases. Which of the following should he not consider as an attribute to describe the phases in a life cycle? |  | Feasibility study | Design | Implementation | Resource requirements | Answer option d. | Answer option d. “Resource requirements” is not a name for a project phase; “Feasibility study” (Answer option a.), “Design” (Answer option b.), and “Implementation” (Answer option c.) are examples of phase names. Answer option d. “Resource requirements” is not a name for a project phase; “Feasibility study” (Answer option a.), “Design” (Answer option b.), and “Implementation” (Answer option c.) are examples of phase names.
Exam 5 | #29. Ben is leading an agile project team in a software development project. He was assigned to this team two months into the Scrum project. As Ben looks at the prior deliveries, he sees the following: Sprint 1: 10 days; 22 Story Points Sprint 2: 10 days; 34 Story Points Sprint 3: 10 days; 33 Story Points Sprint 4: 20 days; 50 Story Points Sprint 5: 10 days; 16 Story Points Sprint 6: 5 days; 16 Story Points Sprint 7: In progress The team has been criticized recently for the delivery of inconsistent results. Which Sprint(s) concern Ben? |  | Sprint 4. The team has a run rate of 3.3 – 3.5 Story Points per day. A 20-day Sprint should have produced closer to 70 Story Points. | Sprints 1, 5 and 6: Each of these Sprints Sprint 5 has a significantly lower run rate than the other three. | Sprint 6. Sprints should always be at least 10 days. | Sprints 4 and 6. Within Scrum projects, each Sprint should be the same length. | Answer option d. | Answer option d. All Sprints should be of equal length to create stability. Answer option d. All Sprints should be of equal length to create stability.
Exam 5 | #30. A project manager aims to determine whether to acquire goods and services from outside the project and, if so, what to acquire as well as how and when to acquire them. Which process should he perform? |  | Plan Procurement Management | Manage Procurement | Control Procurement | Define scope | Answer option a. | Answer option a. “Plan Procurement Management”. Plan Procurement Management is the process of documenting project procurement decisions, specifying the approach, and identifying potential sellers. The key benefit of this process is that it determines whether to acquire goods and services from outside the project and, if so, what to acquire as well as how and when to acquire them. Answer option a. “Plan Procurement Management”. Plan Procurement Management is the process of documenting project procurement decisions, specifying the approach, and identifying potential sellers. The key benefit of this process is that it determines whether to acquire goods and services from outside the project and, if so, what to acquire as well as how and when to acquire them.
Exam 5 | #31. You are the Scrum Master of a well-motivated Scrum team. The development team is working on a project to develop an app that captures the top ten (10) most read articles. As the focus is on the app itself not the nature of the articles, you believe the testing should be performed on articles that target NBA news. You would like to gauge the team’s interest in this approach with “Yes or no” answers using “Thumbs up or down.” Per Scrum, what is this technique called: |  | Roman Voting | DOT Voting | Pooling | Scrum Voting | Answer option a. | Answer option a. Per Scrum framework, Roman Voting is a fast and easy technique used in group decision making if the question is expecting Yes/No answers. It works by using the hands to give a thumbs up or thumbs down to indicate agreement or disagreement. Answer option a. Per Scrum framework, Roman Voting is a fast and easy technique used in group decision making if the question is expecting Yes/No answers. It works by using the hands to give a thumbs up or thumbs down to indicate agreement or disagreement.
Exam 5 | #32. Which scope statement element includes the instructions, manuals and other project related documentation? |  | Product scope description | Project deliverables | Acceptance criteria | Project exclusions | Answer option b | . “Project Deliverables” Lists out the deliverables the team needs to produce in order to meet business objectives. This can include the product itself, instruction and installation manuals, marketing materials, press releases, advertising campaigns and other documents.
Exam 5 | #33. Jack is working on the Project Knowledge management process and seeking to use effective tools and techniques to share tacit knowledge within the project. Which of the following is not one of these tools and techniques? |  | Communities of practice | Knowledge fairs and cafés | Project management information system | Workshops | Answer option c. | Answer option c. The best answer is “Project management information system” (Answer option c.).PMIS is an example of Explicit Knowledge. It can be found in different forms in a project, such as in instruction manuals, specification documents or process documents that can be used by project team members. “Communities of practice” (Answer option a.), “Knowledge fairs and cafés” (Answer option b.), and “Workshops” (Answer option d.) are all models of the development life cycle. Answer option c. The best answer is “ Project management information system ” (Answer option c.) .PMIS is an example of Explicit Knowledge. It can be found in different forms in a project, such as in instruction manuals, specification documents or process documents that can be used by project team members. “ Communities of practice ” (Answer option a.), “ Knowledge fairs and cafés ” (Answer option b.), and “ Workshops ” (Answer option d.) are all models of the development life cycle .
Exam 5 | #34. During a monthly Quality Review Meeting, the Project Manager is concerned about his execution team being unable to meet the acceptance criteria specified by the Customer. There have been a lot of reworks and even some deliverables had been scrapped as a result. This situation is having a bad impact on the image of the performing organization among different stakeholders. The cost associated with such instances is called: |  | Cost of Performance | Cost of Non-performance | Cost of Conformance | Cost of Non-conformance | Answer option d. | Answer option d. “Cost of Non-conformance” includes Internal Failure Costs (Failures found by the project) like Rework and Scrap. Answer option d. “Cost of Non-conformance” includes Internal Failure Costs (Failures found by the project) like Rework and Scrap.
Exam 5 | #35. You are in charge of a super-advanced technology-based project that will help the customers get real-time data from anywhere in the world. You are currently performing the monitor and control project work. Which project document or plan should you use to check if predetermined quality standards are in compliance with the current legal restrictions that are applied for the specific industry and your project? |  | Project charter | Project management plan | Milestone list | Project schedule | Answer option b.” | Answer option b.” Project management plan”. Remember that the Quality Management Plan is also part of the Project Management Plan. The Quality plan has information about what quality standards are applicable and quality metrics that help determine the deviations from the quality standards during Monitoring & Controlling. Answer option b.” Project management plan”. Remember that the Quality Management Plan is also part of the Project Management Plan. The Quality plan has information about what quality standards are applicable and quality metrics that help determine the deviations from the quality standards during Monitoring & Controlling.
Exam 5 | #36. Lucas is working on closing his project. He wants to make sure that all addressed stakeholders’ concerns are closed. Which document should he review? |  | Stakeholder register | Change log | Issue log | Risk register | Answer option c. | Answer option c. “Issue log” Answer option c. “Issue log”
Exam 5 | #37. You have just developed your project plan when the sponsor asked you to accelerate the project delivery date by one month. The sponsor is fine with the increase of the costs and the resources are already available within the organization. Which schedule compression technique would you use? |  | Resource smoothing | Resource optimization | Crashing | Fast-tracking | Answer option c. | Answer option c. “Crashing” since incremental costs and resources are available. Answer option c. “Crashing” since incremental costs and resources are available.
Exam 5 | #38. Rebecca works for a large training organization, and she needs to train junior executives in active listening. She observes that some of the attendees are clearly not engaging during class and they are not completing their daily feedback. Despite the fact that it has been quite a demotivating training, she believes this is an important lesson she has learned. She wants to tell the project manager (who is also a trainer), but the PM doesn’t seem to want to listen. What should Rebecca do? |  | Keep calling the PM until he listens because only a project manager or sponsor can record lessons learned | Write the lesson learned in an email | Record the lesson learned in the lessons learned repository | Record the lesson learned in the lessons learned register | Answer option d. | Answer option d. “Record the lesson learned in the lessons learned register”. Any stakeholder can record lessons learned. The repository holds lessons learned from previous projects and it will be updated with the lessons learned from this project once the project is finished. Answer option d. “Record the lesson learned in the lessons learned register”. Any stakeholder can record lessons learned. The repository holds lessons learned from previous projects and it will be updated with the lessons learned from this project once the project is finished.
Exam 5 | #39. Alex is managing a project where quality is essential. He wants to identify if project activities comply with organizational /project policies, processes, and procedures. Which of the following can Alex use? |  | Audits | Inspections | Performance reviews | Trend analysis | Answer option a. | Answer option a. “Audits”. An audit is a structured, independent process used to determine if project activities comply with organizational and project policies, processes, and procedures. Answer option a. “Audits”. An audit is a structured, independent process used to determine if project activities comply with organizational and project policies, processes, and procedures.
Exam 5 | #40. Alex is elaborating on the final project reports to meet the organizational policies’ requirements. What type of activities is he working on? |  | Activities which are necessary to satisfy completion and exit criteria | Activities which are related to the completion of the contractual agreements | Activities which are related to document the reasons for project termination | Other activities | Answer option a.” | Answer option a.” Activities necessary to satisfy completion and exit criteria” Answer option a.” Activities necessary to satisfy completion and exit criteria”
Exam 5 | #41. Dino Co. appointed Jack to lead delivery, growth, maturity, and the retirement of its latest CRM solution. Which type of lifecycle will he manage? |  | Predictive life cycle | Adaptive life cycle | Hybrid life cycle | Product life cycle | Answer option d. | Answer option d. “Product life cycle”. Delivery, growth, maturity, and retirement are phases of a product development lifecycle. Answer option d. “Product life cycle”. Delivery, growth, maturity, and retirement are phases of a product development lifecycle.
Exam 5 | #42. You are the Scrum Master in an Agile organization. You like to plan all Scrum events according to the framework. Every time a new Sprint is complete (Typically a 1-month Sprint), you schedule a Sprint Retrospective with the Product Owner and the development team to discuss what went right and wrong during the previous Sprint. It is an opportunity for the entire team to improve and learn from mistakes yet you do not allow the Retrospective to exceed: |  | Four (4) hours | Three (3) hours | One (1) hour | It is open ended, depending on the deliverable. | Answer option b. | Answer option b. Per Scrum framework, the Sprint Retrospective meeting must occur after the Sprint review meeting is complete. The Sprint Retro is a review of the past period of work and an opportunity for the entire team to collect feedback and understand ways to improve. Answer option b. Per Scrum framework, the Sprint Retrospective meeting must occur after the Sprint review meeting is complete. The Sprint Retro is a review of the past period of work and an opportunity for the entire team to collect feedback and understand ways to improve.
Exam 5 | #43. A negative risk is becoming a huge concern for you. Being the Project Manager, you have discussed it multiple times with your team members and two vendors on your project site. You have already communicated to the sponsor that this threat is outside the project scope. The sponsor has not only agreed to your view but also, has asked the managers working at the program level to look into it. Which risk response strategy was used here? |  | Escalate | Transfer | Avoid | Mitigate | Answer option a. | Answer option a. Escalation is appropriate when the project team or the project sponsor agrees that a threat is outside the scope of the project or that the proposed response would exceed the Project Manager’s authority. Escalated risks are managed at the program level, portfolio level, or other relevant parts of the organization. Answer option a. Escalation is appropriate when the project team or the project sponsor agrees that a threat is outside the scope of the project or that the proposed response would exceed the Project Manager’s authority. Escalated risks are managed at the program level, portfolio level, or other relevant parts of the organization.
Exam 5 | #44. The agile team detected a major software defect after its release and began working on a correction. It was discovered that the defective release was developed previously through a predictive track, and this caused a field test to fail. Which measure would be most effective to prevent similar problems in the future? |  | Run the same unit tests in the agile lab and in the field sites. | Send project-wide issue log updates via instant messaging. | Ensure that retrospectives are shared with the predictive team. | Re-plan the software track into the predictive schedule. | Answer option b. | Answer option b. Send project-wide issue log updates via instant messaging. Answer option b. Send project-wide issue log updates via instant messaging.
Exam 5 | #45. A project manager is performing the monitor risks process and wants to review the data of the status of the implemented risk responses, risks that happened, active risks, and closed-out risks. Which of the following would contain this information? |  | Risk register | Risk report | Work performance data | Work performance reports | Answer option c. | Answer option c. “Work performance data” Answer option c. “Work performance data”
Exam 5 | #46. A project activity’s pessimistic estimate is 35 days, the optimistic estimate is 25 days, and the most likely estimate is 32 days. Based on beta distribution, what is the activity duration? |  | 30 | 31.33 | 32 | 32.33 | Answer option b. | “31.33” Beta distribution. cE = (cO 4cM cP) / 6= 25 4*32 35=31.33
Exam 5 | #47. Sam is performing the monitor risk process. He wants to review the roles and responsibilities in the monitoring process and reporting formats. Which input should he review? |  | Issue log | Risk management plan | Risk report | Risk register | Answer option b. | Answer option b. “Risk management plan”. Answer option b. “Risk management plan”.
Exam 5 | #48. Your project is running smoothly and almost as per the plan. For an upcoming important meeting, your team members are not available at the head office. 3 of them are currently in Brazil and 2 of them are in Oman. The rest of the team is available to attend the meeting as they are working from the headquarters. Input from all team members is necessary. You can not delay this meeting as this would delay a couple of critical activities on the schedule. How will you avoid this delay? |  | Go ahead with just the members available at head office. | Replace the team members. | Write to the change control board. | Create a Virtual Team where you include all members. | Answer option d. | Answer option d. The virtual team model makes it possible to form teams of people from the same organization who live in widespread geographic areas. Answer option d. The virtual team model makes it possible to form teams of people from the same organization who live in widespread geographic areas.
Exam 5 | #49. _____ is the use of communication technology to bring a team together to fulfill their shared project goals with little face to face interaction. |  | Virtual teams | Colocation | Communication technology | Communication model | Answer option a. | Answer option a. “Virtual teams” Answer option a. “Virtual teams”
Exam 5 | #50. The project team created a web-based knowledgebase where the team can share information, updates, and can collaborate to brainstorm for solutions and ideas using its discussion board. Which communication method is the team using? |  | Push communication | Pull communication | Interactive communication | Public communication | Answer option c. | Answer option c. “Interactive communication” the communication method involves two or more participants in the communication. Answer option c. “Interactive communication” the communication method involves two or more participants in the communication.
Exam 5 | #51. While performing the Implement Risk Responses process, Jack wants to review the roles and responsibilities of the project team members and other stakeholders for risk management. Which input should he review? |  | Risk management plan | Risk register | Risk report | Issue log | Answer option a. | Answer option a. “Risk management plan” Answer option a. “Risk management plan”
Exam 5 | #52. Sam’s project team shows a tendency to work together and adjust their work habits and behaviors to support each other. At which stage does this team stand? |  | Forming | Storming | Norming | Performing | Answer option c. | Answer option c. “Norming” Answer option c. “Norming”
Exam 5 | #53. You are about to complete developing a Project Management Plan for your project. Which is not an expected component of the output of the project management plan? |  | Performance measurement baseline | Development approach | Management reviews | Project schedule | Answer option d. | Answer option d. “Project schedule” is a project document, not a component of the project management plan. Answer option d. “Project schedule” is a project document, not a component of the project management plan.
Exam 5 | #54. Megan and Tom are responsible for different activities in a project to set up an environmentally friendly packaging material. The project also includes a research and development component to test and to pack the materials for the packaging project. The project is progressing great, largely due to Megan’s problem-solving skills. Megan knows that she needs to focus on building and maintaining the team. She is mainly focused on: |  | Conflict management | Negotiations | Pushing the team to perform | Setting clear objectives | Answer option d. | Answer option d. “Setting clear objectives”. Megan knows that there are 12 areas of focus for building and maintaining the team. Setting clear objectives is one of the most important ones. Others are standards, safety requirements, size of the team, team spirit, discipline, consultation, representation, briefing, support. Answer option d. “Setting clear objectives”. Megan knows that there are 12 areas of focus for building and maintaining the team. Setting clear objectives is one of the most important ones. Others are standards, safety requirements, size of the team, team spirit, discipline, consultation, representation, briefing, support .
Exam 5 | #55. During the project execution, some of the critical resources of the project left the company, so there were only a limited number of available resources. You need to adjust the schedule to make it as efficient as possible to reduce the need for hiring external resources. Which schedule technique would you use? |  | Resource smoothing | Resource leveling | Crashing | Fast-tracking | Answer option a. | Answer option a. “Resource smoothing” can be used to reduce the number of required resources without affecting the critical path. Answer option a. “Resource smoothing” can be used to reduce the number of required resources without affecting the critical path.
Exam 5 | #56. You are managing a construction project. There are certain steps that each employee should follow when entering the construction zone and when leaving the construction zone. The civil engineer and safety engineer in your project team listed the steps in a tally sheet that each person must follow. This is also known as ____ . |  | Spreadsheets | Check box | Check sheets | All of the above | Answer option c. | Answer option c. ”Check sheets” are known as tally sheets as well. Answer option c. ”Check sheets” are known as tally sheets as well.
Exam 5 | #57. Which of the following is the name of a graph that shows the relationship between two variables (usually the first variable is independent, and the second variable is dependent on the first variable)? |  | Matrix Diagram | Scatter Diagram | Affinity Diagram | Why-why Diagram | Answer option b. | Answer option b. “Scatter Diagram”. A scatter diagram is primarily used when you want to determine if a pair of numerical data points have a cause-and-effect relationship with each other. Answer option b. “Scatter Diagram”. A scatter diagram is primarily used when you want to determine if a pair of numerical data points have a cause-and-effect relationship with each other.
Exam 5 | #58. Lisa is a Project Manager managing a hybrid software development project that is developing a new Ecommerce website. The Sponsor asks her to provide a high-level summary timeline of the release. What should Lisa do next? |  | Perform risk analysis. | Ask the Sponsor to provide this information. | Conduct a release planning meeting. | Work with the Scrum Master to discuss the summary in the next daily standup. | Answer option c. | Answer option c. The release planning meeting is held at the beginning of each iteration and attended by all members of the team. Agile release planning provides a high-level summary timeline of the release schedule typically ranging between 6 and 12 months. The inputs to release planning are prioritized features, tasks estimated in hours by team velocity measurements/work capacity, and product roadmap. The output from the release planning meeting is a release plan, representing how much scope the team intends to deliver by a given deadline. Option D is incorrect – the daily standup is an internal team meeting for the Development team only. Answer option c. The release planning meeting is held at the beginning of each iteration and attended by all members of the team. Agile release planning provides a high-level summary timeline of the release schedule typically ranging between 6 and 12 months. The inputs to release planning are prioritized features, tasks estimated in hours by team velocity measurements/work capacity, and product roadmap. The output from the release planning meeting is a release plan, representing how much scope the team intends to deliver by a given deadline. Option D is incorrect – the daily standup is an internal team meeting for the Development team only.
Exam 5 | #59. A Project Manager is well known for his skills in successfully guiding his team. He is currently heading a project which is going through estimation of the cost of different activities. A junior team member, Charlie, approaches the PM with questions on how to estimate the cost of different components related to design. The PM explains to Charlie that there is a rule of thumb to calculate the cost of design, saying that every component of the design will cost 5,000 USD. So, he asks Charlie to just multiply the number of components by 5,000 USD to have the estimate for the design. Which type of estimation is this? |  | Parametric Estimation | Analogous Estimation | Three-point Estimation | Bottom-up Estimation | Answer option a. | Answer option a. “Parametric Estimation” Parametric estimation uses a statistical relationship between historical data and other variables (e.g., square footage in construction) to calculate an estimate for activity parameters, such as cost, budget, and duration. Answer option a. “Parametric Estimation” Parametric estimation uses a statistical relationship between historical data and other variables (e.g., square footage in construction) to calculate an estimate for activity parameters, such as cost, budget, and duration.
Exam 5 | #60. You are performing the stakeholder analysis and investigating which stakeholders have a legal title to an asset or a property. Which stakeholder stake are you studying? |  | Interest | Rights | Ownership | Contribution | Answer option c. | Answer option c. “Ownership” Answer option c. “Ownership”
Exam 5 | #61. The project manager needs to build a specific and well-defined sports park. He likes to plan everything upfront and follow the waterfall method. However, the customer doesn’t want everything fixed from the beginning, as she may change her mind once the project is underway. What type of project life cycle should the project manager use? |  | Predictive | Cumulative | Adaptive | Explicative | Answer option c. | Answer option c. ”Adaptive”. Adaptive. In an adaptive or agile life cycle, the deliverables are developed over multiple iterations where a detailed scope is defined and approved for each iteration when it begins. Answer option c. ”Adaptive”. Adaptive. In an adaptive or agile life cycle, the deliverables are developed over multiple iterations where a detailed scope is defined and approved for each iteration when it begins.
Exam 5 | #62. You’re managing a team of ten help desk associates who handle customer incidents on a global service desk. The current system of work emphasizes that developers pull work from the queue, and each developer can have no more than three tickets at a time. Besides, anyone in the organization can see the tickets assigned to each individual. What method are you currently using? |  | Kanban | Dynamic Systems Development | Xtreme Programming | Kaizen | Answer option a. | Answer option a. “Kanban”. Kanban boards enable and promote the visualization and flow of the work through a system that everyone can see. The principle of pulling single items through the process continuously and limiting work in progress to optimize flow is an integral part of the method. Answer option a. “Kanban”. Kanban boards enable and promote the visualization and flow of the work through a system that everyone can see. The principle of pulling single items through the process continuously and limiting work in progress to optimize flow is an integral part of the method.
Exam 5 | #63. While developing the project plan, you needed to reduce your project delivery time due to management requirements. The project is internal, and there is tolerance for some level of quality errors, but there is no extra budget. Which schedule compression technique would you use? |  | Resource smoothing | Resource optimization | Crashing | Fast-tracking | Answer option d. | Answer option d. “Fast-tracking”. Crashing is not possible since there is no extra budget and there is tolerance for quality issues that may occur by fast-tracking. Answer option d. “Fast-tracking”. Crashing is not possible since there is no extra budget and there is tolerance for quality issues that may occur by fast-tracking.
Exam 5 | #64. Christina is a Project Manager working on a Hybrid project using both Waterfall and Agile principles at Company XYZ. At the end of the fourth sprint (Iteration), the sponsor informs her that the project is not performing as planned. What should she do to improve the performance of the next iterations? |  | Hold a retrospective session with all the stakeholders. | Hold a daily standup meeting with the customer to discuss the issue. | Engage the sponsor to assist with finding a solution. | Conduct a backlog refinement session. | Answer option a. | Answer option a. Conducting retrospectives are used to record lessons learned, correct processes, and improve as an Agile team. Held at the end of a Sprint (Iteration), this meeting is held at the end of the iteration with all stakeholders, cross-functional development team members, Scrum master, and Product Owner to discuss and review the overall progress of work, changes that are needed to the schedule or scope, and ideas for improvements for the next Sprints (Iterations). Option B is incorrect – Customers are not involved in standups. Option C. is incorrect – this is the last thing a project manager may do in case he/she has failed to find solutions. Option D is incorrect – Refinement sessions are usually done in the middle of the Sprint (Iteration). Answer option a. Conducting retrospectives are used to record lessons learned, correct processes, and improve as an Agile team. Held at the end of a Sprint (Iteration), this meeting is held at the end of the iteration with all stakeholders, cross-functional development team members, Scrum master, and Product Owner to discuss and review the overall progress of work, changes that are needed to the schedule or scope, and ideas for improvements for the next Sprints (Iterations). Option B is incorrect – Customers are not involved in standups. Option C. is incorrect – this is the last thing a project manager may do in case he/she has failed to find solutions. Option D is incorrect – Refinement sessions are usually done in the middle of the Sprint (Iteration).
Exam 5 | #65. A visual practice that helps the team understand the customer experience by imagining what the customer process might look like in a way that encourages the team to think through what the customer finds valuable: |  | Value Stream Mapping | User Story Mapping | User Story Writing | Specification by Example (SBE) | Answer option b. | Answer option b. “User Story Mapping” is a visual practice for organizing work into a useful model to help understand the sets of high-value features to be created over time, identify omissions in the backlog, and effectively plan releases that deliver value to users. Answer option b. “User Story Mapping” is a visual practice for organizing work into a useful model to help understand the sets of high-value features to be created over time, identify omissions in the backlog, and effectively plan releases that deliver value to users .
Exam 5 | #66. Rupert has developed a quality management plan. He is trying to translate it into executable quality activities that incorporate the organization’s quality policies into the project. Which process is he performing? |  | Control Quality | Validate Quality | Manage Quality | Plan Quality Management | Answer option c. | Answer option c. “Manage Quality”. Manage Quality is the process of translating the quality management plan into executable quality activities that incorporate the organization’s quality policies into the project. The key benefit of this process is that it increases the probability of meeting the quality objectives, as well as identifying ineffective processes and causes of poor quality. Answer option c. “Manage Quality”. Manage Quality is the process of translating the quality management plan into executable quality activities that incorporate the organization’s quality policies into the project. The key benefit of this process is that it increases the probability of meeting the quality objectives, as well as identifying ineffective processes and causes of poor quality.
Exam 5 | #67. You are the Scrum Master of a well-motivated Scrum team. During the daily stand up, Brian raises his concerns about the new feature being implemented. He believes it should be done after the testing part is complete because the customer stated it is the least feature they care for; however, Jessica thinks it needs to be implemented before testing in order to evaluate the benefits. You decide to use the “Fist of Five” technique to gauge Jessica’s point of view; five team members show “Five Fingers”. What does this indicate: |  | They have major concerns with the proposal. | They are not in total agreement but will let it pass. | They are in complete agreement with the proposal. | They are in agreement but would like to discuss some minor issues. | Answer option c. | Answer option c. Per Scrum framework, five fingers indicate the member is in total agreement with the proposal. A closed fist indicates no agreement; 1 finger indicates major issues with the proposal; 2 fingers indicate some issues with the proposal; 3 fingers indicate not being in total agreement but won’t reject the proposal; 4 fingers indicate reasonable agreement with the proposal. Answer option c. Per Scrum framework, five fingers indicate the member is in total agreement with the proposal. A closed fist indicates no agreement; 1 finger indicates major issues with the proposal; 2 fingers indicate some issues with the proposal; 3 fingers indicate not being in total agreement but won’t reject the proposal; 4 fingers indicate reasonable agreement with the proposal.
Exam 5 | #68. You are directing and managing the project work and need to review the links between product requirements and the deliverables that would satisfy them. Which document should you review? |  | Requirements traceability matrix | Requirements documentation | Product scope | Requirements management plan | Answer option a. | Answer option a. “Requirements traceability matrix”. The requirements traceability matrix links product requirements from their origin to the deliverables that would satisfy them. Answer option a. “Requirements traceability matrix”. The requirements traceability matrix links product requirements from their origin to the deliverables that would satisfy them.
Exam 5 | #69. Your project team is investigating stakeholders’ risk appetites, and established communication channels that will influence the Plan Stakeholder Engagement process. Under which category do these elements fall? |  | Enterprise environmental factors | Organizational process assets | Expert judgment | None of the above | Answer option a. | Answer option a. “Enterprise environmental factors”. The enterprise environmental factors that can influence Plan Stakeholder Engagement include but are not limited to: Answer option a. “Enterprise environmental factors”. The enterprise environmental factors that can influence Plan Stakeholder Engagement include but are not limited to: Organizational culture, political climate, and governance framework. Personnel administration policies. Stakeholder risk appetites. Established communication channels. Global regional or local trends, practices, or habits; and Geographic distribution of facilities and resources. Organizational culture, political climate, and governance framework. Organizational culture, political climate, and governance framework. Personnel administration policies. Personnel administration policies. Stakeholder risk appetites. Stakeholder risk appetites. Established communication channels. Established communication channels. Global regional or local trends, practices, or habits; and Global regional or local trends, practices, or habits; and Geographic distribution of facilities and resources. Geographic distribution of facilities and resources.
Exam 5 | #70. A project manager is performing the close project process. He wants to measure whether the project achieved its targeted business value or not. Which document can help him to prepare this report? |  | Project charter | Business case | Benefits management plan | Both A and B | Answer option c. | Answer option c. “Benefits management plan”. The benefits management plan describes the expected plan for realizing the benefits explained in the business case. Answer option c. “Benefits management plan”. The benefits management plan describes the expected plan for realizing the benefits explained in the business case.
Exam 5 | #71. After a 3-week sprint during which your team has completed the sprint review, you conduct a retrospective. Your team discusses a number of defects that were captured during automated testing. After discussing various approaches to discover the cause of the defects, which method should your team decide on? |  | Six Sigma | Lean | Monte Carlo analysis | Value stream mapping | Answer option a. | Answer option a. ”Six Sigma” helps remove defects from a process (but it is not specifically mentioned in the PMBOK).The Six Sigma Methodology comprises five data-driven stages — Define, Measure, Analyze, Improve and Control (DMAIC). Lean removes waste, which increases efficiency. Monte Carlo analysis is used to determine probabilistic outcomes. Value stream mapping is used in Lean projects. Answer option a. ”Six Sigma” helps remove defects from a process (but it is not specifically mentioned in the PMBOK).The Six Sigma Methodology comprises five data-driven stages — Define, Measure, Analyze, Improve and Control (DMAIC). Lean removes waste, which increases efficiency. Monte Carlo analysis is used to determine probabilistic outcomes. Value stream mapping is used in Lean projects.
Exam 5 | #72. You have selected the seller for the procurement of raw material. You have to formalize it with a contractual agreement which will include the cost, quantity, delivery time, and payment method. Upon discussing it with your senior management, you have found out that the raw material has been bought by the company many times in previous projects. Which type of contract will be used for the procurement? |  | Cost-plus incentive fee | Fixed-price | Time and Material | Cost-plus fixed fee | Answer option b. | Answer option b. “Fixed-price” contracts are suitable when the type of work is predictable, and the requirements are well deﬁned and not likely to change. Answer option b. “Fixed-price” contracts are suitable when the type of work is predictable, and the requirements are well deﬁned and not likely to change.
Exam 5 | #73. Which of the following is a factor to consider during the process of acquiring the project resources? |  | The project sponsor should provide all critical resources as reassignment | The Project manager should negotiate and influence others to acquire the required resource | The Project manager should prioritize internal resources over external resources | All of the above | Answer option b. | Answer option b. “The Project manager should negotiate and influence others to acquire the required resource” Answer option b. “The Project manager should negotiate and influence others to acquire the required resource”
Exam 5 | #74. For the Monitor Communications process, corporate policies for social media, ethics, and security are _____ . |  | Emerging practice | Enterprise environmental factors | Organizational process assets | Expertise required for expert judgment | Answer option c. | Answer option c. ”Organizational process assets” Answer option c. ”Organizational process assets”
Exam 5 | #75. You are managing a large data transfer project. During your meeting with the database administrator, you discuss different ways to support quality compliance on the project. However, she says that she cannot change the policies and the procedures used in the project. If they are to be changed, she needs to discuss them with her Functional manager first. What type of compliance category is she talking about? |  | Internal compliance | External compliance | Resource compliance | All of the above | Answer option a. | Answer option a. “Internal compliance” relates to the organizational policies and procedures that need to be applied in every project. Answer option a. “Internal compliance” relates to the organizational policies and procedures that need to be applied in every project.
Exam 5 | #76. Holy is a Quality assurance manager in her pharmaceutical company. She is managing a highly sensitive project that has a very narrow margin of a process error. If the out of compliance data is not detected early, then the whole batch of new drugs will need to be scrapped. Which of the following tools are used to determine whether the new process is stable? |  | Burndown chart | Production chart | Flow chart | Control chart | Answer option d. | Answer option d. ”Control chart” is a graphical tool that is used to understand how the process is changed overtime. It indicates lower and upper control limits and helps in determining whether a new process is in statistical control or not. It helps determine whether the process is stable or not. Answer option d. ”Control chart” is a graphical tool that is used to understand how the process is changed overtime. It indicates lower and upper control limits and helps in determining whether a new process is in statistical control or not. It helps determine whether the process is stable or not.
Exam 5 | #77. Which of the following are the components of the scope baseline in Agile Projects? |  | Project Scope Statement and user stories | Work Breakdown Structure (WBS) and WBS dictionary | Project Scope Statement and Work Breakdown Structure (WBS) | Product Requirements and User Stories | Answer option d. | Answer option d. In Agile Projects, backlogs (including product requirements and user stories) are used as the scope baseline to reflect their current needs. WBS, Work Breakdown Structure are used for Predictive Projects. Answer option d. In Agile Projects, backlogs (including product requirements and user stories) are used as the scope baseline to reflect their current needs. WBS, Work Breakdown Structure are used for Predictive Projects.
Exam 5 | #78. A burndown chart shows that velocity is significantly lower than predicted. Therefore, there is a risk that the project will not be completed on time. What should the Agile Project Manager, Brian do to get the project back on track? |  | Crash the project with resources. | Facilitate a meeting between the Product Owner and the Development Team to discuss any corrective actions that can be taken. | Ask the Development Team to increase velocity to meet the project completion date. | Ask the sponsor to remove features from the Product backlog, then re-plan remaining sprints. | Answer option b. | Answer option b. In Agile frameworks, the Agile Project Manager’s goal is to remove obstacles that get in the way of completing the functionality that the team committed to in each Sprint(iteration). The best thing for the project manager to do is facilitate a meeting to discuss the best go-forward approach. The burndown chart is the first indicator that the iteration is either on or off track, and if the team recognizes that it overcommitted to the sprint, it will discuss this with the Product Owner to determine which low-priority feature should be dropped from the Sprint. Option A is incorrect, as crashing is used in traditional project management to get the project back on track. Answer option b. In Agile frameworks, the Agile Project Manager’s goal is to remove obstacles that get in the way of completing the functionality that the team committed to in each Sprint(iteration). The best thing for the project manager to do is facilitate a meeting to discuss the best go-forward approach. The burndown chart is the first indicator that the iteration is either on or off track, and if the team recognizes that it overcommitted to the sprint, it will discuss this with the Product Owner to determine which low-priority feature should be dropped from the Sprint. Option A is incorrect, as crashing is used in traditional project management to get the project back on track.
Exam 5 | #79. Liza is the project manager for creating a new type of infrared heat lamp for home use. The project successfully passed the first quality compliance tests, and now she is finalizing the project and doing the final tests before release. The project also gets a lot of media coverage, as it is a very useful product, easy to use, and has a lot of health benefits. The product is released and after a month you receive reports that the customers are reporting issues with the product. This is an example of: |  | External failure costs | Internal failure costs | Cost of doing business | Cost of non-conformance | Answer option a. | Answer option a. “External failure costs”. External failure costs are quality costs related to defects found they have been delivered to the customer. D is not correct, as it includes both internal and external failure costs. Answer option a. “External failure costs”. External failure costs are quality costs related to defects found they have been delivered to the customer. D is not correct, as it includes both internal and external failure costs.
Exam 5 | #80. You have been assigned by the Project Manager to bring together different stakeholders and subject matter experts to understand and record their expectations related to the 3 major deliverables of the project. Your role would be to moderate this discussion. Which technique would be most suitable in this case? |  | Interviews | Brainstorming | Focus Group | Survey | Answer option c. | Answer option c. “Focus Group”. Focus groups bring together prequaliﬁed stakeholders and subject matter experts to learn about their expectations and attitudes about a proposed product, service, or result. Answer option c. “Focus Group”. Focus groups bring together prequaliﬁed stakeholders and subject matter experts to learn about their expectations and attitudes about a proposed product, service, or result.
Exam 5 | #81. You analyze how personnel administration policies’ influence the process of managing stakeholders engagement. This element is an example of _____ . |  | Enterprise environmental factors | Organizational process assets | Expert judgment | None of the above | Answer option a. | Answer option a. “Enterprise environmental factors” The Enterprise Environment Factors (EEF) include all of the conditions and systems that are not under the control of the project team that influence, constrain or direct the work of the project. This includes things such as the existing internal and external infrastructure, computer systems, networks and software, naturally occurring phenomena (not just the climate) and legislation that exist, both inside and outside of the organization that will affect the way you manage your project. Answer option a. “Enterprise environmental factors” The Enterprise Environment Factors (EEF) include all of the conditions and systems that are not under the control of the project team that influence, constrain or direct the work of the project. This includes things such as the existing internal and external infrastructure, computer systems, networks and software, naturally occurring phenomena (not just the climate) and legislation that exist, both inside and outside of the organization that will affect the way you manage your project.
Exam 5 | #82. There are two major categories of influences within project environments. Which of the following is not an example of external EEF? |  | Legal Restrictions | Resource Availability | Commercial Database | Financial Considerations | Answer option b. | Answer option b. The best answer is “Resource Availability” (Answer option b.). It is an internal enterprise environmental factor. “Legal Restrictions” (Answer option a.), “Commercial Database” (Answer option c.), and “Financial Considerations” (Answer option d.) are all external EEFs. Answer option b. The best answer is “Resource Availability” (Answer option b.). It is an internal enterprise environmental factor. “Legal Restrictions” (Answer option a.), “Commercial Database” (Answer option c.), and “Financial Considerations” (Answer option d.) are all external EEFs.
Exam 5 | #83. You are just about to start the project. You have worked on many traditional projects and this will be your first agile project. You are assigned to manage the project with the project charter. You know that the organization has just signed the Project Charter. Who signs the Project Charter? |  | The Product Owner | The Project Manager | The Senior Management | The Scrum Master | Answer option c. | Answer option c. “The Senior Management”. The project charter is signed by the performing organization’s senior management. Answer option c. “The Senior Management”. The project charter is signed by the performing organization’s senior management.
Exam 5 | #84. Six agile teams are working on interrelated products. All teams start experiencing impediments and obstacles related to the work performed in other teams. How should the project manager address this problem? |  | Eliminate activity dependencies between teams. | Encourage use of collaboration tools instead of meetings. | Implement a Scrum of Scrums. | Merge into two large teams to reduce issues. | Answer option c. | Answer option c. Implement a Scrum of Scrums. Answer option c. Implement a Scrum of Scrums.
Exam 5 | #85. The consistent time-box of sprints allows the development team to establish a development rhythm. What are the other benefits of a sprint? |  | Short feedback loops | An ideal environment for production and continuous improvement. | Engaged customer who has input into the business decisions via the product owner. | All of the above | Answer option d. | Answer option d. Because of the feedback loop; the customer has input into the business decisions via the product owner. Therefore, customers are always engaged and get what they want. The self-organization and effective collaboration and coordination make it ideal for software production and continuous improvement. Answer option d. Because of the feedback loop; the customer has input into the business decisions via the product owner. Therefore, customers are always engaged and get what they want. The self-organization and effective collaboration and coordination make it ideal for software production and continuous improvement.
Exam 5 | #86. Graeme received a letter from one of his construction project suppliers that their stock of wood is not matching the project specifications. The lead-time for getting the correct material is two months. Graeme wants to apply a penalty on the supplier. To which of the following could Graeme refer? |  | Issue Log | Agreement | Project Charter | SLA | Answer option b. | Answer option b. “Agreement”. Agreements are legally binding and show the liabilities of the seller and buyer. Answer option b. “Agreement”. Agreements are legally binding and show the liabilities of the seller and buyer.
Exam 5 | #87. You are analyzing the influence of your company’s communication requirements on managing the project communications process. Which of the following are you examining now? |  | Enterprise environmental factors | Organizational process assets | Expert judgment | None of the above | Answer option b. | Answer option b. “Organizational process assets”. Answer option b. “Organizational process assets”.
Exam 5 | #88. After performing quantitative risk analysis, one of the risks ranked as high-priority with a high potential negative impact on the project. You are considering the option of isolating the project objectives from the risk’s impact if it were to occur. Which risk response are you considering? |  | Escalate | Transfer | Share | Avoid | Answer option d. | Answer option d. ”Avoid” involves changing some aspect of the project management plan or changing the objective that is in jeopardy in order to eliminate the threat entirely, reducing its probability of occurrence to zero. Answer option d. ”Avoid” involves changing some aspect of the project management plan or changing the objective that is in jeopardy in order to eliminate the threat entirely, reducing its probability of occurrence to zero.
Exam 5 | #89. During the new system testing, it was clear to the project team that the project performance is not aligned with the plan. The project manager directed the team to realign their work to the baseline. This is an example of _____ . |  | Corrective action | Preventive action | Defect repair | Updates | Answer option a. | Answer option a. “Corrective action” Answer option a. “Corrective action”
Exam 5 | #90. Carlos finds the project schedule variance is zero while the cost variance is negative. He consults another project manager for guidance. The project is _____ . |  | On schedule and over budget | Behind schedule and over budget | Ahead of schedule and on budget | On schedule and under budget | Answer option a. | Answer option a. “On schedule and over budget”. CV < 0 means over budget and SV = 0 means on schedule. Answer option a. “On schedule and over budget”. CV < 0 means over budget and SV = 0 means on schedule.
Exam 5 | #91. Zack is directing and managing project work. He wants to review the performance reports, deliverable status, and other information generated by the project. Which document should he review? |  | Change log | Issue log | Project communications | Communication management plan | Answer option c. | Answer option c. ”Project communications” include reports, memos, emails and other project communications that have been distributed to stakeholders as defined in the communications management plan and the stakeholder engagement plan. Answer option c. ”Project communications” include reports, memos, emails and other project communications that have been distributed to stakeholders as defined in the communications management plan and the stakeholder engagement plan.
Exam 5 | #92. You are studying the influence of monitoring and reporting methods and communication requirements on the Develop Project Management Plan process. Under which category do these elements fall? |  | Emerging practices | Enterprise environmental factors | Organizational process assets | Expert judgment | Answer option c. | Answer option c. “Organizational process assets”. Methods of reporting and monitoring can be specific to the project and the needs of the stakeholders; therefore they are considered an OPA. Answer option c. “Organizational process assets”. Methods of reporting and monitoring can be specific to the project and the needs of the stakeholders; therefore they are considered an OPA.
Exam 5 | #93. The completion of the product scope is measured against the: |  | Product Requirements | Project Plan | Project Scope Baseline | Requirement Traceability Matrix | Answer option a. | Answer option a. Completion of project scope is measured against the project management plan, while completion of the product scope is measured against the product requirements. Answer option a. Completion of project scope is measured against the project management plan, while completion of the product scope is measured against the product requirements.
Exam 5 | #94. You are managing a software project. While the team is performing internal validation activities, an error occurred in the software functionality. The technical team took immediate action to fix the error. Which type of actions did they take? |  | Corrective action | Preventive action | Defect repair | Updates | Answer option c. | Answer option c. “Defect repair”. An intentional activity to modify a nonconforming product or product component. Answer option c. “Defect repair”. An intentional activity to modify a nonconforming product or product component.
Exam 5 | #95. _____ is compared to actual results to determine if a change, corrective action, or preventive action is necessary. |  | Scope baseline | Requirements traceability matrix | Scope management plan | Change management plan | Answer option a. | Answer option a. “Scope baseline” Answer option a. “Scope baseline”
Exam 5 | #96. Anita is the scrum master on a new software development project, and they are beginning their first iteration (Sprint) of the project. For the current sprint, there are 35 user story points. Towards the end of the iteration (Sprint), Anita reviews the burnup chart and realizes that the team is falling behind on the work needed to be completed. What would be an excellent strategy to implement in order to improve the team’s efficiency for future iterations? |  | Put more pressure on the team members, so they complete work as planned. | Assess each team member's performance and replace those with low scores. | Do not do anything, as the team will grow and adapt. | Calculate the team's velocity (the sum of story point sizes for features completed in this iteration). | Answer option d. | Answer option d. By calculating the team’s velocity, Anita will be able to plan the subsequent iterations more precisely. Burnup charts serve as tools to improve planning to deliver accurate results, helping project managers make better work estimations. Answer option d. By calculating the team’s velocity, Anita will be able to plan the subsequent iterations more precisely. Burnup charts serve as tools to improve planning to deliver accurate results, helping project managers make better work estimations.
Exam 5 | #97. A project manager is analyzing progress reporting, required expenditure and disbursement reviews, accounting codes, and standard contract provisions to assess their influence on the Plan Cost Management process. Which category do these elements belong to? |  | Emerging practices | Enterprise environmental factors | Organizational process assets | Expert judgment | Answer option c. | Answer option c. “Organizational process assets” Answer option c. “Organizational process assets”
Exam 5 | #98. You are managing the Stakeholder engagement and aiming to stay in touch with the work and dispositions of the project team members and other stakeholders. Which technique would you use? |  | Conflict management | Cultural awareness | Observation/conversation | Political awareness | Answer option c. | Answer option c. ”Observation/conversation”. Observation and conversation enable the project manager to identify issues within the team, conflicts between people, or individual performance issues. Answer option c. ”Observation/conversation”. Observation and conversation enable the project manager to identify issues within the team, conflicts between people, or individual performance issues.
Exam 5 | #99. Betty is a project manager working for a tech company ABC, which develops mobile phones for the market. She is responsible for managing the communication/marketing plan and the production of a well-established model produced every quarter. Recently, management has decided to incorporate a new feature that will probably increase uncertainty, complexity, and risk to the manufacturing process. What is the best action Betty can take to approach this project? |  | Take a fully agile approach to manage uncertainty, complexity, and risk throughout all the stages of production. | Take a hybrid approach - using predictive methods for the marketing and communication; agile methods to manage the new feature's production. | Take a fully predictive approach as there is no need to manage the new uncertainty, complexity, and risk because it is a minor change to the production process. | Seek advice from the development team. | Answer option b. | A hybrid approach can be used to utilize Predictive approaches for the more predictable areas of the project (communication/marketing), and an Agile approach for the development of the new features.
Exam 5 | #100. CA production contracted WIB solutions to deliver an end-to-end supply chain solution to automate its supply chain management. Due to the nature of the project , the delivery agreement involves generally determined project scope at the early stage, but the time and cost estimates are routinely modified, as the project team gets better understanding about the solution requirements. Which development life cycles should be used? |  | Predictive life cycle | Adaptive life cycle | Iterative life cycle | Hybrid life cycle | Answer option c. | Answer option c. “Iterative life cycle”. A project life cycle where the project scope is generally determined early in the project life cycle, but time and cost estimates are routinely modified as the project team’s understanding of the product increases. Iterations develop the product through a series of repeated cycles, while increments successively add to the functionality of the product. Answer option c. “Iterative life cycle”. A project life cycle where the project scope is generally determined early in the project life cycle, but time and cost estimates are routinely modified as the project team’s understanding of the product increases. Iterations develop the product through a series of repeated cycles, while increments successively add to the functionality of the product.
Exam 5 | #101. _____ includes identifying work packages that are ahead or behind schedule, over or under budget or have resource or quality issues. |  | Inspection | Audits | Performance reviews | Trend analysis | Answer option c. | Answer option c. ”Performance reviews” Answer option c. ”Performance reviews”
Exam 5 | #102. You are in the process of implementing the Risk Responses. The CEO, a primary stakeholder, asks you what the status of the project’s risk is and if there is a high risk for any problems. He also wants to know what the potential impacts of risk implementation responses to the budget, timeline, and deliverables are. Which document will provide all this information? |  | Risk register | Risk report | Risk management plan | Issue log | Answer option b. | Answer option b. “Risk report”. Risk Report is a summary of risks that have occurred, actions taken for risks, and the potential impacts to budget, timeline, and deliverables. The difference between a risk register and a risk report is the register is an ongoing document used throughout the project to make informed risk management decisions whereas the risk report is a snapshot of risk management work in a given moment. Answer option b. “Risk report”. Risk Report is a summary of risks that have occurred, actions taken for risks, and the potential impacts to budget, timeline, and deliverables. The difference between a risk register and a risk report is the register is an ongoing document used throughout the project to make informed risk management decisions whereas the risk report is a snapshot of risk management work in a given moment.
Exam 5 | #103. A project team has been efficiently delivering results. The product upgrade they are working on must be released in three months or else a competitor’s new product will make theirs obsolete. Due to this reason, the product owner makes a sudden request for a revision of a feature. However, no one on the project team can do the work. The project sponsor is willing to extend the budget but cannot extend the schedule. What should the project manager do? |  | Meet the new demand by adding new resources with the required skills. | Recommend suspending the project until a firm decision can be made. | Discuss options with the project sponsor and choose the best one. | Challenge the request and initiate customer research to determine whether the new feature is desirable. | Answer option a. | Answer option a. In situations with time constraints, the most efficient option is expanding the team to include skilled resources. Training is also an option if resources have the capability to learn within the timeframe. The project sponsor has already made their request, so it is up to the project manager to realize it. Agile projects are designed to function in highly complex and unpredictable environments, so suspending or canceling the project hardly ever is an option. Answer option a. In situations with time constraints, the most efficient option is expanding the team to include skilled resources. Training is also an option if resources have the capability to learn within the timeframe. The project sponsor has already made their request, so it is up to the project manager to realize it. Agile projects are designed to function in highly complex and unpredictable environments, so suspending or canceling the project hardly ever is an option.
Exam 5 | #104. Alan is studying the organizational communication requirements and standardized guidelines that will be used during the process of managing the Stakeholder engagement. Under which category do these elements fall? |  | Enterprise environmental factors | Organizational process assets | Expert judgment | None of the above | Answer option b. | Answer option b. “Organizational process assets”. OPA =The plans, processes, policies, procedures and knowledge base specific to, developed by, and used by, the organization – and which you actually use in the management of the project. Most organizations have developed a range of templates, proforma contracts, plans, procedures, registers and assessment tools to assist in the management of the project. Organizations have also acquired knowledge in the form of lessons learned and the organization’s knowledge base that can be very useful. Answer option b. “Organizational process assets”. OPA =The plans, processes, policies, procedures and knowledge base specific to, developed by, and used by, the organization – and which you actually use in the management of the project. Most organizations have developed a range of templates, proforma contracts, plans, procedures, registers and assessment tools to assist in the management of the project. Organizations have also acquired knowledge in the form of lessons learned and the organization’s knowledge base that can be very useful.
Exam 5 | #105. Which scope statement element progressively elaborates the characteristics of the features described in the project charter and requirements documentation? |  | Product scope description | Deliverables | Acceptance criteria | Project exclusions | Answer option a. | Answer option a. “Product scope description”. Progressively elaborates the characteristics of the product, service, or result described in the project charter and requirements documentation. Answer option a. “Product scope description”. Progressively elaborates the characteristics of the product, service, or result described in the project charter and requirements documentation.
Exam 5 | #106. You are managing a megaproject. The project team size will be extremely large. To manage the project effectively, you decided to use the resource management and work authorization platform, which will facilitate your team work-assignment. Which evolving trend in integration processes will you adopt in this case? |  | Use of automated tools | Expanding the project manager’s responsibilities | Hybrid methodologies | Expanding the project manager’s responsibilities | Answer option a. | Answer option a. ”Use of automated tools”. The volume of data and information that project managers need to integrate, which makes it necessary to use a project management information system (PMIS) and automated tools to collect, analyze, and use the information to meet project objectives and realize project benefits. Answer option a. ”Use of automated tools”. The volume of data and information that project managers need to integrate, which makes it necessary to use a project management information system (PMIS) and automated tools to collect, analyze, and use the information to meet project objectives and realize project benefits.
Exam 5 | #107. As part of his responsibilities in the organization, Sam is continuously monitoring the changes in the broader internal and external environments that might impact his work. What type of OPM is Sam managing? |  | Project | Program | Portfolio | Both A and B | Answer option c. | Answer option c. “Portfolio”. Portfolio managers continuously monitor changes in the broader internal and external environments. Answer option c. “Portfolio”. Portfolio managers continuously monitor changes in the broader internal and external environments.
Exam 5 | #108. You and your contractor have a dispute regarding payment terms and what constitutes minimum viable product acceptance as described in the agreement. After several weeks of negotiation, an agreement has still not been reached. What should the project manager do next? |  | Litigate in court, as the vendor is in default | Escalate to your lawyers and determine a more effective course of action | Initiate an alternative dispute resolution (ADR) | Renegotiate if possible and re-baseline the agreement | Answer option c. | Answer option c. ADR should be initiated when mutual negotiation fails. If ADR is not successful, then legal proceedings will be initiated if required. Answer option c. ADR should be initiated when mutual negotiation fails. If ADR is not successful, then legal proceedings will be initiated if required.
Exam 5 | #109. Marcus is the Scrum Master for a project that is mid-way through the 5th of 10 Sprints. In a morning Daily Scrum, Marcus announces that the current Sprint has been canceled. The Development Team is told that Sprint Planning for the 6th Sprint will begin the following day. Which of the following is true about the cancellation of a Sprint? |  | The Scrum Master has the power to cancel a Sprint if the Sprint Goal becomes obsolete. | Cancellation of Sprints in Scrum is not an allowed practice. The Sprint must be completed. | The Development Team can cancel the Sprint if the quality of the increment does not meet established standards. | Only the Product Owner has the authority to cancel the Sprint. | Answer option d. | Answer option d. The Development Team does not have the power to cancel Sprints. Only the Product Owner can do this. Answer option d. The Development Team does not have the power to cancel Sprints. Only the Product Owner can do this.
Exam 5 | #110. _____ can be used to determine which process has the highest number of errors and requires the most attention. |  | Affinity diagrams | Flowcharts | Fishbone diagrams | Histograms | Answer option d. | Answer option d. “Histograms”. A bar chart that shows the graphical representation of numerical data. Answer option d. “Histograms”. A bar chart that shows the graphical representation of numerical data.
Exam 5 | #111. During the project execution, the management requested to reduce project delivery time due to new strategy requirements. Management offered to provide extra funds and resources to make it happen. Which schedule compression technique would you use? |  | Resource smoothing | Resource optimization | Crashing | Fast-tracking | Answer option c . | Answer option c. “Crashing” is a technique used to shorten the schedule duration for the incremental cost by adding resources. Answer option c . “Crashing” is a technique used to shorten the schedule duration for the incremental cost by adding resources .
Exam 5 | #112. Eric spends most of his time each day organizing and facilitating activities, coaching the team members, and acting as a change agent. This includes setting up the activities, overseeing their execution, and enabling the rest of the team to perform at a level where high-value results are achieved. What role is Eric playing in the project? |  | Scrum master | Product owner | Project manager | Team manager | Answer option a . | Answer option a. Scrum Master is the coach of the development team and process owner in the Scrum framework. Answer option a . Scrum Master is the coach of the development team and process owner in the Scrum framework.
Exam 5 | #113. You are the Scrum Master of an organization that is moving from one Scrum team to several Scrum teams. These teams will work together on related software development projects. As an expert you recommend the “Scrum of Scrums” technique among the teams. What is Scrum of Scrums? |  | Is a technique in which All Scrum Masters from throughout the organization meet up to share updates and articulate the progress of the larger program. | Is a technique in which All Scrum Masters from throughout the organization hold a monthly standup meeting to discuss challenges and issues relating to the program. | Is a technique in which All Scrum Masters from throughout the organization get together to share Scrum best practices to use for the program. | Is a technique in which All Product Owners from throughout the organization get together and discuss the organization’s program strategy. | Answer option a. | Answer option a. Scrum of Scrums is a technique used by Scrum teams in which Scrum Masters from each team meet up on a weekly or bi-weekly basis to discuss project progress and share updates. The technique has emerged as a way to scale up large groups of developers into smaller teams of 5-10 where each Scrum Master acts as a representative for their respective team. Answer option a. Scrum of Scrums is a technique used by Scrum teams in which Scrum Masters from each team meet up on a weekly or bi-weekly basis to discuss project progress and share updates. The technique has emerged as a way to scale up large groups of developers into smaller teams of 5-10 where each Scrum Master acts as a representative for their respective team.
Exam 5 | #114. A project manager establishes the procedures to investigate and document the reasons for project termination. Which process is he performing? |  | Control scope | Close project | Validate scope | Close phase | Answer option b. | Answer option b. “Close project” Answer option b. “Close project”
Exam 5 | #115. Bryan is leading a project that contains some well-known elements with fixed requirements, but also elements that are still unclear and should be clarified during the project execution. Which development life cycles should he use? |  | Predictive life cycle | Adaptive life cycle | Iterative life cycle | Hybrid life cycle | Answer option d. | Answer option d. “Hybrid life cycle” can be used when a project has a part that is predictive and another part that is adaptive (for deliverables that are still unclear and not specified). Answer option d. “Hybrid life cycle” can be used when a project has a part that is predictive and another part that is adaptive (for deliverables that are still unclear and not specified).
Exam 5 | #116. After developing the project schedule, some of the project critical resources left the company, which limited the available resources. To adjust the schedule to respond to the new resource limitations, which Schedule technique would you use? |  | Resource smoothing | Resource leveling | Crashing | Fast-tracking | Answer option b. | Answer option b. Resource leveling. Resource Leveling is performed to balance the demand and supply of resources. Resource Smoothing is performed to achieve a more uniform resource utilization over a period of time. Resource Leveling may change the critical path of the project, whereas Resource Smoothing does not. Answer option b. Resource leveling. Resource Leveling is performed to balance the demand and supply of resources. Resource Smoothing is performed to achieve a more uniform resource utilization over a period of time. Resource Leveling may change the critical path of the project, whereas Resource Smoothing does not.
Exam 5 | #117. A project manager is analyzing the influence of resource control and assignment policies on the Control Resources process. Under which category do these elements fall? |  | Emerging practices | Enterprise environmental factors | Organizational process assets | Expert judgment | Answer option c. | Answer option c. “Organizational process assets”. OPA =The plans, processes, policies, procedures and knowledge base specific to, developed by, and used by, the organization – and which you actually use in the management of the project. Most organizations have developed a range of templates, proforma contracts, plans, procedures, registers and assessment tools to assist in the management of the project. Organizations have also acquired knowledge in the form of lessons learned and the organization’s knowledge base that can be very useful. Answer option c. “Organizational process assets”. OPA =The plans, processes, policies, procedures and knowledge base specific to, developed by, and used by, the organization – and which you actually use in the management of the project. Most organizations have developed a range of templates, proforma contracts, plans, procedures, registers and assessment tools to assist in the management of the project. Organizations have also acquired knowledge in the form of lessons learned and the organization’s knowledge base that can be very useful.
Exam 5 | #118. Juan is leading a project with ABA Enterprise. He receives a question for specifications related to some of the project deliverables from an external stakeholder. Which of the following documents could Juan use to answer the question? |  | RBS | WBS | OBS | SOW | Answer option b. | Answer option b. “WBS” contains project deliverables and the breakdown of work packages. Answer option b. “WBS” contains project deliverables and the breakdown of work packages.
Exam 5 | #119. Extreme programming (XP) is a software development methodology that is intended to improve software quality and responsiveness to changing customer requirements. It is a type of Agile methodology and it advocates frequent "releases" in short development cycles, which is intended to improve productivity and introduce checkpoints at which new customer requirements can be adopted. Choose the correct combination of XP practice names from the following options: |  | Test-driven design, refactoring, pair programming | Test-driven development, reforecasting, peer programming | Test-driven development, refactoring, pair programming | Test-driven design, refactoring, peer programming | Answer option c . | Answer option c. XP practices include test-driven development, refactoring, and pair programming. “Test-driven design,” “reforecasting,” and “peer programming” are not XP practice names. Answer option c . XP practices include test-driven development, refactoring, and pair programming. “Test-driven design,” “reforecasting,” and “peer programming” are not XP practice names.
Exam 5 | #120. You have been managing Scrum projects for a long time. Yesterday you had a visit from Mr. Frost. He holds one of the highest senior management positions in your company and has been working for over 30 years. His experience in managing projects is impeccable. However, he is not very familiar with scrum. He asks you how the management roles and responsibilities in Scrum projects are divided? You answer that the key roles in the Scrum project are: |  | The Scrum Master and the Product Owner | The Team, the Scrum Master, the Product Owner | The Team, the Product Owner | The Team, the Scrum Master | Answer option b. | Answer option b. There are only three Scrum roles: The Product Owner, the Team, and the Scrum Master. All management responsibilities in a project are divided among these three roles. Answer option b. There are only three Scrum roles: The Product Owner, the Team, and the Scrum Master. All management responsibilities in a project are divided among these three roles.
Exam 5 | #121. Chris has recently received a contract to help Higher Education University to lead a project for their Admissions team. The business case explains that potential students have repeatedly requested updates as to their application status. The funding has been received to allow for an addition to the existing web portal to allow students who are awaiting acceptance to sign-in and see their application status. The scope is broadly defined, and no detailed requirements have been obtained. In Chris’s conversations with the Admissions team, he has learned that their preference would be to deploy this functionality quickly and gain feedback from students so that the most requested features are included. Based on what he knows, which approach would be the best for Chris to recommend? |  | Predictive | Iterative | Incremental | Agile | Answer option d. | Answer option d. Predictive would be an unlikely choice in this situation because the Admissions team does not want to set firm requirements that cannot be changed. Because the team has requested users provide an early and multiple release plan, along with user feedback, this is considered both Iterative and Incremental, and therefore, Agile. Answer option d. Predictive would be an unlikely choice in this situation because the Admissions team does not want to set firm requirements that cannot be changed. Because the team has requested users provide an early and multiple release plan, along with user feedback, this is considered both Iterative and Incremental, and therefore, Agile.
Exam 5 | #122. The senior management of the Company XYZ decided to close all running projects to divert their resources to the new automation initiative. As the project manager of a running project, you completed most of the project deliverables. What would you do to the unfinished deliverables? |  | Dismantle them | Complete the remaining work and thus complete the project | Leave them as they are and document termination reasons | Hand them over the way they are to the concerned parties | Answer option d. | Answer option d. The best answer is to “Hand them over the way they are to the concerned parties” (Answer option d.). If you decided to “Dismantle them” (Answer option a.) or “Complete the remaining work and thus complete the project” (Answer option b.) you would cause unnecessary costs to the company. If you decided to “Leave them as they are and document termination reasons” (Answer option c.) you wouldn’t hand them over to the concerned party. Answer option d. The best answer is to “Hand them over the way they are to the concerned parties” (Answer option d.). If you decided to “Dismantle them” (Answer option a.) or “Complete the remaining work and thus complete the project” (Answer option b.) you would cause unnecessary costs to the company. If you decided to “Leave them as they are and document termination reasons” (Answer option c.) you wouldn’t hand them over to the concerned party .
Exam 5 | #123. The Project Charter was signed off last week and the Project Manager has assigned you to lead the next 3 meetings. These meetings will be held so that you can identify the maximum ideas in this short period of time while facilitating the planning sessions on scope, schedule, and cost. While playing your role as a facilitator, which technique will you employ? |  | Focus Groups | Brainstorming | Checklists | Multi-criteria Decision Making | Answer option b. | Answer option b. “Brainstorming” is used to identify a list of ideas in a short period of time. It is conducted in a group environment and is led by a facilitator. Answer option b. “Brainstorming” is used to identify a list of ideas in a short period of time. It is conducted in a group environment and is led by a facilitator.
Exam 5 | #124. An Agile team is delivering a product per the product requirements. However, at the end of the release, the customer Sarah is unhappy with the final product. What should the Agile Project Manager, Jeanette have done to avoid this? |  | Escalated the issue to the Sponsor. | Invited the customer to the daily standup meetings. | Engage the customer continuously to obtain feedback throughout the project. | Ask the Product Owner for clarity of the Product backlog. | Answer option c. | Answer option c. Agile projects meet with the customer on a frequent and recurring basis in order to obtain customer feedback as the project is being conducted. Answer option c. Agile projects meet with the customer on a frequent and recurring basis in order to obtain customer feedback as the project is being conducted.
Exam 5 | #125. You aim to measure the effectiveness of the communications activities by reviewing the changes between the desired and current engagement of the stakeholders and adjusting project communications as necessary. Which tool are you using? |  | Expert judgment | Project management information systems | Stakeholder engagement-assessment matrix | Interpersonal and team skills | Answer option c. | Answer option c. “Stakeholder engagement-assessment matrix”. The stakeholder engagement assessment matrix displays gaps between current and desired engagement levels of individual stakeholders; it can be further analyzed in this process to identify additional communication requirements (beyond the regular reports) as a method to close any engagement level gaps. Answer option c. “Stakeholder engagement-assessment matrix”. The stakeholder engagement assessment matrix displays gaps between current and desired engagement levels of individual stakeholders; it can be further analyzed in this process to identify additional communication requirements (beyond the regular reports) as a method to close any engagement level gaps.
Exam 5 | #126. When using Agile approaches for a project, all of the knowledge areas have processes usually performed before, during, and after an iteration (Sprint) except for: |  | Scope Management | Schedule Management | Procurement Management | Risk Management | Answer option c. | Answer option c. Procurement Management usually occurs at the beginning of the project in an Agile methodology. There may be instances in which procurements arise at some point in the project, becoming an iteration (Sprint) activity, but they are not performed before, during, and after each iteration. Answer option c. Procurement Management usually occurs at the beginning of the project in an Agile methodology. There may be instances in which procurements arise at some point in the project, becoming an iteration (Sprint) activity, but they are not performed before, during, and after each iteration.
Exam 5 | #127. Spencer has been asked to provide an update on his agile project and is in the process of gathering the data. The person requesting the update is most concerned about the remaining work left in the project. Of the following, which is the MOST appropriate source of information? |  | Feature Burndown chart | Sprint Burndown chart | Work Breakdown Structure (WBS) Dictionary | Requirements Breakdown Structure (RBS) | Answer option a. | Answer option a. The Feature Burndown chart will provide the most information as to what work has been completed. The Sprint Burndown chart will only reflect the status of the current Sprint. The WBS Dictionary and the RBS are utilized in waterfall projects. Answer option a. The Feature Burndown chart will provide the most information as to what work has been completed. The Sprint Burndown chart will only reflect the status of the current Sprint. The WBS Dictionary and the RBS are utilized in waterfall projects.
Exam 5 | #128. While managing the project, you have identified a potential opportunity that will benefit the whole program that your project belongs to. After discussing this benefit with your program manager, you both agreed that it is a high-priority opportunity. Which risk response strategy would you follow? |  | Escalate | Exploit | Share | Enhance | Answer option a. | Answer option a. ”Escalate” since the impact of the opportunity is affecting wider scope than the project it has to be escalated to the relevant authority (the program manager). Escalation is appropriate when the project team or the project sponsor agrees that a threat is outside the scope of the project or that the proposed response would exceed the project manager’s authority. Escalated risks are managed at the program level, portfolio level, or other relevant parts of the organization, and not on the project level. Answer option a. ”Escalate” since the impact of the opportunity is affecting wider scope than the project it has to be escalated to the relevant authority (the program manager). Escalation is appropriate when the project team or the project sponsor agrees that a threat is outside the scope of the project or that the proposed response would exceed the project manager’s authority. Escalated risks are managed at the program level, portfolio level, or other relevant parts of the organization, and not on the project level.
Exam 5 | #129. An agile software project requires outside expertise and delivery to add a specific custom component. An approved vendor asks the project manager to join the daily meeting with the vendor’s agile team, but the project manager's schedule is too full of internal meetings. How could the two teams synchronize their meetings to be efficient although meeting less frequently? |  | Set up meetings at each site. | Execute a Scrum of Scrums. | Agree to implement retrospectives. | Share an electronic Kanban board. | Answer option b. | Answer option b. The Scrum of Scrums allows both teams to have their own daily meetings while adding a more targeted meeting between them at a less frequent pace. Answer option b. The Scrum of Scrums allows both teams to have their own daily meetings while adding a more targeted meeting between them at a less frequent pace.
Exam 5 | #130. You are working for Solution First IT Company. The company decided to develop a new product and assigned you as the project manager. You just received the project business documents. Which documents should be included in the business documents? |  | Project business case | Project benefits management plan | Project charter | Both A and B | Answer option d. | Answer option d. Business documents include “Project business case” (Answer option a.) and “Project benefits management plan” (Answer option b.) Answer option d. Business documents include “Project business case” (Answer option a.) and “Project benefits management plan” (Answer option b.)
Exam 5 | #131. The project team is monitoring stakeholder engagement. As they are seeking to obtain guidance and information on managing stakeholder expectations, which of the following should they review? |  | Stakeholder register | Lessons learned register | Stakeholder engagement plan | Communications management plan | Answer option c. | Answer option c. “Stakeholder engagement plan” Answer option c. “Stakeholder engagement plan”
Exam 5 | #132. Kim had a meeting with the project team and identified six threats in the low-priority zone. Where should the team record these threats? |  | Issue Log | Watch List | Risk Report | None of the Above | Answer option b. | Answer option b. “Watch List”. Risks with low probability and impact may be included within the risk register as part of a watch list for future monitoring. Answer option b. “Watch List”. Risks with low probability and impact may be included within the risk register as part of a watch list for future monitoring.
Exam 5 | #133. Due to the lack of the required technical skills, the technical team failed to meet the quality requirements, which caused the team to rework the deliverables. What type of Cost of Quality the rework belongs to? |  | Prevention Costs | Appraisal Costs | Internal Failure Costs | External Failure Costs | Answer option c. | Answer option c. ”Internal Failure Costs”. Failures found by the project can cause Rework or Scrap. Answer option c. ”Internal Failure Costs”. Failures found by the project can cause Rework or Scrap.
Exam 5 | #134. Your team is getting a better understanding of the items in the product backlog and is preparing for the upcoming sprint. During the activity, they added more features to the existing PBI’s based on their improved understanding of the product and the incremental feedback obtained during examining previous versions of the working product. The goal of this activity is to refine and improve the business value of the given features. What activity is the team engaged in? Who owns it? |  | Sprint planning; the development team | Release planning; release train engineer | Backlog refinement; product owner | Project planning; project manager | Answer option c . | Answer option c. “Backlog refinement; product owner”. Backlog refinement is the progressive elaboration of project requirements and the ongoing activity in which the team collaboratively reviews, updates, and writes requirements to satisfy the need of the customer’s request. Answer option c . “Backlog refinement; product owner”. Backlog refinement is the progressive elaboration of project requirements and the ongoing activity in which the team collaboratively reviews, updates, and writes requirements to satisfy the need of the customer’s request.
Exam 5 | #135. A project manager is analyzing the issue and defect reporting procedures, as well as the communication policies that influence the control quality process. Under which category do these elements fall? |  | Emerging practices | Enterprise environmental factors | Organizational process assets | Expert judgment | Answer option c. | Answer option c. “Organizational process assets” Answer option c. “Organizational process assets”
Exam 5 | #136. Midway through an iteration, the customer Billy requests a small change to be included into the scope. What should Kimberly, the Agile Project Manager do? |  | Ask the Product Owner to cancel the current sprint (iteration) and start planning for a new one. | Add the change request as a new user story in the product backlog for the next sprint (iteration) planning session. | Add the change request as a new user story for the current sprint (iteration). | Submit a change request to the Change Control Board for review and approval. | Answer option b. | Answer option b. The job of the Agile Project Manager is to ensure that until the next Iteration Planning meeting, any new user stories are stored in the Product Backlog. Answer option b. The job of the Agile Project Manager is to ensure that until the next Iteration Planning meeting, any new user stories are stored in the Product Backlog.
Exam 5 | #137. You are the Scrum Master in an Agile organization. You like to plan all Scrum events according to the framework. You are currently working with a junior team; however, the team members are smart developers and are motivated to learn and deliver beyond the expectations. Upon completing their first Sprint, Jennifer reaches out to you and requests to schedule a Retrospective session in order to improve and learn from the first Sprint, you like the idea but reminds her of the logical flow of Scrum events. From the below selections, which flow is right: |  | Sprint Planning, Daily Scrum, Sprint Retrospective, Sprint Review | Daily Scrum, Sprint Planning, Sprint Retrospective, Sprint Review | Sprint Planning, Daily Scrum, Sprint Review, Sprint Retrospective | Sprint Planning, Sprint Retrospective, Sprint Review, Lessons Learned | Answer option c. | Answer option c. Per Scrum framework, Scrum events occur in the following order: Sprint planning: is time-boxed for up to 8 hours; the entire team meets up and sets the implementation plan. Daily Scrum (Daily stand-up): is time-boxed for up to 15 minutes on a daily basis; the development team meets up early in the day to discuss progress and share updates. Answer option c. Per Scrum framework, Scrum events occur in the following order: Sprint planning Sprint planning : is time-boxed for up to 8 hours; the entire team meets up and sets the implementation plan. Daily Scrum Daily Scrum (Daily stand-up): is time-boxed for up to 15 minutes on a daily basis; the development team meets up early in the day to discuss progress and share updates. Sprint Review: is time-boxed for up to 4 hours; the entire team meets up at the end of each Sprint to inspect the deliverable. Sprint Retrospective: is time-boxed for up to 3 hours; the entire team meets up right after a Sprint Review to document the previous work and find ways to improve. Sprint Review: Sprint Review: is time-boxed for up to 4 hours; the entire team meets up at the end of each Sprint to inspect the deliverable. Sprint Retrospective: Sprint Retrospective: is time-boxed for up to 3 hours; the entire team meets up right after a Sprint Review to document the previous work and find ways to improve.
Exam 5 | #138. Andy is using earned value analysis. The project budget at completion (BAC) is $220,000 while the estimate at completion is $235,000. The project variance at completion implies that _____ . |  | Project is on budget | Project is over the budget | Project is under the budget | None of the Above | Answer option b. | “Project is over planned cost” VAC=BAC-EAC=220-235=-$15k.
Exam 5 | #139. A project manager is working on development of project phases. Which is not an attribute that he should consider? |  | Number of phases | Solution development | Resource requirements | Exit criteria for a project to complete a phase | Answer option b. | Answer option b. “Solution development” Answer option b. “Solution development”
Exam 5 | #140. Alex is reviewing the reported lack of resources, delays in raw material supplies, or low grades of raw material. Which input is he reviewing? |  | Resource requirements | Issue log | Physical resource assignments | Resource management plan | Answer option b. | Answer option b. “Issue log”. Issue log is a project document where all issues that are negatively affecting the project are recorded and tracked. When an issue log is created, it provides a tool for reporting and communicating all that is happening within the project. It’s a lot like a support ticket that’s created when you call a help desk: the problem is logged and given an identifier, then the issue is tracked—all the way through to resolution. Answer option b. “Issue log”. Issue log is a project document where all issues that are negatively affecting the project are recorded and tracked. When an issue log is created, it provides a tool for reporting and communicating all that is happening within the project. It’s a lot like a support ticket that’s created when you call a help desk: the problem is logged and given an identifier, then the issue is tracked—all the way through to resolution.
Exam 5 | #141. You are performing the Direct and Manage Project Work process. Which of the following is an input for the process? |  | Deliverables | Approved change requests | Change requests | Both A and B | Answer option b. | Answer option b. “Approved change requests”. Change requests are approved or denied during this process and once the decision has been made, approved changes come back through the process of “direct and manage project work”. Here, the project team will implement the approved changes. Answer option b. “Approved change requests”. Change requests are approved or denied during this process and once the decision has been made, approved changes come back through the process of “direct and manage project work”. Here, the project team will implement the approved changes.
Exam 5 | #142. You just completed performing the quantitative risk analysis in your project. As a result, you have created an assessment of the overall project risk exposure and a detailed probabilistic analysis of the project. Which document should you update with this information? |  | Risk register | Risk management plan | Risk report | Issue log | Answer option c. | Answer option c. “Risk report”. Risk report is used in the Manage Quality process to identify sources of overall project risk and the most important drivers of overall risk exposure that can impact the quality objectives of the project. Answer option c. “Risk report”. Risk report is used in the Manage Quality process to identify sources of overall project risk and the most important drivers of overall risk exposure that can impact the quality objectives of the project.
Exam 5 | #143. A project’s daily stand-up meetings are long, often lasting more than two hours. The project team uses the stand-up meetings for extended discussions about solutions to project obstacles. What should the project manager do to improve the daily stand-up meetings? |  | Allow the meetings to remain long but ensure that the time is productive by using an agenda and recording minutes. | Timebox each speaker using a stopwatch in stand-up meetings. | Nominate a team member to manage obstacles and schedule meetings to discuss possible solutions. | Coach team members towards shortening stand-up meetings to 10-15 minutes and improve their method for identifying solutions. | Answer option d. | Answer option d. Daily stand-ups are important meetings for agile teams. The project manager should coach the team in how a daily stand-up meeting is run and what is discussed. Teams run their own stand-ups, and when run well, they can be very useful. Daily stand-ups are typically 10-15 minutes and three questions are answered: 1) What did you do since the last stand-up? 2) What will you do today? 3) Are there any impediments or roadblocks? Hold separate meetings to discuss the blockers and find the solution. Answer option d. Daily stand-ups are important meetings for agile teams. The project manager should coach the team in how a daily stand-up meeting is run and what is discussed. Teams run their own stand-ups, and when run well, they can be very useful. Daily stand-ups are typically 10-15 minutes and three questions are answered: 1) What did you do since the last stand-up? 2) What will you do today? 3) Are there any impediments or roadblocks? Hold separate meetings to discuss the blockers and find the solution.
Exam 5 | #144. You are studying the influence of general project management practices and sustainability while you are developing the project management plan. Under which category do these elements fall? |  | Emerging practices | Enterprise environmental factors | Organizational process assets | Expert judgment | Answer option b. | Answer option b. “Enterprise environmental factors” Answer option b. “Enterprise environmental factors”
Exam 5 | #145. Nikos is the project manager assigned to a new project that will deploy a new payroll software system within his company. He is asked by the Director of the PMO which approach is most appropriate for this project. As he is reviewing the requirements and objectives, he notices that the requirements have been detailed to a granular level and they are not subject to change. In addition, the activities required to meet the objectives only need to be completed once and there will be a single delivery at the end of the project. Because of this, Nikos chooses which project management approach? |  | Predictive | Iterative | Incremental | Agile | Answer option a. | Answer option a. Predictive is the best course of action in this case because of the fixed, detailed requirements as well as the 1x activity and single delivery facets. Iterative, Incremental and Agile (which includes both Iterative and Incremental) are the appropriate approach when requirements are dynamic, and activities are repeated. Answer option a. Predictive is the best course of action in this case because of the fixed, detailed requirements as well as the 1x activity and single delivery facets. Iterative, Incremental and Agile (which includes both Iterative and Incremental) are the appropriate approach when requirements are dynamic, and activities are repeated.
Exam 5 | #146. _____ includes which deliverables have been accepted and which deliverables have not been accepted. It also includes the reasons why the change requests have been accepted or denied. |  | Accepted deliverables | Acceptance criteria | Work performance information | Requirements documentation | Answer option c. | Answer option c. “Work performance information” Answer option c. “Work performance information”
Exam 5 | #147. Manage stakeholder engagement is an important process. One of its common tools is setting the expected behavior of the project team members, as well as expectations for engagement with stakeholders. This technique is known as ____ . |  | Ground Rules | Team charter | Culture awareness | Political Awareness | Answer option a. | Answer option a. “Ground Rules”. Ground rules is an internal document defined in the team charter that sets the expected behavior for project team members, as well as other stakeholders, with regard to stakeholder engagement. Answer option a. “Ground Rules”. Ground rules is an internal document defined in the team charter that sets the expected behavior for project team members, as well as other stakeholders, with regard to stakeholder engagement.
Exam 5 | #148. _____ calculate(s) schedule and cost variances to determine the degree of variance from the target. |  | Earned Value Analysis (EVA) | Audits | Performance reviews | Trend analysis | Answer option a. | Answer option a. “Earned Value Analysis (EVA)” Answer option a. “Earned Value Analysis (EVA)”
Exam 5 | #149. While working on the close project process, Zain wants to confirm that there are no open risks at the end of the project. Which document should he review? |  | Risk report | Change log | Issue log | Risk register | Answer option a. | Answer option a. “Risk report” Answer option a. “Risk report”
Exam 5 | #150. A project manager wants to define the acceptable target that the implementation of risk responses is required to achieve while performing the Implement Risk Responses process. Which input is he reviewing? |  | Risk register | Risk report | Risk management plan | Issue log | Answer option c. | Answer option c. “Risk management plan” specifies risk thresholds for the project based on the risk appetite of key stakeholders, which define the acceptable target that the implementation of risk responses is required to achieve. Answer option c. “Risk management plan” specifies risk thresholds for the project based on the risk appetite of key stakeholders, which define the acceptable target that the implementation of risk responses is required to achieve.
Exam 5 | #151. Silicon Prod Co. is a company producing kitchen appliances and recently faced public outrage because it failed to meet health and safety standards as determined in the most recent audit. Accordingly, the company decided to start an initiative to improve its health and safety standards and wants to stand out as a leader in the industry. Which type of benefits does this project derive? |  | Direct | Tangible | Intangible | Indirect | Answer option c. | Answer option c. “Intangible” Answer option c. “Intangible”
Exam 5 | #152. Tom is a project manager in an Agile project. Due to the volume of work, Tom is overworked and stressed about managing the project. He is wondering what tasks he may delegate while he focuses on project integration management. Which of the following tasks may he delegate to the project team? |  | Project resource management | Product planning and delivery | Project risk management | Managing work with other projects | Answer option b. | Answer option b. “Project planning and delivery”. Product planning and delivery may be easily delegated to the project team while the project manager focuses on integration. Answer option b. “Project planning and delivery”. Product planning and delivery may be easily delegated to the project team while the project manager focuses on integration.
Exam 5 | #153. Due to the recent go-to-market failure of its latest product, Company XYZ started a new campaign to improve its reputation. Which type of benefits will this initiative bring? |  | Direct | Tangible | Intangible | Indirect | Answer option c. | Answer option c. “Intangible”. Brand image or reputation is intangible. Answer option c. “Intangible”. Brand image or reputation is intangible.
Exam 5 | #154. You are working on formalizing the acceptance of the completed project deliverables. Which process are you performing? |  | Close Phase | Close Project | Validate scope | Control scope | Answer option c. | Answer option c. “Validate scope” Answer option c. “Validate scope”
Exam 5 | #155. You are participating in a planning meeting in which the team is trying to reach a final definition of the major deliverables. Questions are being asked to describe the use, characteristics, and other relevant aspects of what needs to be delivered. This meeting is related to which of the following techniques? |  | Product Analysis | Decomposition | Leads and Lags | Precedence Diagramming Method | Answer option a. | Answer option a. “Product Analysis” can be used to deﬁne products and services. It includes asking questions about a product or service and coming up with answers to describe the use, characteristics, and other relevant aspects of what is going to be delivered. Each application area has one or more generally accepted methods for translating high-level product or service descriptions into meaningful deliverables. Answer option a. “Product Analysis” can be used to deﬁne products and services. It includes asking questions about a product or service and coming up with answers to describe the use, characteristics, and other relevant aspects of what is going to be delivered. Each application area has one or more generally accepted methods for translating high-level product or service descriptions into meaningful deliverables.
Exam 5 | #156. During the project performance review meeting, the information shows that SPI= 0.9, which indicates that _____ . |  | The project is ahead of schedule | The project is behind schedule | The project is on schedule | The project is below budget | Answer option b. | Answer option b. when SPI is less than 1, this indicates “The project is behind schedule” Answer option b. when SPI is less than 1, this indicates “The project is behind schedule”
Exam 5 | #157. Continuous integration consolidates software build, testing, and deployment into an automated, repeatable process. This merges all changes made to the software and: |  | Enables new features for the product backlog. | Integrates all changed components regularly, at least on a daily basis. | Separate each feature into its own development tool. | Ensures no code is changed, avoiding complications. | Answer option b. | Answer option b. Continuous integration is designed to merge all changes made to the software and test them automatically, discovering any defect or issues on a daily basis. Answer option b. Continuous integration is designed to merge all changes made to the software and test them automatically, discovering any defect or issues on a daily basis.
Exam 5 | #158. Alex is performing the control costs process, and he wants to review the project status, such as which costs have been authorized, incurred, invoiced, and paid. What is this data called? |  | Project funding requirements | Organizational process assets | Work performance data | Project documents | Answer option c. | Answer option c. “Work performance data”. Work performance data contains data on project status such as the costs that have been authorized, incurred, invoiced, and paid. Answer option c. “Work performance data”. Work performance data contains data on project status such as the costs that have been authorized, incurred, invoiced, and paid.
Exam 5 | #159. Sam is assessing his project stakeholders according to directions of influence technique. One of the project stakeholders is the marketing manager, who is supposed to provide important insights about consumer behavior, which will influence the project requirements. Under which direction should Sam classify him? |  | Upward | Downward | Outward | Sideward | Answer option d. | “Sideward”. The Subject Matter Experts are considered sideways stakeholders, as they are on the same expert level as Project Managers. Stakeholder classification. Internal/external, impact/influence/power/interest, upward/downward/outward/sideward, or any other classification model chosen by the project manager.
Exam 5 | #160. A project manager took an action to reduce the probability of occurrence and impact of a threat. Which risk response did he take? |  | Avoid | Transfer | Mitigate | Accept | Answer option c. | Answer option c. “Mitigate”. In risk mitigation, the action is taken to reduce the probability of occurrence and/or impact of a threat. An early mitigation action is often more effective than trying to repair the damage after the threat has occurred. Answer option c. “Mitigate”. In risk mitigation, the action is taken to reduce the probability of occurrence and/or impact of a threat. An early mitigation action is often more effective than trying to repair the damage after the threat has occurred.
Exam 5 | #161. Your senior financial analyst has worked for your company for 20+ years and has enormous knowledge about the industry, the company and has great experience in financial projects as he has been managing many throughout the years. What kind of knowledge does he have? |  | Expert knowledge | Tacit knowledge | Explicit knowledge | Informational knowledge | Answer option b. | Answer option b. “Tacit Knowledge” as it is difficult to codify and explain in simple terms. Answer option b. “Tacit Knowledge” as it is difficult to codify and explain in simple terms.
Exam 5 | #162. While developing the project scope statement, the project team discussed “what is out of project scope?” as this information helps in managing stakeholders’ expectations and can reduce scope creep. What element of the scope statement were they discussing? |  | Product scope description | Deliverables | Acceptance criteria | Project exclusions | Answer option d. | Answer option d. “Project exclusions” identify what is excluded from the project. Explicitly stating what is out of scope for the project helps manage stakeholders’ expectations and can reduce scope creep. Answer option d. “Project exclusions” identify what is excluded from the project. Explicitly stating what is out of scope for the project helps manage stakeholders’ expectations and can reduce scope creep.
Exam 5 | #163. During the project execution, the project was delayed from baseline by 10 days. Accordingly, the project manager planned to reduce the duration of the remaining work to compensate for the delay through overtime. Which schedule technique did he use? |  | Resource smoothing | Resource optimization | Crashing | Fast-tracking | Answer option c. | Answer option c. ”Crashing” overtime involves increasing the time and effort resources spend on an activity to reduce the time which is an example of crashing. Answer option c. ”Crashing” overtime involves increasing the time and effort resources spend on an activity to reduce the time which is an example of crashing.
Exam 5 | #164. You are the Scrum Master of a newly formed Scrum team. You are thinking through which approach can be used to reach agreements between the development team on work items. As per Scrum, there are a few techniques to reach consensus; from the selections below, which one is ideal to evaluate the range of agreements: |  | Roman Voting | Pooling | Fist of Five | Dot Voting | Answer option c. | Answer option c. Per Scrum framework, Fist of Five is a technique used to gauge consensus during Sprint standups. It is best for evaluating the range of agreements on certain decisions and features. Answer option c. Per Scrum framework, Fist of Five is a technique used to gauge consensus during Sprint standups. It is best for evaluating the range of agreements on certain decisions and features.
Exam 5 | #165. While managing the quality process, the project manager used a technique to identify opportunities for process improvements. Which technique did he use? |  | Root cause analysis | Process analysis | Document analysis | Alternatives analysis | Answer option b. | Answer option b. “Process analysis”. Process analysis identifies opportunities for process improvements. This analysis also examines problems, constraints, and non-value-added activities that occur during a process. Answer option b. “Process analysis”. Process analysis identifies opportunities for process improvements. This analysis also examines problems, constraints, and non-value-added activities that occur during a process.
Exam 5 | #166. After identifying and analyzing the risk, the project manager decided to sign a contract with a third party to deal with the impact of the identified risk. Which risk response strategy did the project manager take? |  | Avoid | Transfer | Mitigate | Accept | Answer option b. | Answer option b. “Transfer”. The transfer involves shifting ownership of a threat to a third party to manage the risk and to bear the impact of the threat. Risk transfer often involves payment of a risk premium to the party that will deal with the threat. The transfer can be achieved by a range of actions, which include but are not limited to the use of insurance, performance bonds, warranties, guarantees, etc. Agreements may be used to transfer ownership and liability for specified risks to another party. Answer option b. “Transfer”. The transfer involves shifting ownership of a threat to a third party to manage the risk and to bear the impact of the threat. Risk transfer often involves payment of a risk premium to the party that will deal with the threat. The transfer can be achieved by a range of actions, which include but are not limited to the use of insurance, performance bonds, warranties, guarantees, etc. Agreements may be used to transfer ownership and liability for specified risks to another party.
Exam 5 | #167. While you are performing the project closure activities, a new program manager replaced the old one who was in charge of the related projects including yours. He asked you to provide him with a report justifying why the project was initiated. Which document can help you prepare this report? |  | Project charter | Business case | Benefits management plan | Both A and B | Answer option b. | Answer option b. “Business case”. The approved business case, or similar, is the business document most commonly used to create the project charter. The business case describes the necessary information from a business standpoint to determine whether the expected outcomes of the project justify the required investment. Answer option b. “Business case”. The approved business case, or similar, is the business document most commonly used to create the project charter. The business case describes the necessary information from a business standpoint to determine whether the expected outcomes of the project justify the required investment.
Exam 5 | #168. The project lead software engineer has booked an annual vacation for 40 days. The project is at an early stage, and the client insists on keeping the project resources without change. You think of hiring another lead engineer. This is an example of _____ . |  | Risk Transfer | Risk Avoidance | Risk Mitigation | Risk Acceptance | Answer option b. | Answer option b. “Risk Avoidance”. Risk avoidance is when the project team acts to eliminate the threat or protect the project from its impact. It may be appropriate for high-priority threats with a high probability of occurrence and a large negative impact. Avoidance may involve changing some aspects of the project management plan or changing the objective that is in jeopardy in order to eliminate the threat entirely, reducing its probability of occurrence to zero. Answer option b. “Risk Avoidance”. Risk avoidance is when the project team acts to eliminate the threat or protect the project from its impact. It may be appropriate for high-priority threats with a high probability of occurrence and a large negative impact. Avoidance may involve changing some aspects of the project management plan or changing the objective that is in jeopardy in order to eliminate the threat entirely, reducing its probability of occurrence to zero.
Exam 5 | #169. You are studying your organization’s code of ethics and how it might influence the Control Procurements process. Under which category do these elements fall? |  | Enterprise environmental factors | Organizational process assets | Expert judgment | None of the above | Answer option a. | Answer option a. “Enterprise environmental factors”. The Enterprise Environment Factors (EEF) include all of the conditions and systems that are not under the control of the project team that influence, constrain or direct the work of the project. This includes things such as the existing internal and external infrastructure, computer systems, networks and software, naturally occurring phenomena (not just the climate) and legislation that exist, both inside and outside of the organization that will affect the way you manage your project. Answer option a. “Enterprise environmental factors”. The Enterprise Environment Factors (EEF) include all of the conditions and systems that are not under the control of the project team that influence, constrain or direct the work of the project. This includes things such as the existing internal and external infrastructure, computer systems, networks and software, naturally occurring phenomena (not just the climate) and legislation that exist, both inside and outside of the organization that will affect the way you manage your project.
Exam 5 | #170. There is a task in the project that cannot be resolved or completed by the team. Which of the following bid documents would be used when a formal offer is required for the solution? |  | Request For Bid (RFB) | Request For Information (RFI) | Request For Quotation (RFQ) | Request For Proposal (RFP) | Answer option d. | Answer option d. “Request For Proposal (RFP)”. An RFP is used when there is a task in the project that requires a formal response from the seller. This is the most formal of the procurement request documents and has strict procurement rules for content, timeline, and seller responses. Answer option d. “Request For Proposal (RFP)”. An RFP is used when there is a task in the project that requires a formal response from the seller. This is the most formal of the procurement request documents and has strict procurement rules for content, timeline, and seller responses.
Exam 5 | #171. Adam aims to identify the type, quantity, and characteristics of resources required to complete the project. Which process is he performing? |  | Plan Resource Management | Estimate Activity Resources | Manage team | Control Resources | Answer option b.” | Answer option b.” Estimate Activity Resources” Answer option b.” Estimate Activity Resources”
Exam 5 | #172. The project sponsor is concerned that you are spending a lot of time planning the quality of your project. The sponsor understands your efforts as this is a critical and high-value project, but they would like to see some progress and suggest that you could add a couple more team members to check for quality-related issues later, because they want to start with the project as soon as possible. You understand their concern, but you also realize that: |  | Enough time should be spent in planning for quality, as quality should be planned into a project, not tested after the fact. | This is a high-visibility project and production faults might harm your reputation. | The project manager is an expert in planning and should not be questioned. | If you perfect the planning now, there will be no faults in production, and this will save a lot of time and money. | Answer option a. | Answer option a. Quality should be planned into a project, not tested in. This is a basic principle of TQM (total quality management). Answer option a. Quality should be planned into a project, not tested in. This is a basic principle of TQM (total quality management).
Exam 5 | #173. Meagan, in her role as PMO Director, has assigned a Scrum Master to run a new project with a team of 7 Developers. The Product Owner has come to her with a concern that the project is using Scrum instead of a more predictive and planned approach. Which of the following is the BEST reason Meagan could share as to why the agile approach was chosen? |  | The company has recently adopted the Scrum approach and all projects will be run using agile methodologies. | The project is characterized by highly uncertain requirements and therefore a planned approach is not the best approach. | The available project manager is not experienced in predictive approaches. | Meagan should change the approach to predictive as the Product Owner is the lead of the team that will be using the finished product. | Answer option b. | Answer option b. Predictive (waterfall, plan-driven) approaches are best used for projects where the work is definable. High-uncertainty work is best managed via agile approaches. While A and C may be true, they are not the most collaborative and helpful approaches for working with the Product Owner. D would be an inappropriate response as the assumption is that Meagan has valid reasons for using agile for this project. Answer option b. Predictive (waterfall, plan-driven) approaches are best used for projects where the work is definable. High-uncertainty work is best managed via agile approaches. While A and C may be true, they are not the most collaborative and helpful approaches for working with the Product Owner. D would be an inappropriate response as the assumption is that Meagan has valid reasons for using agile for this project.
Exam 5 | #174. You ask the product owner to allocate the financial return expected from the project across all the product features. He says those numbers would be too arbitrary, and asks why you need them anyway? You respond: |  | Just make up some numbers as a starting point, we'll refine the exact amounts as we proceed. | Focus on getting the relative value of the features; don't worry about the details. | We need this information to do a cost-benefit analysis of the product features and prioritize the backlog. | If you can't give us these numbers, we will be forced to guess at them ourselves. | Answer option b . | Answer option b. To understand this question you need to think about why we ask the product owner for this information. The team needs to assign a financial value to each product feature as a starting point for creating a risk-based backlog, where the negative-value of the risks is ranked along with the value of the product features. For this purpose, it is most important to get the relative value of the product features right. The team doesn’t “refine” these numbers or analyze or prioritize the features. They also wouldn’t just make up some numbers; this information has to be supported. Answer option b . To understand this question you need to think about why we ask the product owner for this information. The team needs to assign a financial value to each product feature as a starting point for creating a risk-based backlog, where the negative-value of the risks is ranked along with the value of the product features. For this purpose, it is most important to get the relative value of the product features right. The team doesn’t “refine” these numbers or analyze or prioritize the features. They also wouldn’t just make up some numbers; this information has to be supported.
Exam 5 | #175. Leslie is Scrum Master on a new project to deliver enhancements to a customer-facing application. Leslie has worked dozens of agile projects and is experienced in Scrum. Mark has been assigned a new role of Scrum Product Owner and is unsure of how to begin this new position. As Leslie begins to explain the high-level responsibilities of a Scrum Product Owner, she is NOT likely to mention which of the following duties: |  | Ensure engineering practices are followed. | Define and prioritize the features of the product. | Prioritize features/outcomes and adjust as needed. | Accept or reject work results. | Answer option a. | Answer option a. Ensuring engineering practices are followed is a Scrum Master responsibility. B, C, and D are all duties the Product Owner will fulfill. Answer option a. Ensuring engineering practices are followed is a Scrum Master responsibility. B, C, and D are all duties the Product Owner will fulfill.
Exam 5 | #176. Jim is performing stakeholders' assessment using the ability of the stakeholder to cause changes to the project’s planning or execution and his ability to influence the project's outcomes to classify the stakeholders. Which data representation technique is he using? |  | Impact/influence grid | Power/influence grid | Stakeholder cube | Salience model | Answer option a. | Answer option a. “Impact/influence grid” is the right answer. The stakeholder has an impact on the project decisions and can request changes. The stakeholder can influence the outcomes of the project. Power/interest grid, power/influence grid, or impact/influence grid are techniques that support a grouping of stakeholders according to their level of authority (power), level of concern about the project’s outcomes (interest), ability to influence the outcomes of the project (influence), or ability to cause changes to the project’s planning or execution. Answer option a. “Impact/influence grid” is the right answer. The stakeholder has an impact on the project decisions and can request changes. The stakeholder can influence the outcomes of the project. Power/interest grid, power/influence grid, or impact/influence grid are techniques that support a grouping of stakeholders according to their level of authority (power), level of concern about the project’s outcomes (interest), ability to influence the outcomes of the project (influence), or ability to cause changes to the project’s planning or execution.
Exam 5 | #177. The PMO has asked you to generate some financial information to summarize the business benefits of your project. They are expecting to see in your report the financial gains and the return you hope the project will bring to the company. To best describe this, you should show an estimate of: |  | Internal rate of return (IRR) | Return on investment (ROI) | Gross domestic product (GDP) | Net present value (NPV) | Answer option b. | Answer option b. “Return on investment (ROI)”. The PM needs to show how much the project will return therefore he needs to choose the return on investment (ROI). Maybe you wanted to select the net present value (NPV) since this calculation accounts for inflation, but the question did not ask for an adjusted value. Instead, it simply asked how much money the project would return. Answer option b. “Return on investment (ROI)”. The PM needs to show how much the project will return therefore he needs to choose the return on investment (ROI). Maybe you wanted to select the net present value (NPV) since this calculation accounts for inflation, but the question did not ask for an adjusted value. Instead, it simply asked how much money the project would return.
Exam 5 | #178. The team decides to run the next phase in their project using the agile approach. Unfortunately, some team members don’t have the appropriate agile training. How should the project manager respond to the lack of agile training? |  | Replace some of them with resources with agile training. | Ensure that you have project reserves that can cover agile training for all team members. | Organize online training sessions for all key team members, covering the main agile topics. | Identify and implement the most cost-effective agile training for the team members. | Answer option d. | Answer option d. Training for project team members can result in added skills that could be useful for future phases or projects. The project manager should identify and implement agile training for team members. Training lessons and related costs should be evaluated and included in the resource management plan, budget, and schedule. Answer option d. Training for project team members can result in added skills that could be useful for future phases or projects. The project manager should identify and implement agile training for team members. Training lessons and related costs should be evaluated and included in the resource management plan, budget, and schedule.
Exam 5 | #179. You are negotiating a contract to engage temporary resources since you are facing a shortage of internal resources. Which contract type would you use? |  | Fixed price with economic price adjustments (FPEPA) | Firm fixed price (FFP) | Cost plus fixed fee (CPFF) | Time and material (T&M) | Answer option d. | Answer option d. “Time and material (T&M)” is usually used to acquire resources whether team resources or physical resources. Answer option d. “Time and material (T&M)” is usually used to acquire resources whether team resources or physical resources.
Exam 5 | #180. As a Scrum Master for a large development team, Bill understands the need to operate with openness and transparency with the team. How will he engage knowledge sharing throughout the project? |  | Make key information visible and ensure all impacted stakeholders are invited to daily standups, retrospectives, and Sprint(iteration) planning sessions. | Write a process document for the development team to read during off hours. | Consult with senior management to share project information, establishing a good reputation within the company. | Lock the agile tools so that only the Scrum Master has access to edit them. | Answer option a. | Answer option a. An Agile team makes project information accessible to all, with a preference to people and interactions over processes and tools. Answer option a. An Agile team makes project information accessible to all, with a preference to people and interactions over processes and tools.

## exam6
Exam Name | Question | quesimgsrc | Answer1 | Answer2 | Answer3 | Answer4 | Correct-Answer | Explanation | answerimgsrc
Exam 6 | #1. When introducing Agile approaches to a company that has historically managed all its projects using predictive approaches, which of the following approaches is more likely to succeed? |  | Trying the new approaches on completed projects. | Trying the new approaches on current projects. | Trying the new approaches on a less risky pilot project. | Trying the new approaches on the projects with the highest budget. | Answer option c. | Trying new techniques on lower risk projects with higher chances of success is the best approach. Successfully completing the lower risk projects would allow a smoother transition of Agile into the company.
Exam 6 | #2. According to the project team assessment of the stakeholders, the operations team leader engagement level is resistant while the desired engagement level is supportive. Which of the following tactics would be useful to use? |  | Invite him to a project introduction seminar | Request his support regularly | Provide him with a project briefing | Explain to him how the project would benefit his area of work | Answer option d. | The best course of action is to “Explain to him how the project would benefit his area” (option d.). If you decide to choose to “Invite him to a project introduction seminar” (answer option a.), “Provide him with a project briefing, “(answer option d.) it would not help since he is already aware of the project. If you decide to “Request his support regularly “(answer option b.), there are no guarantees that he will be supporting the project since he is already resistant.
Exam 6 | #3. Planned and ad hoc project reports and presentations are outputs for the _____ . |  | Manage quality process | Manage communications process | Manage Stakeholder Engagement process | Monitor communications process | Answer option b. | “Manage communications process” Planned and ad hoc project reports and presentations are included within Organizational process assets that may be updated as a result of the Manage communications process.
Exam 6 | #4. As a result of the stakeholder engagement assessment, one of the stakeholders is aware of the project but not interested in it. Accordingly, how would you categorize this stakeholder? |  | Resistant | Neutral | Supportive | Leading | Answer option b. | “Neutral”. A neutral stakeholder doesn’t support or detract from your project. Ideally, you want her to support your project, but she won’t do any real harm by being neutral.
Exam 6 | #5. The quality testing results of a software integration project showed that there was a deviation from the quality requirements. Thus, the project manager asked the quality team to investigate the root cause of the deviation and resolve it. What type of action did the project manager request? |  | Corrective action | Preventive action | Defect repair | All of the above | Answer option a. | The action that fits the described request is Corrective action (option a). Corrective action focuses on realigning the performance of the project work with the project plan (baseline). Preventive action (Answer option b.) focuses on ensuring the future performance of the project work will be aligned with the project management plan. “Defect repair” (Answer option c.) focus on modifying nonconforming product component to become conforming.
Exam 6 | #6. You are the Product Owner of a major software development project. A junior team member reaches out to you and asks if he should start verifying the functionality of the newly developed software component at the end of the project. You inform the junior member that this approach is not ideal because: |  | Quality inspection within Agile is not important because the requirements constantly change so the final deliverable defines the quality of the product. | Quality inspection within Agile is addressed proactively through face-to-face interaction with the customer and ongoing testing throughout. | Quality inspection is important but it is the quality manager function so the team should only focus on delivering the software on schedule. | Quality inspection should be verified by the client because Agile manifesto calls for customer collaboration. | Answer option b. | In Agile, quality is addressed proactively throughout the development stages and reactively upon discovering a technical issue. The entire Scrum team is responsible for Quality within Agile applications.
Exam 6 | #7. You are managing a biotechnology project. The sponsor notified you that an external team from a consultancy firm will visit you, and the project team to identify nonconformity, gaps, and shortcomings of the work. This is an example of _____ . |  | Inspection | Quality assurance | Quality control | Audit | Answer option d. | ”Audit” A quality audit is usually conducted by a team external to the project, such as the organization’s internal audit department, PMO, or by an auditor external to the organization. The audit is objective and may identify nonconformities, gaps, and shortcomings.
Exam 6 | #8. Quality is a big concern on the Project Alpha that you are managing. The Quality Control team is having conflicts with the Execution team. They have declared 2 deliverables as non-compliant according to Quality standards. You are looking for a document that mentions the exact product attributes and a guideline on how to verify them during quality control. Which of the following documents contains these details? |  | Quality Management Plan | Quality Metrics | Risk Management Plan | Lessons Learnt Register | Answer option b. | A quality metric specifically describes a project or product attribute and how the Control Quality process will verify compliance with it.
Exam 6 | #9. A group of experienced team resources, each has spent at least two years in the company, recently joined your project team, and working with each other for the first time. According to the Tuckman ladder, this team is in the _____ stage. |  | Forming | Storming | Norming | Performing | Answer option a. | “Forming”. In this phase the team members meet and learn about the project and their formal roles and responsibilities. According to the question, the team consists of experienced members, but they are working with each other for the first time. That means they are still in the forming stage.
Exam 6 | #10. A senior designer has requested a day off for the coming Monday. You look at the Project Schedule and find out that he is assigned a critical activity and can not be given a day off in the coming week. He mentions that he will not be able to come as he has to go to the airport on Monday and pick up a relative and drive him home. You devise a win-win solution to this conflict by assigning another team member to do the designer’s task by going to the airport, while the designer will come to the office on Monday and do his assigned task. The designer seems happy to hear this solution. Which conflict resolution technique did you use? |  | Withdraw | Smooth | Compromise | Collaborate | Answer option d. “ | Collaborate” technique involves incorporating multiple viewpoints and insights from differing perspectives; requires a cooperative attitude and open dialogue that typically leads to consensus and commitment. This approach can result in a win-win situation.
Exam 6 | #11. You are the Scrum Master of a junior Scrum team. You keep informing your team members about the importance of proper implementation and following the process for if the process is not followed, the team may end up in “technical debt;” What is technical debt? |  | Technical debt is a collection of tasks that are challenging for the current development Team to implement and complete. | Technical debt is a collection of tasks that are left behind by the development Team to complete at the end of the project. | Technical debt is the consequence of using proper implementation techniques usually resulting in high financial debts. | Technical debt is the consequence of speeding up the software delivery process without implementing a full-scale solution. | Answer option d. | Technical debt describes the consequences of using quick fixes to expedite the delivery of a piece or a functionality of a product or software, which later needs to be reworked (refactored). In other words, it is the result of prioritizing fast delivery over perfect code.
Exam 6 | #12. You are in the early stages of the project with very limited data about the scope, time, and cost. The sponsor asked to provide an early estimate for the budget based on your experience. What estimation technique would you use? |  | Parametric estimating | Rough order of magnitude | Analogous cost estimating | Bottom-up estimating | Answer option b. | “Rough order of magnitude” is used during the project initiation phase to estimate cost, duration, or resources in the range of −25% to 75%.
Exam 6 | #13. The customer requested to change one of the major requirements during the project planning, just after the project scope planning completion. What should the project manager do first? |  | Reject the change | Review the change against the scope statement | Raise change request | Apply the change immediately | Answer option b. | The best course of action is to “Review the change against the scope statement” (option b.) to validate the change against what is already agreed and analyze its impact on the project scope/Product scope. If you decide to “Reject the change” (answer option a.), there are no valid reasons for such action. If you decide to “Raise change request“ (answer option c.), the project plan is not approved yet so, there is no need for such action. If you decide to “Apply the change immediately “(answer option d.), the change hasn’t been validated against the scope baseline yet.
Exam 6 | #14. Geraldine is working with a client to assist in their transition from predictive to agile project approaches. In her discussions with the internal team who will be responsible for managing this change, she lists potential roadblocks to success. Which of the following is NOT a roadblock to the transition from predictive to agile project management? |  | Many employees are specialized contributors and have limited incentives to diversify their skills. | Leaders are often rewarded for the efficiencies and success of their individual areas and are unaccustomed to working toward an end-to-end project delivery flow. | The company has visible and active executive sponsorship. | Siloed departments create dependencies that prevent accelerated delivery and do not build cross-functional teams. | Answer option c. | Answer option c. Visible and active executive sponsorship is a benefit, not roadblock. The other three are potential roadblock to the change to agile project management. Answer option c. Visible and active executive sponsorship is a benefit, not roadblock. The other three are potential roadblock to the change to agile project management.
Exam 6 | #15. A team member has taken unplanned leave during the execution of a project, causing the project team to reschedule some tasks. As a result, critical activities are now occurring at the same time. What is the first thing the project manager should do? |  | Assess the newly introduced risks with the project team. | Mitigate risks by reverting to the original schedule. | Revise the risk register and then rank the project's risks. | Identify suitable responses for the newly introduced risks. | Answer option a. | The project manager and the project team should evaluate the newly discovered risk. The project manager should also update the risk register, analyze, and prioritize the risk, and plan the response.
Exam 6 | #16. There is an ongoing project to upgrade the existing system to a newly launched technology. However, the company decided to terminate it. What should the project manager do next? |  | Document the reasons for termination | Complete the current phase then close the project | Amend the project business case to accommodate the new technology | None of the above | Answer option a. | Answer option a. The best course of action is to “Document the reasons for termination” (option a.). If you decide to “Complete the current phase then close the project” (answer option b.) you would be wasting the company resources unnecessarily. If you decide to “Amend project business case to accommodate the new technology“ (answer option c.) it is not your decision to make since it’s up to the sponsor and senior management to decide. Answer option a. The best course of action is to “Document the reasons for termination” (option a.). If you decide to “Complete the current phase then close the project” (answer option b.) you would be wasting the company resources unnecessarily. If you decide to “Amend project business case to accommodate the new technology“ (answer option c.) it is not your decision to make since it’s up to the sponsor and senior management to decide.
Exam 6 | #17. You are working on Plan Cost Management for your current running project. Which is not an enterprise environmental factor you would consider? |  | Financial databases | Project management information system that provides alternatives for managing costProject management information system that provides alternatives for managing cost | Published commercial information | Organizational culture and structure that can influence cost management | Answer option a. | The best answer is “Financial databases” (Answer option a.) as it is an Organizational Process Asset. “Project management information system provides alternatives for managing cost” (Answer option b.) and “Published commercial information” (Answer option c.) and “Organizational culture and structure can influence cost management” (Answer option d.) are all enterprise environmental factors that can influence the process while the question is asking which is NOT thus these answers are not valid.
Exam 6 | #18. Your organization has always managed its projects using the traditional approach, but market conditions are quickly changing and in order to stay competitive, management decides to give Agile a try. Your new project will have to adopt some of these practices, yet you are unsure how to obtain the necessary expertise for yourself and other managers, and for the team members. After discussions with top-level executives, an agreement is reached that holding ___________is the most appropriate option. |  | One-on-one Agile mentoring | Sprint planning sessions | Scrum certification training | Agile workshops | Answer option d. | Answer option d. The scenario mentioned the PM and team all needing training in Agile, and the organization having no prior experience in it. General workshops on Agile would be the most effective for providing everybody a basic understanding of Agile. One-on-one mentoring may be too time consuming, and the organization lacks experienced Agile staff, and Scrum certifications may be overkill at this stage. Also, the question mentions Agile, and not specifically Scrum. Sprint planning is a Scrum event. Answer option d. The scenario mentioned the PM and team all needing training in Agile, and the organization having no prior experience in it. General workshops on Agile would be the most effective for providing everybody a basic understanding of Agile. One-on-one mentoring may be too time consuming, and the organization lacks experienced Agile staff, and Scrum certifications may be overkill at this stage. Also, the question mentions Agile, and not specifically Scrum. Sprint planning is a Scrum event.
Exam 6 | #19. Alex is working on a new product deployment project. His company just found out that their competitor will introduce an alternative product one month earlier than the project's end date. Despite all risks, the company decided to launch the new product two months earlier. Additionally, there is no extra budget. Which technique can help Alex achieve this objective? |  | Fast-tracking | Crashing | Resource leveling | Resource smoothing | Answer option a | . “Fast-tracking” is the best answer since it won’t cause extra costs and management is fine with the associated risks.
Exam 6 | #20. You are working with a project team that works on different company premises. This distance causes trust and communication issues. You have tried various communication tools and technologies, but the situation didn't improve. What technique can you use to improve the situation? |  | Virtual teams | Communication technology | Colocation | Recognition and rewards | Answer option c. | The best answer is “Colocation” (Answer option c.); bringing them in the same location would increase trust and strengthen their relationships. “Virtual teams” (Answer option a.), and “Communication technology” (Answer option b.) are already mentioned to be ineffective within the question. “Recognition and rewards” (Answer option d.) is irrelevant to the question.
Exam 6 | #21. Bill’s project team is currently executing a warehouse management system project for logistics company ABC. The project is high risk, highly complex, and has ambiguous requirements, and the project team has decided to adopt Agile. If a higher rate of process improvement is required of the project team assigned to the project, which Agile technique can help to achieve this objective? |  | Adopting FDD for the development phase. | Completing all requirements before beginning the development work. | Scheduling daily standups to determine work in progress (WIP). | Frequent retrospection on project team processes. | Answer option d. | Conducting frequent Retrospectives (after each iteration) can facilitate discussions on team processes that went well and what can be improved.
Exam 6 | #22. A project manager is communicating with the customer’s project manager. What type of communication dimension is this considered to be? |  | Internal | Hierarchical Horizontal | Hierarchical Upward | External | Answer option d. | “External” Focus on external stakeholders such as customers, vendors, other projects, organizations, government, the public, and environmental advocates.
Exam 6 | #23. During the monthly review, the quality team discussed a repeated fault made by the technical team. After the discussion , you decided to apply the proper corrective action. Of the following, which can be defined as corrective action? |  | Provide the entire technical team with extensive training | Fix all reported issues | Instruct the technicians how to do it right | All of the above | Answer option c. | Answer option c. The best answer is “Instruct the technicians how to do it right” (Answer option c.) is the only corrective action. “Provide the entire technical team with extensive training” (Answer option a.) is a preventive action. “Fix all reported issues” (Answer option b.) is a defect repair. “All of the above” (Answer option d.) not accurate since A and B are not correct. Answer option c. The best answer is “Instruct the technicians how to do it right” (Answer option c.) is the only corrective action. “Provide the entire technical team with extensive training” (Answer option a.) is a preventive action. “Fix all reported issues” (Answer option b.) is a defect repair. “All of the above” (Answer option d.) not accurate since A and B are not correct.
Exam 6 | #24. While reviewing the performance reports, the project manager found the SPI equals to 1. This indicates to _____ . |  | The project is ahead of schedule with 10% | The project is behind schedule | The project is on schedule | The project is ahead of schedule with 100% | Answer option c. | “The project is on schedule” when the schedule performance index equals 1 means the project is on schedule.
Exam 6 | #25. A project manager is working on ensuring the information needs of the project and its stakeholders are met. He is trying to identify the enterprise environmental factors that can influence this process. What should he consider to reach his goal? |  | Organizational communication requirements | Corporate Policies and procedures | Global, regional, or local trends, practices, or habits | Historical information | Answer option c. | “Global, regional, or local trends, practices, or habits” is the enterprise environmental factor that can influence this process, the rest of the answer options are organizational process assets.
Exam 6 | #26. Which technique supports the concept of progressive elaboration in iterative cycles of mock-up creation, user experimentation, feedback generation, and revision? |  | Prototyping | Context diagram | Facilitation | Observation/conversation | Answer option a. | “Prototyping” technique supports the concept of progressive elaboration in iterative cycles of mock-up creation, user experimentation, feedback generation, and prototype revision.
Exam 6 | #27. The project is well underway. Your team is well organized; they are working on their iterations without major issues. They share their feedback during daily standups and seem to be a quite interdependent team. On Friday, weeks before the final release is planned, you find out that the funding for the project is being cut. Who provides ongoing funding of the project in Scrum? |  | The Project Manager | The Management | The Scrum Master | The Product Owner | Answer option d. | “The Product Owner” achieves initial and ongoing funding for the project by creating the project’s initial overall requirements, return on investment (ROI) objectives, and release plans.
Exam 6 | #28. Geraldine is working with a client to assist in their transition from predictive to agile project approaches. In her discussions with the internal team who will be responsible for managing this change, she lists potential approaches to improve the likelihood of success. Which of the following is NOT a helpful approach to the transition from predictive to agile project management? |  | Create a plan for and implement the education and coaching of teams. | Progressively pace the adoption of agile practices instead of flipping a switch. | Encourage leadership to lead by example using agile techniques and practices. | Assure anyone resistant to the change that no personnel changes will occur due to the new project approaches. | Answer option d. | There is no guarantee that personnel changes will not occur, and ethical leaders will not make statements that are untrue.
Exam 6 | #29. You are managing a new project with a high volume of PM tasks. Accordingly, the sponsor approved adding a project coordinator to your team. To lighten your workload, which of the following tasks would you assign to him? |  | Engage different teams and align their work together | Oversee different workstreams and realign the ones off-track | Oversee project risk management activities | Develop and maintain business documents | Answer option c. | The best course of action is to “Oversee project risk management activities” (Answer option c.). If you assign “Engage different teams and align their work together” (answer option a.) or “Oversee different workstreams and realign the ones off-track work” (answer option b.) you would be delegating a project integration management activity that cannot be delegated to someone other than the project manager. “Develop and maintain business documents” (answer option d.) is the project sponsor duty as business documents consist of a Business case and Benefits management plan and both are developed by the project sponsor.
Exam 6 | #30. Jerry is an Agile Product Owner assigned to work with Program Manager Todd who is leading a complex Software Program for Company XYZ. Todd insists that the team create highly detailed project plans before initiating project work. What should Jerry do? |  | Begin applying for other Product Owner openings within the organization. | Draw the line, and don’t compromise on Agile values and principles. | Escalate the issue to Senior Management. | Show Todd the benefits and past successes of using Agile techniques on previous projects. | Answer option d. | Helping the project manager to understand the benefits of Agile approaches over Predictive approaches is the best approach.
Exam 6 | #31. A project manager is using historical data to understand what was going on in a project with several defects in the software program that is being developed as a part of the project. What technique will you use for this? |  | Alternatives analysis | Trend analysis | Root cause analysis | Variance analysis | Answer option b. | “Trend analysis” focuses on detecting patterns in historical data. Actions may be taken to maintain, change, or stop the current trend as required.
Exam 6 | #32. You are assigned to an up-coming internal project that aims to realign the company performance to the annual financial target. While reading the project charter, the sponsor stressed that there is no time for developing a project plan, and you need to start the execution as soon as possible, then re-plan as you go. What would you do? |  | Reject the project | Explain the importance of planning and insist on performing planning activities | Accept the project after the sponsor officially accepts the risks | Accept the assignment as an agile project | Answer option b. | Answer option b. The best course of action is to “Explain the importance of planning and insist on performing planning activities” (option b.). If you decide to “Reject the project” (answer option a.) it will be a premature decision. If you decide to “Accept the project after the sponsor officially accepts the risks“(answer option c.) you are risking the project failure in return for saving yourself which is unethical behavior. If you decide to “Accept the assignment as an agile project “(answer option d.) you are risking the project with a wrong development approach leading to either its failure or inefficiency. Answer option b. The best course of action is to “Explain the importance of planning and insist on performing planning activities” (option b.). If you decide to “Reject the project” (answer option a.) it will be a premature decision. If you decide to “Accept the project after the sponsor officially accepts the risks“(answer option c.) you are risking the project failure in return for saving yourself which is unethical behavior. If you decide to “Accept the assignment as an agile project “(answer option d.) you are risking the project with a wrong development approach leading to either its failure or inefficiency.
Exam 6 | #33. The rescheduling of the project schedule and the project budget to fit funding availability is a result of _____ . |  | Financing | Project funding requirements | Funding limit reconciliation | Estimating and budgeting | Answer option c. | “Funding limit reconciliation” is the process of comparing the planned expenditure of project funds against any limits on the commitment of funds for the project to identify any variances between the funding limits and the planned expenditures.
Exam 6 | #34. Sue is a project manager looking for a new career opportunity. According to her career plans, she is targeting a company where the project managers are highly empowered. As she just received multiple job offers, which of the following offers should she accept? |  | Company XYZ follows an Organic structure | Company ICT follows a Multidivisional structure | Company WV follows Matrix – balanced structure | Company STY follows Matrix – strong structure | Answer option d. | Answer option d. The best course of action is to “Company STY follows Matrix – strong structure” (option d.) as her authority level would be Moderate to high. If she decides to accept “Company XYZ follows an Organic structure” (answer option a.), “Company ICT follows Multi-divisional structure “(answer option b.). “Company WV follows Matrix – balanced structure “ (answer option c.) her level of authority would be Low to moderate.
Exam 6 | #35. The use of websites, web publishing, blogs, and applications to engage with stakeholders is called _____ . |  | Social media management | The use of automated tools | Electronic communications management | Electronic project management tools | Answer option a. | “Social media management” which includes websites, web publishing, blogs, and applications, offers the opportunity to engage with stakeholders and form online communities.
Exam 6 | #36. During the monthly project meeting, one of the key stakeholders complained that his previous concern was not resolved since the last meeting. In order to track that concern, which of the following documents would you review? |  | Stakeholder register | Risk register | Issue log | Change log | Answer option c. | “Issue log” contains records of all project issues
Exam 6 | #37. Mary just earned her Scrum Master Certificate, and is excited to use Scrum as a new approach to managing software development projects. However, the organization is not knowledgeable about scrum practices, and they naturally resist listening to her. What would be the best approach for Mary to introduce Agile and Scrum methods successfully? |  | Train the organization in the basics of Scrum and order them to use their new knowledge to manage projects. | Ask the organization to get acquainted with Scrum practices to start working on the new projects as soon as possible. | Show the organization the Scrum Roadmap and ask them to start using the methodology. | Train the organization in the foundations of the agile mindset and its principles. Also, facilitate workshops where project teams can learn and implement the new method more easily. | Answer option d. | Change is better managed when we mentor others. In this case, mentoring implies teaching the new method and facilitating practical sessions that allow people to grasp the methodology. Also, this approach helps team members to learn, unlearn, and relearn.
Exam 6 | #38. A project manager is managing a new car development project. As the car model is targeting a specific market segment, the initial prototype is designed to meet their requirements. During consumer model testing, the car features didn't satisfy 5% of the participants. Since the testing participants were not representing the whole targeted segment (100%), what should the project manager do? |  | Rectify the reported issues and develop a new prototype | Disregard the feedback, since it’s only 5% | Investigate to confirm that the 5% who were dissatisfied are not from the targeted segment | Discard the old design and start all over | Answer option c. | The best course of action is “Investigate to confirm the dissatisfied 5% are not from the targeted segment” (option c.) which will confirm whether or not the feedback should be accounted for. If he decides to “Rectify the reported issues and develop a new prototype” (answer option a.) or “Discard the old design and start all over” (answer option d.), there is no confirmation of the 5% representing the targeted segment, which means a loss for the company and possible product failure. If he decides to “Disregard the feedback it’s only 5%“( answer option b.) there are no guarantees that this 5% of feedback is not a requirement of the targeted segment.
Exam 6 | #39. You are about to complete your project. You are preparing a presentation to summarize the project's performance and gather evidence on how the project met its completion criteria. You are preparing __________ of the project. |  | Project business documents | Final report | Assumption log | Project charter | Answer option b. | “Final report” provides a summary of the project performance.
Exam 6 | #40. A project manager has been assigned to a recently approved project. While reading the project charter, he noticed that it contains the names of the multiple specialized technicians who are already assigned to the project. This is an example of _____ . |  | Pre-assignments | Negotiation | Resource availability | Team assignments | Answer option a. | “Pre-assignments”. Pre-assignment might include the team members who have already been assigned during the process of developing the Project Charter.
Exam 6 | #41. Louis is a Program Manager responsible for deploying a new resource management system for client Company ABC. He needs to analyze the company’s current processes and procedures, and design future-state processes with the Company ABC’s subject matter experts to suit the needs of the business. According to the contract, all prototypes presented to the client must accompany user instruction guides. His team objects to this documentation requirement and insists on developing a user manual only at the very end of the project. What should Louis do? |  | Accept the team’s approach; Agile Manifesto values working software over comprehensive documentation. | Negotiate with the team and convince them to develop the instruction guides before releasing any prototypes. | Let the team know that producing the user instruction set with the released prototype is a contractual requirement. | Negotiate with the client company and convince them to remove the instruction guide requirement. | Answer option c. | Although Agile prefers working software over comprehensive documentation, it does not mean there is no need for documentation at all. The project manager must conform to all contractual agreements and these agreements must be communicated to the team.
Exam 6 | #42. You are working with the product owner to determine a viable product iteration plan. As you discuss various features and prioritize them, you are both trying to understand what features should have higher priority. What project document should the project manager and product owner consult? |  | Task list | Iteration plan | Release plan | Scrum backlog | Answer option c. | “Release plan” is a tactical document designed to capture and track the features planned for an upcoming release. A release plan usually spans only a few months and is typically an internal working document for product and development teams.
Exam 6 | #43. A project manager is developing informal relationships and interacting with multiple stakeholders to exchange information and build contacts. Which interpersonal and team skills is he using? |  | Active listening | Political awareness | Networking | Cultural awareness | Answer option c. | “Networking” is interacting with others to exchange information and develop contacts.
Exam 6 | #44. As a Product Owner who believes in teamwork, you attend the daily stand ups to inspire the team and motivate them to work better. You believe that a team’s success with Scrum depends on five values that are defined in the methodology. What are Scrum’s values? |  | Commitment, Courage, Focus, Openness, Respect | Commitment, Dedication, Initiative, Productivity, Respect | Commitment, Courage, Cooperation, Teamwork, Respect | Commitment, Courage, Focus, Openness, Respect | Answer option a. | The Scrum Guide has determined five (5) values; they include: Commitment, Courage, Focus, Openness, Respect
Exam 6 | #45. You replaced another project manager on a two-year project. During the handover meeting, the previous project manager highlighted that the team has many conflicts, especially when it comes to team meetings. What should you do? |  | Limit the team meeting attendees | Review team charter and update ground rules | Apply Conflict resolution techniques | Use cultural awareness | Answer option b. | The best course of action is to “Review team charter and update ground rules” (option b.). Setting ground rules will reduce the tension between the team members and increase the team trust. If you decide to “Limit the team meeting attendees” (answer option a.) There are no valid reasons for such action to be effective. If you decide to “Apply Conflict resolution techniques“ (answer option c.) this action might solve arising issues however it won’t prevent them from happening. “Use cultural awareness“ (answer option b.) is not a good answer as the question did not mention any cultural differences as the root cause of the issues.
Exam 6 | #46. Your project team just completed a major deliverable. After passing the internal testing, the project sponsor advised you to invite the customer technicians to perform a review to confirm that the deliverable is matching the original requirements. What technique will they use? |  | Audit | Inspection | Quality assurance | Testing & product Evaluation | Answer option b. | “Inspection” is the examination of a work product to determine if it conforms to documented standards.
Exam 6 | #47. A project manager recently joined the Company XYZ to manage the operations of a restructuring project. As soon as he joined, he mapped out the organization structure and gathered information about the informal power within the company. This is an example of _____ . |  | Active listening | Political awareness | Networking | Cultural awareness | Answer option b. | “Political awareness” concerns the recognition of power relationships, both formal and informal, and the willingness to operate within these structures.
Exam 6 | #48. Alex is a project manager who is planning how to manage the project scope. As he is trying to identify the enterprise environmental factors that can influence this process, he should not consider _____ . |  | Organization’s culture | Policies and procedures | Personnel administration | Marketplace conditions | Answer option b. | The best answer is “Policies and procedures” (Answer option a.) since it is not an EEF. “Organization’s culture” (Answer option a), “Personnel administration” (Answer option c.), and “Marketplace conditions” (Answer option d.) are all enterprise environmental factors that can influence the process while the question is asking which is NOT, thus these answers are not valid.
Exam 6 | #49. Company XYZ initiated a new transformation project that aims to digitize employees’ internal requests. Due to budgetary and resource constraints, the company requested the project manager to use the available internal resources, and in return, they confirmed that they are flexible with the project time-frame. What scheduling technique would you advise to use? |  | PDM Critical chain method | On-demand scheduling | Critical path method | Iterative scheduling with a backlog | Answer option b. | “On-demand scheduling” is based on the theory of constraints and pull-based scheduling concepts from lean manufacturing to limit a team’s work in progress to balance the demand against the team’s delivery throughput.
Exam 6 | #50. Your team is confused about the idea of "ideal time." They think that this ideal time is when they are not disturbed by emails, meetings, when they can work 100% on their tasks. You explain that the concept of “ideal time” refers to: |  | The best time to undertake a story | The shortest realistic estimate for doing the work | How long a task will take without interruptions or impediments | How long a task will take including predictable delays and distractions | Answer option c. | Ideal time refers to how long it will take to complete a work item if there are no interruptions, impediments, delays, or distractions.
Exam 6 | #51. During the project implementation, the sponsor invited you to a meeting and asked to speed up the project by two months without affecting the quality or scope of the project, and offered an additional budget in return. Which technique can help you to achieve this objective? |  | Resource leveling | Resource smoothing | Fast-tracking | Crashing | Answer option d. | “Crashing” is a technique used to shorten the schedule duration for the least incremental cost by adding resources and may result in increased risk and/or cost.
Exam 6 | #52. At the monthly project review meeting, the quality team presented their report for the latest product review results. What technique did they use? |  | Inspections | Expert judgment | Prototyping | Audit | Answer option a. | “Inspections” Inspections are sometimes called reviews, product reviews, and walkthroughs.
Exam 6 | #53. _____ is a project scheduling method based on adaptive life cycles, where product features are developed using time-boxed periods of work. |  | Iterative scheduling with a backlog | On-demand scheduling | Critical path method | Kanban system | Answer option a. | “Iterative scheduling with a backlog” in an adaptive approach project scheduling method based on adaptive life cycles. Where product features are developed using time-boxed periods of work.
Exam 6 | #54. During the development of the project management plan, you need to define the right lifecycle approach. As you turn to your sponsor, he advises you to gather ideas from the project team and key stakeholders. Which of the following techniques can best help you to achieve this goal? |  | Checklists | Interviews | Brainstorming | Survey | Answer option c. | The best answer “Brainstorming” (Answer option b.) Brainstorming is a technique that is used to identify a list of ideas in a short period. It is conducted in a group environment and is led by a facilitator.
Exam 6 | #55. You received the quality report informing you about defects and their potential causes. You need to identify the areas of priority in order to focus on the most important issues first. Which Data representation technique would you use? |  | Cause-and-effect diagrams | Histograms | Affinity diagrams | Matrix diagrams | Answer option c. | “Affinity diagrams” can organize potential causes of defects into groups showing areas that should be focused on the most.
Exam 6 | #56. Velocity is a measure of the amount of work a Team can tackle during a single Sprint and is the key metric in Scrum The velocity of your Scrum team should be estimated before completing the first few iterations, Based on a series of past sprints, the estimation of velocity typically stabilizes and provides a more reliable basis for improving the accuracy of both short-term and longer-term planning of your Scrum projects. What measure will you most likely use for calculating the velocity of the Team? |  | Ideal Hours | Story Points | Elapsed Hours | Man-hours | Answer option b. | “Story points” are an indication of how much work the team can get done. Stories should be estimated collaboratively by the team and never by a single developer. Story points reward team members for solving problems based on difficulty, not time spent. This keeps team members focused on delivering value, not spending time.
Exam 6 | #57. You have been awarded a certificate for the most liked project manager in the company. The CEO presents you with the award and reads out the citation, “An excellent project manager; always helping and putting others first; interacting one-on-one with all team members, helping them grow and transform to be the best they can be; and transforming the team into a collaborative union, and always charismatic personality .” What type of leadership style do you have? |  | Transactional | Laissez-faire | Charismatic | Servant leader | Answer option d. | “Servant leader” demonstrates a commitment to serve and put other people first; focuses on other people’s growth, learning, development, autonomy, and well-being; concentrates on relationships, community, and collaboration; leadership is secondary and emerges after service.
Exam 6 | #58. You’re a scrum master for a new automotive app that detects car faults and reports them back to the service center. Before the start of the next sprint, the product owner wants to write a checklist of the types of work that the team is expected to complete by the end of the current sprint. Meeting this criteria means that the work is potentially shippable. Besides, this checklist should serve as an acceptance criteria that applies to the product backlog items within this sprint. What is the product owner trying to define? |  | Sprint Goal | Definition of Ready (DoR) | Definition of Done (DoD) | Project Exit Criteria | Answer option c. | Definition of Done (DoD) is a team’s checklist of all the criteria required to be met so that a deliverable can be considered ready for customer use (shippable).
Exam 6 | #59. The project manager is discussing with the team about delivering a viable product for the customer in each increment. They agree that the core value must be in line with customer expectations. Based on the essential value requested by the customer, you want to discuss what is the bare minimum value of the product that can be realized or established. What is the team about to create? |  | Minimum Viable Product | Completed deliverable | Product roadmap | Minimum Business Increment | Answer option a. | “Minimum Viable Product” is a version of a product with just enough features to be usable by early customers who can then provide feedback for future product development.
Exam 6 | #60. Suzy is a project manager working on identifying her project’s stakeholders. Her company has a strong PMO knowledge base. She requested from PMO to provide her a stakeholder register template that she can use in her project. Stakeholder register template is part of _______ . |  | Project documents | Organizational process assets | Enterprise environmental factors | Agreement | Answer option b. | “Organizational process assets” contains all project document templates including Stakeholder register templates.
Exam 6 | #61. During the sprint meeting for a software development project, the project manager was taking votes for a decision, and one team member held his fist closed. What does this mean? |  | He is not interested to participate | He is fine with the decision | He disagrees with the decision | He fully supports the decision | Answer option c. | Holding a closed fist in the “fist of five” voting technique means the member disagrees with the decision. The best answer is “He disagrees with the decision” (Answer option c.).
Exam 6 | #62. You received a new project assignment, where the project sponsor provided you with advanced drafts of the business documents and asked for your comments and recommendations before their final signature. At which stage does this project stand? |  | Initiation | Post project work | Planning | Pre-project initiation work | Answer option d. | “Pre-project initiation work” (Answer option d.) project business documents include business case and benefits management plan and both documents are developed and signed off before the project start.
Exam 6 | #63. Ivan is working as a Project Manager on an Agile project team. The project sponsor sits on another floor and prefers to communicate by email. What will he do next? |  | Stop communicating with the project sponsor until they come to a daily standup. | Ensure he communicates by email only so that the sponsor is comfortable. | Ask the sponsor to co-locate with the Agile team for a few days a week, to ensure face-to-face communication and access to the visual project information. | Set additional meetings with the sponsor so he can update them personally. | Answer option c. | Agile promotes working in co-located spaces, where ideas and information can be best shared freely. Face-to-face communication provides the best opportunity to ask questions and gather immediate feedback, resolving any misunderstandings.
Exam 6 | #64. You are managing a software development project with an agile approach. You just completed release One, what should you do to prepare for the next release? |  | Confirm Scope baseline is up to date | Review Backlogs | Confirm Scope statement still valid | Review previous release WBS | Answer option b. “ . “ | Answer option b. The best answer is “Review Backlog” (Answer option b.) as it contains current requirements. “Confirm Scope baseline is up to date” (Answer option a.) and “Confirm Scope statement still valid” (Answer option c.) are both more relevant with predictive life cycles. “Review previous release WBS” (Answer option d.) will not be useful for obtaining current requirements. Answer option b. The best answer is “Review Backlog” (Answer option b.) as it contains current requirements. “Confirm Scope baseline is up to date” (Answer option a.) and “ Confirm Scope statement still valid” (Answer option c.) are both more relevant with predictive life cycles . “ Review previous release WBS” (Answer option d.) will not be useful for obtaining current requirements.
Exam 6 | #65. A project manager is worried about the project risk management processes’ effectiveness. To ensure effectiveness, what technique should he use? |  | Quality Audits | Inspection | Risk audits | PMO audit | Answer option c. | “Risk audits” Risk audits are a type of audit that may be used to consider the effectiveness of the risk management process.
Exam 6 | #66. During the project review, the report shows that the budget is $50K, estimate to complete is $33K, and the actual cost is $20K. This indicates that _____ . |  | Project is over budget | Project is on budget | Project is under budget | Cannot say | Answer option a. “ | Project is over budget“ VAC = BAC – EAC, EAC = AC Bottom-up ETC accordingly, EAC=20 33=$53K, VAC=50-53=-$3K, when VAC is Negative = Over planned cost
Exam 6 | #67. Your project team began to work together, trust each other, and adjust their work habits and behaviors to support the team. Where does your team stand in the Tuckman ladder? |  | Forming | Storming | Norming | Performing | Answer option c. | “Norming” In this phase, team members begin to work together and adjust their work habits and behaviors to support the team. The team members learn to trust each other.
Exam 6 | #68. Johnny is leading an agile team that has not been working together for long. As he considers the Agile Manifesto value of “importance of individuals and interactions,” he thinks about the benefits of teams once they have reached their peak performance. These benefits include all of the following, EXCEPT: |  | People are more likely to collaborate in teams that have reached peak performance. | Teams finish valuable work faster. | Teams with clearly specified roles that segregate duties reach peak performance at a faster rate than cross-functional groups. | Teams waste much less time because they do not multitask. | Answer option b. | Teams that have reached peak performance are more collaborative, finish valuable work faster and waste less time due to the ability to focus. A core tenant of agile approaches is the use of cross-functional development groups.
Exam 6 | #69. A project team is distributed across multiple cities. To facilitate the team communications, the project manager created a portal for the team to share knowledge and information and arranged a weekly video conference meeting for the team to meet online and discuss the project challenges. This is an example of _____ . |  | Pre-assignments | Cultural awareness | Colocation | Communication technology | Answer option d. | “Communication technology” the use of the shared portal and Video conference is an example of Communication technology and virtual teams and since virtual teams are not among the answers then Communication technology is the best answer.
Exam 6 | #70. The uncontrolled expansion to the product or project scope without adjustments to time, cost, and resources is referred to as _____ . |  | Integrated Change Control | Scope creep | Gold plating | Change management | Answer option b. | “Scope creep” refers to uncontrolled expansion to product or project scope without adjustments to time, cost, and resources which harms the project and extends its scope beyond the original objectives impacting not only scope but also cost, time, resources, risks, and other project parameters.
Exam 6 | #71. During the review for approval of your project management plan, a stakeholder raised a concern that a key component of the project deliverable is missing in the plan. You should _____ . |  | Submit change request | Amend the plan with the missing requirement | Disregard the concern | Review the requirements documentation and traceability matrix | Answer option d. | Answer option d. The best answer is “Review the requirements documentation and traceability matrix” (Answer option d.) to confirm whether the requirement was discussed before and what its status is. If you have decided to “Submit a change request” (Answer option a.) you should know that the project plan is not yet approved, therefore there is no need for a change request. “Amend the plan with the missing requirement” (Answer option b.) the requirement may have been reviewed and rejected before for any reason. “Disregard the concern” (Answer Option c.) will both harm the relationship with the stakeholder and might harm the project itself if it was dropped by mistake. Answer option d. The best answer is “Review the requirements documentation and traceability matrix” ( Answer option d.) to confirm whether the requirement was discussed before and what its status is. If you have decided to “Submit a change request” (Answer option a.) you should know that the project plan is not yet approved, therefore there is no need for a change request. “Amend the plan with the missing requirement” (Answer option b.) the requirement may have been reviewed and rejected before for any reason. “Disregard the concern” (Answer Option c.) will both harm the relationship with the stakeholder and might harm the project itself if it was dropped by mistake.
Exam 6 | #72. Your Agile project has run into some difficulties due to the economic situation. This change caused your key stakeholders to reconsider the requirements. During a ___________session, the need to split some of the stories becomes apparent, and the project owner strives to make sure the team has enough work they can execute in the next iterations. |  | Sprint planning | Retrospective | Backlog grooming | Iteration planning | Answer option c. | Backlog grooming. Backlog grooming, or refinement sessions, is a recurring event for an Agile product development team. The main goal is to make sure the team has enough user stories ready to work on in the next few sprints.
Exam 6 | #73. During which process the project manager receives formal documentation from the customer or sponsor acknowledging the formal acceptance of the project’s deliverables? |  | Close project | Control scope | Control quality | Validate scope | Answer option d. | “Validate scope” while performing validate scope process, verified deliverables get reviewed by customer/sponsor, and once approved it becomes validated deliverable and gets signed off.
Exam 6 | #74. You have just been hired as a Project Manager at the Alpha Omega Group. A Senior Project Manager takes you on a visit to the project site that he manages. He shows you the different processes that are being followed at the site. He asks you to compare and learn about the best practices that you can apply on your project site. Which technique is the most suitable one to apply in this case? |  | Control Charts | Surveys | Questionnaires | Benchmarking | Answer option d. | “Benchmarking” involves comparing actual or planned products, processes, and practices to those of comparable organizations to identify best practices, generate ideas for improvement, and provide a basis for measuring performance.
Exam 6 | #75. You are managing a software project. The project team has just completed and published the first development release. In the next step, test engineers will start an organized and constructed investigation to detect bugs or any other points which do not conform to quality requirements. What technique will the test engineers use? |  | Audit | Quality assurance | Inspection | Testing & Product Evaluation | Answer option d. | “Testing & product evaluation” is an organized and constructed investigation conducted to provide objective information about the quality of the product or service that is being tested in accordance with the project requirements. The intent of testing is to find errors, defects, bugs, or other nonconformance problems in the product or service.
Exam 6 | #76. Julie has been brought into a Scrum team to take over for the Scrum Master who is going out on leave for several months. She attends her first Stand-up meeting where each of the eight Developers explain what they are working on today and any obstacles they have encountered. The exiting Scrum Master, Marcus, mentions that the team has failed to complete everything on their Sprint for each of the last three Sprints and he hopes that will not be the case in this sprint or in the future. Julie recognizes one thing immediately that is contributing to this failure to deliver within the Sprints. Which of the following could be a contributing factor? |  | The team is experiencing upheaval with the changing of Scrum Masters. | In the daily Scrum, there is no mention of what has been accomplished. | The Scrum Master did not ask additional questions to determine the cause of the obstacles. | The Scrum Team is too large. 8 Developers is too many. | Answer option b. | A primary focus of Scrum Project Management is what is accomplished, and the Daily Scrum does not include any mention of this. If managed appropriately, a self-organizing team should not experience any decrease in productivity due to the replacement of the Scrum Master. The Scrum Master is expected to NOT delay the completion of the Scrum by discussing obstacles at length. If more information is required, this can be handled in a 1:1 interaction. The best team size of Developers is between 3 and 9.
Exam 6 | #77. _____ examines project performance over time and can be used to determine whether the performance is improving or deteriorating? |  | Alternatives analysis | Cost-benefit analysis | Performance reviews | Trend analysis | Answer option d. | “Trend analysis” is used to forecast future performance based on past results. Accordingly, it can examine project performance over time and can be used to determine whether performance is improving or deteriorating.
Exam 6 | #78. Bryce is an experienced project manager, and a large software corporation TechNow just hired him to manage projects. He’s also realized that he will need to use agile project management to succeed in his future endeavors. However, the company blindly supports predictive project management. What is the best strategy for Bryce to transition the company to agile project management? |  | Make an overnight change of direction and instruct all collaborators to start using agile methods. | Train teams in agile project management and then ask them to start using the agile management approach. | Use iterative methods at the beginning to promote learning and alignment among teams and stakeholders. Then, using incremental methods to create business value and return on investment to project sponsors. | Not change anything, as the predictive approach is sufficient to lead the company towards achieving its goals. | Answer option c. | Transitioning to an agile mindset will take time, and teams and stakeholders need tangible results to accept change. Therefore, it is best to go step by step with low to medium uncertainty, complexity, and risks projects.
Exam 6 | #79. During the installation of the cabling system in a construction site, the technicians found a conflict about the cabling system design with the existing plumbing channels left from the previous project. As you need to contact the right stakeholders, which document can support you in your goal? |  | Risk register | Issue log | Change log | Stakeholder register | Answer option d. | “Stakeholder register” contains all project stakeholders’ contact information.
Exam 6 | #80. During the implementation of a software project, test results showed an unknown defect. Accordingly, a technician was assigned to discover the main reason behind the issue. Which technique should he use? |  | Root cause analysis | Alternatives analysis | Process analysis | Variance analysis | Answer option a. | “Root cause analysis” is an analytical technique used to determine the basic underlying reason that causes a variance, defect or risk.
Exam 6 | #81. You have been asked to manage a troubled time-critical project. You must engage with other projects as they are impacting your already delayed schedule. The delayed activities are on the critical and near-critical paths. What should be your first step? |  | Getting rid of underutilized resources | Consult with an expert | Re-baseline the project management plan | Coordinate the projects as a joint effort | Answer option d. | “Coordinate the projects as a joint effort”. You need to contact the Program Manager or the PMO to ensure that the projects are seen and managed jointly. That is the only way to minimize the impact of schedule delays.
Exam 6 | #82. A project manager intends to strictly follow his company’s formal procurement policies to avoid any potential legal issues. What category do these policies belong to? |  | Project documents | Organizational process assets | Enterprise environmental factors | Both B and C | Answer option b. | “Organizational process assets” as input for plan procurement management contains formal procurement policies and buying organizations.
Exam 6 | #83. Your company launched a new product development project, which requires an adaptive approach. The PMO assigned you as the project manager for this project. Since your experience is in managing the predictive life cycle, you should _____ . |  | Reject the project since your main role will change. | Accept the project under the condition of using predictive life cycle. | Accept the project and use hybrid methodology. | Accept the project and reverse shadow with a colleague familiar with agile. | Answer option d. | Answer option d. The best course of action is to “Accept the project and reverse shadow with a colleague familiar with agile” (option d.) it is a good idea for you to become familiar with the agile approach before you start your project through reverse shadowing. If you decide to “Reject the project, since your main role will change” (answer option a.), the project manager role does not change when the project approach is changed. “Accept the project under the condition of using predictive life cycle “(answer option b.) and “Accept the project and use hybrid methodology “(answer option c.) are incorrect because your decision will have negative consequences since you will be using the wrong project development approach. Answer option d. The best course of action is to “Accept the project and reverse shadow with a colleague familiar with agile” (option d.) it is a good idea for you to become familiar with the agile approach before you start your project through reverse shadowing. If you decide to “Reject the project, since your main role will change” (answer option a.), the project manager role does not change when the project approach is changed. “Accept the project under the condition of using predictive life cycle “(answer option b.) and “Accept the project and use hybrid methodology “(answer option c.) are incorrect because your decision will have negative consequences since you will be using the wrong project development approach.
Exam 6 | #84. During the project performance review meeting, the project manager presents that the SPI is 0.8. This indicates that _____ . |  | The project is 20% ahead of schedule | The project is 20% behind schedule | The project is on schedule | The project is 2% behind schedule | Answer option b. | “The project is 20% behind schedule”. When SPI is less than 1 it means the project is behind schedule and since in this case SPI is 80% it means that the project is missing 20% of the planned progress.
Exam 6 | #85. Your company assigned you to a project that aims to unify global PM practice across its different branches. Accordingly, you would work with multiple teams from different countries. To get the team together, you are planning to use web-based meetings. This is an example of _____ . |  | Colocation | Cultural awareness | Virtual teams | Communication methods | Answer option c. | “Virtual teams” are teams consisting of members geographically distant from each other and connecting through communication technology such as email, audio conferencing, social media, web-based meetings, and video conferencing.
Exam 6 | #86. Jennifer was given her first opportunity to be a team leader last month. After doing the job for a little while, she is now gaining confidence and is able to make independent decisions. Which stage of skill acquisition is this? |  | Competent | Coaching | Master | Norming | Answer option a. | “Competent” is the right answer since the other options are clearly incorrect. Coaching is a leadership style, mastery is the highest level of skill, and Norming is a stage of team development.
Exam 6 | #87. You are experiencing a major issue in your construction project due to delays in the delivery of the materials. Although you have already identified this situation as a risk during the project planning, an unpredictable factor caused the issue. What are the correct steps you would take? |  | Identify root-cause, Define the problem, generate solutions, implementing the solution, and verifying solution effectiveness | Define the problem, identify root-cause, generate solutions, implementing the solution, and verifying solution effectiveness | Define the problem, identify root-cause, generate solutions, verifying solution effectiveness, and implementing the solution | Define the problem, generate solutions, identify root-cause, implementing the solution, and verifying solution effectiveness | Answer option b. | “Define the problem, Identify root-cause, Generate solutions, Implementing the solution, and Verifying solution effectiveness” is the only answer in the correct order.
Exam 6 | #88. You are the Product Owner of a major software development project. A junior team member is trying to understand the terminology used by your other team members; he asks you what is “Ready” in Scrum? |  | Ready is a condition in which the team knows exactly what needs to be done and the amount of work needed to complete the backlog item. | Ready is a condition in which the team confirms the requirements missing from the previous iteration are now available for the upcoming Sprint. | Ready is a condition in which the team agrees on the individuals that have the specific skills needed to complete a specific task on the increment. | Ready is a situation where the development team feels ready to share the results with the client before release. | Answer option a. | In Scrum, the definition of “Ready” (DoR) is used to determine that the team is ready to action out the user stories on a specific Sprint or Increment. It is an indication that the team knows the criteria to complete the work as expected.
Exam 6 | #89. The key benefit of the Control Scope process is _____ . |  | Maintain scope baseline throughout the project | Govern Change management process | Eliminate scope creep | Both A and B | Answer option a. | “Maintain scope baseline throughout the project” is the key benefit of the control scope process.
Exam 6 | #90. You are classifying your project stakeholders according to directions of influence technique. Under which way would you classify the middle managers? |  | Upward | Downward | Outward | Sideward | Answer option d.” | Sideward”. The middle managers who are considered equal and with whom the project manager negotiates/shares the limited resources are considered sideward stakeholders.
Exam 6 | #91. As a project manager for a mega IT infrastructure project, you are managing the stakeholder engagement. Which of the following enterprise environmental factors would you consider? |  | Personnel administration policies | Organizational communication requirements | Historical information from previous similar projects | Corporate policies and procedures for social security | Answer option a. | Answer option a. The best answer is “Personnel administration policies” (Answer option c.). “Organizational communication requirements” (Answer option b), “Historical information from previous similar projects” (Answer option b.), and “Corporate policies and procedures for social security” (Answer option c.) are all organizational process assets NOT Enterprise environmental factors. Answer option a. The best answer is “Personnel administration policies” (Answer option c.). “Organizational communication requirements” (Answer option b), “Historical information from previous similar projects” (Answer option b.), and “Corporate policies and procedures for social security” (Answer option c.) are all organizational process assets NOT Enterprise environmental factors.
Exam 6 | #92. There is a possibility that the newly discovered tasks may take longer and cannot be completed during the iteration. The development team may need to reduce the functionality of a story or drop one entirely. With whom should the team discuss the possible solutions in this situation? |  | Product Owner | Scrum Master | Upper Management | Stakeholders | Answer option a. | “Product Owner”. It is possible that the newly discovered tasks will take longer so they cannot be completed during the iteration. In that case, the team will need to discuss the situation with the Product Owner and see if there is still a way to meet the iteration goal; they may need to reduce the functionality of a story or drop one entirely.
Exam 6 | #93. Company XYZ launched an internal project to improve its operations' performance. You have been assigned as the project manager on this project. What are you expected to do with the operations team? |  | Work closely with operations management to solve everyday problems | Plan for each project phase knowledge transfer | Support operations staff selection | Perform quality audits | Answer option b. , “ “ | Answer option b. The best answer is “Plan for each project phase knowledge transfer” (Answer option b.).“Work closely with operations management to solve everyday problems” (Answer option a.), “Support operations staff selection” (Answer option c.), and “Perform quality audits” (Answer option d.) are all operational work not related to project work. Answer option b. The best answer is “Plan for each project phase knowledge transfer” (Answer option b.).“Work closely with operations management to solve everyday problems” (Answer option a.) , “ Support operations staff selection” (Answer option c.), and “ Perform quality audits” (Answer option d.) are all operational work not related to project work.
Exam 6 | #94. During the early phases of the planning, the project manager requested to account for the cost related to training, processes documentation, and the time to do it right within the project budget as a cost of quality. To what type of cost of quality do these items belong? |  | Appraisal Costs | Prevention Costs | Internal Failure Costs | External Failure Costs | Answer option b. | “Prevention costs” are costs related to the prevention of poor quality in the products, deliverables, or services of the specific project. These costs include Training, Document processes, Equipment and Time to do it right.
Exam 6 | #95. Agile has certain core practices that are used within any team working within an iterative lifecycle. Which of the following is NOT a core practice of Agile? |  | Reporting to Senior Management, to ensure they are happy with the project. | Daily standups, to report on progress and raise blockers. | Early and frequent feedback to ensure a common understanding of the product. | The “whole team” approach, where any person needed is brought into the project team. | Answer option a. | While reporting to senior management has its place in running a project, Agile projects would rather be done by including them in other Agile core practices such as Product Demos or Product Reviews.
Exam 6 | #96. The top management team of software company ABC has decided that they need to transform their processes to eliminate non-value-added activities. The company needs to develop and deploy its corporate strategy for short term quarterly and longer duration goals. After aligning on the corporate strategy, the company has initiated and successfully deployed projects focused on improving many processes within the organization. The company will now shift to projects establishing governance and working methods supporting the new processes that have been recently implemented. What is the best approach for this? |  | Plan and execute predictive projects because the intermediate value cannot be delivered. | Plan and execute agile projects for the initial heavy-lifting that requires the transformation and incorporating predictive projects as needed afterward. | Only use agile projects, as organizational transformation requires constant feedback, which the transformational team will use to plan the next component of work. | Only to use an incremental approach as organizational transformation is a lot like building a product with added functionality. | Answer option b. | Even though organizational transformation requires constant evaluation of results, in the beginning, agile methods help learn from the implementation. However, a predictive approach is more useful when people accept the changes brought along with the transformation. Also, the goal of project management is to produce business value in the best possible way provided by the current business environment.
Exam 6 | #97. A car company is starting with a new electric car production. The project that you are working on needs to make sure that all car dealerships are ready to sell the new electric cars. Since there is a lot to learn, the project must be delivered regularly over the one year period. To ensure that various teams involved in the project are working efficiently and there are no bottlenecks in the production, how would you identify the potential issues in the process? |  | Use Value Stream Map | Use the Project Management Plan | Use Velocity Chart | Follow the Project Proposal Document | Answer option a. | “Use Value Stream Map”. The Value stream map is a visual representation of a project process and the action in each step to check for efficiencies as well as inefficiencies in the process.
Exam 6 | #98. David has been assigned to a new project involving technology with high levels of disruption. The project scope is unclear and has a high level of risk. He has requested to use Agile to manage this project. What is the benefit for applying Agile techniques to this project? |  | Agile techniques effectively manage disruptive technologies, scope changes and project risk. | Agile techniques effectively manage the senior management team. | Agile techniques effectively manage schedule changes. | There is no benefit to using Agile techniques. | Answer option a. | Captures all aspects in total.
Exam 6 | #99. The stakeholders are very involved in your project. They are interested in agile project management and want to be informed about all aspects of the project. You know that transparency is a key to successful projects, so you are willing to share and teach the stakeholders about the varieties between agile and traditional project management. Your stakeholder asks you about the value stream analysis and what are the steps that need to be followed? |  | Create a value stream map to document delays and wasted time in execution | Create a value stream map of the current process, identifying steps, queues, delays, and information flows | Create a value stream map of the current process and compare it to the goals set forth in the project charter | Create the value stream charter to be more flexible in the agile project | Answer option b. | Create a value stream map of the current process, identifying steps, queues, delays, and information flows. It analyses the current state and designs a future state for the series of events that take a product or service from the beginning of the specific process until it reaches the customer. Value stream maps show the flow of both materials and information as they progress through the process.
Exam 6 | #100. Your Agile team is having its first sprint planning meeting. They are discussing the use of appropriate tools and techniques to identify risks. The following tools and techniques are all appropriate except: |  | Root cause analysis | Checklists | Prompt lists | Context diagrams | Answer option d. | “Context diagrams” are used when we are collecting requirements with stakeholders.
Exam 6 | #101. The project sponsor asked you to provide a representation of the remaining work in the backlog for a software project. Which tool can assist you with this requirement? |  | Trend analysis | Variance analysis | Iteration burndown chart | Earned value analysis | Answer option c. | “Iteration burndown chart” is a chart used in an adaptive approach that shows the remaining work to be completed in the backlog.
Exam 6 | #102. As a Product Owner who believes in continuous improvement, you perform the Value Stream Mapping (VSM) exercise each time a Sprint is complete; then, during the Sprint Review and before the next Sprint, you meet up with the entire team to discuss the results of the VSM exercise. What is the purpose of Value Stream Mapping? |  | VSM is an activity in which the development team is offered the opportunity to provide alternatives to carry out the work. | VSM is an activity in which the Product Owner discusses what went right or wrong during the last Sprint and what can be done better in the next Sprint. | VSM is an activity in which the work stages are analyzed in order to determine the efficiencies and inefficiencies of the process. | VSM is an activity where based on previous results, the Product Owner enforces new tactics to deliver more enriched content to the client. | Answer option c. | In Lean theory, Value Stream Mapping (VSM) provides the user with a structured visualization of the key steps and the corresponding data needed to evaluate the work stages and understand how to be more efficient and effective in performing.
Exam 6 | #103. The project manager of a construction project is acquiring the project resources. As he is about to acquire the team resources, what criteria should he consider? |  | Experience | Cost | International factors | All of the above | Answer option d. | The best answer is “All of the above” (Answer option d.). “Experience” (Answer option a.) and “Cost” (Answer option b.) and “International factors” (Answer option c.) are all selection criteria that can be applied to team resources.
Exam 6 | #104. After completing the schedule on the application delivery project, the sponsor asked you to minimize the number of programmers needed for the project without affecting the originally planned project end date. Which technique can help you to achieve this objective? |  | Resource leveling | Resource smoothing | Resource loading | Crashing | Answer option b. | “Resource smoothing” is used when the time constraint takes priority. The objective is to complete the work by the required date while avoiding to exceed certain predefined resource limitations. Resource smoothing is used when the project’s critical path is not changed, and the completion date may not be delayed.
Exam 6 | #105. Which tool can help a project manager to assess the process stability? |  | Cause-and-effect diagrams | Control charts | Histograms | Scatter diagrams | Answer option b. | “Control charts” are used to determine whether a process is stable or has predictable performance.
Exam 6 | #106. Due to an unexpected increase in the value of the system upgrade project, the company board decided to recognize your efforts with an award as an exceptional project manager. You think that the value increase may be a result of the system engineer’s idea for improvement which was implemented during the project. Knowing this fact you should _____ . |  | Accept the award directly | Refuse the award, you're not sure of the reason behind the increase | Accept the award, and distribute it to the team according to performance | Recommend the system engineer to be awarded accordingly for his idea | Answer option d. | The best answer is “Recommend the system engineer to be awarded accordingly for his idea” (Answer option d.) since it only makes sense to award the person who leads to the improvement. “Accept the award directly” (Answer option a.) and “Accept the award and distribute it to the team according to performance” (Answer option c.) both are unfair to the system engineer since his contribution might be the only reason for the improved performance. “Refuse the award, you’re not sure of the reason behind the increase” (Answer option b.) will not be fair for anyone.
Exam 6 | #107. The customer submitted a change request on a current project. According to your company policy, the decision on the disposition of the change request is made if the CCB reaches unanimity. In which case you should accept the change? |  | Three out of five approve | Four out of five approve | The project sponsor approves | None of the above | Answer option d. | Unanimity is achieved only when all members of the board agree on one course of action. With “Three out of the five approved” (Answer option a.), “Four out of the five approved” (Answer option b.), and “The project sponsor approved” (Answer option c.) unanimity is not achieved. The best course of action is to “None of the above” (Answer option d.).
Exam 6 | #108. A Kanban development team for a small software company OrangeTech experiences unforeseen delays between product analysis, development, and release for testing. The customer is concerned that this will impact the release of the product in the market. What should Chris, the Agile Project Manager, do next? |  | Increase the timebox of the daily standup to 30 minutes. | Escalate the issue to the Sponsor. | Provide a workshop on the approach so the development team can learn how to use it. | Ask the team to track impediments on the impediment board. | Answer option d. | As an Agile Project Manager is to recognize, address, and remove obstacles, impediments, and blockers from the team. If impediments exist, a Project Manager will prioritize them and address them in order of importance or impact they have on the project. Using the impediment board will allow him to gather ways of resolution with the team involved in the project work.
Exam 6 | #109. As a project manager, you are depending on effective working relationships and connections with colleagues or other partners to plan your work and make progress in it. To make this happen, you also utilize collaboration tools. Which type of organization are you working in? |  | Virtual organization | Functional organization | Matrix organization | Multidivisional organization | Answer option a. | In “virtual organizations”, team members and other stakeholders network with each other and use technology to collaborate.
Exam 6 | #110. Johnny is a Project Manager using an agile approach to deliver business value incrementally on his project. What other element of business value should he be focused on? |  | Examining Business value throughout the entirety of the project. | Accepting suggestions about delivering business value only when the project is complete. | Reporting on business value only when the project is initiated and closed out. | All of the above. | Answer option a. | The project manager should examine and report on business value throughout the entirety of the project.
Exam 6 | #111. The operations team manager is a risk response owner in your project. However, he is not in your project team. You need to persuade and convince him to take the necessary action. What interpersonal skills should be used? |  | Influencing | Facilitation | Observation/conversation | Conflict management | Answer option a. | “Influencing” when risk response actions are owned by people outside the immediate project team or who have other competing demands, influencing can be used to encourage nominated risk owners to take necessary action where required.
Exam 6 | #112. Company XYZ hired Adam to manage an internal project. As he started the project planning, he requested from one member of the project team to investigate the correlation between available resources and their productivity. This is an example of _____ . |  | Tailoring considerations for project schedule management | Tailoring considerations for project integration management | Trends and emerging practices for project schedule management | Agile planning techniques | Answer option a. | “Tailoring considerations for project schedule management” refers to the correlation between available resources and their productivity.
Exam 6 | #113. What is the correct description for an Agile approach? |  | Fixed requirements, performed once for the entire project, in frequent small deliveries. | Fixed requirements, repeated until correct, in frequent small deliveries. | Variable and Dynamic Requirements, repeated until correct, in frequent small deliveries. | Variable and Dynamic Requirements, repeated until correct, in one large delivery. | Answer option c. | Variable and Dynamic Requirements, repeated until correct, in frequent small deliveries.
Exam 6 | #114. Which of the following is a key benefit of implementing the Risk Responses? |  | Minimize individual project threats and maximize individual project opportunities | Identify appropriate ways to address overall project risk and individual project risks | Quantify overall project risk exposure | Enable project decisions to be based on current information about overall project risk exposure | Answer option a. | “Minimize individual project threats, and maximize individual project opportunities”. The key benefit of this process is that it ensures that agreed-upon risk responses are executed as planned in order to address overall project risk exposure, minimize individual project threats, and maximize individual project opportunities.
Exam 6 | #115. It is better to spend more time, cost, and resources to design high-quality products than find quality issues during review and fix them. This is a reference to _____ . |  | Cost of quality | Prevention over inspection | Quality improvement | Quality and grade | Answer option b. | “Prevention over inspection” Prevention is preferred over inspection. It is better to design quality into deliverables, rather than to find quality issues during the inspection.
Exam 6 | #116. Due to the budget cut, your company decided to terminate your eight-month project during its 3rd month. As the project manager, what should you do next? |  | Try to convince the management to reconsider their decision | Ask the management to consider the project successful according to the current rate of performance | Do nothing since the management decision is final | Transfer the finished and unfinished deliverables to the concerned parties | Answer option d. | The best course of action is to “Transfer the finished and unfinished deliverables to the concerned parties” (Answer option c.) as a part of the formal project closure process. If you decide to “Try to convince the management to reconsider their decision” (Answer option a.) or “Ask the management to consider the project successful according to the current rate of performance” (Answer option b.) neither of them would provide value add. If you decide to “Do nothing since the management decision is final” (Answer option c.) it is not the best practice as the project needs to be closed formally.
Exam 6 | #117. William is a Scrum Master is managing a supply chain software development project for Company LogiSupply. The Product Owner attempted to add an unplanned feature to the current Sprint (iteration) while the development team focused on the work of the Sprint. What should William do next? |  | Ask the Product Owner to update the product backlog and the new feature will be discussed in the next Sprint Planning Meeting. | Force the development team to add the additional feature. | Submit a change request to the Change Control Board. | Acquire additional resources to help the development team to accomplish adding the new feature in the current sprint. | Answer option a. | Answer option a. The Scrum Master serves as a safeguard to the Scrum Team from a false sense of urgency. The Scrum Team cannot be forced to take on new stories in the current Sprint (iteration). The job of the Scrum Master is to ensure that until the next Sprint Planning Meeting, these new user stories are stored in the Scrum Product Backlog. Answer option a. The Scrum Master serves as a safeguard to the Scrum Team from a false sense of urgency. The Scrum Team cannot be forced to take on new stories in the current Sprint (iteration). The job of the Scrum Master is to ensure that until the next Sprint Planning Meeting, these new user stories are stored in the Scrum Product Backlog.
Exam 6 | #118. Rewards are effective only when they are _____ . |  | Valued by others | Satisfying a need of the individual | Monetary | Rewarding desirable behavior | Answer option b. | “Satisfy a need of the individual”. Rewards will be effective only if they satisfy a need that is valued by that individual.
Exam 6 | #119. What are the main responsibilities of the project manager in terms of managing and engaging with the stakeholders? |  | The project manager needs to instruct the stakeholders to give approvals on the project. | The project manager does not manage the stakeholders. | The senior management needs to manage the stakeholders. | The project manager is required to analyze and manage stakeholders’ needs and engage with the stakeholders to improve their support and influence throughout the life cycle of the project. | Answer option d. | “The Project manager is required to analyze and manage stakeholders’ needs and engage with the stakeholders to improve their support and influence throughout the life cycle of the project”.
Exam 6 | #120. Sam is managing an important project. Due to the previous bad experience with the same customer in similar projects, Sam wants to ensure that he provides an accurate schedule. Accordingly, he started to gather information about staff availability, skills, and physical resource availability. Staff availability, skills, and physical resource availability is part of _______ . |  | Project documents | Organizational process assets | Enterprise environmental factors | Both B and C | Answer option c. | “Enterprise environmental factors” include team resource availability, skills, and physical resource availability.
Exam 6 | #121. A new business case recently initiated a project for developing a web-based knowledge database. Due to budget limitations, the project needs to rely on limited internal resources. The management has a high tolerance for longer project duration as long as a basic version of the site is delivered initially, then the rest of the requirements can be delivered in later stages. Which life cycle would you select for this project? |  | Predictive | Agile | Incremental | Waterfall | Answer option c. | Answer option c. “Incremental” (Answer option c.) the deliverable is produced through a series of iterations that successively add functionality within a predetermined period which is the most appropriate for the situation. Answer option c. “Incremental” (Answer option c.) the deliverable is produced through a series of iterations that successively add functionality within a predetermined period which is the most appropriate for the situation.
Exam 6 | #122. Your company is launching an IT infrastructure upgrade project. Despite having a clear scope, the sponsor is concerned with the project size and complexity. When the project manager is assigned to this project, you would advise him/her to _____ . |  | Use agile approach | Divide the project into phases | Manage the project as a program | Any of the above | Answer option b. | The best course of action is to “Divide the project into phases” (option b.) that will help you gain more control over the project scope, time, quality, and cost. If you decide to “Use agile approach” (answer option a.), there are no valid reasons for such action since the project scope is clear and no major changes are expected. If you decide to “Manage the project as a program“ (answer option c.), there are no valid reasons for such action, as it will not improve the project results accordingly.
Exam 6 | #123. A major communication project is running into problems because the sponsor is not satisfied with the key deliverable. He says that the product is missing a major requirement. Therefore, there is a need for a scope change to redesign the product and add the needed requirement. Key members of the project team work with the Project manager to recommend options to deliver the scope as per the sponsor’s request. The best way to move forward with the sponsors request is to: |  | Tell the sponsors that it is too late to add a request. | Analyze the request and offer recommendations and submit the change request to CCB. | Tell the project team to discuss this issue with the sponsors. | Do nothing, sponsors will be satisfied with the product anyway when they start using it. | Answer option b. | “Analyze the request and offer recommendations and submit the change request to CCB”. This is the only way to proceed as per the guidelines from PMI.
Exam 6 | #124. Melinda has been brought into a Scrum team to take over for the Scrum Master who recently left the company without any explanation. Melinda received a phone call an hour ago that she was to take over this team immediately. She attends her first Stand-up meeting that includes the eight Developers. Due to the abrupt departure of the previous Scrum Master and having no information to review prior to this meeting with the team, Melinda decides to extend the length of this meeting to understand how the project has been going. She begins to ask questions and quickly learns that the team has failed to produce an approved delivery at the Sprint Reviews for the past four Sprints. As she learns more, she understands some of the sources of issues for this team. Which of the following would NOT be a contributing factor of this team’s failure to deliver? |  | The team starts each Sprint with a one-hour Planning Meeting that includes the Scrum Master and Developers. | The team has two Stand-up meetings each week to review what is completed, who is in-progress and any obstacles. These meetings include the Scrum Master and the Developers. | The Sprint Review meeting occurs every two weeks, at the end of the Sprint. In this meeting the Developers demonstrate to the Product Owner and Stakeholders the deliverable. In this meeting the Product Owner and Stakeholders frequently voice concerns over the quality of the product. | The Sprint Retrospective occurs immediately following the Sprint Review and usually lasts thirty minutes. This meeting includes the Scrum Master, Scrum Product Owner, and the Developers. | Answer option c. | Answer option c. The Sprint Review meeting is the only event listed that is being run according to Scrum practices. The Planning Meeting should be a longer one and include the Product Owner. The Stand-up meetings should occur each day. Lastly, the Sprint Retrospective is an opportunity for the Developers to improve upon their practices and should last significantly longer than thirty minutes. Answer option c. The Sprint Review meeting is the only event listed that is being run according to Scrum practices. The Planning Meeting should be a longer one and include the Product Owner. The Stand-up meetings should occur each day. Lastly, the Sprint Retrospective is an opportunity for the Developers to improve upon their practices and should last significantly longer than thirty minutes.
Exam 6 | #125. You are considering using prompt lists to help you identify the sources of the overall project risk. Accordingly, you are using some common risk frameworks. Which is not an example of these frameworks? |  | PESTLE | RACI | TECOP | VUCA | Answer option b. | Answer option b. The best answer is “RACI” (Answer option b.) is a responsibility assignment matrix that helps in defining and documenting roles and responsibilities. PESTLE” (Answer option a.), “TECOP” (Answer option c.) and “VUCA” (Answer option d.) are all common risk frameworks and since the question asks which is NOT a benefit accordingly, these answers are not valid. Answer option b. The best answer is “RACI” (Answer option b.) is a responsibility assignment matrix that helps in defining and documenting roles and responsibilities. PESTLE” (Answer option a.), “TECOP” (Answer option c.) and “VUCA” (Answer option d.) are all common risk frameworks and since the question asks which is NOT a benefit accordingly, these answers are not valid.
Exam 6 | #126. When a development team has a lot of work in progress items, it delays the activities that are necessary to finalize that work. Which of the following Agile Manifesto values deal with the concept of WIP (Work in Progress)? |  | Individuals and interactions over processes and tools | Working software over comprehensive documentation | Customer collaboration over contract negotiation | Responding to change over following a plan | Answer option b. | When a development team has a lot of work in progress, it delays taking the actions necessary to finalize that work, and therefore impacts their ability to produce working software. By limiting the work-in-progress, we allow teams to work at a sustainable pace with quality output.
Exam 6 | #127. A project manager assigned a coordinator to collect the project’s performance data and compile it weekly in the project documents to support the decision-making process. The output of this task is an example of _____ . |  | Work performance data | Work performance information | Work performance reports | Project management information system | Answer option c. | Answer option c. The best answer is “Work performance reports” (Answer option c.) “Work performance data” (Answer option a.) are the raw observations and measurements identified during activities performed to carry out the project work. “Work performance information” (Answer option b.) is the analyzed performance data collected from various controlling processes. “Project management information system” (Answer option d.) provides access to information technology (IT) software tools. Answer option c. The best answer is “Work performance reports” (Answer option c.) “Work performance data” (Answer option a.) are the raw observations and measurements identified during activities performed to carry out the project work. “ Work performance information” (Answer option b.) is the analyzed performance data collected from various controlling processes. “ Project management information system” (Answer option d.) provides access to information technology (IT) software tools.
Exam 6 | #128. There is a high probability of a certain threat on your project site. You are a risk-averse Project Manager and you have decided to get insured against it. You have just finalized a deal with a well-established insurance company. You have agreed to pay a huge amount as a risk premium to the insurance firm so that now they can take full responsibility for this threat. Which risk response strategy did you just use? |  | Escalate | Transfer | Avoid | Mitigate | Answer option b. | “Transfer” involves shifting ownership of a threat to a third party to manage the risk and to bear the impact of the threat. Risk transfer often involves payment of a risk premium to the party taking on the threat.
Exam 6 | #129. The project team is meeting at the project end to collect and summarize the lessons learned. Which of the following techniques can be useful for this objective? |  | Expert judgment | Trend analysis | Document analysis | Variance analysis | Answer option c. | “Document Analysis” involves Assessing available documentation that will allow identifying lessons learned and knowledge sharing for future projects and organizational assets improvement.
Exam 6 | #130. During the execution of a construction project, you are monitoring and controlling the Project work. Which of the following activities belong to this process? |  | Checking the status of individual project risks | Providing forecasts to update current cost and schedule information | Providing initial estimates for activities costs, duration, and resources | Both A and B | Answer option d. | “Checking the status of individual project risks” (Answer option a.) and “Providing forecasts to update current cost and schedule information” (Answer option b.) are both activities done during monitoring and control. The best answer is “Both A and B” (Answer option d.). “Providing initial estimates for activities costs, duration and resources” (Answer option c.) should be performed in planning, not in monitoring and controlling.
Exam 6 | #131. During project risk planning, several risks were identified with sufficient time to implement a response plan. What risk response will you plan? |  | Avoid | Contingency response | Accept | Transfer | Answer option b. | “Contingency response” is a response plan that will only be executed under certain predefined conditions, if it is believed that there will be sufficient warning to implement the plan.
Exam 6 | #132. Which technique depicts the product scope visually, shows inputs to the business system, the stakeholders who provide the input, the outputs from the business system, and the stakeholders who receive the output? |  | Affinity diagrams | Mind mapping | Context diagrams | Matrix diagrams | Answer option c. | “Context diagrams” Context diagrams visually depict the product scope by showing a business system (process, equipment, computer system, etc.), and how people and other systems (actors) interact with it.
Exam 6 | #133. Your agile consultant is suggesting that you start writing your user stories on cards, where each of them represents a single piece of work. Each card acts as a signal of status and indicates when a new task can be pulled, when it is being worked on and when it is completed. This board will help you visualize your workflow. What tool is the consultant suggesting? |  | Scrum board | Kanban board | Task board | User-stories board | Answer option b. | “Kanban Board”. A visualization tool that enables improvements to the flow of work by making bottlenecks and work quantities visible.
Exam 6 | #134. You are leading a 10- members team working on an agile project. Your company has recently gone through a major reorganization and a new manager has been assigned to your team. The manager informs that the priority of the project has been dropped so instead of 10 members you will have to work with eight members. Nevertheless, the project is still required to be delivered on time. What will you do as a team leader to deliver the project on time with the reduced number of team members? |  | Work as per the current product plan and product backlog and ask the remaining team members to work overtime to complete the project within the original deadline. | Work as per the current product plan and develop a risk analysis report to check the instances where anticipated work is not delayed due to insufficient work resources. | Discuss the new situation with the project stakeholders. | Prepare a new product map and product backlog to reprioritize the remaining features so the project could be completed within the original deadline | Answer option c. | Responding to changes is more valuable and important than following a plan. Therefore, discussing all these things with stakeholders is the best option. It will help in preparing the new product road map with the actual new needs and expectations of the client.
Exam 6 | #135. Kevin, your longtime customer, is well known for frequently asking for changes in the product scope even though the product requirements and the project plan were established at the planning stage. What type of development life cycle is this likely to be? |  | Incremental | Adaptive | Hybrid | Waterfall | Answer option d. | “Waterfall”. This is predictive. Requirements are determined at the beginning of the project. Changes are processed through the Integrated change control process.
Exam 6 | #136. Jill, an Agile Project Manager, has been managing an innovation project for some time now. However, she has realized that the product increments are not delivering the quality required. What should Jill do in this situation? |  | Ensure that she checks on all quality requirements once the project finishes. | Do not worry about quality, as she can always rely on rework. | Use different tests as error-proofing to deliver on the required quality in each iteration. | Redesign the project and start all over again. | Answer option c. | Quality must be planned in and not inspected. This principle holds for all project management approaches. By using error-proofing methods, projects can be tailored to address quality issues.
Exam 6 | #137. You are the Product Owner of a major software development project. A junior team member is trying to understand the terminology used by your other team members; he asks you what is “Done” in Scrum? |  | Done is a condition in which the team is ready to implement the code as per the client requirements. | Done is a condition in which the team formalizes the acceptance of the client requirements before proceeding. | Done is a condition in which the team comes to agreement on what it takes to make the increment releasable. | Done is a condition in which the product is developed and the team is ready to share the deliverable with the client for testing. | Answer option c. | In Scrum, the definition of “Done” (DoD) represents a shared understanding of a checklist of requirements that must be met before the increment, or the deliverable is ready for client use.
Exam 6 | #138. You were assigned to replace a project manager leading a web development project. The project is managed with an agile approach. Of the following, which scope management processes would you repeat? |  | Validate Scope and Control Scope | Plan scope and Validate Scope | Define scope and plan scope | All of the above | Answer option a. | The best answer is “Validate Scope and Control Scope” (Answer option a.) both processes are repeated in an agile approach. “Plan scope and Validate Scope” (Answer option b), “Define scope and plan scope” (Answer option c.), and “All of the above” (Answer option d.) Plan scope is not a repeated process in an agile approach.
Exam 6 | #139. The project team is having difficulties assigning new work as soon as existing work is completed. This is because there is no proper reporting, nor is there control of work in progress and the work remaining. What do you suggest the team do in such a situation? |  | Use a Kanban sign board | Remove waste from the work to create extra capacity for work | Remove defects by applying the Six Sigma process | Use an Agile development approach | Answer option a. | The Kanban signaling and pull system may be used to address the given issue.
Exam 6 | #140. You received repeated reports from different stakeholders that there are deviations from the agreed communication requirements. How can you find and analyze the gap? |  | Compare communication plan with issue log | Compare communication plan with Project communications | Compare Work performance data with Project communications | Compare Work performance data with issue log | Answer option b. | “Compare communication plan with Project communications” Project communications include the project communications that have been distributed to stakeholders as defined in the communications management plan and the stakeholder engagement plan which can be compared to a communication plan to analyze the communication gaps.
Exam 6 | #141. The testing team just completed the product end-to-end testing and verified all defects' fixes. What would be the output of this process? |  | Final product | Deliverable | Verified deliverables | Validated deliverables | Answer option c. | “Verified deliverables” are the outcomes of performing the Control Quality process which includes internal testing and defect repair to determine that deliverables are conforming to the requirements.
Exam 6 | #142. You have been called in to represent the Client of a Construction Industry Project. Your task is to review the deliverables presented by the performing organization’s Quality Control Team. They have shown you three deliverables verified by the QC team. After reviewing in detail, you have accepted 2 out of the three deliverables on behalf of the client. Which process have you just performed? |  | Direct and Manage Project Work | Control Scope | Validate Scope | Monitor and Control Project Work | Answer option c. | “Validate Scope” is the process in which the veriﬁed deliverables obtained from the Control Quality process are reviewed with the customer or sponsor to ensure they are completed satisfactorily and have received formal acceptance of the deliverables by the customer or sponsor.
Exam 6 | #143. When considering the Scrum Master role, we need to decide who is best suited for it. Which of the following tasks should not be performed by a scrum master? |  | Performing refresher training to remind a new team about the rules of Planning Poker when estimating product backlog items | Updating sprint and release burndown or burnup charts. | Having discussions with non-Scrum-team members | Meeting with both the internal and external stakeholders to rank the priorities for the upcoming sprint | Answer option d. | Meeting with both the internal and external stakeholders to ensure that priorities for the upcoming sprint are right. This is not a task performed by the Scrum Master.
Exam 6 | #144. The project manager of a mega project invited all stakeholders and project teams to a webinar where he and the sponsor will provide the project's brief and explain its benefits, timelines, and high-level risks. At the end of the webinar they will answer all questions. What type of communication methods is the project manager using? |  | Push communication | Pull communication | Interpersonal communication | Interactive communication | Answer option d. | “Interactive communication” is a multidirectional exchange of information in real-time.
Exam 6 | #145. You are a project manager handling an agile team that is working on a software development project. A new developer who has two years of experience working with an agile team has recently joined your team. You notice that the former manager of the developer regularly asks for his help to resolve the issues in the previous project. What would you do in this situation as a project manager? |  | Discuss this issue with the product owner and stakeholders | Ask the developer not to work on the previous project | Move the developer back in the old team | Allow the developer to work on both projects | Answer option b. | The developers should be fully dedicated to the project they are working on now. When the development team is not fully dedicated to the project the project suffers.
Exam 6 | #146. After developing the project management plan including Stakeholder Engagement Plan, the company announced a new organizational structure. Accordingly, you should _____ . |  | Revise the whole project management plan | Update stakeholder engagement plan to reflect the updates | Request sign off from all new stakeholders | Do nothing | Answer option b. | The best course of action is to “Update stakeholder engagement plan to reflect the updates” (option b.). It is not necessary to “Revise the whole project management plan” (answer option a.) or “Request sign off from all new stakeholders “(answer option c.). If you decide to “Do nothing “(answer option d.) you are risking having communications issues with multiple stakeholders either with the new stakeholders or those who have left.
Exam 6 | #147. During the execution of a construction project, the project manager realized that there is a need for procurement due to resource limitations. As the project manager needs to know how much the resources will cost and the time-frame the supplier would provide the required resources, which bid document should he use? |  | RFI | RFQ | RFP | Both A and B | Answer option b. | “RFQ” is commonly used when more information is needed on how vendors would satisfy the requirements and/or how much it will cost.
Exam 6 | #148. The Project Manager is seriously concerned about the number of problems, inconsistencies, and conﬂicts they encounter during the project execution. Overall, during the completion of the first 3 phases of this mega project there were more than 320 reported problems. He wants to investigate and resolve all these pending problems at the earliest. Which document will be most helpful for him? |  | Assumption Log | Constraints Log | Issue Log | Change Log | Answer option c. | “Issue log” is a project document where all the issues are recorded and tracked. It will help the Project Manager effectively track and manage issues, ensuring that they are investigated and resolved.
Exam 6 | #149. You delivered the final version of the project management plan to the sponsor for approval. However, he requested additional improvements in the schedule considering the option of having an incremental cost and without risking quality. Which technique can help you achieve this objective? |  | Critical path method | Fast-tracking | Crashing | Kanban system | Answer option c. | The best answer is “Crashing” (Answer option c.) is a technique used to shorten the schedule duration for the least incremental cost by adding resources and may result in increased risk and/or cost. “Critical path method” (Answer option a.) is a scheduling technique not a schedule compression technique. “Fast-tracking” (Answer option b.) is associated with quality risks. “Kanban system” (Answer option d.) is a resource constraint-based technique that cannot help with schedule compression.
Exam 6 | #150. Sean is having difficulties to estimate the duration of a new project assigned to him. Sean reached out to his Program Manager for his opinion about how much time will take to complete the remaining schedule. The Program Manager tells him if things keep moving organically and everything goes well the project can finish in 7 months. However, if the project site faces delayed delivery and late execution then it can take even 15 months. On the other hand, if people finish in time and you are lucky with a few deliverables, you can finish it in 3 months. Based on the values mentioned above, which estimation should Sean use? |  | Parametric Estimation | Analogous Estimation | Three-point Estimation | Bottom-up Estimation | Answer option c. | “Three-point Estimation” involves duration estimates based on three points with an assumed distribution.
Exam 6 | #151. A project manager is presented with the following situation: - An iteration just ended. - A team member tells the project manager that a planned task is not complete due to an issue that appeared 4 days ago that was not resolved. The project manager wants to prevent this scenario in the future. When is an appropriate time to discuss this issue? |  | During the retrospective | In the demo | During the next iteration planning meeting | In the next daily standup meeting | Answer option a. | During the retrospective, the development team identifies and discusses issues with the sprint (iteration) execution and shares ideas for improvement.
Exam 6 | #152. You are creating a value stream map to document the workflow of a new cell phone. What can a value stream map be used to show? (Choose two answers) |  | Bottlenecks | New product features | Delays | Net present value | Answer option a,c. | A value stream map can help you understand bottlenecks, slowdowns, delays, lead time, waste, and cycle time.
Exam 6 | #153. You are developing a schedule for the newest project assigned to you. After completing the schedule with all proper optimizations, it still does not meet the completion-date requested by the management. The company has tolerance for quality risks. Which technique can help you to achieve this objective? |  | Critical path method | Fast-tracking | Crashing | Kanban system | Answer option b | . “Fast-tracking” is the best answer since it won’t cause extra costs and the management is fine with the associated quality risks.
Exam 6 | #154. The use of internal or external resources to provide a sanity check against the proposals submitted by the bidders is called _____ . |  | Independent cost estimates | External cost estimates | Third-party cost estimates | Benchmarking | Answer option a. | “Independent cost estimates” are developed either internally or by using external resources and provide a sanity check against the proposals submitted by bidders.
Exam 6 | #155. You are considering the assistance of an expert to help you with the plan cost management processes. What expertise would you look for? |  | Strong leadership | Earned value management | Understanding the politics and power structures | Communication management | Answer option b. | “Earned value management” EVM expertise is highly required for the cost management knowledge area in general, especially plan cost management and control costs processes.
Exam 6 | #156. Why would a buyer decide to sign agreements with more than one seller? |  | To benefit from the sellers’ competition | To mitigate damage caused by a single seller having problems | To use the other as a pressure tool | None of the above | Answer option b. | “To mitigate damage caused by a single seller having problems” For risk mitigation, the buyer may decide to sign agreements with more than one seller to mitigate damage caused by a single seller having problems that impact the overall project.
Exam 6 | #157. You are the project manager of an adaptive project and trying to find the actual progress and to estimate the time needed to have a releasable product. To achieve this objective, what scheduling technique would you use? |  | Iterative scheduling with a backlog | On-demand scheduling | Agile release planning | Kanban system | Answer option c. | “Agile release planning” is a technique that determines how much needs to be developed and how long it will take to have a releasable product based on business goals, dependencies, and impediments.
Exam 6 | #158. A team misunderstood one product functionality documented in an earlier stage of the project. During the current iteration, the functionality has NOT yet been developed, but a business representative has mentioned the deficiency. How should the project manager proceed? |  | The functionality was formally approved, so initiate the change management process. | Schedule a meeting to discuss and brainstorm the functionality with the project team and business representative. | Ensure that the issue is addressed by escalating it to the project sponsor, who should discuss it with the representative. | Continue with the current sprint, recognizing that the issue will be identified during the testing phase. | Answer option b. | As the functionality has NOT been built, the project manager should facilitate building common understanding and empowering the team to evaluate the impact of a possible change, thus avoiding re-work.
Exam 6 | #159. After a heated discussion with the operations manager to sign off the project transition outputs, he is resisting and saying that his team needs work instructions and an operational manual for the new system. You are confident that you have delivered a pack of similar documents to them. Which of the following documents would contain the work instructions and an operational manual? |  | Project documents | Operational and support documents | Project or phase closure documents | Final report | Answer option b. | “Operational and support documents” are Documents required for the organization to maintain, operate, and support the product or service delivered by the project.
Exam 6 | #160. At the monthly team meetings, your team discusses the effectiveness of project processes and gives recommendations about improvements. During today’s meeting, your team is focusing on the design process for a new feature. During the last process, there were some issues reported on the faults with the design. What tool or technique can you use to help identify where the problem came from? |  | Process analysis | Monte Carlo analysis | Root cause analysis | Design analysis | Answer option c. | “Root cause analysis” is one of the data analysis methods in managing quality. This is the most likely tool for detecting the cause of the design problem.
Exam 6 | #161. You are the Scrum Master in an Agile organization. The Product Owner has just hired an experienced development team that she expects their velocity to be a factor in meeting the project delivery requirements. You like the idea and suggest the team to also start using Burndown chart to track progress; what is Burndown chart? |  | Burndown chart is a graphical illustration of how fast your team is working; it works by plotting user stories against time. | Burndown chart is a tool used to depict the user stories that must be completed first per the assigned milestones. | Burndown chart refers to the process of recording what user stories are done first in order to measure the progress. | Burndown chart is a tool used to fast-track user stories and tasks that are challenging to complete as per the assigned milestones. | Answer option a. | In Scrum, Burndown charts are visual representations of the remaining user stories for a given period of time on a Sprint. The chart is key in communicating the progress across all stakeholders.
Exam 6 | #162. At the project closure meeting, in order to improve organization metrics, the project team was discussing the project outcome and to what extent it has deviated from what was originally planned. What technique did the team use? |  | Expert judgment | Trend analysis | Document analysis | Variance analysis | Answer option d. | “Variance analysis” is used to measure to what extent it has deviated from what was originally planned during the close project process.
Exam 6 | #163. During the performance review meeting, the project manager found in the issue log that stakeholders do not receive a sufficient level of communication. What should he compare with the communication management plan in order to resolve the issue? |  | Project communications | Enterprise environmental factors | Organizational process assets | Work performance data | Answer option d. | “Work performance data” Work performance data contains data on the types and quantities of communications that have been distributed.
Exam 6 | #164. As April is considering her responsibilities to the team as a servant leader, she is NOT likely to consider the following: |  | Her responsibilities of educating the stakeholders about agile practices. | Her responsibilities to the team through mentoring, encouragement, and support. | Her responsibilities to direct the activities of risk analysis. | Her responsibilities to the team to celebrate success. | Answer option c. | While the servant leader may help with risk analysis activities, they are not expected to direct this work. Servant leaders prefer to use more facilitative skills, rather than directive ones.
Exam 6 | #165. After performing stakeholders' assessment, the project manager classified the stakeholders according to their level of authority and their ability to influence the project's outcomes. Which data representation technique did he use? |  | Impact/influence grid | Power/influence grid | Stakeholder cube | Salience model | Answer option b. | The best answer is “Power/influence grid” (Answer option b.). The question description level of authority (Power) and their ability to influence the project outcomes (influence) refer to the power/influence grid.
Exam 6 | #166. A new product development project is running for almost six months. Recently, you replaced the former project manager, and since then, you hear the project team talking about changes in the previously approved scope and the ever-changing requirements, despite the robust change-control process in place. You should _____ . |  | Consider changing the development approach | Reject all upcoming changes | Revisit the change management process | Inform the team to welcome all changes as long as they are funded | Answer option a. | The best course of action is to “Consider changing the development approach” (Answer option a.) since the new product development project is usually iterative and requires an agile approach. If you decide to “Reject all upcoming changes“ (Answer option b.) it would impact the end product fit for purpose. If you decide to “Revisit the change management process” (Answer option c.) it would not improve the situation since it is confirmed to be a robust process. If you decide to “Inform the team to welcome all changes as long as they are funded” (Answer option d.) without controls, it might harm project scope and other project elements.
Exam 6 | #167. You have just joined a software company that requires going through the complete requirements and design phases before writing the code. Such a delivery process is aligned with which of the following? |  | Agile Manifesto. | Predictive Life Cycle. | Plan-Do-Check-Act. | Scaled Agile Framework (SAFe®) | Answer option b. | Predictive Life Cycle is a more traditional approach, with the bulk of planning occurring up-front, then executing in a single, sequential process.
Exam 6 | #168. You are the project manager for a new product development project, and you received information about a major software tool you are using that will be retired soon. Since your project is the only project using this tool, what should you do? |  | Accept the risk | Mitigate by buying another software tool | Escalate to top management | Transfer through insurance | Answer option b. | The best course of action is “Mitigate by buying another software tool” (option b.) as this will help avoid the consequences of the tool retirement. If you decide to “Accept the risk” (answer option a.) you would impact your project badly since the tool is important to your project. If you decide to “Escalate to top management“ (answer option c.), there are no valid reasons for such action as no other projects are impacted. If you decide to “Transfer through insurance “(answer option d.) there is no logic behind the action.
Exam 6 | #169. Which of the following is not one of the 5Cs of written communications in composing a traditional written or spoken message? |  | Correct grammar and spelling | Coherent logical flow of ideas | Communication tool | Concise expression and elimination of excess words | Answer option c. | The best answer is “Communication tool” (Answer option c.) “Correct grammar and spelling” (Answer option a.), “Coherent logical flow of ideas” (Answer option b.) and “Concise expression and elimination of excess words” (Answer option d.) are all from the 5Cs of written communications in composing a traditional written or spoken message while the question is asking which is NOT thus these answers are not valid.
Exam 6 | #170. April is getting ready for her first agile project. She is new to project management and is nervous about the complexities of the work. While she is thinking about how best to lead the team, she is remembering the servant leadership training she has received. Which of the following are features of servant leadership? |  | Coaching vs. controlling | Promoting safety, respect, and trust. | Promoting self-awareness. | All of the above. | Answer option d. | All of these are features of servant leadership.
Exam 6 | #171. You welcome Peter to your agile team. He is a highly experienced software engineer who has been working on many government projects. Due to the nature of the work, he has been part of big and robust teams that have been working sequentially on completing the tasks. As this is his first Agile project, you explain to him the main difference between teams working in predictive projects and teams working in Agile projects. What do you say? |  | Strong team unity in Agile teams. | Reduced conflicts in Agile teams. | Better project management in Agile teams. | Self-organizing teams in Agile teams. | Answer option d. | The main characteristic of the Agile teams is that they are self-organizing and empowered when compared to predictive teams.
Exam 6 | #172. Betty has been recently hired as the Head of the PMO for a large software company ABC. The PMO has been following a waterfall-based project management approach for all current projects, and she identifies the need to instill Agile approaches for new projects on the roadmap. Although she identifies key benefits of Agile, the team members are not experienced in the use of Agile approaches. What should Betty do first? |  | Train the team members in effectively using the Lean Management methodology. | Train the team members in the fundamentals of the Agile Mindset and principles. | Train the team members in effectively using the XP (Xtreme Programming) approach. | Train the team members in effectively using the FDD (Feature Driven Development) approach. | Answer option b. | Starting with Agile Mindset/principles, training is the best approach. Once understanding the principles, the team can decide which specific approach (i.e. XP, Scrum, etc.) they want to move forward with. Additional workshops can be set up to train the team on which specific approach is chosen.
Exam 6 | #173. How can the flowcharts assist the project manager while managing the Quality? |  | Show a series of steps that lead to a defect | Show the number of defects per deliverable | Draw processes for the implementation team to follow | Show the strength of relationships among factors, causes, and objectives | Answer option a. | The best answer is “Show a series of steps that lead to a defect” (Answer option a.) as Flowcharts show a series of steps that lead to a defect in the process of managing quality. “Show the number of defects per deliverable” (Answer option b.) is a benefit of Histograms. “Draw processes for the implementation team to follow” (Answer option c.) is a benefit of flowcharts in plan Quality. “Show the strength of relationships among factors, causes, and objectives” (Answer option d.) is related to Matrix diagrams.
Exam 6 | #174. Two project team members are disagreeing on how internal testing should be done. One of them is reluctant to change the planned testing scenarios, and the other deem them insufficient. As the project manager, you decided to proceed with the planned scenarios due to time constraints. What conflict resolution technique did you use? |  | Smooth | Compromise | Force | Collaborate | Answer option c. | “Force” is pushing one’s viewpoint at the expense of others, usually enforced through a power position to resolve an emergency.
Exam 6 | #175. The project manager is surprised to learn during a sprint review that a team is behind schedule and that not all the work for the iteration has been completed. This is coming as a surprise because the product backlog had been sequenced to maximize value generation and decomposed into sprint backlogs for each team. Going forward, how can the project manager prevent this type of surprise from happening? |  | Build the appropriate level of contingency reserves into the sprint planning process. | Update the communication management plan with specific protocols to empower team members to warn about impending delays. | Encourage self-organization in the team and clarify high-level objectives. | Monitor team velocity over the next few iterations and implement the appropriate training to correct for underperformance. | Answer option c. | Agile projects are characterized by empowered teams who can self-organize and collaborate in assessing the best approach to carry out the work and meet project objectives, rather than having a project manager choose the approach and determine the work the team needs to execute. This results in more realistic plans and higher buy-in from team members.
Exam 6 | #176. You are working with your project team to resolve an internal failure. The issue looks more complicated than it seems. To solve the problem effectively, what are the problem-solving steps you should take? |  | Identify the problem, Define the problem, Analyze, Investigate, Solve, and Check the solution | Define the problem, Identify the problem, Analyze, Investigate, Solve, and Check the solution | Analyze, Identify the problem, Define the problem, Investigate, Solve, and Check the solution | Investigate, Identify the problem, Define the problem, Analyze, Solve, and Check the solution | Answer option a. | “Identify the problem, Define the problem, Analyze, Investigate, Solve and Check the solution” is the only answer in the right order.
Exam 6 | #177. While assessing a resource scarcity risk, you realized that the risk is major, and it would impact the whole portfolio. What risk response will you plan? |  | Avoid | Contingency response | Accept | Escalate | Answer option d. | “Escalate” is the only viable option since the impact of the risk is beyond the project manager’s authority and control.
Exam 6 | #178. Adam is managing a multi-country project where his project team is distributed across three different countries. Which of the following skills is the best for management of this team? |  | Active listening | Political awareness | Networking | Cultural awareness | Answer option d. | “Cultural awareness” is an understanding of the differences between individuals, groups, and organizations and adapting the project’s communication strategy in the context of these differences. Cultural awareness and cultural sensitivity help the project manager to plan communications based on the cultural differences and requirements of stakeholders and team members.
Exam 6 | #179. Which Agile Methodology describes the “Seven Wastes” in project management? |  | Scrum | Kanban | Kaizen | Six Sigma | Answer option c. | Kaizen describes the seven wastes, Lean Management Methodology.
Exam 6 | #180. Your project is facing a major deviation of the schedule performance. During the discussions with your team, multiple options were suggested including overtime, process improvements, and using outsourcing. You analyzed the different proposed options with the team and compared them to the current situation to make a decision. This is an example of _____ . |  | Alternatives analysis | Cost-benefit analysis | Performance reviews | Trend analysis | Answer option a. | “Alternatives analysis” Alternatives can be analyzed to select the best resolution for correcting variances in the project against the plan. Alternatives such as paying for overtime or additional team resources can be weighed against a late delivery or phased deliveries.

## exam7
Exam Name | Question | quesimgsrc | Answer1 | Answer2 | Answer3 | Answer4 | Correct-Answer | Explanation | answerimgsrc
Exam 7 | #1. A seller’s performance period spans two years. Which contract type should the project manager use? |  | Firm fixed price (FFP) | Fixed price incentive fee (FPIF) | Fixed price with economic price adjustments (FPEPA) | Time and material contracts (T&M) | Answer option c. | Answer option c. “Fixed price with economic price adjustments (FPEPA)” type of contract is used whenever the seller’s performance period spans a considerable period of years, or if the payments are made in a different currency. Answer option c. “Fixed price with economic price adjustments (FPEPA)” type of contract is used whenever the seller’s performance period spans a considerable period of years, or if the payments are made in a different currency.
Exam 7 | #2. Product Owner Gregg has requested that the first 10 items on the Product Backlog be moved into the next Sprint. Scrum Master Sheila explains that the work cannot be completed in the Sprint, and there needs to be fewer items moved into the Sprint. In her explanation of why this is, Sheila is likely to say all of the following EXCEPT: |  | Teams keep work-in-progress sizes small to better identify issues early. | Teams keep work-in progress sizes small to reduce rework should changes be required. | The items have not been sequenced yet, and therefore cannot all go into the Sprint. | The estimated effort of the work identified is longer than the length of the Sprint. | Answer option c. | Sequencing Activities is a process that occurs in predictive approach project management.
Exam 7 | #3. After six months of working together, the project team organized a meeting to review and discuss the team values and ground rules. As a result, they came up with an updated version of both. Which document should they update accordingly? |  | Lessons learned register | Project charter | Project team assignments | Team charter | Answer option d. | Answer option d. “Team charter” (Answer option d.). Team values and ground rules are recorded in the team charter. Any changes will result in the team charter update. Answer option d. “ Team charter” (Answer option d.). Team values and ground rules are recorded in the team charter. Any changes will result in the team charter update.
Exam 7 | #4. During the milestone review, the performance reports showed the following results VAC=$25K, ETC=$200K, and PV=$25K. How is the project performing? |  | On schedule | Behind schedule | Ahead of schedule | Cannot say | Answer option d. | “Cannot say”. EV is missing and the available information is not sufficient to determine the Earned Value (EV).
Exam 7 | #5. You are the Product Owner of a highly effective Scrum team. You tasked your development team to assist you with breaking down themes and epics into user stories in order to start working on Sprints and deliver results. Upon completing the set-up for user stories on the log, estimation comes next. Who is in charge of estimates in Scrum? |  | The Product Owner is in charge because they own and maintain the Product backlog. | The development team is in charge because they are performing the work and should be seen as subject matter experts. | The Scrum Master is in charge because they ensure the framework is followed and display the progress in high-level meetings with other Scrum Masters. | The Product Owner and the Scrum Master are in charge because they are similar to a Project Sponsor and a Project Manager in a traditional approach. | Answer option b. | In Scrum framework, even though the Product Owner is in charge of the Product Backlog, estimating how long each task will take is performed by the development team as they are the subject matter experts. The Team will use several techniques to estimate and agreement must be reached before proceeding with the work.
Exam 7 | #6. A project manager is working on finalizing the activities necessary to satisfy completion or exit criteria for the phase. Which of the following activities should he consider? |  | Confirming the formal acceptance of the seller’s work | Finalizing open claims, | Updating records to reflect final results | Finalizing product support document | Answer option a. | “Confirming the formal acceptance of the seller’s work” (Answer option a.) is an activity necessary to satisfy completion or exit criteria for the phase. “ Finalizing open claims” (Answer option b.) and “Updating records to reflect final results” (Answer option c.) are all activities related to the completion of the contractual agreements. “Finalizing product support document” (Answer option d.) falls under activities necessary to transfer the project’s products, services, or results to the next phase or to production and/or operations.
Exam 7 | #7. Your project is facing an issue with a specific activity. As the project manager, you want to address the responsible person. Which chart can help you? |  | Resource Assignment Matrix | Resource Breakdown Structure | Organizational breakdown structure | Work breakdown structures | Answer option a. | Answer option a. “Resource Assignment Matrix” (Answer option a.) contains responsibilities assignments to different stakeholders and project team members. Answer option a. “ Resource Assignment Matrix” (Answer option a.) contains responsibilities assignments to different stakeholders and project team members.
Exam 7 | #8. The quality team completed all planned test scenarios for a group of deliverables, and they passed the tests successfully. What is the next best action? |  | Perform Manage Quality | Perform Control Quality | Perform Validate Scope | Perform Control Quality | Answer option c. | Answer option c. “Perform Validate Scope” The deliverables just passed the Control Quality process and became a verified deliverable, which means that it should go through Validate Scope as an input. Answer option c. “Perform Validate Scope” The deliverables just passed the Control Quality process and became a verified deliverable, which means that it should go through Validate Scope as an input.
Exam 7 | #9. You have received a complaint from a customer of your IT project, stating that she intends to reject a product that was delivered in one of the early iterations as she was not able to review the product upon completion. How could you have prevented this issue with the customer? |  | Inform the customer of the purpose of sprint reviews. | Actively involve the customer, the team, and the product owner in the development of the project scope. | Make sure your team did a better job at monitoring and documenting scope changes in the early iterations. | Provide additional testing, which would have helped in making sure the product conformed to specifications. | Answer option a. | Sprint reviews are valuable meetings during which the team demonstrates the work that has been done in the iteration, suggests improvements and new features, and collects feedback from the product owner and other relevant stakeholders. It seems that the customer was not aware of these demonstrations and did not participate in them. She failed to stay engaged with the team and the project to make sure the product met her expectations.
Exam 7 | #10. A newly formed project team faces regular conflicts due to cultural differences. Which of the following can help the project manager to reduce the amount of conflict? |  | Set team ground rules | Apply solid project management practices | Increase team cultural awareness | All of the above | Answer option d. | Answer option d. The best answer is “All of the above” (Answer option d.). Answer option d. The best answer is “All of the above” (Answer option d.) . “Set team ground rules” (Answer option a.), “Apply solid project management practices” (Answer option b.), and “Increase team cultural awareness” (Answer option c.); all of them can help the project manager reduce conflict. “ Set team ground rules” (Answer option a.), “Apply solid project management practices” (Answer option b.), and “Increase team cultural awareness” (Answer option c.); all of them can help the project manager reduce conflict.
Exam 7 | #11. During the planning meeting, the project manager asked the team to vote for postponing the next meeting. To make a decision, the largest block of the team must agree on a course of action, even if they are not more than half. Which voting method is used? |  | Unanimity | Majority | Plurality | Fist to five | Answer option c. | Answer option c. “Plurality”. Decisions are made by the largest block in a group, even if a majority is not achieved. Answer option c. “ Plurality”. Decisions are made by the largest block in a group, even if a majority is not achieved.
Exam 7 | #12. At an early stage of the project, the project manager asked the quality team to document all project processes in a systematic guide and conduct training based on this guide for the project team. The cost of these activities is considered _____ . |  | Prevention Costs | Appraisal Costs | Internal Failure Costs | External Failure Costs | Answer option a. | “Prevention Costs” include document processes and training.
Exam 7 | #13. During a monthly status meeting the key stakeholders point out that the project is facing a lot of variance and defects. The Project Manager has invited the concerned members of the execution team to discuss in detail the underlying cause of a certain defect. He has directed the team members to identify all the underlying reasons leading to that defect. Which technique is most ideal to use in this case? |  | Alternatives analysis | Document analysis | Process analysis | Root cause analysis | Answer option d. “ | Root cause analysis” is an analytical technique used to determine the basic underlying reason that causes a variance, defect, or risk. When all root causes for a problem are removed, the problem does not recur.
Exam 7 | #14. During internal project planning, the project manager planned a series of workshops for the team to improve their self-awareness. This is an example of _____ emotional intelligence training. |  | Outbound (EI) | Inbound (EI) | Resource management methods | Self-organizing teams | Answer option b. | Improving self-awareness is an “Inbound (EI)”.
Exam 7 | #15. After analyzing the viability of BAC, the project manager found it is no longer realistic. What should the project manager do? |  | Escalate to project sponsor | Consider the forecasted EAC | Prepare justification for the management | All of the above | Answer option b. | Answer option b. “Escalate to project sponsor” (Answer option a.) and “Prepare justification for the management” (Answer option c.) are not required actions. The best answer is “Consider the forecasted EAC” (Answer option b.). Answer option b. “Escalate to project sponsor” (Answer option a.) and “Prepare justification for the management” (Answer option c.) are not required actions. The best answer is “Consider the forecasted EAC” (Answer option b.).
Exam 7 | #16. You have been assigned to manage an environmental project. You are reading the business documents, the feasibility study, and various scientific reviews of the impact of similar projects. You are particularly interested in how different aspects of the project are connected and interact with one another. All that you are doing is trying to understand the project’s: |  | Project Management Plan | Business case | Project requirements | Complexity | Answer option d. | Answer option d. “Complexity”. Complexity is something that contains multiple parts, possesses a number of connections between the parts, and exhibits dynamic interactions between the parts. It should help the project manager identify key areas when planning, managing, and controlling the project. Answer option d. “ Complexity”. Complexity is something that contains multiple parts, possesses a number of connections between the parts, and exhibits dynamic interactions between the parts. It should help the project manager identify key areas when planning, managing, and controlling the project.
Exam 7 | #17. You are planning your project’s schedule. Due to the project nature, the project requirements are expected to change as the project progresses. To plan the release schedule effectively, which scheduling method would you use? |  | Kanban Systems | Critical path | Iterative scheduling with a backlog | On-demand scheduling | Answer option c. | Answer option c. There are a number of keywords that indicate the project requires an agile approach like (the release schedule and the changing requirements due to the project nature). The best scheduling technique for this case will be “Iterative scheduling with a backlog” (Answer option c.) Answer option c. There are a number of keywords that indicate the project requires an agile approach like (the release schedule and the changing requirements due to the project nature). The best scheduling technique for this case will be “ Iterative scheduling with a backlog” (Answer option c.)
Exam 7 | #18. Company XYZ launched a new product development project. During the early stages, the project team needs the highest level of innovation possible. Which style should the project manager need to apply? |  | Management | Leadership | Both a and b | None of the above | Answer option b. | Answer option b. Leadership focuses on innovation while management focuses on administration. The best answer is “Leadership” (Answer option b.) Answer option b. Leadership focuses on innovation while management focuses on administration. The best answer is “ Leadership” (Answer option b.)
Exam 7 | #19. A project team has multiple communication issues and conflicts. Which technique can help the project manager to resolve this situation? |  | Ground rules | Meetings | Political awareness | Negotiation | Answer option a. | Answer option a. “Ground rules” (Answer option a.) set the expected behavior for project team members, as well as other stakeholders. Answer option a. “ Ground rules ” (Answer option a.) set the expected behavior for project team members, as well as other stakeholders.
Exam 7 | #20. During the implementation of your project, the sponsor invited you for a meeting and asked you to accelerate the project delivery by one month. You started re-planning your project activities accordingly and found that faster completion is possible with tight coordination and strict administration. Which style do you need to apply? |  | Management | Leadership | Both a and b | None of the above | Answer option a. | Answer option a. The situation requires a high level of administration and coordination which is a focus of management “Management” (Answer option a.) Answer option a. The situation requires a high level of administration and coordination which is a focus of management “ Management” (Answer option a.)
Exam 7 | #21. The project manager requested an explanation why in the past two weeks a particular activity took longer than planned. The quality team advised that it is due to the new applied processes that the staff has to follow to ensure adherence to standards. Under which category of cost does this fall? |  | Cost of Conformance | Cost of Nonconformance | Internal Failure Costs | External Failure Costs | Answer option a. | “Cost of Conformance” includes the time to do it right.
Exam 7 | #22. You are assigned as a Project Manager to a project in Vietnam for the last 6 months. You have received a call from the client yesterday and he has asked if you can finish the remaining deliverables in 90 days instead of 110 days. After that, you called up your team and discussed the requirements of the client. Later on, you updated the client that to complete the project 20 days earlier, an additional $200,000 will be charged. Which technique did you use to compress the project schedule? |  | Fast-tracking | Crashing | Resource leveling | Resource Smoothing | Answer option b. | “Crashing” is the technique used to shorten the schedule duration for the least incremental cost by adding resources.
Exam 7 | #23. According to the project team assessment for stakeholders, one of the technical leads has been classified as aware. However, she is neither supportive nor opposing. How would you classify her? |  | Unaware | Resistant | Neutral | Leading | Answer option c. | Answer option c. The statement describes, “Neutral” (Answer option c.) stakeholders since he is aware but has no interest in the project. Answer option c. The statement describes, “ Neutral” (Answer option c.) stakeholders since he is aware but has no interest in the project.
Exam 7 | #24. _____ are formally signed off deliverables that meet the acceptance criteria and approved by the customer or sponsor. |  | Verified deliverables | Validated deliverables | Accepted deliverables | Tested deliverables | Answer option c. “ | Accepted deliverables”
Exam 7 | #25. The Project Manager together with the project team has completed the stakeholders identification process and has identified their communications needs. The stakeholder’s engagement strategy was developed based on those needs. The team has also created a team charter and a list of roles and responsibilities. Which process should the project manager do next? |  | Develop project charter and the stakeholder register | Plan Communications Management | Monitor Stakeholders engagement | Identify Stakeholders’ risks | Answer option b. | Initiating processes are complete. Once the team charter is completed and the roles and responsibilities are defined, then you can determine stakeholder strategies and based on the strategy you create the communications management plan.
Exam 7 | #26. Mary is a project manager in a company that is adapting to a more agile project management approach. She has been chosen to initiate the first project to use an agile approach. During the first meeting with management, the sponsor asks Mary for details of how the project will be tailored. She replies that the project will be tailored taking into consideration the project scope, schedule, cost, resources, quality, and risk, as well as considering the project environment. The sponsor agrees that this sounds good but then asks Mary how the project manager role will be tailored. She replies: |  | The PM role will be tailored to be more of a facilitator, and senior team members will have greater decision-making authority within sprints | You can’t tailor the project manager role; it is defined by the organization. | As we have a PMO (project management office), all project roles must be unified across all projects. | The team members will take the role of the project manager and everyone will be in charge of the project. | Answer option a. | The PM role will be tailored to be more of a facilitator, and senior team members will have greater decision-making authority within sprints. The project management role is tailored to fit the organization in the same way that the project management processes are tailored to fit the project.
Exam 7 | #27. During the project review, the project team found some of the identified risks did not happen. What should you do with the unused contingency reserves? |  | Use them as planned to cover the cost of risk responses or other contingencies | Free up resources for other projects | Remove them from the project budget | Both A and C | Answer option d. | Answer option d. The best answer is “Both A and C” (Answer option d.). “Use them as planned to cover the cost of risk responses or other contingencies” (Answer option a.), and “Remove them from the project budget” (Answer option c.) are all valid options. Answer option d. The best answer is “ Both A and C” (Answer option d.). “Use them as planned to cover the cost of risk responses or other contingencies” (Answer option a.), and “ Remove them from the project budget” (Answer option c.) are all valid options.
Exam 7 | #28. After identifying the root cause of the recent quality issue, the project manager evaluated the possible options to resolve this cause. Which technique is he using? |  | Alternatives analysis | Document analysis | Process analysis | Performance analysis | Answer option a. | Answer option a. “Alternatives analysis”. This technique is used to evaluate identified options in order to select which different quality options or approaches are most appropriate to use. Answer option a. “Alternatives analysis”. This technique is used to evaluate identified options in order to select which different quality options or approaches are most appropriate to use.
Exam 7 | #29. During the project closure, the project manager is investigating the level of compliance with the quality requirements. Which document should he review? |  | Quality control measurements | Quality reports | Requirements documentation | Both A and C | Answer option a. | Answer option a. “Quality control measurements” (Answer option a.). This document contains the results of Control Quality activities and demonstrates compliance with the quality requirements. Answer option a. “ Quality control measurements” (Answer option a.) . This document contains the results of Control Quality activities and demonstrates compliance with the quality requirements.
Exam 7 | #30. You are the Product Owner of a junior Scrum team. A team member reached to you and asked how he would know what defines completion when a Sprint is complete? What is the best way to answer him: |  | The Product Owner is responsible for setting the requirements for completion. | The development team is responsible for setting the requirements for completion. | The Scrum Master and the development team are responsible for setting the requirements for completion. | The Product Owner and the development team are responsible for setting the requirements for completion. | Answer option d. | In Scrum framework, even though the Product Owner is in charge of the Product Backlog, setting up the requirements for completion and the definition for done is a joint effort between the development team and the Product Owner.
Exam 7 | #31. You are the Project Manager of a performing organization delivering an IT Project to a customer in France. You just receive an email from the customer’s Project Manager. You have to respond within the next hour as it discusses an urgent matter related to the current phase. Which type of communication is it? |  | Formal and Internal | Formal and External | Informal and Internal | Informal and External | Answer option d. | External Communication focuses on external stakeholders such as customers, vendors, other projects, organizations, government, the public, and environmental advocates. Informal communications deal with general communications activities using emails, social media, websites, and informal ad hoc discussions.
Exam 7 | #32. You are analyzing the organizational process assets that influence the monitoring of the stakeholders' engagement. Which is not one of them? |  | Organizational culture | Local trends and practices | Standardized guidelines for development | Stakeholder risk thresholds | Answer option c. | Answer option c. The best course of action is “Standardized guidelines for development” (option c.) as it is the only organizational process asset. “Organizational culture “(answer option a.), “Local trends and practices” (answer option b.), “Stakeholder risk thresholds “(answer option d.) are all enterprise environmental factors that influence this process. Answer option c. The best course of action is “ Standardized guidelines for development” (option c.) as it is the only organizational process asset . “ Organizational culture “(answer option a.), “ Local trends and practices” (answer option b.), “ Stakeholder risk thresholds “(answer option d.) are all enterprise environmental factors that influence this process.
Exam 7 | #33. A project manager is planning the scope for a system upgrade initiative. After requirements collection, the team categorized the agreed system features and functions. These details are called as _____ . |  | WBS dictionaries | Product scope | Project scope | WBS | Answer option b. | Answer option b. “Product scope” is the features and functions that characterize a product. Answer option b. “ Product scope” is the features and functions that characterize a product.
Exam 7 | #34. Amy, the Product Owner, has requested some major changes that will have a significant impact on the project and require a reprioritization of the remaining items in the backlog. What should be done in this scenario? |  | Complete the current sprint, reprioritize the backlog and adapt the new plan for the next sprint. | Cancel the current sprint and immediately call a sprint retrospective. | Complete the started stories but do not begin any “ready” stories in the current sprint. | Cancel the current sprint and reprioritize the entire backlog. | Answer option a. | It is uncommon for Agile teams to adjust their backlogs during a sprint (iteration) unless all of the items in the sprint are removed from the backlog. The ideal approach is to complete the current sprint and adapt the new plan for the next sprint.
Exam 7 | #35. A project manager is managing the communications. Of the following, which is an enterprise environmental factor that can influence this process? |  | Standardized guidelines for the development of information | Lessons learned repository | Established communication channels | All of the above | Answer option c. | Answer option c. “Established communication channels” (option c.) is an enterprise environmental factor. “Standardized guidelines for the development of information “(answer option a.) and “Lessons learned repository” (answer option b) are both organizational process assets, not enterprise environmental factors that influence this process. Answer option c. “ Established communication channels” (option c.) is an enterprise environmental factor. “ Standardized guidelines for the development of information “(answer option a.) and “Lessons learned repository” (answer option b) are both organizational process assets, not enterprise environmental factors that influence this process.
Exam 7 | #36. While planning the schedule management, a scheduling software is considered as _____ . |  | Enterprise environmental factors that can influence the process | Organizational process asset that can influence the process | Expertise required for performing the process | Both A and C | Answer option d. | Answer option d. The best course of action is to “Both A and C” (option d.). Answer option d. The best course of action is to “ Both A and C” (option d.). Scheduling software is considered both “Enterprise environmental factor that can influence the process “(answer option a.), and an “Expert knowledge required for performing the process” (answer option c.). Scheduling software is considered both “E nterprise environmental factor that can influence the process “(answer option a.), and an “ Expert knowledge required for performing the process” (answer option c.).
Exam 7 | #37. Jill is a Project Manager responsible for designing and a new scheduling software followed by a launch/rollout to the identified market. The project has been requested as a result of her company’s strategic roadmap, and if successful, will create a niche market solely owned by the company itself. However, the project has a high level of uncertainty with unclear requirements that can only be finalized through the design phase. Which is the best approach for Jill to manage the project? |  | Using a predictive approach for both design and launch/rollout. | Using a hybrid model; predictive approach for the design phase followed by an Agile approach for the launch/rollout. | Using a hybrid model; Agile approaches for the design phase followed by a predictive approach for the launch/rollout. | Using an Agile approach for both design and launch/rollout. | Answer option c. | Since the requirements are unclear and can only be finalized through Design, an Agile approach is best suited for this phase. Once the software has been developed and tested, the launch/rollout can be managed using a predictive approach.
Exam 7 | #38. During the implementation of a new website, the project manager decided to launch the site prototype version to a small group of stakeholders to collect their feedback for the upcoming development phases. Which of the following tools and techniques should he use? |  | Surveys | Context diagram | Control charts | All of the above | Answer option a. | Answer option a. “Surveys” (Answer option a.) is the only feedback tool mentioned in the options. Answer option a. “ Surveys” (Answer option a.) is the only feedback tool mentioned in the options.
Exam 7 | #39. You are managing a software development project. Your company wants to see frequent deliverables in short periods since the project is large, and it will take a long time to complete the project. There are a few dependencies between the features of the project activities. Which of the following scheduling techniques would you use in this case? |  | Critical path method | On-demand scheduling | Critical chain method | Iterative scheduling with a backlog | Answer option d. | Answer option d. “Iterative scheduling with a backlog” (Answer option d.) is often used to deliver incremental value to the customer or when multiple teams can concurrently develop a large number of features that have few interconnected dependencies. Answer option d. “ Iterative scheduling with a backlog” (Answer option d.) is often used to deliver incremental value to the customer or when multiple teams can concurrently develop a large number of features that have few interconnected dependencies.
Exam 7 | #40. Jack is leading a software development project. Since the project requires specialized programmers available internally, he needs to assign resources on a sharing basis. With whom should he negotiate? |  | Other project managers | Functional managers | External organizations and suppliers | None of the above | Answer option a. | Answer option a. The project manager negotiates with “Other project managers” to appropriately assign or share scarce or specialized resources Answer option a. The project manager negotiates with “ Other project managers” to appropriately assign or share scarce or specialized resources “Government or industry standards” (Answer option a.), “Project management body of knowledge” (Answer option b.), and “Organizational governance framework” (Answer option c.) are all enterprise environmental factors, not organizational process assets. “ Government or industry standards” (Answer option a.), “ Project management body of knowledge” (Answer option b.), and “ Organizational governance framework” (Answer option c.) are all enterprise environmental factors, not organizational process assets.
Exam 7 | #41. While performing the Validate Scope process, the team seeks to review the requirements of the deliverables and the way to validate them. Which input document contains such details? |  | Requirements traceability matrix | Requirements documentation | Quality reports | Quality measurements | Answer option a. | Answer option a. “Requirements traceability matrix” contains requirements that are compared to the actual results to determine if a change, corrective action, or preventive action is necessary. Answer option a. “Requirements traceability matrix” contains requirements that are compared to the actual results to determine if a change, corrective action, or preventive action is necessary.
Exam 7 | #42. You are a Scrum Master in a Scrum team. You have been working in this role for over eight years now on different projects. You are in the midst of an iteration and you have an issue: The Product Owner doesn't want to prioritize items in the Product Backlog. He says everything is important and is critical. What is the best you can do? |  | Let the Scrum Team work without prioritizing. Anyway, you will have to deliver all the features. It is not a critical problem | Be firm and insist on prioritizing | Prioritize the Product Backlog yourself | Let the Team decide which features are most important | Answer option b. | Answer option b. Be firm. Yes, everything is important, but something has to come first and something will come last. Someone has to make the tough schedule decisions. That’s the Product Owner’s job. Answer option b. Be firm. Yes, everything is important, but something has to come first and something will come last. Someone has to make the tough schedule decisions. That’s the Product Owner’s job .
Exam 7 | #43. You are using a new project management software, social media, and video conferencing to help your virtual project team work together more effectively. Which project integration level are you implementing? |  | Process level | Cognitive level | Context level | All of the above | Answer option c. | Answer option c. “Context level” (Answer option c.) Context level is when the project managers consider contemporary communications planning and knowledge management to guide the project team. Answer option c. “ Context level” (Answer option c.) Context level is when the project managers consider contemporary communications planning and knowledge management to guide the project team.
Exam 7 | #44. When the planning horizon is near, detailed estimation and planning should be done. This is particularly true of Agile projects. What is this planning approach known as? |  | Rolling wave planning | Summary task planning | Planning package | Short-term milestone plan | Answer option a. | “Rolling wave planning” is detailed planning for the near-term work and high-level planning for the work that will be delivered later in the project. Rolling waves can be used in predictive projects as well.
Exam 7 | #45. You are the Product Owner of an Agile organization that is producing several different products. You have multiple teams working on separate Backlogs. Under what condition should separate Product Backlogs be created and maintained? |  | There are multiple teams working on the components of the same product. Each team should have an independent Product Backlog. | There are multiple teams working on independent products. Each unique combination of team and product should have an independent Backlog. | There are multiple products being developed by the same team. Each product should be the subject of an independent Product Backlog. | There are several Product Owners for one product. Each Product Owner should have their own Product Backlog. | Answer option b. | In the Scrum framework, different products should have independent Backlogs and separate teams should be created, where each team will focus only on a single product. The Product Owner should architect the number of teams created and maintain the separate Backlogs throughout.
Exam 7 | #46. You have been a Scrum Master for over seven years now. During a meeting with your development team, product owner, and the customers you mention that Agile teams focus on people rather than processes and tools. The product owner responds, "I'm confused, what do you mean by that?" You answer what it means. |  | It is harder to find people and keep them happy than it is to develop processes and tools. | If we get the right people on the team, the processes and tools they are using won't matter. | Having an empowered team is more important for project success than the processes and tools being used. | A project's chances of success are heavily dependent on whether we can get the best people on the team. | Answer option c. | Agile teams follow Agile Manifesto value 1, “individuals and interactions over processes and tools,” because experience has shown that having an empowered team is more important to the success of an agile project than the processes and tools they choose to use.
Exam 7 | #47. _____ presents the calculated correlation coefficient for each element of the quantitative risk analysis model that can influence the project outcome. |  | Monte Carlo analysis | Tornado diagram | Decision trees | Both A and B | Answer option b. “ | Tornado diagram” is a typical display of sensitivity analysis that presents the calculated correlation coefficient for each element of the quantitative risk analysis model that can influence the project outcome.
Exam 7 | #48. David has been hired by company BlueDrive to introduce Agile principles into its Project Management Office. During one of the initial presentations to the team, he presents a tough question: Is Agile an approach, a method, a practice, a technique, or a framework? What is the correct response? |  | Agile is a framework that contains methods and techniques. | Agile is neither an approach nor a framework, however it contains some methods and techniques. | Agile is an approach and not a framework, it contains methods and techniques | Any or all these terms could apply depending on the situation. | Answer option d. | Agile can be viewed as any of these items (approach, framework, practice, or technique) depending on the context of use.
Exam 7 | #49. A project manager is struggling due to the high workload in an Agile project. She is quite experienced in traditional project management and this is her first Agile project. By default, she is applying the tools and techniques from traditional project management. She is swamped with work and is looking if she can delegate some tasks. What tasks may be delegated while attempting to focus on project integration management? |  | Project governance | Product planning and delivery | Project risk management | Managing linkages to the program | Answer option b. | Answer option b. Detailed product planning and delivery may be easily delegated to the project team while the project manager focuses on integration. Answer option b. Detailed product planning and delivery may be easily delegated to the project team while the project manager focuses on integration .
Exam 7 | #50. The activity cost based on realistic effort assessment is $20, based on the best-case scenario, it is $18, and based on the worst-case scenario it is $25. What is the activity cost estimate using triangular distribution? |  | 20 | 20.5 | 21 | 41 | Answer option c. “ “. | Answer option c. “$21“. Triangular distribution. cE = (cO cM cP) / 3= (18 20 25)=$21 Answer option c. “ $21 “. Triangular distribution. cE = (cO cM cP) / 3= (18 20 25)=$21
Exam 7 | #51. A project manager allows the project team to make their own decisions and establish their own goals. Which leadership style is he employing? |  | Laissez-faire | Transactional | Transformational | Interactional | Answer option a. | Answer option a. Laissez-faire style allows the team to make their own decisions and establish their own goals “Laissez-faire” (Answer option a.) Answer option a. Laissez-faire style allows the team to make their own decisions and establish their own goals “ Laissez-faire” (Answer option a.)
Exam 7 | #52. You’re a tester for a health information management interface. You’re in the middle of a 3rd sprint before a significant release, and you’re facing unstable production servers that the team is using during testing (as part of its definition of done). The group itself had no control over these servers — that is the responsibility of the VP of Operations. What do you think is the best approach to handle this situation? |  | The Scrum Master should take ownership of improving the server stability by working with the VP of Operations and others who could do something about the stability issue. | The testing team should work on this with the VP of Operations and others to embrace the self-organizing agile values. | The product owner must help change the faulty servers as it is part of the product that he is accountable for. | Functional team managers must escalate the whole issue to the CEO. | Answer option a. | The ScrumMaster also takes responsibility for removing impediments that inhibit the team’s productivity.
Exam 7 | #53. A project team is analyzing the quality reports, test reports, performance reports, and variance analysis to identify and focus on out of control processes. Which technique should he use? |  | Alternatives analysis | Document analysis | Process analysis | Root cause analysis | Answer option b. | “Document analysis” is the analysis of different documents produced as part of the output of project control processes, such as quality reports, test reports, performance reports, and variance analysis, can point to and focus on processes that may be out of control and may jeopardize meeting the specified requirements or stakeholders’ expectations.
Exam 7 | #54. During the project cost management planning, the project manager reviewed the Business case, Agreements, and Project schedule. In which processes the project manager uses these inputs? |  | Plan Cost Management | Estimate Costs | Determine Budget | All of the above | Answer option c. | Business case, Agreements, and Project schedule are all inputs for the “Determine Budget” process.
Exam 7 | #55. While implementing the risk response to a threat in a project, the risk owner reported that there is a remaining risk at an acceptable level. Often, we call these remaining risks _____ . |  | Known risks | Acceptable risks | Residual risks | Secondary risks | Answer option c. | “Residual risks” are expected to remain after planned responses have been taken, as well as those that have been deliberately accepted.
Exam 7 | #56. While implementing the risk responses, the project team needs to know about the agreed-upon risk responses for each individual risk and the nominated risk owners. Which input document contains this information? |  | Risk register | Risk report | Risk management plan | All of the above | Answer option a. | “Risk register” records the agreed-upon risk responses for each individual risk and the nominated owners for each response plan.
Exam 7 | #57. To receive better results from the team members, the project manager empowered them to participate in decision making and encouraged them to work independently. This is an example of _____ . |  | Conflict management | Influencing | Motivation | Team building | Answer option c. | Answer option c. “Motivation” is providing a reason for someone to act. Teams are motivated by empowering them to participate in decision making and encouraging them to work independently. Answer option c. “ Motivation” is providing a reason for someone to act. Teams are motivated by empowering them to participate in decision making and encouraging them to work independently.
Exam 7 | #58. During the project closure, the project manager is investigating the level of compliance with the project scope. Which document should he review? |  | Quality control measurements | Quality reports | Requirements documentation | Requirement traceability matrix | Answer option c. | Answer option c. “Requirements documentation” (Answer option c.) is an artifact that demonstrates compliance with the project scope. Answer option c. “ Requirements documentation” (Answer option c.) is an artifact that demonstrates compliance with the project scope.
Exam 7 | #59. David and his team are executing the first Agile project for software company XYZ. This is considered a pilot project, as this will be the first time Agile principles have been used. As the last Sprint (iteration) is being completed, David realizes some of the user stories are still incomplete. Can the team extend the Sprint (iteration) duration by a couple of days in order to complete all remaining stories in the Sprint (iteration) plan? |  | No; the Sprint (iteration) is a time-boxed event. | Yes, but the extension cannot be more than 4 days. | Yes, but requires the approval of the Product Owner. | Yes, but requires the approval of the Scrum Master. | Answer option a. | Sprints are time-boxed and cannot be extended. Any stories that are incomplete need to be returned to the Product Backlog to be re-prioritized with the other stories.
Exam 7 | #60. Scrum Master Janice is about to head into a meeting with the Developers. Occasionally the Product Owner attends this meeting, but he is not expected today. In this meeting, each Developer will detail what they completed yesterday, what they are working on today and any obstacle that is currently impeding their progress. This meeting is called: |  | Daily Stand-up | Sprint Planning | Sprint Review | Sprint Retrospective | Answer option a. | The Daily Stand-up (or Daily Scrum) is the meeting where the Developers share this information.
Exam 7 | #61. You are managing a software development project. As you are developing the project schedule, how frequently should you perform this process? |  | Performed throughout the project | Once during planning | Once every iteration or release | Only when needed | Answer option a. | Answer option a. “Performed throughout the project” (Answer option a.) Develop Schedule is an iterative process thus it is performed throughout the project. Answer option a. “ Performed throughout the project” (Answer option a.) Develop Schedule is an iterative process thus it is performed throughout the project.
Exam 7 | #62. What is the difference between explicit knowledge and tacit knowledge? |  | Tacit knowledge is shared by codifying, recording, and circulating, but explicit knowledge is shared by human interaction | Explicit knowledge is shared by codifying, recording, and circulating, but tacit knowledge is shared by human interaction. | Writing a book is an example of explicit knowledge, but writing a poem is an example of tacit knowledge. | The human mind can only retain a small amount of tacit knowledge, but large amounts of explicit knowledge. | Answer option b. “ | Explicit knowledge is shared by codifying, recording, and circulating, but tacit knowledge is shared by human interaction.”
Exam 7 | #63. The daily Scrum in your project has turned out to be a problem-solving activity and a status meeting. Your team decided to talk about problems during the daily Scrum, and the 15-minutes time slot is no longer viable. Going forward, who must attend this meeting? |  | The scrum master, the product owner, and the development team. | The development team and the scrum master only. | The development team and the product owner only. | The development team with the scrum master as an optional attendee. | Answer option d. | The daily Scrum is a brief collaboration meeting in which the team reviews progress from the previous day, declares intentions for the current day, and highlights any obstacles encountered or anticipated. We should Encourage any team member to facilitate the stand-up instead of a project manager or leader to ensure it does not turn into a status meeting but instead is used as a time for the team to self-organize and make commitments to each other.
Exam 7 | #64. John, in his role as Scrum Master, has the responsibility of introducing the Developers to the principles and processes of agile. The newest Developer, Alicia, has some questions about how to estimate the work required. When John explains the use of the Fibonacci sequence, what is he referring to? |  | Define Scope | Planning Poker | Estimate Activity Durations | Sequence Activities | Answer option b. | Planning Poker is an activity that takes place in the Sprint Planning Session. This activity allows the Developers to estimate the time required to complete the activities necessary to fulfill the objective in the User Story.
Exam 7 | #65. Your project team is unsure about the difference between configuration control and change control, and how Agile projects may benefit from these. How will you explain it to them? |  | Change control is concerned with managing changes at the iteration level, while configuration control is about making sure the project executes only the scope included in the scope baseline. | They are two names for basically the same thing, and Agile organizations use it as they best see fit. | Change control is focused on schedule and cost changes, while configuration control is focused on changes to the product backlog. | Change control is focused on changes to project documents, deliverables, or baselines, while configuration control is focused on the specification of deliverables and processes. | Answer option d. | Configuration control and change control are both performed at the integration level, and plans are developed to define the specific approach the project will follow. In Agile, requirements can often change even late in the development process, so it is especially important to be prepared to manage changes and to account for project artifacts.
Exam 7 | #66. During the milestone review, the performance reports showed the following cost performance results: EAC=$255K, ETC=$200K, and EV=$60K. What can you say about the cost performance of the project? |  | Under planned cost | On planned cost | Over planned cost | Cannot say | Answer option a. “ “. | Answer option a. “Under planned cost“. To measure the project cost performance, you need to calculate either CPI, CV, or VAC. The available data is EAC=$255k, ETC=$200k, and EV $60k. From the available data we can derive CV and SPI through the following calculations: EAC=ETC AC; AC= EAC-ETC=255 200=$55k, CV =EV – AC= 60-55=5. CV is greater than zero. Thus, the project is under planned cost. Answer option a. “ Under planned cost “. To measure the project cost performance, you need to calculate either CPI, CV, or VAC. The available data is EAC=$255k, ETC=$200k, and EV $60k. From the available data we can derive CV and SPI through the following calculations: EAC=ETC AC; AC= EAC-ETC=255 200=$55k, CV =EV – AC= 60-55=5. CV is greater than zero. Thus, the project is under planned cost.
Exam 7 | #67. During the kick-off meeting, the project manager says that during the project planning, they need to consider the constraints that they will have in the project. Which document contains these details? |  | Issue log | Assumptions log | Change log | All of the above | Answer option b. | Answer option b. “Assumptions log” (Answer option b.) contains high-level strategic and operational assumptions and constraints Answer option b. “ Assumptions log” (Answer option b.) contains high-level strategic and operational assumptions and constraints
Exam 7 | #68. A project is experiencing a breakdown in communications and a high level of conflict among team members. Status meetings are disorganized, and it is very difficult to come to any sort of agreement, due to differences in opinions of the stakeholders involved. How should the project manager address the situation? |  | Set ground rules for the meetings and do not allow team members to derail the proceedings with personal disagreements. | Start each meeting with an overview of the agenda and be very clear about the expectations and outcome of the meeting. Set aside some time at the end of the meeting to tackle disagreements as a group. | Deal with the issues at the beginning of the meetings by setting aside some one-on-one time with concerned team members. If left unattended, the disagreements will make it impossible to get anything done during the meeting. | Acknowledge team members' concerns during the meeting and meet with them privately at another time to discuss the concerns. | Answer option d. | The project manager must understand the reasons and nature of a conflict and listen to all sides. However, the status meetings should not become conflict-solving sessions involving the whole team, so it is best to approach the concerned stakeholders privately first, and with a clear picture of the situation, then decide on how to proceed.
Exam 7 | #69. You are the Product Owner of a newly formed Scrum team. To help the team understand the difference between a Product Backlog (PBL) and a Sprint Backlog (SBL), you draft a chart and explain the difference in certain categories; on estimation level, the Sprint Backlog (SBL) is different from the Product Backlog (PBL) in the sense: |  | The Sprint Backlog estimates the remaining work in story points assigned to a particular Sprint. | The Sprint backlog estimates the remaining work in hours assigned to a particular task. | The Sprint Backlog does not contain any estimation units because that is included in the Product Backlog. | Both Logs (SBL-PBL) estimate the remaining work in story points because Scrum poker technique does not create hours for tasks. | Answer option b. | Per Scrum framework, the team is allowed to estimate the remaining work in hours on the Sprint Backlog and for single tasks (items). Those hours are quantified based on story points from the Product Backlog.
Exam 7 | #70. You are aiming to increase the likelihood of final product acceptance, and bring objectivity to the acceptance process by validating each deliverable. Which process can help you to achieve this? |  | Validate scope | Control scope | Manage quality | Both A and C | Answer option a. | Answer option a. “Validate scope” The key benefit of this process is that it brings objectivity to the acceptance process and increases the probability of final product, service, or result acceptance by validating each deliverable. Answer option a. “ Validate scope” The key benefit of this process is that it brings objectivity to the acceptance process and increases the probability of final product, service, or result acceptance by validating each deliverable.
Exam 7 | #71. A project manager has taken charge of a low complexity Agile project. This individual is not so familiar with Agile communication approaches but was appointed due to an urgent need until an Agile certified project manager is hired. However, it was expected that this individual was familiar with some of the basic aspects of Agile project communications. This manager established a new communication method not found in traditional approaches. What was it? |  | Establishing information radiators | Utilizing sensitivity charts | Including more stakeholders in project meetings | Using social media tools for communications | Answer option a. | Use of information radiators at the employee workplace is unique to Agile projects.
Exam 7 | #72. The project manager on a two year project left and was replaced with a new one. The new project manager analyzed the team plan for team communications. Although the team performance is not optimal, members learned to trust each other. At which stage does this team stand? |  | Forming | Storming | Norming | Adjourning | Answer option c. | “Norming” team members start to trust each other and cooperate in the norming stage while their performance may not reflect it.
Exam 7 | #73. If the project manager wants to acquire the best internal resources possible in the required timeframe, with whom should he negotiate? |  | Other project management teams | Functional managers | External organizations and suppliers | All of the above | Answer option b. | Answer option b. “Functional managers” project managers need to negotiate internal resources with functional managers to acquire the required resources in the required timeframe. Answer option b. “ Functional managers” project managers need to negotiate internal resources with functional managers to acquire the required resources in the required timeframe.
Exam 7 | #74. David has asked a publisher to create flashcards containing Agile principles. After the flashcards were delivered, he found some of the flashcards had incorrect Agile principles listed on them. Which of the following flashcards has an incorrect Agile principle printed on it? |  | “Virtual Teams are the most efficient and effective method of conveying development team information.” | “Working software is the primary measure of progress.” | “Focus on technical excellence.” | “Continuous delivery of valuable software.” | Answer option a. | Face to Face conversation is the most efficient and effective method of conveying development team information. All remaining items are correct.
Exam 7 | #75. You are the Product Owner of a software development project. Your team is working hard on the new iteration. The release is planned for the end of the month and all is going according to the plan. Just now, you get a call from the customer and he wants to completely change the functionality your team is working on, as he thinks that it is no longer relevant. You need to change the plan to accommodate the request. When can a plan be changed in Agile Management? |  | At the end of the Iteration | When we find out something new or when we need to change something | At the daily standup meeting | You cannot change once the plan is prepared | Answer option b. | Answer option b. In Agile, you can change the plan when something new is learned or when you find out that something needs to be changed in order to avoid a problem. Answer option b. In Agile, you can change the plan when something new is learned or when you find out that something needs to be changed in order to avoid a problem .
Exam 7 | #76. You are the Product Owner of a newly formed Scrum team. To help the team understand the difference between a Product Backlog (PBL) and a Sprint Backlog (SBL), you draft a chart and explain the difference in certain categories; on ownership level, the Sprint Backlog (SBL) is different from the Product Backlog (PBL) in the sense: |  | It is owned by the Product Owner because she/he owns the Product Backlog. | It is owned by the Product Owner and the development team due to the detail level. | It is owned by the Scrum Master because he/she articulates the team to deliver the tasks. | It is owned by the entire team including the Product Master, Scrum Master, and the development team. | Answer option b. | Per Scrum framework, the entire Scrum team including the Product Owner, Scrum Master and the development team member will share ownership of the Sprint Backlog.
Exam 7 | #77. As Alicia is reviewing the proposal for her next project, she is determining which approach is most appropriate. She determines that a hybrid approach of predictive and agile is the best path. She decided to tailor her approach to the best needs of the customer. She could have made this decision for all of these reasons EXCEPT: |  | Quality history of the current team is poor. | The project team is inexperienced in agile approaches. | The customer does not have high quality needs in the project. | The customer has detailed requirements but expects a large quantity of additions and deletions to the feature list to occur during the project. | Answer option c. | Agile approaches are not designed to minimize quality. Both A and B are valid reasons to choose a hybrid approach. Poor quality can be improved by using agile methodologies as there is frequent inspection. Team’s inexperienced in agile approaches can benefit from a higher level of planning in the Initiating phase of a project while they gain experience. D is an example of hybrid methods allowing the perfect combination of planning and iteration as a tailored approach to the project.
Exam 7 | #78. A project manager is investigating the preferred communication method, format, and content for planned communication activities to engage unsupportive stakeholders. Which technique is he using? |  | Stakeholder engagement assessment | Communication styles assessment | Stakeholder analysis | Political awareness | Answer option b. | “Communication styles assessment” is a technique used to assess communication styles and identify the preferred communication method, format, and content for planned communication activities and is often used with unsupportive stakeholders.
Exam 7 | #79. _____ is the process of identifying and analyzing new risks and evaluating the effectiveness of risk processes. |  | Plan Risk Management | Identify Risks | Plan Risk Responses | Monitor risks | Answer option d. | “Monitor risks”is the process of identifying and analyzing new risks, and evaluating the effectiveness of risk processes.
Exam 7 | #80. While planning for a system integration project, the project manager realized that his company has a limited number of system integration experts. To procure these experts, which contract type should the project manager consider? |  | Firm fixed price (FFP) | Cost plus fixed fee (CPFF) | Time and material contracts (T&M) | Cost plus award fee (CPAF) | Answer option c. | Answer option c. “Time and material contracts (T&M)” They are often used for staff augmentation, acquisition of experts. Answer option c. “ Time and material contracts (T&M)” They are often used for staff augmentation, acquisition of experts.
Exam 7 | #81. Company XYZ is planning to introduce a new product to the market. The project team for this new product development is working to determine how to meet the goal of the product’s performance and reliability. Which technique does the team use? |  | Quality metrics | Test and evaluation documents | Test and inspection planning | Quality planning | Answer option c. “ | Test and inspection planning” determine how to test or inspect the product, deliverable, or service to meet the stakeholders’ needs and expectations, as well as how to meet the goal for the product’s performance and reliability.
Exam 7 | #82. Betty is responsible for designing a new data repository system for startup company XYZ. As a part of the project, she needs to consult with a number of senior stakeholders and assess their business needs. Once requirements have been approved, the system will need to be developed, and rolled out. Prior to rollout however, all employees have to be trained in effective use of the new system. Which of the following life cycles should be adopted for the user training phase of the project? |  | Agile | Predictive | Iterative | Incremental | Answer option b. | User training, unlike the development phase, can be planned in advance. The predictive approach can be used to manage the training phase of the project.
Exam 7 | #83. It is a very complex project with many changes to the requirements. The customer is trying to create a project that is unique and an early comer at the market. Everyone is working very hard and is pulling a lot of hours on the project. Currently, the situation does not look very optimistic. Your team planned to complete six stories in the current sprint. But as you reach the end of the sprint, only four of them are done. What should you do? |  | Return the remaining stories to the backlog for re-planning | Ask the product owner to extend the sprint | Work on the remaining stories when you can fit them in | Schedule the remaining stories at the start of the next sprint | Answer option a. | Since sprints are timeboxed, when a sprint ends, we stop working and return any incomplete work to the backlog for re-planning. In the next planning meeting, we will need to consider the customer’s updated priorities and new information; the work we didn’t get done this time might or might not be our top priority for the next sprint.
Exam 7 | #84. Your team is working on a software development project and using the Kanban method. A new team member has been added to the team to finish the remaining work. This new team member received many comments from others that there is too much work in progress (WIP). Which of the following options represent the example of WIP? |  | User stories that have not been prioritized by the product owner | User stories that are committed and pending customer feedback | User stories with the code that has been deployed and integrated | User stories that have been selected by the team | Answer option b. | Answer option b. Work in progress represents all the work items the team is currently involved in. It represents the work items the team is actively working on, items the team is waiting for verification or deployment, and the unfinished items that are required to be completed to deliver the business values of the customers. This scenario clearly shows that the team is working on user stories and it is still not finished. There may be a need to work even after receiving customer feedback. Answer option b. Work in progress represents all the work items the team is currently involved in. It represents the work items the team is actively working on, items the team is waiting for verification or deployment, and the unfinished items that are required to be completed to deliver the business values of the customers. This scenario clearly shows that the team is working on user stories and it is still not finished. There may be a need to work even after receiving customer feedback .
Exam 7 | #85. A project manager set a meeting with the quality manager to discuss the recent quality report. What communication method are they using? |  | Interpersonal communication | Interactive communication | Push communication | Both A and B | Answer option d. | Answer option d. The best answer is “Both A and B” (option d.) “Interpersonal communication “(answer option a.). Information is exchanged between individuals, typically face-to-face. “Interactive communication” (answer option b.) is between two or more parties performing a multidirectional exchange of information in real-time. They both describe the situation. Answer option d. The best answer is “Both A and B” (option d.) “ Interpersonal communication “(answer option a.). Information is exchanged between individuals, typically face-to-face. “Interactive communication” (answer option b.) is between two or more parties performing a multidirectional exchange of information in real-time. They both describe the situation.
Exam 7 | #86. After your recent sprint retrospective, you’ve decided with the team to start implementing changes and process improvements in an iterative approach. Which of the following methodologies/tools should you use? |  | PDCA (Plan, Do, Check, Act) | Root Cause Analysis | Total Productive Maintenance (TPM) | Value Stream Mapping | Answer option a. | Plan-Do-Check-Act (PDCA) is an iterative management method used in organizations to facilitate the control and continual improvement of processes and products.
Exam 7 | #87. While monitoring and controlling the project work, which activities are you expected to perform? |  | Comparing actual project performance against the project management plan | Assessing performance periodically | Monitoring implementation of approved changes | All of the above | Answer option d. “ | Answer option d. The best answer is “All of the above” (Answer option d.). Answer option d. The best answer is “All of the above” (Answer option d.). “Comparing actual project performance against the project management plan” (Answer option a.), “Assessing performance periodically” (Answer option b.), and “Monitoring implementation of approved changes” (Answer option c.) are all activities performed while Monitor and Control Project Work process. “ Comparing actual project performance against the project management plan” (Answer option a.), “Assessing performance periodically” (Answer option b.), and “Monitoring implementation of approved changes” (Answer option c.) are all activities performed while Monitor and Control Project Work process.
Exam 7 | #88. During the execution of an IT upgrade project, one of the risk owners found out that the implemented strategy was only partially effective. Therefore, he should implement _____. |  | Fallback plan | Contingency plan | Escalate risk strategy | Both A and B | Answer option a. | Answer option a. A fallback plan is an action plan that will be executed if a contingency plan fails. Answer option a. A fallback plan is an action plan that will be executed if a contingency plan fails.
Exam 7 | #89. Your company decided to suspend some of the low-priority projects due to the financial crisis. The suspension period will continue for at least six months. Your project is also one of the projects that will be suspended. However, you cannot suspend the project since it will be considered as a failure if you cannot complete it on time. You explained the situation to the senior management, and they advised you to terminate the project. What should you do next? |  | Document the reasons for termination | Release project resources | Handover the completed and incomplete deliverables | All of the above | Answer option d. | Answer option d. The best answer is “All of the above” (Answer option d.) Answer option d. The best answer is “ All of the above” (Answer option d.) “Document the reasons for termination” (Answer option a.), “Release project resources” (Answer option c.) and “Handover the completed and incomplete deliverables” (Answer option d.) are all activities required for this situation. “ Document the reasons for termination” (Answer option a.), “ Release project resources” (Answer option c.) and “ Handover the completed and incomplete deliverables” (Answer option d.) are all activities required for this situation.
Exam 7 | #90. During retrospectives, some of the plans placed under configuration control do not seem to reflect the updates the team agrees on at the end of each iteration. The project manager is concerned about poor version control and archiving issues. What can the project manager do in this case? |  | Include the issue in the issue log, appoint an issue owner to track it, and let the team decide on the best approach, while assisting them if needed. | Assign a member of the technical team to manually enter the changes and validate that they are accessible across the platform. | Determine if updating the plans contributes to providing business value in the subsequent iterations and decide accordingly. | Outsource the fix to external resources to avoid overburdening the developing team. | Answer option c. | The project manager needs to help the team by removing blocks and impediments that may prevent them from performing effectively and allow them to focus on development work. Taking away technical team members from their work to perform manual administrative tasks is not the best way to deal with the issue.
Exam 7 | #91. After the final project plan got approval, the customer started requesting additional features to the product scope as the requirement details became clearer. Since the project approach is predictive, how would you handle this request? |  | Manage changes progressively | Amend the scope immediately | Reject the request | Ask the customer to wait for the next release | Answer option a. | Answer option a. The best course of action is to “Manage changes progressively” (option a.). In a predictive approach, scope changes are progressively managed. Answer option a. The best course of action is to “Manage changes progressively” (option a.). In a predictive approach, scope changes are progressively managed. If you decide to “Amend the scope immediately“ (answer option b.) or “Reject the request” (answer option c.) They are both premature decisions, as you did not assess the changes. “Ask the customer to wait for the next release “(answer option d.) The project approach is predictive, not agile. If you decide to “Amend the scope immediately“ (answer option b.) or “Reject the request” (answer option c.) They are both premature decisions, as you did not assess the changes. “Ask the customer to wait for the next release “(answer option d.) The project approach is predictive, not agile.
Exam 7 | #92. You have just visited the project site and come across a deliverable that does not meet the criteria specified in the documents. After a detailed review, it is finalized that this deliverable does not conform to the predetermined requirements mentioned in the requirements documentation. You have decided to write down a change request for the situation at hand. Which type of change request will you initiate? |  | Corrective Action | Preventive Action | Defect Repair | Updates | Answer option c. | Answer option c. “Defect repair” is an intentional activity to modify a nonconforming product or product component. Answer option c. “ Defect repair” is an intentional activity to modify a nonconforming product or product component.
Exam 7 | #93. During the performance review meeting, you and the project team discussed the deviations and proposed alternatives to resolve them. You asked the team to estimate the expected driven value from each alternative and the cost associated with it. Which Data analysis technique are you using? |  | Documents analysis | Cost-benefit analysis | Performance reviews | Trend analysis | Answer option b. | Answer option b. The technique you are using, in this case is “Cost-benefit analysis” (Answer option b.). Answer option b. The technique you are using, in this case is “ Cost-benefit analysis” (Answer option b.).
Exam 7 | #94. The project team is working on assuring that the workflow does not contain problems, constraints, or non-value-added activities. Which "manage quality process technique" can help? |  | Alternatives analysis | Document analysis | Process analysis | Root cause analysis | Answer option c. “ | Process analysis” identifies opportunities for process improvements. This analysis also examines problems, constraints, and non-value-added activities that occur during a process.
Exam 7 | #95. You are leading a new project team. As you want to exhibit the qualities and skills of a leader, you should manage the team conflicts by _____ . |  | Being optimistic and positive | Satisfying concerns | Seeking consensus | Both B and C | Answer option d. “ | Answer option d. The best answer is “Both B and C” (Answer option d.) Answer option d. The best answer is “Both B and C” (Answer option d.) “Being optimistic and positive” (Answer option a.) is indeed one of the Qualities and skills of a leader; however, it is not a way of resolving conflict. “Satisfying concerns” (Answer option b.) and “Seeking consensus” (Answer option c.) are both Qualities and skills of a leader and a way of resolving a conflict. “ Being optimistic and positive” (Answer option a.) is indeed one of the Qualities and skills of a leader ; however, it is not a way of resolving conflict. “ Satisfying concerns” (Answer option b.) and “Seeking consensus” (Answer option c.) are both Qualities and skills of a leader and a way of resolving a conflict.
Exam 7 | #96. Todd, a Predictive Project Manager took over the leadership of Betty’s Agile project while away on maternity leave. In her absence, Todd has asked for a detailed project schedule and the team developed a detailed task-level, resource loaded Gantt chart. What should be Betty’s next step? |  | Create schedule buffers and pad the schedule. | Continue tracking the project against the recently developed schedule. | Retain the schedule but drop the activity durations. | Reject the detailed schedule and explain his reasons to the sponsor. | Answer option d. | Agile projects are not plan driven and do not follow traditional project plans. This traditional approach needs to be rejected and discussed with the Predictive Project Manager.
Exam 7 | #97. During the planning meeting, the project manager asked the team to vote whether they are satisfied with the current version of the plan. To make a decision, more than half of the team must agree on a course of action. Which voting method is the project manager using? |  | Unanimity | Majority | Plurality | Fist to five | Answer option b. | Answer option b. “Majority” A decision is reached with support obtained from more than 50% of the members of the group. Answer option b. “ Majority” A decision is reached with support obtained from more than 50% of the members of the group.
Exam 7 | #98. Doug is hosting a brainstorming session with some of the key stakeholders. The main agenda item is to identify suitable project lifecycles for new initiatives on the company’s strategic roadmap. Some of the stakeholders are requesting exclusive use of Predictive and Agile approaches respectively for each project. What should be Doug’s response? |  | A blended life cycle needs to be designed which can then be exclusively used on all projects. | Exclusive use of a life cycle on all projects is not recommended, as there is no perfect approach for any project. | Exclusive use of Agile life cycle is recommended as this will allow the teams to move faster through each project. | Exclusive use of Predictive life cycle is recommended as this is a tried and tested method. | Answer option b. | No lifecycle can be perfect for all projects. Each project is unique and will need to be assessed for which approach would best suit it.
Exam 7 | #99. You have been experimenting with quality techniques and discovered that increasing the amount of money spent on the prevention of defects and quality control is related to the improvement in quality of the products. However, the value of the improvement in the quality reduces as spending on the prevention of defects and quality control increases. You are able to use a computer software model to check the point at which investing in additional prevention/appraisal costs is neither beneficial nor cost-effective in terms of quality. What is this point called? |  | Cost of quality | Cost of nonconformance | Optimal quality | Quality cost | Answer option c. | “Optimal quality”. Models show that there is an optimal quality cost for projects, where investing in additional prevention/appraisal costs is neither beneficial nor cost-effective.
Exam 7 | #100. The project sponsor asked you to prepare a presentation during the project closure process to determine if the expected outcomes from the economic feasibility study were used to justify the project. Which document should he review? |  | The project charter | The business case | The benefits management plan | All of the above | Answer option b. | Answer option b. “Business case” (Answer option b.) is used to determine if the expected outcomes from the economic feasibility study used to justify the project occurred Answer option b. “ Business case” (Answer option b.) is used to determine if the expected outcomes from the economic feasibility study used to justify the project occurred
Exam 7 | #101. Which person on the Agile team is responsible for organizing and managing the product backlog when using an Agile project management approach? |  | Project Manager | Product Owner | Development Team Lead | Scrum Master | Answer option b. | The Product Owner is responsible for organizing and managing the Product Backlog.
Exam 7 | #102. The project team needs to measure the completeness, compliance, and fitness for use of a product or service before the user acceptance and final delivery. Which process should they perform? |  | Manage Quality | Control Quality | Validate Scope | Control Quality | Answer option b. | “Control Quality” the process is performed to measure the completeness, compliance, and fitness for use of a product or service prior to user acceptance and final delivery.
Exam 7 | #103. You are considering the assistance of an expert to help you with managing the project work. What expertise would you look for? |  | Legislation and regulations | Project planning | Requirements analysis | Only A and B | Answer option a. | Answer option a. “Legislation and regulations” (Answer option a.) is the only mentioned expertise the process requires. Answer option a. “ Legislation and regulations” (Answer option a.) is the only mentioned expertise the process requires.
Exam 7 | #104. A project manager is looking into the quality assurance issues managed or escalated by the team, and recommendations for improvement. Which document should he review? |  | Quality control measurements | Quality reports | Requirements documentation | Requirement traceability matrix | Answer option b. | Answer option b. “Quality reports” (Answer option b.) include all quality assurance issues managed or escalated by the team, recommendations for improvement, and the summary of findings from the Control Quality process Answer option b. “ Quality reports” (Answer option b.) include all quality assurance issues managed or escalated by the team, recommendations for improvement, and the summary of findings from the Control Quality process
Exam 7 | #105. You are managing a software project with an agile approach. The team will develop the product scope over multiple iterations. When do you define and approve a detailed scope? |  | Once at the beginning of project | Once at the end of the project | At the beginning of each iteration | At the end of each iteration | Answer option c. “ | At the beginning of each iteration” in an Adaptive or agile life approach, the scope requires updates at the beginning of each iteration to respond to the high levels of change.
Exam 7 | #106. King of AI Company is specialized in AI-based solutions. Due to the limited number of available specialized resources, all company projects need to work on resources’ availability basis. Which scheduling method should the company project managers use? |  | Critical path method | On-demand scheduling | Critical chain method | Iterative scheduling with a backlog | Answer option b. | Answer option b. “On-demand scheduling” (Answer option b.) pulls work from a backlog or intermediate queue of work to be done immediately as resources become available. Answer option b. “ On-demand scheduling ” (Answer option b.) pulls work from a backlog or intermediate queue of work to be done immediately as resources become available.
Exam 7 | #107. A project manager is managing the project work. Which of the following enterprise environmental factors would he consider? |  | Organizational standard policies | Performance measurement database | Organizational culture | Change control and risk control procedures | Answer option c. | Answer option c. The best answer is “Organizational culture” (Answer option c.). Answer option c. The best answer is “Organizational culture” (Answer option c.). “Organizational standard policies” Answer option a.), “Performance measurement database”, (Answer option b.), and “Change control and risk control procedures” (Answer option d.) are all organizational process assets. “Organizational standard policies” Answer option a.), “Performance measurement database”, (Answer option b.), and “Change control and risk control procedures” (Answer option d.) are all organizational process assets.
Exam 7 | #108. A project deliverable passed the testing scenarios successfully, and you need to formalize this deliverable’s acceptance. What should the project manager do first? |  | Perform deliverable verification | Perform Control Quality process | Perform product reviews | Perform Control scope process | Answer option c. | Answer option c. The best course of action is to “Perform product reviews” (option c.) as the next step is to validate the deliverable to determine if it meets the requirements and product acceptance criteria. “Perform Control scope process“(answer option a.). This process is an altered step for the next activity/ process. “Perform deliverable verification” (answer option b.) or “Perform Control Quality process“(answer option d.), both are related to quality testing and quality auditing. Based on the situation, they are already completed. Answer option c. The best course of action is to “Perform product reviews” (option c.) as the next step is to validate the deliverable to determine if it meets the requirements and product acceptance criteria. “ Perform Control scope process“(answer option a.). This process is an altered step for the next activity/ process. “Perform deliverable verification” (answer option b.) or “Perform Control Quality process“(answer option d.), both are related to quality testing and quality auditing. Based on the situation, they are already completed.
Exam 7 | #109. A project manager encourages his team to innovate and empowers them to make proper decisions on their own. Which leadership style is he applying? |  | Laissez-faire | Transactional | Transformational | Charismatic | Answer option c. | Answer option c. Transformational leadership style empowers followers through idealized attributes and behaviors and encourages them for innovation “Transformational” (Answer option c.). Answer option c. Transformational leadership style empowers followers through idealized attributes and behaviors and encourages them for innovation “ Transformational” (Answer option c.).
Exam 7 | #110. If a project’s SPI=1.1, CPI =1.0, BAC=$200K, and EV =$25K; how is the project performing? |  | Under planned cost | On planned cost | Over planned cost | Cannot say | Answer option b. “ | On planned cost“ since CPI =1
Exam 7 | #111. The project team is collecting final suggestions for improving or updating the policies and procedures of the organization. At which stage does the project stand? |  | Planning | Execution | Monitoring and controlling | Closing | Answer option d. | Answer option d. “Closing” (Answer option d.). The mentioned activities are part of the close project process, which is one of the closing process group processes. Answer option d. “ Closing” (Answer option d.). The mentioned activities are part of the close project process, which is one of the closing process group processes.
Exam 7 | #112. An Agile project is running into problems because the team is not communicating well. Key members of the team are in different buildings around the city and get distracted by being asked to perform minor non-project tasks by other managers. Which of the following approaches should the project manager take? |  | Tell each team member to only communicate using video conferencing technology. | Tell other managers to stop giving the team other tasks. | Create a virtual team. | Co-locate the team if possible. | Answer option d. | Co-locate means to bring the team members to one location to work for better collaboration. In the past, this has also been referred to as a tight matrix organization and is typical of many Agile projects. Telling other managers to leave your folks alone was not the problem—distraction was. If the team is not co-located and they work remotely from each other, they already are a virtual team.
Exam 7 | #113. During the milestone review, the performance reports showed the following results; VAC=$8K, ETC=$80K, PV=$50K. How is the project performing? |  | Under planned cost | On planned cost | Over planned cost | Cannot say | Answer option a. | Since VAC is Positive then the project is “Under planned cost”
Exam 7 | #114. A project manager is identifying actions and activities necessary to transfer the project’s products. Which of the following activities should he consider? |  | Ensuring that all costs are charged to the project | Finalizing open claims | Updating records to reflect final results | Finalizing product support documents | Answer option d. | Answer option d. The best answer is “Finalizing product support documents” (Answer option d.) “Confirming the formal acceptance of the seller’s work” (Answer option a.) is an activity necessary to satisfy completion or exit criteria for the phase. “Finalizing open claims” (Answer option b.) and “Updating records to reflect final results” (Answer option c.) are all activities related to the completion of the contractual agreements. “Ensuring that all costs are charged to the project” (Answer option a.). Answer option d. The best answer is “Finalizing product support documents” (Answer option d. ) “ Confirming the formal acceptance of the seller’s work” (Answer option a.) is an activity necessary to satisfy completion or exit criteria for the phase. “Finalizing open claims” (Answer option b.) and “Updating records to reflect final results” (Answer option c.) are all activities related to the completion of the contractual agreements. “Ensuring that all costs are charged to the project” (Answer option a.).
Exam 7 | #115. Lina is working for the procurement department. Recently, her company has started working in a more dynamic, Agile environment. The projects are geared more towards embracing the new technology and she needs to start applying Agile principles in managing the procurements. In order to be more successful at her job, she needs to understand what the Agile Manifesto value “customer collaboration over contract negotiation” means. You explain that: |  | Agile approaches encourage you not to focus too much on negotiating contracts, since most vendors are just out for themselves anyway. | Agile approaches focus on what we are trying to build with our vendors, rather than debating the details of contract terms. | Agile approaches prefer not to use contracts, unless necessary, because they hamper our ability to respond to change requests. | Agile approaches recommend that you only collaborate with vendors who are using agile processes themselves. | Answer option b. | Valuing customer collaboration over contract negotiation means we look for mutual understanding and agreement, rather than spend our time debating the fine details of the agreement.
Exam 7 | #116. Which form of power is based on the ability to provide arguments that move people to a desired course of action? |  | Persuasive | Charismatic | Ingratiating | Relational | Answer option a. | Answer option a. Persuasive includes the ability to provide arguments that move people to the desired course of action “Persuasive” (Answer option a.) Answer option a. Persuasive includes the ability to provide arguments that move people to the desired course of action “ Persuasive” (Answer option a.)
Exam 7 | #117. You are classifying your project stakeholders according to directions of influence data representation technique. Under which way would you classify your company’s other Project managers? |  | Upward | Downward | Outward | Sideward | Answer option d. | Answer option d. Your company’s other Project managers are peers to you as a project manager accordingly they are considered “Sideward” (Answer option d.). Answer option d. Your company’s other Project managers are peers to you as a project manager accordingly they are considered “ Sideward” (Answer option d.).
Exam 7 | #118. William, an experienced Scrum Master, is facilitating a Daily Stand-up Meeting. Which of the following questions would he ask during the session? |  | What did I accomplish yesterday? | What will I work on today? | Are there any roadblocks preventing me from doing my work? | All of the above | Answer option d. | These questions are all to be asked during a Daily Stand-up meeting.
Exam 7 | #119. Project manager 1 accepts the status quo and asks “how and when” and focuses on near-term goals and the bottom line. Project manager 2 challenges the status quo and asks “what and why” and focuses on long-range vision and the horizon. This means that: |  | Project manager 1 is a better manager than project manager 2. | Project manager 1 is a leader, and project manager 2 is a manager. | Project Manager 1 is a manager, and Project Manager 2 is a leader. | Project manager 2 is a better manager than project manager 1. | Answer option c. | Answer option c. Project manager 1 is a manager, and project manager 2 is a leader. In some situations, a manager is better, and in others, a leader is better. But the two are not mutually exclusive. Managers are a blend of the two types. Answer option c. Project manager 1 is a manager, and project manager 2 is a leader. In some situations, a manager is better, and in others, a leader is better. But the two are not mutually exclusive. Managers are a blend of the two types .
Exam 7 | #120. A Scrum Team is a collection of individuals (typically between five and nine members) working together to deliver the required product increments. The Scrum framework encourages a high level of communication among team members so that the team can follow a common goal of delivering unique functionality during one Sprint. The scrum team includes the: Product Owner, Scrum Master, and Development team. These individuals share different tasks and responsibilities related to the delivery of the product. Who manages the Scrum Team? |  | The Team | The Scrum Master | The Product Owner | The Management | Answer option a. | It is not the Scrum Master’s job to manage the Team. The Team has to learn to manage itself, to constantly adjust its methods in order to optimize its chances of success.
Exam 7 | #121. During the risk review meeting, the project manager discusses with the team about the impact of multiple activities that are on convergence paths. How likely would they affect the overall project risk? |  | Decrease overall project risk | Increase overall project risk | No change | It depends on other factors | Answer option b. | Answer option b. “Increase overall project risk” (Answer option b.). Activities with divergence and convergence have greater risks as they are affected by multiple activities or can affect multiple activities. Answer option b. “ Increase overall project risk” (Answer option b.). Activities with divergence and convergence have greater risks as they are affected by multiple activities or can affect multiple activities.
Exam 7 | #122. Which conduct procurement input describes how to evaluate bidder proposals, including evaluation criteria and weights? |  | Independent cost estimates | Source selection criteria | Proposal evaluation | Seller proposals | Answer option b. | Answer option b. “Source selection criteria” describes how bidder proposals will be evaluated, including evaluation criteria and weights. Answer option b. “ Source selection criteria” describes how bidder proposals will be evaluated, including evaluation criteria and weights.
Exam 7 | #123. During a sprint review, a key stakeholder reveals that they will not be available to participate in the next sprint because they will be traveling and attending an international conference out of the country. After learning of the key stakeholder's absence during that time, what is the first thing the project manager should do? |  | In the next sprint planning session, only schedule tasks not related to the key stakeholder. | Request that the stakeholder cancel the conference and support development. | Consult with the sponsor and project team members on how to best replace the key stakeholder. | Update the issue log and inform the other impacted stakeholders. | Answer option d. | The first thing the PM needs to do is to capture the issue and then notify other stakeholders. Until then, no action can or should be taken.
Exam 7 | #124. It is a common knowledge in Agile approaches that the teams share different tasks and responsibilities related to the delivery of the product. The teams consist of individuals working together to deliver the required product increments. The Scrum framework encourages a high level of communication among team members, The Scrum team roles are interrelated. It is also recommended for Scrum team members to work together in the same location whenever possible. What are other considerations that need to be taken into account when describing a Scrum team: |  | Self-managing, Self-organizing, and Cross-functional | Self-directing, Self-organizing, and Cross-functional | Self-directing, Self-empowered, and Cross-functional | Self-monitoring, Self-managing, and Self-functioning | Answer option a. | Teams are self-managing, self-organizing, and cross-functional, and they are responsible for figuring out how to turn Product Backlog into an increment of functionality within an iteration and managing their own work to do so.
Exam 7 | #125. The ability to work with the project sponsor, team, and subject matter experts to develop an appropriate project delivery strategy is an example of _____ . |  | Technical project management | Leadership | Strategic and business management | Both A and C | Answer option c. | Answer option c. The ability to work with the project sponsor, team, and subject matter experts to develop an appropriate project delivery strategy is one of the skills of “Strategic and business management” (Answer option c.) Answer option c. The ability to work with the project sponsor, team, and subject matter experts to develop an appropriate project delivery strategy is one of the skills of “ Strategic and business management” (Answer option c.)
Exam 7 | #126. In the process of conducting the project procurements, _____ provides guidance on how sellers will manage and satisfy the requirements under contract. |  | Requirements management plan | Requirements documentation | Requirements traceability matrix | All of the above | Answer option a. | Answer option a. “Requirements management plan” may include how sellers will manage the requirements under contract. Answer option a. “Requirements management plan” may include how sellers will manage the requirements under contract.
Exam 7 | #127. A project manager is performing the monitor communications process. Of the following, which is not an enterprise environmental factor that can influence this process? |  | Established communication channels | Previous projects Stakeholder and communications data | Organizational culture | Geographic distribution of facilities and resources | Answer option b. | Answer option b. Since the question is asking which is not, the best answer is “Previous projects’ stakeholders and communications data” (Answer option b.). Answer option b. Since the question is asking which is not, the best answer is “Previous projects’ stakeholders and communications data” (Answer option b.). “Established communication channels” (Answer option a.), “Organizational culture” (Answer option c.), and “Geographic distribution of facilities and resources” (Answer option d.) are all enterprise environmental factors. “ Established communication channels” (Answer option a.), “Organizational culture” (Answer option c.), and “Geographic distribution of facilities and resources” (Answer option d.) are all enterprise environmental factors.
Exam 7 | #128. Bill’s company has been awarded a contract to implement a new Enterprise Resource Planning (ERP) system for a client in California. Senior Management has requested Bill to relocate the development team to the client’s location separate from the other project team members. What would be the BIGGEST challenge in Bill establishing virtual teams across different locations? |  | Efficient and effective communication | Documenting sprint retrospectives | Controlling project risk | Monitoring project progress | Answer option a. | According to Agile, face-to-face conversation promotes efficient and effective communication. When a project has a virtual team, the biggest challenge is ensuring the above.
Exam 7 | #129. Keith is managing a highly complex software project. Some team members have complained they have to work beyond normal working hours in order to complete some of the assigned project work. What should Keith do to resolve this issue with the team? |  | Call a Sprint Planning Session. | Establish working agreements. | Establish a Kanban board and set WIP limits. | Determine the root cause using Quality Management techniques. | Answer option c. | The root cause is no defined limit to work in progress (WIP). The best solution is to set WIP limits based on team capacity.
Exam 7 | #130. After reviewing the quality testing report, the project manager instructed the team to fix all the errors found by the testing team. What type of action did the project manager request? |  | Corrective action | Preventive action | Defect repair | All of the above | Answer option c. | Answer option c. It is a request for fixing nonconforming components. The best answer is “Defect repair” (Answer option c.). Answer option c. It is a request for fixing nonconforming components. The best answer is “ Defect repair” (Answer option c.).
Exam 7 | #131. You are considering the assistance of an expert to help you plan the schedule management. What expertise would you look for? |  | Monitoring and reporting tools | Organizational culture and structure | Schedule development, management, and control | All of the above | Answer option c. | Answer option c. “Schedule development, management, and control” (Answer option c.) is the only mentioned expertise the project manager requires. Answer option c. “ Schedule development, management, and control” (Answer option c.) is the only mentioned expertise the project manager requires.
Exam 7 | #132. _____ process determines if the planned communications artifacts and activities have had the desired effect of increasing or maintaining stakeholders’ support for the project’s deliverables and expected outcomes. |  | Manage communications | Monitor communications | Manage stakeholder engagement | Monitor stakeholder engagement | Answer option b. | Answer option b. “Monitor communications” process determines if the planned communications artifacts and activities have had the desired effect of increasing or maintaining stakeholders’ support for the project’s deliverables and expected outcomes Answer option b. “Monitor communications” process determines if the planned communications artifacts and activities have had the desired effect of increasing or maintaining stakeholders’ support for the project’s deliverables and expected outcomes
Exam 7 | #133. You are aiming to define the optimal information flow in the communications management plan and the stakeholder engagement plan. Which process can help you to achieve this? |  | Manage communications | Manage stakeholder engagement | Monitor stakeholder engagement | Monitor communications | Answer option d. | “Monitor communications” process determines if the planned communications artifacts and activities have had the desired effect of increasing or maintaining stakeholders’ support for the project’s deliverables and expected outcomes.
Exam 7 | #134. You are considering the assistance of an expert to help you with the “Collect Requirements“ process. What expertise would you look for? |  | Proposal evaluation | Expertise in estimating | Business analysis | Both A and B | Answer option c. | Answer option c. “Business analysis” (Answer option c.) collect requirements requires requirements related expertise business analysis is one of this expertise. Answer option c. “ Business analysis ” (Answer option c.) collect requirements requires requirements related expertise business analysis is one of this expertise.
Exam 7 | #135. A project manager is working with a globally distributed team. Which technique can help him to facilitate this situation? |  | Conflict management | Cultural awareness | Negotiation | Political awareness | Answer option b. | Answer option b. “Cultural awareness” (Answer option b.) is used to help the project manager and team to communicate effectively by considering cultural differences and the requirements of stakeholders. Answer option b. “ Cultural awareness ” (Answer option b.) is used to help the project manager and team to communicate effectively by considering cultural differences and the requirements of stakeholders.
Exam 7 | #136. While collecting requirements, the project team was voting on which requirements to include. To make a decision, all of the team must agree on a course of action. Which voting method are they using? |  | Unanimity | Majority | Fist to five | Both A and C | Answer option d. | Answer option d. “Unanimity “(answer option a.) A decision is reached whereby everyone agrees on a single course of action, and “Fist to five” (answer option c.) a decision is reached when the team achieves consensus. The best course of action is to “Both A and C” (option d.). Answer option d. “Unanimity “(answer option a.) A decision is reached whereby everyone agrees on a single course of action, and “ Fist to five” (answer option c.) a decision is reached when the team achieves consensus . The best course of action is to “ Both A and C” (option d.).
Exam 7 | #137. To measure the stability of the process’s performance, the project manager intends to represent the performance data in the form of a graphical chart. Which chart can achieve this? |  | Burn down charts | Bar charts | Control charts | Gantt charts | Answer option c. | Answer option c. “Control charts” use an upper limit and a lower limit to determine whether a process is stable or not. Answer option c. “ Control charts” use an upper limit and a lower limit to determine whether a process is stable or not.
Exam 7 | #138. The phrase terms of reference (TOR) is used when contracting for services. Similar to the _____ . |  | Purchase order | Memoranda of agreements (MOAs) | Procurement SOW | All of the above | Answer option c. | The phrase terms of reference (TOR) are sometimes used when contracting for services. Similar to the “Procurement SOW”.
Exam 7 | #139. Due to the massive number of project stakeholders and the frequent changes in stakeholders’ community, you are facing a complex issue with stakeholder management. Which of the following techniques can help you facilitate this situation? |  | Stakeholder analysis | Prioritization | Directions of influence | Document analysis | Answer option b. | Answer option b. “Prioritization” (Answer option b.) is necessary for projects with a large number of stakeholders, where the membership of the stakeholder community is changing frequently. Answer option b. “ Prioritization ” (Answer option b.) is necessary for projects with a large number of stakeholders, where the membership of the stakeholder community is changing frequently.
Exam 7 | #140. You are the Product Owner of a newly formed Scrum team. To help the team understand the difference between a Product Backlog (PBL) and a Sprint Backlog (SBL), you draft a chart and explains the difference in certain categories; on a detail level, the Sprint Backlog (SBL) is different from the Product Backlog (PBL) in the sense: |  | The Sprint Backlog is more detailed because it is focused on a single user story and decomposes into smaller tasks. | The Product Backlog is more detailed because it is built for the entire project and must contain information that addresses all project specifics. | The Sprint Backlog could be more detailed or less detailed depending on the project and the user story that is being worked on. | Both Logs (SBL-PBL) are high-level detailed because Scrum calls for less documentation and the developers are self-organized. | Answer option a. | Per Scrum framework, the Sprint Backlog (SBL) is more detailed as it contains information and tasks of the Backlog specific to a particular Sprint only. Sprint Backlog (SBL) is a subset of the Product Backlog (PBL), which is more high-level for the entire project.
Exam 7 | #141. Knowledge transfer for project continuity as well as ensuring the alignment of the project objectives and goals with those of the portfolio, program, and organizational business strategy, is a key role and responsibility of? |  | Project manager | Change Board | Project sponsor | Program manager | Answer option a. | Answer option a. “Project manager”. He/she is in charge of all of these aspects of the project. Look at the chapter “Role of the Project Manager” in the PMBOK. Answer option a. “ Project manager”. He/she is in charge of all of these aspects of the project. Look at the chapter “Role of the Project Manager” in the PMBOK.
Exam 7 | #142. You are the Product Owner of an Agile organization and a senior executive reaches out to you to understand how the Product Backlog items are arranged in the log? How should you answer her? |  | Product Backlog items should be arranged by business category and/or feature. | Product Backlog items should be sorted by level of complexity in descending order. | Product Backlog items should be sorted by business priority in descending order. | Product Backlog items should be date sorted in a descending order. | Answer option c. | In the Scrum framework, Product Backlog items should be sorted by business priority in descending order. The Product owner will determine the business priority and implement the strategy to progress towards project completion.
Exam 7 | #143. The project team needs to determine how to validate their requirements. Which input contains such details? |  | Requirements traceability matrix | Requirements documentation | Requirements management plan | Both A and C | Answer option d. | The best answer is “Both A and C” (Answer option d.). “Requirements traceability matrix” contains requirements that are compared to the actual results to determine if a change, corrective action or preventive action is necessary, and “Requirements management plan” describes how the project requirements are validated.
Exam 7 | #144. The project team is aiming to increase the probability of meeting the quality objectives as well as identifying ineffective processes and causes of poor quality. Which process should they perform? |  | Manage Quality | Control Quality | Validate scope | Control scope | Answer option a. | Answer option a. “Manage Quality”. The key benefits of this process are that it increases the probability of meeting the quality objectives as well as identifying ineffective processes and causes of poor quality. Answer option a. “ Manage Quality”. The key benefits of this process are that it increases the probability of meeting the quality objectives as well as identifying ineffective processes and causes of poor quality.
Exam 7 | #145. A project team is set to work together remotely. The team will use a company portal to share the project knowledge. Which communication method will the team use? |  | Interactive communication | Networks and social computing communication | Push communication | Pull communication | Answer option d. | Answer option d. “Pull”. It is used for large complex information sets, or for large audiences, and requires the recipients to access the content at their own discretion subject to security procedures Web portals and other information repositories are an example of pull communication. Answer option d. “Pull”. It is used for large complex information sets, or for large audiences, and requires the recipients to access the content at their own discretion subject to security procedures Web portals and other information repositories are an example of pull communication.
Exam 7 | #146. David is a project manager assigned to an IT system upgrade project in a pharmaceutical company. The project sponsor requested him to assess the possibility of fast-tracking the remaining activities. The analysis showed that a group of activities is depending on the completion of a single activity. This is an example of _____ . |  | Path Divergence | Path Convergence | Mandatory dependencies | Discretionary dependencies | Answer option a. | Answer option a. “Path Divergence “(answer option a.) It is a relationship where scheduled activity has more than one successor. Answer option a. “ Path Divergence “(answer option a.) It is a relationship where scheduled activity has more than one successor.
Exam 7 | #147. A project manager is assigned to a running construction project. In his first meeting with the team, most of the members showed thoughtless behavior towards him and each other. Moreover, they tend to criticize each other's opinions carelessly. At which stage does this team stand? |  | Forming | Storming | Norming | Adjourning | Answer option b. | The team is in the “storming” stage. During this phase, the team begins to address the project work, technical decisions, and the project management approach. If team members are not collaborative or open to differing ideas and perspectives, the environment can become counterproductive.
Exam 7 | #148. During the presentation of project performance reports, the quality team used a diagram that breaks down the causes of the problem statement into discrete branches, identifying the main or root cause of the problem. Which type of diagram did they use? |  | Affinity diagram | Context diagram | Matrix diagram | Why – why diagram | Answer option d. | Answer option d. “Why-why diagrams”are also known as Cause-and-effect diagrams that break down the causes of the problem statement into discrete branches, helping to identify the main or root cause of the problem. Answer option d. “Why-why diagrams”are also known as Cause-and-effect diagrams that break down the causes of the problem statement into discrete branches, helping to identify the main or root cause of the problem.
Exam 7 | #149. The internal sponsor is happy with the work completed so far on the project and informs you that there will be a new project in the very near future that they would like to be done by the same project team. You are the project manager on the project. What should you do to exploit this opportunity? |  | Hold regular meetings with the sponsor | Involve the legal department of your company and sign a contract with the internal sponsor | Exploit this opportunity | Obtain confirmation from the sponsor about the other project being awarded to your project team in the near future | Answer option c. | Exploit means doing everything to ensure that the event happens. In this risk response strategy, you make sure you realize the opportunity, take the opportunity seriously and develop a strategy to realize it.
Exam 7 | #150. Company XYZ is deploying automation software that will replace the IT support team to help the company achieve efficiency, and at the same time relocate the impacted staff to other jobs. Some staff members are unwilling to participate in the process mapping due to their misinterpretation of the project objectives. Under which category would you classify them? |  | Unaware | Resistant | Neutral | Both A and B | Answer option b. | Answer option b. “Resistant” since the team is not supportive they are considered resistant. Answer option b. “Resistant” since the team is not supportive they are considered resistant.
Exam 7 | #151. During the implementation of an internal project, the project team had to update the activity list periodically as the project progressed. The reason behind this is to reveal more details about the project scope over time. This is an example of _____ . |  | Poor change control process | Rolling wave planning | Scope creep | Gold plating | Answer option b. | Answer option b. “Rolling wave planning” is an iterative planning technique in which the work to be accomplished in the near term is planned in detail, while work further in the future is planned at a higher level. Answer option b. “ Rolling wave planning” is an iterative planning technique in which the work to be accomplished in the near term is planned in detail, while work further in the future is planned at a higher level.
Exam 7 | #152. A project manager is managing the project work. Which of the following enterprise environmental factors would he consider? |  | Organizational standard policies | Industry standards | Financial controls procedures | Monitoring and reporting methods | Answer option b. | Answer option b. The best answer is “Industry standards” (Answer option b.) as it is the only enterprise environmental factor. “Organizational standard policies” (Answer option a.), “Financial controls procedures” (Answer option c.), and “Monitoring and reporting methods” (Answer option d.) are all organizational process assets, not enterprise environmental factors. Answer option b. The best answer is “ Industry standards” (Answer option b.) as it is the only enterprise environmental factor. “ Organizational standard policies” (Answer option a.), “ Financial controls procedures” (Answer option c.), and “ Monitoring and reporting methods” (Answer option d.) are all organizational process assets, not enterprise environmental factors.
Exam 7 | #153. You are considering seeking the assistance of an expert to help you with the close project process. What expertise would you look for? |  | Audit | Risk analysis techniques | Proposal evaluation | All of the above | Answer option a. | Answer option a. The best answer is “Audit” (Answer option a.) Answer option a. The best answer is “Audit” (Answer option a.) “Risk analysis techniques” (Answer option b.) and “Proposal evaluation” (Answer option c.) are both planning techniques. “ Risk analysis techniques” (Answer option b.) and “Proposal evaluation” (Answer option c.) are both planning techniques.
Exam 7 | #154. Scrum Master Cathy is about to head into a meeting at the end of an agile project with the developers and the Product Owner. In this meeting, the team will discuss what they learned in the last Sprint and work to adapt and improve their processes. This meeting is called: |  | Daily Stand-up | Sprint Planning | Sprint Review | Sprint Retrospective | Answer option d. | The Sprint Retrospective is designed to help the team reflect on becoming more effective and then adjust their behaviors accordingly.
Exam 7 | #155. While planning the risk responses, the project team came to a list of low-priority threats. Which risk strategy should they use? |  | Avoid | Transfer | Mitigation | Accept | Answer option d. | Answer option d. “Accept” Risk acceptance acknowledges the existence of a threat, but no proactive action is taken, it is appropriate for low-priority threats. Answer option d. “ Accept” Risk acceptance acknowledges the existence of a threat, but no proactive action is taken, it is appropriate for low-priority threats.
Exam 7 | #156. Although the project team members have a close engagement with all the key actors in the project, some of them have difficulty understanding stakeholder concerns. You have provided al general training in this regard, but obviously, they are lacking other skills. You decide to organize another training as soon as possible. Which training should it be? |  | Emotional intelligence skills | Active listening skills | Stakeholder engagement skills | Social skills | Answer option b. | “Active listening skills” are the most relevant in this context.
Exam 7 | #157. Gerry is transitioning from traditional to Agile projects. He is trying to compare these two methodologies and wants to learn as much as possible about dynamic project management. In particular, he is interested in learning Scrum. What of the following is required to be used in Scrum? |  | User Stories | Features | Use Cases | None of the above is required | Answer option d. | User Stories, Features, Use Cases can be successfully used in Scrum, but they are not required. This question refers to the best practices and core of Scrum that can be found in the Scrum Guide.
Exam 7 | #158. The project team is collecting requirements for a new product development project by comparing the requirements of previous successful products. Which technique are they using? |  | Data analysis | Affinity diagrams | Facilitation | Benchmarking | Answer option d. “ | Benchmarking” involves comparing actual or planned products, processes, and practices to those of comparable organizations to identify best practices, generate ideas for improvement, and provide a basis for measuring performance.
Exam 7 | #159. Time-boxing is a time-management technique that helps organize the performance of work and manage scope. Which of the following is NOT a characteristic of a sprint? |  | Force Prioritization by performing an amount of work that matters most. | Demonstrate relevant progress by completing and validating essential pieces of work by the end of the sprint. | Unlike Kanban, it has no limits for the amount of WIP (work in process). | Each sprint takes place in a time frame with specific start and end dates. | Answer option c. | The team plans to work on only those items that they believe can start and finish within the sprint; timeboxing establishes a WIP limit for each sprint.
Exam 7 | #160. A project manager is monitoring stakeholder engagement. Which of the following enterprise environmental factors would he consider? |  | Organizational culture | Local trends and practices | Stakeholder risk thresholds | All of the above | Answer option d. | Answer option d. “Organizational culture “(answer option a.), “Local trends and practices” (answer option b.), “Stakeholder risk thresholds “(answer option c.) are all enterprise environmental factors that influence this process. The best answer is “All of the above” (option d.). Answer option d. “ Organizational culture “(answer option a.), “Local trends and practices” (answer option b.), “Stakeholder risk thresholds “(answer option c.) are all enterprise environmental factors that influence this process. The best answer is “All of the above” (option d.).
Exam 7 | #161. A project manager has the ability to identify the project’s critical success factors, to make time to plan thoroughly, and prioritize diligently. These skills are an example of _____ . |  | Technical project management | Leadership | Strategic and business management | Both A and C | Answer option a. | Answer option a. Critical success factors for the project and make time to plan thoroughly and prioritize diligently are “Technical project management” skills. (Answer option a.) Answer option a. Critical success factors for the project and make time to plan thoroughly and prioritize diligently are “ Technical project management” skills. (Answer option a.)
Exam 7 | #162. While performing the control cost process, which data analysis technique examines the project performance over time to determine if the performance is improving or deteriorating? |  | Earned value analysis | Variance analysis | Trend analysis | Forecasting | Answer option c. “ | Answer option c. “Trend analysis” examines project performance over time to determine if performance is improving or deteriorating Answer option c. “ Trend analysis ” examines project performance over time to determine if performance is improving or deteriorating
Exam 7 | #163. Scrum Master Zack is about to head into a meeting at the end of an agile project with the developers, stakeholders, and the Product Owner. In this meeting, the Developers will demonstrate the increment they most recently completed and obtain feedback from both the stakeholders and the Product Owner. This meeting is called: |  | Daily Stand-up | Sprint Planning | Sprint Review | Sprint Retrospective | Answer option c. | The Sprint Review is the meeting in which the Developers demo the deliverable. In this meeting, the Product Owner will accept or reject the work and provide feedback to assist in future increments.
Exam 7 | #164. A project manager is managing the project work. Which of the following organizational process assets can influence the process? |  | Organizational culture | Change control and risk control procedures | Stakeholder risk thresholds | All of the above | Answer option b. | Answer option b. The best answer is “Change control and risk control procedures” (Answer option b.) “Organizational culture” (Answer option a.) and “Stakeholder risk thresholds” (Answer option c.) are both enterprise environmental factors, not organizational process assets. Answer option b. The best answer is “ Change control and risk control procedures” (Answer option b.) “ Organizational culture” (Answer option a.) and “ Stakeholder risk thresholds” (Answer option c.) are both enterprise environmental factors, not organizational process assets.
Exam 7 | #165. After the 1st release of formal sign-off, the customer reported a fatal functionality issue with the software. What type of costs would the project endure? |  | Prevention Costs | Appraisal Costs | Internal Failure Costs | External Failure Costs | Answer option d. | “External Failure Costs” include all failures found by the customer.
Exam 7 | #166. While performing plan communication management, the project team needs to understand how to engage stakeholders through appropriate communication strategies. Which input contains these details? |  | Communications management plan | Stakeholder register | Stakeholder engagement plan | All of the above | Answer option c. “ | Stakeholder engagement plan” describes how stakeholders will be engaged through appropriate communication strategies.
Exam 7 | #167. The project team classified the stakeholders by using a three-dimensional model that helped in identifying and engaging the stakeholder community. Which data representation technique did the project team use? |  | Power/interest grid | Impact/influence grid | Stakeholder cube | Salience model | Answer option c. | Answer option c. The statement describes, “Stakeholder cube” (Answer option c.). This is a refinement of the grid models previously mentioned. This model combines the grid elements into a three-dimensional model that can be useful to project managers and teams in identifying and engaging their stakeholder community. Salience model is a Venn diagram comprising three attributes: power, legitimacy and urgency. Answer option c. The statement describes, “ Stakeholder cube” (Answer option c.). This is a refinement of the grid models previously mentioned. This model combines the grid elements into a three-dimensional model that can be useful to project managers and teams in identifying and engaging their stakeholder community. Salience model is a Venn diagram comprising three attributes: power, legitimacy and urgency.
Exam 7 | #168. During the implementation, the project manager found that the team members are not working well together due to the fact that they are working remotely. Accordingly, he scheduled a monthly face-to-face meeting for all members at the company’s headquarters. This action is an example of _____ . |  | Colocation | Virtual teams | Meeting management | All of the above | Answer option a. | “Colocation” involves placing many or all of the most active project team members in the same physical location to enhance their ability to perform as a team. It includes face-to-face team meetings as well.
Exam 7 | #169. A project manager shows his leadership skills, charismatic charm, and business management skills to orchestrate his project work effectively. Which project integration level is he working on? |  | Process level | Cognitive level | Context level | All of the above | Answer option b. | Answer option b. “Cognitive level” (Answer option b.) involves the project managers applying their experience, insight, leadership, and technical and business management skills to the project. Answer option b. “ Cognitive level” (Answer option b.) involves the project managers applying their experience, insight, leadership, and technical and business management skills to the project.
Exam 7 | #170. You have been assigned to gather the required information from a large number of stakeholders in a short amount of time. The stakeholders are in different geographical locations and you plan to statistically work on the collected information. Which technique would be the most suitable in this situation? |  | Benchmarking | Interviews | Questionnaires and Surveys | Focus Groups | Answer option c. “ | Questionnaires and surveys” are written sets of questions designed to quickly accumulate information from a large number of respondents. Questionnaires and/or surveys are most appropriate with varied audiences.
Exam 7 | #171. Brian is an Agile coach helping a software development company LoDev transition from traditional to Agile approaches. He informs the teams within company that the single most important attribute of any product or feature is: |  | The schedule to deliver the product or feature to the customer. | The value customers associate with that product or feature. | The team velocity to execute the development of that product or feature. | The ideal duration estimated to develop the minimum viable product. | Answer option b. | Agile focuses on the value the product or features delivers to the customer. Project success depends heavily on this metric, as customers are less concerned with how the product or feature is developed or delivered.
Exam 7 | #172. While validating the scope, the team asks to receive all quality assurance issues managed or escalated by the team in order to review these issues before product acceptance. Which input contains such details? |  | Testing and evaluation | Issue log | Quality reports | Quality measurements | Answer option c. | Answer option c. “Quality reports” may include all quality assurance issues managed or escalated by the team, recommendations for improvement, and the summary of findings from the Control Quality process. This information is reviewed prior to product acceptance. Answer option c. “Quality reports” may include all quality assurance issues managed or escalated by the team, recommendations for improvement, and the summary of findings from the Control Quality process. This information is reviewed prior to product acceptance.
Exam 7 | #173. Your current release plan has raised some concerns among key stakeholders. They are worried that you will not be able to deliver the expected business value, while also meeting agreed-upon milestones. What is the best approach to make sure the key stakeholders' concerns are addressed? |  | Review the release plan and consult with the sponsor to eliminate the most time-consuming components. | Augment your team with external resources to immediately increase velocity for the next iterations. | Collaborate with the stakeholders and the team to identify and prioritize the Minimum Viable Products (MVP) needed. | Follow change management to modify the schedule baseline and include the iterations necessary to provide the critical business value. | Answer option c. | Identifying the minimum viable product allows the team to define and prioritize the must-have items that will satisfy the stakeholders’ urgent business needs, as well as to be able to deliver them within expected timelines.
Exam 7 | #174. You are working as a Project Manager in China with Qurex Inc. on a project that has 5 key deliverables. 4 out of 5 deliverables have been completed and completion of the last deliverable is due next month according to the plan. A state-wide lockdown has been imposed due to the COVID-19 pandemic. As a result, your team will not be able to deliver the last deliverable on time. Now you have to write to the PMO stating the cause of the delay. This delay is due to: |  | Enterprise Environmental Factors | Natural disasters | Organizational process assets | COVID-19 | Answer option a. “ | Enterprise environmental factors” (EEFs) refer to factors and conditions, not under the control of the project team, that inﬂuence, constrain, or direct the project.
Exam 7 | #175. The Project XYZ team is working on the risk management processes. To make project decisions based on the current information about overall project risk exposure, which process should they perform? |  | Identify Risks | Monitor Risks | Implement Risk Responses | Plan Risk Responses | Answer option b. | “Monitor risks”. The key benefit of this process is that it enables project decisions to be based on current information about overall project risk exposure and individual project risks.
Exam 7 | #176. While managing communications, the project manager used the document, which is shared with those who can take corrective actions to achieve the project quality expectations. Which of the following project documents did the project manager use? |  | Issue log | Quality report | Risk report | Change log | Answer option b. | Answer option b. “Quality report” (Answer option b.) Information in the quality report includes quality issues, project and product improvements, and process improvements. This information is forwarded to those who can take corrective actions in order to achieve the project quality expectations. Answer option b. “ Quality report” (Answer option b.) Information in the quality report includes quality issues, project and product improvements, and process improvements. This information is forwarded to those who can take corrective actions in order to achieve the project quality expectations.
Exam 7 | #177. _____ is appropriate selection for standard or routine procurements where well-established practices and standards exist. |  | Least cost | Qualifications only | Quality and cost-based | Fixed budget | Answer option a. | Answer option a. “Least cost” method may be appropriate for standard or routine procurements where well-established practices and standards exist. Answer option a. “ Least cost” method may be appropriate for standard or routine procurements where well-established practices and standards exist .
Exam 7 | #178. _____ provides sellers with a clearly stated set of goals, requirements, and outcomes so they can provide a quantifiable response. |  | RFQ | RFP | RFI | Procurement SOW | Answer option d. | “Procurement SOW” provides sellers with a clearly stated set of goals, requirements, and outcomes so they can provide a quantifiable response.
Exam 7 | #179. During the project review meeting, the project manager asked the team to decide on adding more resources to testing activities using the fist of five technique. How can a team member show that he needs more details? |  | Hold a closed fist | Show full hand | Show 3 fingers | Show 2 fingers | Answer option d. | Answer option d. “Show 2 fingers” is the first of five techniques. If a team member holds up fewer than three fingers, the team member is given the opportunity to discuss any objections with the team. Answer option d. “ Show 2 fingers” is the first of five techniques. If a team member holds up fewer than three fingers, the team member is given the opportunity to discuss any objections with the team.
Exam 7 | #180. Scrum Master Marcus is about to head into a meeting with the Developers and the Product Owner. In this meeting, the Product Owner will explain the features on the Product Backlog and answer any questions the Developers may have. The Developers will then estimate the effort for each of the Product Backlog stories that have been selected for the current Sprint. This meeting is called: |  | Daily Stand-up | Sprint Planning | Sprint Review | Sprint Retrospective | Answer option b. | The Sprint Planning Meeting is the meeting in which the Developers estimate the work required to complete the items identified for the next iteration.

## exam8
Exam Name | Question | quesimgsrc | Answer1 | Answer2 | Answer3 | Answer4 | Correct-Answer | Explanation | answerimgsrc
Exam 8 | #1. Rusty, as the Scrum Master, is chairing the Sprint Planning Session that includes four developers. They are playing planning poker and estimating story points on one of the backlog items that have been brought into the current Sprint. When the Fibonacci Sequence cards are revealed, the Developers have the following cards showing: ?, ?, ?, and 100. As each User Story is discussed, similar cards continue to be revealed. Mark’s next step may include all of the following EXCEPT: |  | To encourage the Developer who estimated 100 to explain to the group the reasoning for the estimates. | To encourage the Developers to ask questions of the Product Owner to obtain more detail about the User Story. | To remove the “?” card from the Fibonacci decks. | To encourage one of the Developers who estimated “?” to explain to the group the reasoning for the estimate. | Answer option c. | The “?” card is a helpful tool in that it shows that there is not sufficient information to estimate the work required to complete the objective of the User Story.
Exam 8 | #2. While you are conducting project procurement, what would be the most common data analysis technique you use to select the right sellers? |  | Alternative analysis | Cost-benefit analysis | Proposal evaluation | Benchmarking | Answer option c. | While conducting procurement multiple data analysis techniques might be used but the most common is “Proposal evaluation” (Answer option c.)
Exam 8 | #3. A project manager is working in a weak matrix organization where he has no direct authority over team members. Which interpersonal and team skills should the project manager use? |  | Motivating | Emotional intelligence | Influencing | Leadership | Answer option c. | Answer option c. “Influencing”. An influencing skill used in this process is gathering relevant and critical information to address important issues and reach agreements while maintaining mutual trust. Answer option c. “Influencing”. An influencing skill used in this process is gathering relevant and critical information to address important issues and reach agreements while maintaining mutual trust.
Exam 8 | #4. You are working for a telecommunication vendor and your company is doing projects with telecom operators in the region. Your company started to work with Operator ABC as one of the three possible vendors for a prospective project. However, you are a former employee of the ABC telecom operator and you have information regarding how Operator ABC evaluates vendors before awarding a contract. You understand that this could be a potential conflict of interest situation. Which of the following options is the best course of action? |  | Do nothing and continue to work . | Contact with an appropriate person in Operator ABC. | Disclose the evaluation criteria to your organization and help their business growth. | Remove yourself from the project. | Answer option b. | Answer option b. Answer B is the correct answer. Since the evaluation criteria are the proprietary information of Operator ABC, it is important for you to discuss the matter directly with the appropriate person in the Operator ABC. Answer option b. Answer B is the correct answer. Since the evaluation criteria are the proprietary information of Operator ABC, it is important for you to discuss the matter directly with the appropriate person in the Operator ABC .
Exam 8 | #5. During the project review, the following performance data were revealed, VAC=0 and AC=$200K. What is the EV? |  | $200K | $250K | $190K | Cannot say | Answer option a. | “200” VAC is zero which means there’s no performance variance thus EV=AC= 200k
Exam 8 | #6. A description of how a project management team should implement the overall intention and direction of an organization with regard to quality (as articulated by top management) is available in: |  | Operational definitions | Quality management plan | Checklists | Quality policy | Answer option b. | The quality management plan describes how the project management team will implement the performing organization`s quality policy.
Exam 8 | #7. Matthew has been assigned as Project Manager to a new enterprise technology project. This project resulted from the new corporate strategy Company ABC has adopted, but the company is unsure how the new technology would work after the rollout and in standard operations. What should he do? |  | Develop a product backlog. | Determine the conditions of satisfaction. | Create a proof of value (POV) or proof of concept (POC). | Identify the Scope Baseline. | Answer option c. | A proof of value or proof of concept will allow the company to explore the desired results and obtain feedback from the customers that will use the technology.
Exam 8 | #8. While performing the close phase process, the project manager needed to review the project success criteria. Which document does contain these details? |  | Project charter | Scope baseline | Project management plan | Project documents | Answer option a. | Answer option a. “Project charter” (Answer option a.) documents the project success criteria and the approval requirements. Answer option a. “ Project charter” (Answer option a.) documents the project success criteria and the approval requirements.
Exam 8 | #9. During the project review meeting, the project team compared and analyzed the planned resource utilization to the actual resource utilization. Which data analysis technique are they using? |  | Documents analysis | Cost-benefit analysis | Performance reviews | Trend analysis | Answer option c. | “Performance reviews” measure, compare, and analyze the quality metrics defined by the Plan Quality Management process against the actual results.
Exam 8 | #10. You are promoted to a new role in your company to replace someone who recently retired. To be an effective leader, which of the following should you do FIRST? |  | Enroll in appropriate training programs | Understand all the leadership theories | Find out your strong and weak areas | Take advice from the person who retired from the company | Answer option c. | Answer option c. Finding out your strong and weak areas helps determine how you can do the job better and become an effective leader. This may also result in identifying the needed training programs. Therefore, option A (enroll in appropriate training programs) and option B (learning all leadership theories) are not recommended. Option D (Taking advice from the person who retired from the company) is recommended, but this can be done after determining your strong and weak areas. Answer option c. Finding out your strong and weak areas helps determine how you can do the job better and become an effective leader. This may also result in identifying the needed training programs. Therefore, option A (enroll in appropriate training programs) and option B (learning all leadership theories) are not recommended. Option D (Taking advice from the person who retired from the company) is recommended, but this can be done after determining your strong and weak areas .
Exam 8 | #11. You have asked a project team member to list the activities that result in the cost of non-conformance to quality in your project. The list he submits is inaccurate because one of the following four options is a cost of conformance. Which of the following did your project team member list incorrectly? |  | Rework | Scrap | Quality Training | Warranty costs | Answer option c. | Answer option c. Quality Training: Through the process of elimination, Answers a. Rework, b. Scrap, and d. Warranty costs can be eliminated as associated with Cost of non-conformance. Quality Training leads to quality products and services and would be considered a Cost of Conformance. Answer option c. Quality Training: Through the process of elimination, Answers a. Rework, b. Scrap, and d. Warranty costs can be eliminated as associated with Cost of non-conformance. Quality Training leads to quality products and services and would be considered a Cost of Conformance .
Exam 8 | #12. A project manager has been hired to work on a new project. The organization is trying to implement some Agile practices but is not ready to abandon the plan-driven approaches that have mostly worked well in the past. After becoming familiar with the organization, its culture, history, and established practices, what should the project manager do next? |  | Assemble all available information from stakeholders and pre-project documentation and develop the project charter. Next, plan the project in a way that each phase can deliver value incrementally. | Understand stakeholders' risk tolerance when it comes to this new Agile initiative and design an engagement strategy to minimize any negative impacts that could come from resistant stakeholders. | Examine pre-project documentation, interview key stakeholders, assess the capabilities of team members and other resources, and review key requirements and deliverables. | Develop the project management plan iteratively, allowing the team to pivot quickly if requirements change, while providing a plan solid enough to implement it using the predictive approach. | Answer option c. | Any number of combinations between Agile and plan-driven approaches could work, but before deciding, the PM needs a thorough understanding of the existing organization and its culture, available skills, the specific details of the project, and its known requirements and deliverables, as well as the attitudes and risk tolerances of key stakeholders.
Exam 8 | #13. Jack is subdividing the project deliverables and project work into smaller and more manageable components. Which process is he performing? |  | Plan Scope Management | Collect Requirements | Define Scope | Create WBS | Answer option d. | Answer option d. “Create WBS”. Create Work Breakdown Structure (WBS) is the process of subdividing project deliverables and project work into smaller, more manageable components. Answer option d. “Create WBS”. Create Work Breakdown Structure (WBS) is the process of subdividing project deliverables and project work into smaller, more manageable components.
Exam 8 | #14. You are working in the Project Office of your organization. What is your role most likely to be? |  | Managing the different activities of a project | Always being responsible for the results of the project | Providing support functions to Project Managers in the form of training, software, templates, etc. | Providing subject matter expertise in the functional areas of the project | Answer option c. “ | Providing support functions to Project Managers in the form of training, software, templates, etc.”. Supportive PMOs “provide a consultative role by supplying the templates, best practices, training, access to information, and lessons learned from other projects.” Answer a., working in the PMO implies you are supporting Project Managers tasked with b., Project Managers responsible for the results of the project. Answer d., the key deal-breaker for the Answer is ‘functional aspects’ of the project, functional implies the technical detail of the product of the project. If the word was operational, it would align more with how the project could / should be run in concert with the rest of the projects performed within the company.
Exam 8 | #15. What is the role of a PMO in an Agile environment? |  | Develop Agile standards for all projects and assure compliance. Coach team members and ensure communications. | Act as a sort of Agile center of excellence, developing standards, resources, and skills, as well as managing stakeholders. | Leverage historical institutional knowledge and tailor existing waterfall practices to be effective in the new Agile environment. | Increase efficiency in value delivery by developing uniformity of processes and standards and managing compliance. | Answer option b. | The Agile PMO exists to guide business value through the organization, helping the project achieve its goals; facilitating communication, collaboration, and employee engagement; developing standards; coaching personnel; facilitating learning; and more.
Exam 8 | #16. You are in the process of creating customized reports for project stakeholders where you explain project compliance categories and analyze the consequences of noncompliance. You are reviewing various plans and project documents but find that some important aspects are missing. What could it be? |  | Project analysis report | The schedule baseline | The scope baseline | Work performance reports | Answer option d. | Answer option d. “Work performance reports”. The work performance report is tailored based on the communications needs of the stakeholders. The work performance reports are disseminated in the Merge Communications process. Answer option d. “ Work performance reports”. The work performance report is tailored based on the communications needs of the stakeholders. The work performance reports are disseminated in the Merge Communications process.
Exam 8 | #17. After performing quality control using checklists, the completed checklists should become part of the: |  | Organizational process assets updates | Project document updates | Project management plan updates | Lessons learned documentation | Answer option a. | When checklists are used, the completed checklists become part of the organizational process assets updates.
Exam 8 | #18. Your Agile project has been working well, until you discover at one of the demonstrations that some stakeholders are having concerns with the way a feature has been developed. What is the best way to deal with this situation? |  | Meet with the stakeholders privately and understand why they are objecting. | Depending on who these stakeholders are, you may be able to postpone addressing their objection to prevent disrupting the smooth flow of the iteration. | Ask your team to work together to identify a more suitable approach based on the feedback from these stakeholders. | Suggest that the sponsor get involved to ensure the issue is addressed and a win-win resolution is achieved. | Answer option a. | This is a situation that could escalate if the project manager does not address it promptly and properly. To address conflict, the project manager must have all the facts and help all the parties reach a satisfactory resolution in a collaborative way. Meeting in private directly with those who raise an objection is a productive way to obtain clear information.
Exam 8 | #19. You are on a business trip abroad to meet with a potential vendor. During the meetings, the vendor pays for your lunches and also plans a city tour during the weekend as this is common in their country. You must: |  | Accept the lunch payments but refuse the city tour politely since it is unethical. | Refuse both lunch payments and city tour, because accepting them could be understood as a personal gain. | Accept the payments and city tour as it is a local custom and promptly inform your manager. | Refuse both lunch payments and city tour, and warn the customer that this attitude might blacklist their company from the bidding process. | Answer option c. | Answer option c. A project manager has the responsibility to refrain from offering or accepting inappropriate payments, gifts, or other forms of compensation for personal gain, unless it is in agreement with applicable laws or customs of the country where the project management services are being provided. Answer option c. A project manager has the responsibility to refrain from offering or accepting inappropriate payments, gifts, or other forms of compensation for personal gain, unless it is in agreement with applicable laws or customs of the country where the project management services are being provided .
Exam 8 | #20. Existing formal and informal scope, control-related policies and monitoring and reporting methods and templates to be used are examples of _____ . |  | Considerations for tailoring project scope processes | Organizational process assets | Enterprise environmental factors | Emerging trends for project scope processes | Answer option b. | Answer option b. “Organizational process assets” Answer option b. “Organizational process assets”
Exam 8 | #21. Victor was brought into a Scrum team to assist in the project. This Scrum team has experienced conflict, poor quality and is unable to complete everything on the Sprint backlog in each Sprint. Which of the following is a potential reason for the project being problematic? |  | The Scrum Master coaches the Developers in self-organization and cross-functionality. | The Product Owner prioritizes the Product Backlog to maximize value to the business. | The Product Owner provides direction of the technical aspects of the work and adherence to engineering practices. | Each member of the Development Team has the title of Developer and does not divide into sub-teams. | Answer option c. | The Product Owner is responsible for “what” and the Development Team is responsible for “how.” The Scrum Master is responsible for ensuring engineering practices are followed.
Exam 8 | #22. Sam is planning a new product development project. Due to the nature of the project, the project scope might not be fully clear in the early stages. Which considerations for tailoring should he focus on? |  | Knowledge and requirements management | Validation and control | Development approach | Governance | Answer option c. | The nature of the project is a concern of “Development approach”. The method used to create and evolve the product, service, or result during the project life cycle, such as predictive, iterative, incremental, agile, or a hybrid method.
Exam 8 | #23. You are the Product Owner in an Agile organization and your Product Backlog is jeopardized by a level of complexity that your current junior team is not able to bear; you explain to the upper management the need to hire a more experienced team to match up their “Velocity” with the delivery requirements; What is Velocity? |  | Velocity refers to the experience a team is able to possess and use to complete the scheduled work on time. | Velocity refers to the progress a team is able to achieve while working on tight deadlines. | Velocity refers to the measurement of speed at which story points can be completed. | Velocity refers to the level of aggressiveness that only experienced team members are able to use to deliver on tight deadlines. | Answer option c. | In Scrum, Velocity refers to the average amount of work a team can complete in a Sprint; it is a key metric to measure how much work can be completed by a single team.
Exam 8 | #24. In the Precedence Diagramming Method (PDM), ______________ is the most commonly used and ______________ is a rarely used type of precedence relationship. |  | Finish-to-start (FS), Start-to-start (SS) | Finish-to-start (FS), Start-to-finish (SF) | Finish-to-finish (FF), Start-to-finish (SF) | Start-to-start (SS), Finish-to-finish (FF) | Answer option b. | In PDM, finish-to-start is the most commonly used type of precedence relationship. The start-to-finish relationship is very rarely used but is included to present a complete list of the PDM relationship types.
Exam 8 | #25. Who is responsible for delivering the required levels of both quality and grade? |  | All sponsors | Project Sponsor | Project Team | Project Manager and Project Management Team | Answer option d. | The project manager and the project management team are responsible for managing the tradeoffs associated with delivering the required levels of both quality and grade.
Exam 8 | #26. Brittany is a Product Owner working on a new Shopping website for an Ecommerce company. While meeting with the customers, they introduce several new functionalities into the product backlog. The deadline, however, cannot be changed. What should Brittany do next? |  | Ensure alignment with the customer, that lower priority features may drop from the project completely. | Encourage the team to work overtime to deliver the new features in the backlog. | Tell the customer the project will not be delivered on time. | Agree with the customer and place all new items into a separate sub-backlog that will be completed at a later time. | Answer option a. | An Agile project can accept changes even late in development. But while the competing constraints of schedule, scope, and cost are often fixed, Agile constraints can vary. This means some features may need to drop off as others become prioritized.
Exam 8 | #27. After assessing the project risks, the project team was discussing the action to ensure the realization of a high-priority opportunity. What risk strategy should they use? |  | Escalate | Exploit | Share | Enhance | Answer option b. | Answer option b. “Exploit” strategy may be selected for high-priority opportunities where the organization wants to ensure that the opportunity is realized. Answer option b. “ Exploit” strategy may be selected for high-priority opportunities where the organization wants to ensure that the opportunity is realized.
Exam 8 | #28. Which of the following is a concern of the Control Resources process? |  | Identifying and dealing with resource shortage/surplus in a timely manner | Ensuring that resources are used and released according to the plan and project needs | Informing appropriate stakeholders if any issues arise with relevant resources | All of the above. | Answer option d. | Answer option d. “Identifying and dealing with resource shortage/surplus in a timely manner” (Answer option a.), “Ensuring that resources are used and released according to the plan and project needs” (Answer option b.) and “Informing appropriate stakeholders if any issues arise with relevant resources” (Answer option c.). “All of the above” (Answer option d.). Answer option d. “ Identifying and dealing with resource shortage/surplus in a timely manner” (Answer option a.) , “Ensuring that resources are used and released according to the plan and project needs” (Answer option b.) and “Informing appropriate stakeholders if any issues arise with relevant resources” (Answer option c.). “All of the above” (Answer option d.).
Exam 8 | #29. You have just completed performing the “implement risk responses” process, which of the following documents may be updated accordingly? |  | Risk breakdown structure | Project team assignments | Issue log | Both B and C | Answer option d. | “Risk breakdown structure” (Answer option a.) will not be updated due to this process. “Project team assignments” (Answer option b.) would be updated with the updates of the risk roles. “Issue log” (Answer option c.) updated when issues are identified as part of the process. The best answer is “Both B and C” (Answer option d.)
Exam 8 | #30. Which of the following conflict resolution techniques should be used when the deadline is critical, and tasks are at risk of slipping? |  | Smooth/Accommodate | Force/Direct | Collaborate/Problem Solve | Compromise/reconcile | Answer option b. | “Force/Direct”. All four Answers are good and acceptable, after a., Smoothing, d., Compromising, and c., Problem Solving has been tried, if time is slipping and no resolution is in sight Forcing / Directing is the logical choice.
Exam 8 | #31. As a Project Manager, you are looking at the defects at all inspection runs for the past year, and you noticed that the number of flaws per inspection increases over time. You create a quality task force to try to figure out what is causing these defects. Which process are you performing? |  | Control Quality | Manage Quality | Plan Quality Management | Quality Planning | Answer option b. “ | Answer option b. “Manage Quality”. ‘You are looking at defects in all the inspection runs for the past year…’ Sounds like an audit? There are three basic functions done in Quality, Planning, and process audits (Assurance) and monitoring and recording results (Control). Answer options a., Control Quality, c., Plan Quality Management and d., Quality Planning can be removed from consideration leaving Manage Quality. Answer option b. “ Manage Quality”. ‘You are looking at defects in all the inspection runs for the past year…’ Sounds like an audit? There are three basic functions done in Quality, Planning, and process audits (Assurance) and monitoring and recording results (Control). Answer options a., Control Quality, c., Plan Quality Management and d., Quality Planning can be removed from consideration leaving Manage Quality .
Exam 8 | #32. You are the Product Owner of a newly formed Scrum team. You schedule a meeting with the entire team and explain how you prioritize features of a product based on the Kano Model; the Kano Model prioritizes features on the basis of: |  | Performance Delivery, Satisfaction | Basic, Performance, Excitement | Basic, Technical capability, Excitement | Delivery, Performance, Excitement | Answer option b. | The Kano Model is a tool used to prioritize features on a product. The model is based on the degree to which those features satisfy the customer. Basic features are needed to exist and compete in the market. Excitement features are used to create a signature brand or a degree of uniqueness. Performance features are the extras you add to the performance to increase customer satisfaction.
Exam 8 | #33. In your project, you wish to include certain significant events in the milestone list for the project based on historical information. Such milestones are: |  | Optional | Mandatory | Statutory | Authorized | Answer option a. | A milestone list identifies all milestones and indicates whether the milestone is mandatory, such as those specified by contract, or optional, such as those based upon historical information.
Exam 8 | #34. What is the best time to assign a project manager for a project? |  | Right after the contract award. | When team members will start performing project activities. | After the activity estimates have been identified. | While the project charter is being developed before the planning starts. | Answer option d. | A project manager is identified and assigned as early in the project as is feasible, preferably while the project charter is being developed and always prior to the start of planning.
Exam 8 | #35. Alex is a project manager with a very limited procurement experience due to the way of the project management practices he experienced in his former company. As he is currently working on the “control procurement” process, he is seeking expert assistance. What expertise should he be looking for? |  | Contract change control system | Earned value management | Proposal evaluation | Claims administration | Answer option d. | Expertise should be considered for the Control Procurements process including “Claims administration” (Answer option d.) Relevant functional areas and Laws, regulations, and compliance requirements.
Exam 8 | #36. Your Agile team comes to you with a concern. While the product roadmap and backlog have been developed, they are unable to start working on any of the PBI's. Apparently, none of the user stories meet the definition of _____________. They are under pressure to start delivering value, as this is a time-sensitive project undertaken to take advantage of a market opportunity. |  | Ready | Done | Quality | Value | Answer option a. | Ready. The Definition of Ready is a set of criteria that each PBI must meet before they can be accepted or developed. The team must have a sufficiently detailed level of understanding of the PBI. The work must be clear, understood, and well described.
Exam 8 | #37. The Product Owner is a key stakeholder who is responsible for maximizing the value of the products on the product backlog. They own the backlog and prioritizes work during Sprint planning meetings. From the below domain skills, which skill is NOT a “must have” for the Product Owner? |  | Must have proper domain knowledge and appropriate business skills. | Must possess a product vision and lead the team to achieve the vision. | Must be a visionary. | Must anticipate everything upfront. | Answer option d. | In the Scrum framework, a Product Owner is not required to anticipate everything upfront. Scrum is a dynamic framework and change in scope is expected despite having planned sprints. Therefore anticipating everything upfront is not possible in this environment.
Exam 8 | #38. Despite working at the same office, the project manager finds his team interactions are full of conflicts as the team is relatively new to each other. Therefore, he arranged an event outside the company premises to enhance the team’s social relations. His action is an example of _____ . |  | Colocation | Team building | Virtual teams | Meeting management | Answer option b. | Answer option b. “Team building”. The situation is describing a team building activity that intends to improve interpersonal relationships. Answer option b. “ Team building”. The situation is describing a team building activity that intends to improve interpersonal relationships.
Exam 8 | #39. You are leading an internal project when your sponsor informed you to terminate the project, as it is no longer fitting the new company strategy. Accordingly, you need to document the reasons for project termination. What should you do? |  | Engage all the proper stakeholders in the process | Review business documents | Complete near completion deliverables | All of the above | Answer option a. | Answer option a. “Engage all the proper stakeholders in the process” is the best action to take first to gather information and insights around the termination. Answer option a. “Engage all the proper stakeholders in the process” is the best action to take first to gather information and insights around the termination.
Exam 8 | #40. When you encounter constraints as a project manager, in which document will you record the information about these constraints? |  | Project scope statement | Risk register | Issue log | Change management plan | Answer option a. | Answer option a. Information on constraints may be listed in the project scope statement or in a separate log. Answer option a. Information on constraints may be listed in the project scope statement or in a separate log .
Exam 8 | #41. _____ can demonstrate a relationship between any element of a process, environment, or activity on one axis, and a quality defect on the other axis. |  | Affinity diagrams | Fishbone diagrams | Scatter diagrams | Matrix diagrams | Answer option c. | Answer option c. “Scatter diagrams”. A scatter diagram is a graph that shows the relationship between two variables. Scatter diagrams can demonstrate a relationship between any element of a process, environment, or activity on one axis and a quality defect on the other axis. Answer option c. “Scatter diagrams”. A scatter diagram is a graph that shows the relationship between two variables. Scatter diagrams can demonstrate a relationship between any element of a process, environment, or activity on one axis and a quality defect on the other axis.
Exam 8 | #42. John aims to enhance his project team’s social relations and build a collaborative and cooperative working environment through conducting multiple activities, including facilitated workshops and offsite meetings. This is an example of _____ . |  | Influencing | Motivation | Team building | Colocation | Answer option c. | Answer option c. “Team building” includes formal and informal activities. It aims to enhance his project team’s social relations and build a collaborative and cooperative working environment. Answer option c. “Team building” includes formal and informal activities. It aims to enhance his project team’s social relations and build a collaborative and cooperative working environment.
Exam 8 | #43. During the team meeting, two key stakeholders had an argument around removing some value-added features from the project scope. As the project manager seeks to maintain harmony and relationships, which conflict resolution technique should he follow? |  | Avoid | Smooth | Compromise | Reconcile | Answer option b. | Answer option b. “Smooth”. Emphasizing areas of agreement rather than areas of difference; conceding one’s position to the needs of others to maintain harmony and relationships. Answer option b. “ Smooth”. Emphasizing areas of agreement rather than areas of difference; conceding one’s position to the needs of others to maintain harmony and relationships.
Exam 8 | #44. In a scatter diagram, if points are close to the diagonal line, it indicates that: |  | Scatter diagram has some erroneous data | Three variables are closely correlated | Independent and dependent variables are related | No inference can be made from the analysis | Answer option c. | A scatter diagram shows the relationship between two variables. This tool allows the quality team to study and identify the possible relationship between changes observed in two variables. Dependent variables versus independent variables are plotted. The closer the points are to a diagonal line, the more closely they are related.
Exam 8 | #45. The software development project team gathers regularly to discuss the effectiveness of the organization’s quality processes used on your project. They look for the root causes of issues relating to the integration of the system as it is being developed. This meeting is an example of: |  | A retrospective meeting. | A sprint review. | A Scrum standup meeting. | SME review. | Answer option a. | A retrospective meeting.
Exam 8 | #46. You are the Product Owner of a highly effective Scrum team that keeps delivering on plan every time a new challenge is accepted. The upper management has identified a new software feature that if it gets developed right, a huge turnaround in revenue is expected. You meet up with the development team and explain the project, the challenges and the gains expected if implemented and delivered on time. You demand the team use the “Fail Fast approach.” What is Fail Fast? |  | Fail Fast is a technique used by Product Owners to anticipate those who cannot work on certain tasks on the Sprint. | Fail Fast is a technique used to test the entire product early in order to determine the value of the project. | Fail Fast is a technique used to allow team members to fail early and learn fast from their mistakes in order to deliver faster. | Fail Fast is a technique used by Scrum teams in which the most challenging-highest risk items are worked on first. | Answer option d. | Per Agile and Scrum, Fail Fast is a technique in which the developers work on the most challenging-highest risk items first in order to catch up and fix those problems early in the process. Failing early in the process yields lessons learned that can be used by the team throughout therefore eliminating failure by the end. It also provides a way to determine the feasibility early enough, particularly for newly developed products.
Exam 8 | #47. Your organization is involved in Total quality management and is continuously improving the processes and the work all throughout the departments at all levels. In the past, the organization didn’t have quality processes in place, so the defects were only discovered by the end-users. Over the years, quality processes have been established. Considering the above, what should the project manager do next to further improve the level of quality management in the project? |  | Implement quality control for the project and product | Implement an organizational quality culture | Implement ISO 9000 | Implement quality assurance for process analysis | Answer option d. | ”Implement quality assurance for process analysis”. Quality assurance for process analysis is a proactive way to ensure the improvement of the process flows and the overall quality of the processes and the project work. With this, the defects and rework will be avoided.
Exam 8 | #48. The four values considered to be the most important to support the PMI Code of Ethics and Professional Conduct are: |  | Honesty, Respect, Fairness, and Responsibility | Integrity, Respect, Fairness, and Responsibility | Honesty, Respect, Patient, and Responsibility | Honesty, Integrity, Analytical, and Responsibility | Answer option a. | Honesty, Respect, Fairness, and Responsibility: PMI Values from the Code of Ethics and Professionalism.
Exam 8 | #49. Two stakeholders have begun arguing over the functionality of your project. Who should resolve this conflict? |  | Senior management | Project Manager | Sponsor | Customer | Answer option b. | “Project Manager”. Conflict resolution in the project context begins, and is normally expected to end, with the Project Manager. The project experiences different conflicts at different points. In the Question we are early on in the project, negotiating opposing stakeholder requirements; it may be necessary for the Project Manager to occasionally escalate such issues to the Project Sponsor. Later, Team conflict is more often the case. Here, the Project Manager should initially let the team try to resolve the differences and if that fails to work, intercede with a solution.
Exam 8 | #50. Jack is leading a project team, where members are not collaborating and in conflict all the time. To review the team value, which document should he review? |  | Project team assignments | Team charter | Resource calendars | Organizational process assets | Answer option b. | Answer option b. “Team charter” includes team values and ground rules Answer option b. “Team charter” includes team values and ground rules
Exam 8 | #51. All the following statements relating to communications management are correct EXCEPT: |  | Communication planning involves determining the information and communication needs of the stakeholders. | Communicating is the most critical skill for a project manager. | Project managers spend more than 90% of their time communicating. | To be effective, a project manager should control all communication channels. | Answer option d. | Answer option d. A project manager cannot control all the communication channels, because the number of such channels could be very large. Also, the number of communication channels is fixed. For N people, the number of communication channels is N * (N-1) / 2. Answer option d. A project manager cannot control all the communication channels, because the number of such channels could be very large. Also, the number of communication channels is fixed. For N people, the number of communication channels is N * (N-1) / 2.
Exam 8 | #52. Your director has appointed you as a portfolio manager in the company. Your responsibility as a portfolio manager is to: |  | Select and support projects or program investments. | Manage groups of projects in a coordinated way. | Create a unique product, service, or result. | Ensure that customer requirements are satisfied through progressive elaboration of projects. | Answer option a. | A portfolio refers to a collection of projects or programs and other work that are grouped together to facilitate effective management of that work to meet strategic business objectives.
Exam 8 | #53. During the project deliverables review, the project manager suggested adding a new success criterion, then started voting to raise a change request. The team is following the fist of five-technique for voting. In which case a member fully supports the suggestion? |  | Holding closed fist | Raising 2 fingers | Raising 5 fingers | Raising 1 finger | Answer option c. | Answer option c. “Raising 5 fingers” Answer option c. “Raising 5 fingers”
Exam 8 | #54. Sam is trying to resolve a conflict between the customer and the technical lead as the customer insists on including a new requirement that will affect the scope. Sam decided to accept the customer requirement to satisfy the customer. Which conflict resolution technique did he use? |  | Withdraw | Compromise | Force | Problem solving | Answer option c. | “Force”. Because the project manager adopted one direction without problem-solving.
Exam 8 | #55. You are the Product Owner of a highly effective Scrum team; your team has a reputation of bringing new products and overcoming quality and schedule challenges. Recently your team has just delivered a new application, where the user can track empty parking spots around the city you live in. The app was delivered relatively fast and it has already been tested by a variety of users. An Agile expert who was hired by the upper management on a consultancy basis approaches you and requests “Refactoring” the app. What does Refactoring mean? |  | Refactoring is a process in which the development team cleans up the code now to save time that may be needed to upgrade it later. | Refactoring is a process in which the development team enters a new code to deliver a relatively similar product in functionality but much better. | Refactoring is a process in which the development team retests the product among a new set of users and collects different feedback. | Refactoring is a process in which the development team re-codes the code to produce better elements within the product. | Answer option a. | Per Scrum framework, Refactoring is the activity of cleaning and improving the internal structure of the code without changing its external behavior. The code already works before Refactoring so this process will not target the code functionality, however it is focused on making it more readable, more streamline and more efficient before full release into the market.
Exam 8 | #56. As a project manager, you consider that early commitment to clear guidelines decreases misunderstandings and increases productivity. Therefore, you define guidelines such as “Way of interruption during meetings”, “who is allowed to give information about the project to the senior management”, “how will be the communication between the team members”. This is an example of: |  | Project Ethics | Code of Conduct | Ground Rules | Employee Motivation | Answer option c. | Answer option c. Ground rules establish clear expectations regarding acceptable behavior by project team members. An early commitment to clear guidelines decreases misunderstandings and increases productivity. Answer option c. Ground rules establish clear expectations regarding acceptable behavior by project team members. An early commitment to clear guidelines decreases misunderstandings and increases productivity .
Exam 8 | #57. John, in his role as PMO Director, is putting together his quarter end report for the leadership team. A portion of this report includes information about what deliverables will be deployed within the coming months. John goes into the PMO software and looks at each of the agile projects his team has in progress. What is the BEST document to review to determine what features will be deployed next in each project? |  | Product Backlog | Burndown graph | Sprint backlog | Issue Log | Answer option a. | The Product Backlog is the best tool as it includes the User Stories that explain the features that will be included in each project.
Exam 8 | #58. Software company XYZ has recently hired Todd to manage some of its key projects on the yearly roadmap. During his orientation at the organization, Todd was informed that the organization has recently adopted Agile practices for project management. A chart was provided where Agile, and Kanban were shown as subset of Lean. What should Todd’s views be on these items? |  | The chart is wrong - Kanban is a subset of Lean while Agile is not. | The chart is wrong - Agile, Kanban and Lean are three different approaches to project management. | The chart is wrong - Agile is a subset of Lean while Kanban is not. | Agile and Kanban are subsets of Lean because they are named instances of Lean thinking. | Answer option d. | Agile and Kanban are subsets of Lean, sharing the concepts of Lean Management. These concepts include eliminating waste, focus on value, and emphasizing small batch sizes.
Exam 8 | #59. Susan is a very motivated project team member in your project. In one of the team meetings, Susan suggested adding a new small function to the product of the project. The function is not in scope, however, it will improve satisfaction. Your approach would be to: |  | Allow for the functionality, because satisfying the customer is your objective | Make changes to the project plan to accommodate the new requirement | Ask the customer for additional funding to implement the requirement | Disallow the new functionality, because it changes the project scope, and the customer did not explicitly state this requirement | Answer option d. | Project Scope Management includes the processes required to ensure that the project includes all the work required, and only the work required, to complete the project successfully. Managing the project scope is primarily concerned with defining and controlling what is and is not included in the project.
Exam 8 | #60. The product owner needs to schedule a meeting with the team where they can collaboratively prepare some user stories for an upcoming iteration. What is the project manager scheduling? |  | A sprint planning meeting | A sprint review | A sprint retrospective | A sprint backlog refinement | Answer option d. | In iteration-based Agile, the product owner works with the team to prepare some stories for the upcoming iteration during one or more sessions in the middle of the iteration.
Exam 8 | #61. A key stakeholder is unsatisfied with the project team because his quality requirement was neglected. As the project manager investigated the requirement, he found that the requirement was unnecessary. However, the project manager agreed to include the requirement since it would not affect the project elements. Which conflict resolution technique did he use? |  | Withdraw | Compromise | Force | Problem solving | Answer option b. | Answer option b. “Compromise” since the project manager sought a solution that brings some degree of satisfaction to all parties in order to temporarily or partially resolve the conflict. Answer option b. “Compromise” since the project manager sought a solution that brings some degree of satisfaction to all parties in order to temporarily or partially resolve the conflict.
Exam 8 | #62. Which conflict resolution technique does emphasize the areas of agreement rather than areas of difference? |  | Reconcile | Accommodate | Compromise | Collaborate | Answer option b. | Answer option b. “Accommodate” Answer option b. “Accommodate”
Exam 8 | #63. A project manager is communicating with the project sponsor to assist him in acquiring scarce resources for the project. This is an example of _____ . |  | Formal communication | Hierarchical upward communication | Hierarchical Horizontal communication | Official communication | Answer option b. | Answer option b. “Hierarchical upward communication”. There are horizontal and vertical levels within the organization. These hierarchical levels range from the line management level through to the executive management level. The responsibility, accountability, and authority assigned to the hierarchical level indicate how the individual may perform the noted function within that organizational structure. The project sponsor is generally at a higher level compared to the project manager. Answer option b. “Hierarchical upward communication”. T here are horizontal and vertical levels within the organization. These hierarchical levels range from the line management level through to the executive management level. The responsibility, accountability, and authority assigned to the hierarchical level indicate how the individual may perform the noted function within that organizational structure. The project sponsor is generally at a higher level compared to the project manager.
Exam 8 | #64. While closing project procurements, there were some unsettled disputes. In order to settle these disputes, which technique should the project manager use? |  | Facilitation | Negotiation | Meeting management | Bidding | Answer option b. | Answer option b. “Negotiation” is often used to close unsettled disputes. Answer option b. “ Negotiation” is often used to close unsettled disputes.
Exam 8 | #65. You are the Project Manager, where the project's product has to be of very high quality to be competitive in the market. To create quality awareness, you address your project team about the importance of quality. To achieve the maximum benefits from the quality management processes in your project, what will be the most suitable approach towards quality? |  | It will cost more money to build quality into the project. | Quality is prevention driven. | Quality is inspection driven. | It will cost less money to build quality into the project process. | Answer option b. | Answer option b. “Quality is prevention driven”. A tenet of PMI’s Project Management Standard is that every Project should have a Quality Management Plan that is compatible with the International Organization for Standardization (ISO) quality standards. The first three governances toward that end are Customer Satisfaction, Prevention over Inspection, and Continuous Improvement. It reinforces Answer b., Quality is prevention driven. It precludes the other three Answers Answer option b. “ Quality is prevention driven”. A tenet of PMI’s Project Management Standard is that every Project should have a Quality Management Plan that is compatible with the International Organization for Standardization (ISO) quality standards. The first three governances toward that end are Customer Satisfaction, Prevention over Inspection, and Continuous Improvement. It reinforces Answer b., Quality is prevention driven. It precludes the other three Answers
Exam 8 | #66. As a project manager, you are aware that quality has costs associated with it. Which of the following statements is NOT related to cost of quality? |  | Cost of appraising the product or service for conformance to requirements | Cost of rework | Costs incurred by investment in preventing non-conformance to requirements | Cost of evaluating alternative projects | Answer option d. | Answer option d. Cost of quality includes all costs incurred over the life of the product by investment in preventing nonconformance to requirements, appraising the product or service for conformance to requirements, and failing to meet requirements (rework). Answer option d. Cost of quality includes all costs incurred over the life of the product by investment in preventing nonconformance to requirements, appraising the product or service for conformance to requirements, and failing to meet requirements (rework) .
Exam 8 | #67. Company XYZ invited all potential sellers to a meeting to provide them extensive details about the required work and answer their questions. This is an example of _____ . |  | Advertising | Bidder conferences | Review meetings | All of the above | Answer option b. | Answer option b. “Bidder conferences” are meetings between the buyer and prospective sellers prior to proposal submission. Answer option b. “ Bidder conferences” are meetings between the buyer and prospective sellers prior to proposal submission.
Exam 8 | #68. You are the Product Owner of a Scrum team and upon completing a Sprint Review, you and the Scrum Master gather with the team to attend a Sprint Retrospective session; a Sprint Retrospective is: |  | Is a recurring opportunity for the Scrum team to inspect the deliverables and create a plan for improvement for the next Sprint. | Is a recurring opportunity for the Scrum team to capture the missing elements in the previous Sprint. | Is a recurring opportunity for the Scrum team to review the upcoming Sprints before implementation. | Is a recurring opportunity for the Product Owner and the Scrum Master to evaluate the team performance. | Answer option a. | The Sprint Retrospective is a recurring event held at the end of a Sprint in which the Product Owner, the Scrum Master and the development team discuss what went right and what went wrong during the previous Sprint and create a plan for improvement for the next sprints.
Exam 8 | #69. Jane’s project team members are not collaborative or open to differing ideas and perspectives. At which stage does this team stand? |  | Forming | Storming | Norming | Performing | Answer option b. | Answer option b. “Storming” During this phase, the team begins to address the project work, technical decisions, and the project management approach. If team members are not collaborative or open to differing ideas and perspectives, the environment can become counterproductive. Answer option b. “Storming” During this phase, the team begins to address the project work, technical decisions, and the project management approach. If team members are not collaborative or open to differing ideas and perspectives, the environment can become counterproductive.
Exam 8 | #70. Joseph, as the Scrum Master, is chairing the Sprint Planning Session that includes four developers. They are playing planning poker and estimating story points on one of the backlog items that have been brought into the current Sprint. When the Fibonacci Sequence cards are revealed, the Developers have the following cards showing: 40, 40, 40, and 100. To obtain consensus, Mark’s next step should be: |  | To encourage the Developers whose estimates were 40 to explain to the group their reasoning for their estimates. | To use the estimate of 40 as this represents the mode of the numbers. | To request that the Developer that estimated 100 explain their reasoning for the estimate. | To use the estimate of 40 as this represents consensus. | Answer option d. | Consensus in a team of four Developers, three need to be in an agreement. In this situation, consensus has been reached and is 40.
Exam 8 | #71. You have finally completed the development and testing of your project. Your sponsor just signed for the final acceptance of your project's deliverable. As you enter the project closing process, you know that you need to follow the organizational culture in following the closing procedures. Your company is considered to be hierarchical. What type of organizational culture is this? |  | Entrepreneurial | Nurturing | Controlling | Participative | Answer option c. | Answer option c. Hierarchical organizational culture is the one that values structure, control, coordination, efficiency, and stability. Answer option c. Hierarchical organizational culture is the one that values structure, control, coordination, efficiency, and stability .
Exam 8 | #72. A project manager is managing a team distributed across different countries. Which technique can help him to develop and manage the team? |  | Communication models | Virtual teams | Colocation | Conflict management | Answer option b. | Answer option b. “Virtual teams” since the teams are in different countries, colocation would prove to be difficult thus virtual teams are the best option. Answer option b. “Virtual teams” since the teams are in different countries, colocation would prove to be difficult thus virtual teams are the best option.
Exam 8 | #73. In your project, you have been subcontracting your software development work to three different consultancy firms through fixed-price contracts. In this context, all the following statements related to transferring of risk are correct EXCEPT: |  | Risk transference often involves a risk premium. | Fixed price contracts always transfer the risk to the seller. | Contracts may be used for transferring the liability of specified risks to another party. | Cost-plus contracts may transfer the cost risks to the buyer. | Answer option b. | In many cases, use of a cost-plus contract may transfer the cost risk to the buyer, while a fixed-price contract may transfer risk to the seller.
Exam 8 | #74. Cost estimates of the project activities should be reviewed and refined throughout the project. During the initiation phase, you estimated costs in the range of -25% or +75%. This is an example of: |  | Precise estimate | Budget estimate | Definitive estimate | Rough Order of Magnitude (ROM) estimate | Answer option d. | Cost estimates should be reviewed and refined during the course of the project to reflect additional detail as it becomes available and assumptions are tested. For example, a project in the initiation phase may have a rough order of magnitude (ROM) estimate in the range of -25% to 75%.
Exam 8 | #75. You are performing the “monitor risk” process for your current project. Which technique can help you to assure that a contingent response amount is still required and sufficient? |  | Technical performance analysis | Variance analysis | Reserve analysis | Cost-benefit analysis | Answer option c. | “Reserve analysis” compares the amount of the contingency reserves remaining to the amount of risk remaining at any time in the project in order to determine if the remaining reserve is adequate.
Exam 8 | #76. The sponsor requests that you do an analysis of the business case and provide a feasibility report on the project that might be of strategic benefit to the organization. You have some assistance from other departments in the organization. What should you do when you finish the feasibility report? |  | Submit your report to the sponsor | Start with initiating process group | Start writing the project charter | Share it with the senior management | Answer option a. | Answer option a. “Submit your report to the sponsor”. The sponsor has asked you to create a feasibility report, so, you should submit it to the sponsor when completed. The sponsor will decide on the next steps. Answer option a. “Submit your report to the sponsor”. The sponsor has asked you to create a feasibility report, so, you should submit it to the sponsor when completed. The sponsor will decide on the next steps.
Exam 8 | #77. Weak matrix organizations maintain many of the characteristics of a functional organization, and the role of the project manager is: |  | Management with full authority | Line management | Expediter | People management | Answer option c. | Weak matrix organizations maintain many of the characteristics of a functional organization, and the role of the project manager is more of a coordinator or expediter.
Exam 8 | #78. ABC Corporation is planning to implement a major improvement to one of its products, with the goal of increasing customer retention. It has hired an experienced project manager from outside the organization to manage the project. Which approach should the PM adopt for this project? |  | Quickly delivering only the minimum value necessary (Minimum Viable Product) while obtaining feedback from users and pivoting if necessary. | Create a Work Breakdown Structure, since this is an existing product, it is well known, and the improvements can be documented early and planned, reducing the need for excessive feedback. | Create a Minimum Business Increment, since this is an existing organization improving an existing product with an existing market, the focus should be on delivering value frequently and incrementally. | Release the initial functional core feature as soon as possible, generate immediate value, and then continuously add value incrementally. | Answer option c. | Minimum Business Increment, is a better approach for situations where the value of an improvement of a product is reasonably well known, and the goal is to validate and realize that business value faster.
Exam 8 | #79. To identify the most appropriate choice for successful stakeholder engagement, the project manager is prioritizing and weighing a set of criteria. Which technique is he using? |  | Multicriteria decision analysis | Stakeholder analysis | Document analysis | Stakeholder engagement-level assessment | Answer option a. | Answer option a. “Multicriteria decision analysis”. Multicriteria decision analysis uses a decision matrix to provide a systematic approach for establishing key decision criteria, evaluating and ranking alternatives, and selecting a preferred option. Answer option a. “Multicriteria decision analysis”. Multicriteria decision analysis uses a decision matrix to provide a systematic approach for establishing key decision criteria, evaluating and ranking alternatives, and selecting a preferred option.
Exam 8 | #80. Sam is leading a team of technical experts that aim to develop a new product. He is aiming to provide a reason for the team members to act on their own. Which interpersonal and team skills can help him to achieve this objective? |  | Influencing | Motivation | Negotiation | Recognition and rewards | Answer option b. | Answer option b. “Motivation” is providing a reason for someone to act. Teams are motivated by empowering them to participate in decision making and encouraging them to work independently. Answer option b. “Motivation” is providing a reason for someone to act. Teams are motivated by empowering them to participate in decision making and encouraging them to work independently.
Exam 8 | #81. Which of the following options is performed during the Monitoring and Control Process Group? |  | Identifying the people, groups, or organizations that could impact or be impacted by a decision, activity, or outcome of the project | Auditing the quality requirements and the results from quality control measurements to ensure that appropriate quality standards and operational definitions are used | Improving competencies, team member interaction, and overall team environment to enhance project performance | Formalizing acceptance of the completed project deliverables | Answer option d. | Answer option d. Answer option d. (A) Identify Stakeholders -> Initiating Process Group (A) Identify Stakeholders -> Initiating Process Group (B) Manage Quality -> Executing Process Group (B) Manage Quality -> Executing Process Group (C) Develop Team -> Executing Process Group (C) Develop Team -> Executing Process Group (D) Validate Scope -> Monitoring and Controlling Process Group (D) Validate Scope -> Monitoring and Controlling Process Group
Exam 8 | #82. Lewis is a Project Manager for software company XYZ using the Waterfall lifecycle. The customer wants a initiate a new software project, but Lewis should consider the use of Agile when: |  | The customer request is clear and concise. | The scope lacks specificity and stability is unlikely. | There are no ambiguous requirements. | There is a stable product definition and will remain without changes. | Answer option b. | Agile Project Management is not suitable for all projects but is better suited for projects being executed in dynamic environments.
Exam 8 | #83. In your project, you use the earned value technique (EVT) to measure: |  | Work performance and magnitude of variation | Work schedule | Risk responses | Activity duration | Answer option a. | Answer option a. Earned value technique (EVT) is a specific technique for measuring the performance of work and used to establish the performance measurement baseline (PMB). Answer option a. Earned value technique (EVT) is a specific technique for measuring the performance of work and used to establish the performance measurement baseline (PMB) .
Exam 8 | #84. Below are statements that describe the Product Owner and the dynamics of performing work within Scrum, which of the below statements best describes how a Product Owner interacts with their respective teams: |  | “If you guys had read the requirements document more carefully, you would have achieved what I really wanted." | “The requirements have changed. We need to implement the new features as soon as possible.” | “I have been waiting for 12 days for you to read the requirements document, when can you start building the product?” | “If you guys had delivered this product sooner, we would have avoided the customer requesting a new feature on the product.” | Answer option b. | In Scrum framework, the Product Owner and the Developers are expected to embrace and welcome change throughout the project lifecycle. Scrum teams are self-organizing teams, and the developers are expected to deliver with a minimum amount of supervision.
Exam 8 | #85. Tom is a who works full-time on projects. However, in his current assignment, Tom has very little formal authority. He serves mostly as a staff assistant to an executive, who is ultimately responsible for leadership and decision-making on the projects. Tom is working in a ______. |  | Projectized Organization | Expeditor Organization | Weak Matrix Organization | Strong Matrix Organization | Answer option c. | Answer option c. “Weak Matrix Organization”. A Project Manager with “very little formal authority” would not be working in either a d., Strong Matrix Organization or an a., Projectized Organization, in which Project Managers operate with considerable or total authority. b., “Expeditor Organization” is not an organizational model. Answer option c. “ Weak Matrix Organization”. A Project Manager with “very little formal authority” would not be working in either a d., Strong Matrix Organization or an a., Projectized Organization, in which Project Managers operate with considerable or total authority. b., “Expeditor Organization” is not an organizational model.
Exam 8 | #86. Company XYZ needs to procure specialized technical resources from a vendor due to its lack of expertise in this area. Which source selection criteria would be most decisive in this case? |  | Delivery dates | Technical expertise and approach | Specific relevant experience | Financial stability of the firm | Answer option b. | Since technical expertise is the issue that led to procurement from the first place, it only makes sense that “Technical expertise and approach” (Answer option b.) would be the most decisive source selection criteria.
Exam 8 | #87. All of the following are true for Fixed-price contracts EXCEPT: |  | Total price is defined at the beginning for a defined product/service. | Change requests might be delivered with an increase in the contract price. | Value of the contract can grow during project execution. | Buyers need to specify their product/service requirements precisely. | Answer option c. | Fixed-price contracts involve setting a fixed total price for a defined product, service or result to be provided. Fixed-price contracts may also incorporate financial incentives for achieving or exceeding selected project objectives, such as schedule delivery dates, cost and technical performance, or anything that can be quantified and subsequently measured. Sellers under fixed-price contracts are legally obligated to complete such contracts, with possible financial damages if they do not. Under the fixed-price arrangement, buyers need to precisely specify the product or services being procured. Changes in scope may be accommodated, but generally with an increase in contract price.
Exam 8 | #88. Which of the following quality theorists suggested the 80/20 rule and “fitness for use” concepts to quality management discipline? |  | Deming | Juran | Crosby | Herzberg | Answer option b. | 80/20 rule and “fitness for use” are concepts of Joseph Juran.
Exam 8 | #89. All of the following are part of the Direct and Manage Project Work process activities EXCEPT: |  | Change control meetings | Manage sellers and suppliers | Manage stakeholders and their engagement | Create project deliverables | Answer option a. | Answer option a. Following three are Direct and Manage Project Work activities: Answer option a. Following three are Direct and Manage Project Work activities: Create project deliverables to meet the planned project work Manage sellers and suppliers Manage stakeholders and their engagement Create project deliverables to meet the planned project work Create project deliverables to meet the planned project work Manage sellers and suppliers Manage sellers and suppliers Manage stakeholders and their engagement Manage stakeholders and their engagement
Exam 8 | #90. Michael is a Project Manager managing a new website for online retailer Bluefin. Both the project team and the client (Bluefin) are happy with the clarity of requirements defined in the contract’s SOW. He has recommended the Agile project management approach to the client company, and they are happy with any management approach as long as they receive a working product. Michael now has to decide how long the sprint (iteration) durations will need to be. A sprint duration of two weeks could add additional pressure on the team as complex requirements will be tough to build in a single sprint. A sprint duration of four weeks would make the project less Agile, but the project might get finished early as the customer will meet with the team less often. What sprint size should be selected? |  | Four weeks should be selected since the project would get finished early and satisfy the customer. | Three weeks should be selected as that is the average of two numbers. | Two weeks should be selected since Agile Manifesto mandates frequent delivery of working software. | A sprint size needs to be determined that maximizes customer value and satisfaction. | Answer option d. | Customer satisfaction is the highest priority of the Agile team. A sprint (iteration) size needs to be determined that maximizes customer value and satisfaction.
Exam 8 | #91. A project manager is investigating the constraints that limited the technical specifications of the project. Which document should he review? |  | Issue log | Business case | Assumptions log | Change log | Answer option c. | Answer option c. “Assumptions log” (Answer option c.) records all the assumptions and constraints that guided the technical specifications. Answer option c. “ Assumptions log” (Answer option c.) records all the assumptions and constraints that guided the technical specifications.
Exam 8 | #92. Your team member got into a conflict with the member of the vendor’s team. The issues just don’t seem to get resolved, despite efforts from other team members from both sides. What should you, as a Project Manager do in this situation? |  | Write an email to the vendor | Write a formal letter to the vendor explaining the conflict and how detrimental it is to the project | Don’t do anything. The two conflicting parties should be able to resolve the problem by themselves | Ask for an in-person meeting with the vendor to discuss the conflict | Answer option d. | This conflict needs to be resolved as soon as possible, as it affects your project. Therefore, a face to face meeting is the best communication option.
Exam 8 | #93. The project report shows a high amount of construction material leftovers. Which type of costs did the project endure? |  | Prevention Costs | Appraisal Costs | Internal Failure Costs | External Failure Costs | Answer option c. | Answer option c. “Material leftovers are Scrap, which is an Internal Failure Cost. Answer option c. “ Material leftovers are Scrap, which is an Internal Failure Cost.
Exam 8 | #94. A conflict between the two project team members was reported to you. After a brief investigation, you concluded that one of them is approaching matters personally due to the recent death of his father. You approached this individual by sympathizing with his issue and persuaded him to take a short vacation. You advised him to resolve the conflict with his colleague when he is back from vacation. This is an example of _____ . |  | Emotional intelligence | Conflict resolution | Active listening | Both A and B | Answer option d. | “Emotional intelligence” (Answer option a.) was used through understanding the personal emotions and appreciating them. “Conflict resolution” (Answer option b.) was also used through investigating the root cause and taking the proper action to solve it. “Active listening” (Answer option c.) there is no mention of the use of active listening. The best answer is “Both A and B” (Answer option d.)
Exam 8 | #95. You are the project manager in a “Build Fast” construction company. There has been a flood in one of the major cities in your country, and your company has recently signed a contract with the government to reconstruct the state buildings damaged by the flood. In this context, the government’s role will impact your _________. |  | Stakeholder management plan | Project charter | Communication management plan | Project scope statement | Answer option b. | Answer option b. Agreements are used to define initial intentions for a project. Agreements may take the form of contracts, memorandums of understanding (MOUs), service level agreements (SLA), letter of agreements, letters of intent, verbal agreements, email, or other written agreements. Typically, a contract is used when a project is being performed for an external customer. Answer option b. Agreements are used to define initial intentions for a project. Agreements may take the form of contracts, memorandums of understanding (MOUs), service level agreements (SLA), letter of agreements, letters of intent, verbal agreements, email, or other written agreements. Typically, a contract is used when a project is being performed for an external customer. Agreements are one of the inputs for Develop Charter Process. Agreements are one of the inputs for Develop Charter Process.
Exam 8 | #96. For contracts, _____ measure, compare and analyze quality, resource, schedule, and cost performance against the agreement. |  | Earned Value Analysis (EVA) | Trend analysis | Performance reviews | Both A and C | Answer option c. | Answer option c. “Performance reviews” for contracts measure, compare and analyze quality, resource, schedule, and cost performance against the agreement. Answer option c. “Performance reviews” for contracts measure, compare and analyze quality, resource, schedule, and cost performance against the agreement.
Exam 8 | #97. The new software development project is in progress. The Scrum Master says “There is one more increment to complete before finalizing the entire software”. Ryan who recently joined your team as junior intern, asks you what is an “increment”? From the selections below, how would you answer Ryan: |  | An increment is the sum of all product backlog items completed during a Sprint. | An increment is the sum of all the final features of a product that is completed during a Sprint. | An increment is the sum of all the additional requirements that are recently added by the client on a Sprint. | An increment is the sum of all the testing that is completed after building the software. | Answer option b. | Answer option b. In Scrum framework, an increment (sometimes called potentially shippable increment) is defined as the sum of all the product backlog items completed during a Sprint and all previous Sprints. Answer option b. In Scrum framework, an increment (sometimes called potentially shippable increment potentially shippable increment ) is defined as the sum of all the product backlog items completed during a Sprint and all previous Sprints.
Exam 8 | #98. Elaine, in her role as Scrum Master, has the responsibility of introducing the Developers to the principles and processes of agile. The newest Developer, Janeen, has only worked with planned, waterfall project management and is excited about learning new things. As Elaine explains Scrum Artifacts, she lists all of the following EXCEPT: |  | Activity List | Product Backlog | Sprint Backlog | Increment | Answer option a. | An Activity List is part of a predictive approach and Scrum approaches do not create this document for projects. Kickoff Meeting may occur if a company chooses to do so but is not a required event in Scrum Projects. B, C and D are all Scrum Artifacts that the framework requires of every project.
Exam 8 | #99. Alex is facing some trust issues with his project team due to previous conflicts. Which interpersonal and team skills can help him to build trust and harmony among the team members? |  | Influencing | Motivation | Negotiation | Recognition and rewards | Answer option c. | Answer option c. “Negotiation” among team members is used to reach consensus on project needs. It can build trust and harmony among the team members. Answer option c. “Negotiation” among team members is used to reach consensus on project needs. It can build trust and harmony among the team members.
Exam 8 | #100. You are the Product Owner and by definition you have the most important role in Scrum- Agile. As you are the person in charge of the deliverables, you have similarities with the Project Manager in a typical Waterfall environment. In this comparison, who is analogous to a Product Owner in a Waterfall environment: |  | The Project Manager | The Director | The Sponsor | No one – Each method is different | Answer option c. | In Scrum framework, the Product Owner acts as a liaison between the customer and the team and manages all the communication with the customer to ensure mutual collaboration therefore the best response is the Sponsor (Waterfall) is analogous to the the Product Owner (Scrum) because both are the primary liaisons to the customer.
Exam 8 | #101. Project organization charts are a component of the Resource Management Plan and provide a graphic display of project team members and their reporting relationships. All of the following might be included in the Resource Management Plan EXCEPT: |  | Resource calendars | Recognition plans | Acquiring resources | Training strategies | Answer option a. | Resource calendars are part of the project documents and are not part of the resource management plan.
Exam 8 | #102. The project team is identifying the degree of an agreed-upon allowed variation amount before some action needs to be taken. Which element are they establishing? |  | Units of measure | Level of precision | Level of accuracy | Control thresholds | Answer option d. | Answer option d. “Control thresholds”. Variance thresholds for monitoring schedule performance may be specified to indicate an agreed-upon amount of variation to be allowed before some action needs to be taken. Thresholds are typically expressed as percentage deviations from the parameters established in the baseline plan. Answer option d. “Control thresholds”. Variance thresholds for monitoring schedule performance may be specified to indicate an agreed-upon amount of variation to be allowed before some action needs to be taken. Thresholds are typically expressed as percentage deviations from the parameters established in the baseline plan.
Exam 8 | #103. Two team members conflict due to the vagueness of certain quality requirements. The project manager needs to clarify these requirements to avoid the vagueness effect on the deliverables. Which conflict resolution technique should he follow? |  | Avoid | Smooth | Compromise | Collaborate | Answer option d. | Answer option d. “Collaborate”. Clearing the vagueness means reaching the root cause of the issue. Accordingly, it will require problem-solving/ collaboration. Answer option d. “ Collaborate”. Clearing the vagueness means reaching the root cause of the issue. Accordingly, it will require problem-solving/ collaboration.
Exam 8 | #104. You are a project manager. You have completed a project recently. While reviewing the costs, you observed that most of the project's budget was utilized for activities performed in the processes of ____________. |  | Planning Process Group | Executing Process Group | Monitoring and Controlling Process Group | Closing Process Group | Answer option b. | A large portion of the project’s budget will be expended in performing the Executing Process Group processes.
Exam 8 | #105. “ aligns with the organizational strategies by selecting the right programs or projects, prioritizing the work, and providing the right resources…”. |  | Project Management | Program Management | Portfolio Management | Project Plan Management | Answer option c. | “Portfolio Management”. This question tests the student’s knowledge of Portfolio Management and where it fits in the company’s strategic plan and product delivery methodology.
Exam 8 | #106. A decision was made that the new project is managed using a hybrid approach, while the final phases of the project will be managed using Agile methodologies. As the team readies for this work, the project manager realizes that some of the team members are not quite comfortable with Agile methodologies. How should the project manager address this issue? |  | Given that the project is underway, arrange for the appropriate on-the-job training to update those team members' capabilities. | Use part of the risk management budget to provide expedited training to the team, without excluding those who already have some experience. | At this stage in the project, it would be more cost-effective and expeditious to bring on board resources that are familiar with Agile methodologies. | Speak to the sponsor and discuss reverting back to a predictive approach to avoid schedule delays. | Answer option a. | One of the responsibilities of a project manager is to make sure the team possesses the necessary skills to do the job. The team should be given the opportunity to learn, grow, and increase their capabilities. Even when addressed in the later stages of a project, the team and the organization will benefit from its members updating their skills.
Exam 8 | #107. Resit was brought into a Scrum team to assist in a project that has been described as “problematic” by senior leadership. Resit was asked to observe the team and review the project documents. In his analysis of the project and team dynamics, Resit has recognized a few issues that could be impacting performance. Which of the following is a potential reason for the project being problematic? |  | The Sprint Planning session is scheduled for 2 hours. | The Daily Scrum is scheduled for 15 minutes. | The Sprint Review is scheduled for 4 hours. | The Sprint Retrospective is scheduled for 3 hours. | Answer option a. | The Sprint Planning session can take up to 7 hours and should take longer than 2 hours. The longest event for a Scrum should be the Sprint Planning session as this includes estimating effort and obtaining details as to the deliverable requirements. The other events are time-boxed appropriately.
Exam 8 | #108. Depending on the expectation of the buyer and the nature of the project, there are several types of contracts that can be used between the buyer and seller. All of the following are types of contract EXCEPT: |  | Fixed Price | Cost Reimbursable | Reciprocal | Time and Material | Answer option c. | Answer option c. There are 3 types of contracts in procurement management: Answer option c. There are 3 types of contracts in procurement management: Fixed Price Contract Cost Reimbursable Contract Time and Material Contract Fixed Price Contract Fixed Price Contract Cost Reimbursable Contract Cost Reimbursable Contract Time and Material Contract
Exam 8 | #109. Ethan is doing the scheduling for a project. He is currently in the process of calculating the duration of each activity and possible factors that might have an impact on the overall schedule. Ethan called up the meeting of his subordinates and discussed the possible variables which can impact the schedule. One of his subordinates tells him that the delivery of raw material from China is not confirmed to reach in the estimated time of 3 weeks. It can get delayed or it may arrive early and execution will be affected accordingly. Which technique in the given situation is the best to help Ethan calculate the right schedule? |  | Parametric Estimation | What-if analysis | Simulation | Bottom-up Estimation | Answer option b. | Answer option b. “What-if analysis” is the process of evaluating scenarios to predict their effect, positive or negative, on project objectives. Answer option b. “What-if analysis” is the process of evaluating scenarios to predict their effect, positive or negative, on project objectives.
Exam 8 | #110. While developing the project scope statement, the project team discussed the required set of conditions to be met before deliverables are accepted. What element of the scope statement were they discussing? |  | Product scope description | Deliverables | Acceptance criteria | Project exclusions | Answer option c. | Answer option c. “Acceptance criteria”. A set of conditions that are required to be met before deliverables are accepted. Answer option c. “Acceptance criteria”. A set of conditions that are required to be met before deliverables are accepted.
Exam 8 | #111. _____ are especially useful for gathering attributes data while performing inspections to identify defects. |  | Checklists | Check sheets | Statistical sampling | Questionnaires and Surveys | Answer option b. | Answer option b. “Check sheets” Answer option b. “Check sheets”
Exam 8 | #112. You are halfway through your one-year project. The key sponsor just submitted a change request to compress the project schedule by 6 weeks for the product to be released around Christmas time. You ask your project management team to perform an impact analysis and determine what should be the best course of action? |  | Reduce the scope | Add resources on your shortest path of the project | Add resources on the activities that are on the critical path | Fast-track activities that are on the shortest path of the project | Answer option c. | Answer option c. “Add resources on the activities that are on the critical path”. Reducing the duration of the activities on the critical path will shorten the project schedule. Answer option c. “Add resources on the activities that are on the critical path”. Reducing the duration of the activities on the critical path will shorten the project schedule .
Exam 8 | #113. In your project, you documented the project, service, or results that will be outcomes of the project. You listed the collected requirements, identified the requirements that are included and excluded in the scope. Which of the following processes have you performed? |  | Plan Scope Management | Collect Requirements | Define Scope | Control Scope | Answer option c. | Answer option c. Define Scope is the process of developing a detailed description of the project and product. The key benefit of this process is that it describes the project, service, or result boundaries by defining which of the requirements collected will be included in and excluded from the project scope. Answer option c. Define Scope is the process of developing a detailed description of the project and product. The key benefit of this process is that it describes the project, service, or result boundaries by defining which of the requirements collected will be included in and excluded from the project scope .
Exam 8 | #114. _____ is updated to reflect the actual experience in acquiring resources for the project as a result of carrying out the acquire resources process. |  | Resource management plan | Resource breakdown structure | Resource requirements | Lessons learned register | Answer option a. | Answer option a. “Resource management plan” Answer option a. “Resource management plan”
Exam 8 | #115. The project team seems to be unable to internally assign work among themselves once they complete their tasks. It seems that there is a lack of coordination in the remaining work and proper reporting is lacking. What should the team do? |  | Use a Kanban signboard | Review the ground rules | Check the coordination plan | Apply agile project approach | Answer option a. | Answer option a. “Kanban signboard” is a visualization tool that enables you to optimize the flow of your work. Kanban signboard is used to manage work across the team or organization. Answer option a. “Kanban signboard” is a visualization tool that enables you to optimize the flow of your work. Kanban signboard is used to manage work across the team or organization.
Exam 8 | #116. The process of identifying the product needs that can be met by acquiring products outside the project organization is done as part of: |  | Conduct Procurements | Administer Procurements | Close Procurements | Plan Procurement Management | Answer option d. | Answer option d. Plan Procurement Management is a process that identifies those project needs, which can best be, or must be, met by acquiring products, services, or results outside of the project organization, versus those project needs, which can be accomplished by the project team. Answer option d. Plan Procurement Management is a process that identifies those project needs, which can best be, or must be, met by acquiring products, services, or results outside of the project organization, versus those project needs, which can be accomplished by the project team .
Exam 8 | #117. A project manager has been assigned for an internal project before initiation where he will perform the initiation activities as well as the post-project benefit measurement activities. This is an example of _____. |  | Evolving trends in integration processes | Considerations for tailoring integration processes | Considerations for agile environments | Both A and B | Answer option a. | The case is describing expanding the project manager’s responsibilities which is an “Evolving trends in integration processes”.
Exam 8 | #118. A project manager is attempting to influence the stakeholders in a project using various techniques. He finds out that the application of emotional intelligence tools gives the most positive results. What exactly is emotional intelligence? |  | It is a way to stop being too emotional and open towards your stakeholders. | The project manager should be more emotional and show feelings towards your most challenging stakeholders. | It is part of the encoded knowledge where you explain how to listen and follow instructions from stakeholders. | Emotional intelligence is the ability to monitor your emotions or the emotions of others and use this to guide your actions. It is used to recognize or regulate emotions in ourselves and others. | Answer option d. | Answer option d. Emotional intelligence is the ability to monitor your emotions or the emotions of others and use this to guide your actions. It is used to recognize or regulate emotions in ourselves and others. Answer option d. Emotional intelligence is the ability to monitor your emotions or the emotions of others and use this to guide your actions. It is used to recognize or regulate emotions in ourselves and others.
Exam 8 | #119. While performing the close project process, Sue is reviewing the configuration management knowledge base, which contains the versions and baselines of all official organizational standards, policies, and procedures. This configuration management knowledge base is a(n) _____. |  | Organizational process asset | Enterprise Environmental factor | Expert judgment | None of the above | Answer option a. | Answer option a. “Organizational process asset”. Answer option a. “Organizational process asset”.
Exam 8 | #120. After performing the stakeholders’ analysis, the project manager found one of the stakeholder’s power has been rated as high power while the stakeholder does not hold any managerial position or possess any expertise the project needs. Which type of power might he possess? |  | Relational | Positional | Informational | Punitive | Answer option a. | Answer option a. The best answer is “Relational” (Answer option a.) “Positional” (Answer option b.) and “Punitive” (Answer option d.) are both formal power, which contradicts what the question mentioned. “Informational” (Answer option c.) is relevant with expertise which contradicts what the question mentioned as well. Answer option a. The best answer is “Relational” (Answer option a.) “Positional” (Answer option b.) and “Punitive” (Answer option d.) are both formal power, which contradicts what the question mentioned. “Informational” (Answer option c.) is relevant with expertise which contradicts what the question mentioned as well.
Exam 8 | #121. You are heading a big project with numerous people working at a time. Dan, the planning lead comes to you and says that instead of 130 days the project will take 140 days to complete. He told you that the Critical path has been extended as no resource is allowed to work more than 8 hours a day and software has extended the schedule to 140 days instead of 130 days. What is the technique used that has led to the extension of Critical Path in the given situation? |  | Fast-tracking | Crashing | Resource Leveling | Resource Smoothing | Answer option c. | Resource leveling can be used when shared or critically required resources are available only at certain times or in limited quantities or when there is a need to keep resource usage at a constant level.
Exam 8 | #122. Which of the following engagement levels best describes the Stakeholder who is not only aware of the project, along with its potential impacts, but is also actively engaged in activities designed to ensure the project will be ultimately successful? |  | Leading | Project Manager | Supportive | Project Sponsor | Answer option a. | Answer option a. “Leading”. A stakeholder who at the Leading engagement level is one who is “aware of the project and potential impacts and actively engaged in ensuring the project is a success.” Answer c., Supportive is “Aware of project and potential and supportive to change.” Answers b., Project Manager, and d., Project Sponsor, while stakeholders themselves are titles and not engagement levels. Answer option a. “ Leading”. A stakeholder who at the Leading engagement level is one who is “aware of the project and potential impacts and actively engaged in ensuring the project is a success.” Answer c., Supportive is “Aware of project and potential and supportive to change.” Answers b., Project Manager, and d., Project Sponsor, while stakeholders themselves are titles and not engagement levels.
Exam 8 | #123. In a project, the process of developing a detailed description of the project and product is referred to ____________. |  | Define Scope | Validate Scope | Control Scope | Collect Requirements | Answer option a. | Answer option a. Define Scope is the process of developing a detailed description of the project and product. Answer option a. Define Scope is the process of developing a detailed description of the project and product.
Exam 8 | #124. You are managing the procurement for a project and you are not satisfied with the existing lists of potential sellers, you should _____ . |  | Arrange bidder conference | Place advertisements in selected newspapers | Arrange vendor conference | Arrange pre-bid conference | Answer option b. | If you decide to “Arrange bidder conference” (Answer option a.), “Arrange vendor conference “(Answer option c.) or “Arrange pre-bid conference “(Answer option d.) they all have the same meaning and they are used to ensure that all prospective bidders have a clear and common understanding of the procurement and no bidders receive preferential treatment thus taking this course of action will not guarantee to have new potential sellers. The best course of action is to “Place advertisements in selected newspapers” (option b.) as the target is to expand the list of sellers, Existing lists of potential sellers can be expanded by placing advertisements in general circulation publications such as selected newspapers or in specialty trade publications.
Exam 8 | #125. In which of the following processes is decomposition used as a tool? |  | Define Activities | Sequence Activities | Estimate Activity Resources | Estimate Activity Durations | Answer option a. | Answer option a. Decomposition is a tool used in the Define Activities process. Answer option a. Decomposition is a tool used in the Define Activities process.
Exam 8 | #126. During the execution of a construction project, the customer requested to reduce the project remaining time by 2 months instead of 6 months. Considering the fact that the customer is sensitive to quality but more flexible with the cost, which schedule compression technique would you use? |  | Resource smoothing | Resource optimization | Fast tracking | Crashing | Answer option d. | Answer option d. “Crashing” is allocating more resources to activities to reduce its duration which does not necessarily impact quality but it affects cost. Answer option d. “Crashing” is allocating more resources to activities to reduce its duration which does not necessarily impact quality but it affects cost.
Exam 8 | #127. During a Sprint Review, the product owner requests a change to the product. However, during the Sprint Retrospective, your team voices concerns over the changes the product owner is requesting in the next release. What should you do? |  | Meet with the product owner off-line and explain that the team is uncomfortable with the changes. | Negotiate with the product owner for introducing the change in a later build until the team is on board. | Draft a change request and submit the change to the change control board, making sure there is time and a schedule available. | Explain to the team that Agile projects are change-driven and how the team should respond to change. | Answer option d. | This is the only correct Answer. Agile projects are change-driven.
Exam 8 | #128. You are working in “Wipe Out Corporation” which is a vacuum cleaner manufacturer. A recently produced model of the vacuum cleaner has been sold a lot, and the current capacity of the manufacturing lines cannot reach the demand of the consumers. Your company decided to create new manufacturing lines to produce more vacuum cleaners. You have been assigned as the project manager for this project. Who will be the users of this project? |  | Future users of the new vacuum cleaners | Employees who will use the new manufacturing lines | Project Sponsor | Project Team | Answer option b. | Answer option b. Customers are the persons or organizations that will approve and manage the project’s product, service or result. Users are the persons or organizations that will use the project’s product, service or result. Answer option b. Customers are the persons or organizations that will approve and manage the project’s product, service or result. Users are the persons or organizations that will use the project’s product, service or result. Since workers will use the new manufacturing lines, they will be the users of this project. Since workers will use the new manufacturing lines, they will be the users of this project.
Exam 8 | #129. Jonathan has completed resource planning, assembled the team, and acquired the necessary physical resources. Then he developed the training strategies and improved the team competency and performance. Now he wants to track the performance of individual members and find out what particular skills they have gained while working on the project. He will need all this information to optimize the team's performance. Which process should the project manager do next? |  | Manage Team | Control Resources | Develop Team | Building Team | Answer option a. | Answer option a. All this is performed in the Manage Team process. Answer option a. All this is performed in the Manage Team process.
Exam 8 | #130. Sam is leading a project team consisting of 20 members, as the team is a group of technical experts, he chooses to demonstrate a commitment to serve and put them first when making any decision. Which leadership style does Sam adopt? |  | Laissez-faire | Charismatic | Servant leader | Interactional | Answer option c. | Answer option c. “Servant leader”. Answer option c. “Servant leader”.
Exam 8 | #131. Implementing agile frameworks, like Scrum and Kanban, lets the organizations deliver solutions to customers faster, with more predictability, and gives them the ability to react quickly based on new information. Implementing agile at the individual team level is relatively easy - the benefits are clear, and the resources are plenty. But the real challenge is extending it across multiple teams in a large organization. Who is responsible for scaling Scrum to the greater organization? |  | Project Manager | Scrum Master | Product Owner | Functional Manager | Answer option b. | Responsibilities of the Scrum Master role are: Empowering and shepherding the team, removing impediments, Keeping the process moving, Socializing Scrum to the greater organization.
Exam 8 | #132. You are a Project Manager at MKB Constructions and you have been recently assigned to a project in Oman. Project schedule development is in process and you are calculating the duration for each activity. Your subordinate comes to you and tells you that the project team is yet to get the clearance from the environmental department and site preparation cannot start without it. Which kind of dependency is hurdling in this scenario? |  | Mandatory dependency | External dependency | Discretionary dependency | Internal dependency | Answer option b. | Answer option b. ”External dependency”. External dependencies are outside of the project team’s control. Answer option b. ”External dependency”. External dependencies are outside of the project team’s control.
Exam 8 | #133. A project team member seemed unfocused and disoriented all the time. As Noah is the project manager, he arranged a one-on-one meeting to address the issue. It turned out that the team member is homesick and misses his homeland. Accordingly, Noah decided to arrange some informal activities to make him more comfortable with the team. Which interpersonal and team skills did Noah use? |  | Influencing | Conflict management | Emotional intelligence | Motivation | Answer option c. | Answer option c. The case project manager is showing sympathy for the team member which is an element of “Emotional intelligence” the ability to identify, assess, and manage the personal emotions of oneself and other people, as well as the collective emotions of groups of people. Answer option c. The case project manager is showing sympathy for the team member which is an element of “Emotional intelligence” the ability to identify, assess, and manage the personal emotions of oneself and other people, as well as the collective emotions of groups of people.
Exam 8 | #134. Tom is a Project Manager that has been hired by Company ABC to manage a software implementation project using the Agile lifecycle. Tom discovers that three of the software developers are contractors. What should Tom do to ensure the project schedule is under control? |  | Frequently revise the Scrum (iteration) backlog. | Frequently revise the Work Breakdown Structure (WBS). | Frequently communicate to Senior Management to identify their needs. | Ensure recurring milestone status updates from contractors and consistently identify variances using burndown charts. | Answer option d. | When work is being contracted, regular and milestone status updates from contractors are a means to ensure the work is progressing as agreed upon to ensure the schedule is under control.
Exam 8 | #135. _____ process is primarily concerned with the correctness of the deliverables and meeting the quality requirements specified for the deliverables. |  | Control quality | Manage quality | Validate scope | Control scope | Answer option a. | Answer option a. “Control quality”. Answer option a. “Control quality”. Control quality: is concerned with the correctness of the deliverable and meeting quality standards Manage quality: is concerned with ensuring that planned processes and standards are correct and being applied Validate scope: is concerned with acceptance of the deliverables Control scope: is concerned with the ensuring that scope is being executed and only what’s in scope Control quality: is concerned with the correctness of the deliverable and meeting quality standards Control quality: is concerned with the correctness of the deliverable and meeting quality standards Manage quality: is concerned with ensuring that planned processes and standards are correct and being applied Manage quality: is concerned with ensuring that planned processes and standards are correct and being applied Validate scope: is concerned with acceptance of the deliverables Validate scope: is concerned with acceptance of the deliverables Control scope: is concerned with the ensuring that scope is being executed and only what’s in scope Control scope: is concerned with the ensuring that scope is being executed and only what’s in scope
Exam 8 | #136. Project deliverables are formally accepted during the Validate Scope process. Which of the following is an input for the Validate Scope process? |  | Accepted Deliverables | Change Requests | Verified deliverables | Scope management plan | Answer option c. | Answer option c. Validate scope is the process of formalizing acceptance of the completed project deliverables. The following figure shows inputs, tools & techniques and outputs of this process. Answer option c. Validate scope is the process of formalizing acceptance of the completed project deliverables. The following figure shows inputs, tools & techniques and outputs of this process. Verified deliverables is an input of the Validate Scope process. Verified deliverables is an input of the Validate Scope process. | images/image11.jpg
Exam 8 | #137. Nikos is the Scrum Master of a software upgrade project and discovered that a close competitor has released functionality that is on our Product Backlog. This feature is currently prioritized at 35th and, based on our current run rate, will be ready for release in 4 months. What is the BEST thing for Nikos to do next? |  | Move the item up to 1st priority as the team needs to deploy the items that provide the best business value. | Do nothing, the item was prioritized at 35th after a lengthy exercise of prioritizing the backlog and was finalized. | Share this information with the Product Owner. Surveying changes to external business environments is a responsibility of the Scrum Master. | Do nothing, the competitor’s feature does not include all the features of ours and is inferior to our offering. | Answer option c. | The Product Owner may not know this information and should be informed. At that point, the Product Owner has the information necessary to make an informed decision on whether the Product Backlog prioritizations should be changed. “A” is incorrect as the Scrum Master is not responsible for the prioritization/ordering of Product Backlog items. “B” is incorrect as the Product Backlog is not considered finalized and changes as the Product Owner decides. “D” is incorrect as the activities of competitors directly affects this business.
Exam 8 | #138. John, in his role as Scrum Master, has the responsibility of introducing the Developers to the principles and processes of agile. The newest Developer, Alicia, has only worked with planned, waterfall project management and is excited about learning new things. As John explains the makeup of the Scrum Team, he lists all of the following EXCEPT: |  | Product Owner | Sponsor | Development Team | Scrum Master | Answer option b. | A, C and D are all members of the Scrum Team. The term Sponsor would most closely match the Product Owner in Scrum Framework.
Exam 8 | #139. The project manager asked the quality team to find the main reason behind the recurring bugs in the software program that the project team is developing. Which technique would the quality team use? |  | Alternatives analysis | Document analysis | Process analysis | Root cause analysis | Answer option d. | Answer option d. “Root cause analysis” is an analytical technique used to determine the basic underlying reason that causes a variance, defect, or risk. A root cause may underlie more than one variance, defect, or risk. Answer option d. “ Root cause analysis” is an analytical technique used to determine the basic underlying reason that causes a variance, defect, or risk. A root cause may underlie more than one variance, defect, or risk.
Exam 8 | #140. Adam, in his role as Scrum Master, has the responsibility of introducing the Developers to the principles and processes of agile. The newest Developer, Kathleen, has only worked with planned, waterfall project management and is excited about learning new things. As Adam explains Scrum Events, he lists all of the following EXCEPT: |  | The Sprint | Sprint Planning | Kickoff Meeting | Sprint Review | Answer option c. | A Kickoff Meeting may occur if a company chooses to do so but is not a required event in Scrum Projects. A, B and D are all Scrum Events that the framework requires of every project.
Exam 8 | #141. During the project planning phase, which of the following steps does happen at the latest? |  | Hold a kick-off meeting | Gain formal approval of the plan | Develop Budget | Develop Schedule | Answer option a. | Answer option a. Following is the order of steps in the planning phase: Answer option a. Following is the order of steps in the planning phase: Develop schedule Develop budget Gain formal approval of the plan Hold kick-off meeting Develop schedule Develop schedule Develop budget Develop budget Gain formal approval of the plan Gain formal approval of the plan Hold kick-off meeting Hold kick-off meeting The kick-off meeting is the last step of the planning phase. The kick-off meeting is the last step of the planning phase.
Exam 8 | #142. The project team just completed the Monitor Stakeholder Engagement process. Which of the following is not an output of the process? |  | Work performance information | Work performance data | Change requests | Risk register update | Answer option b. | Answer option b. “Work performance data” is an input for the process. Answer option b. “Work performance data” is an input for the process.
Exam 8 | #143. A project manager is working on a project that requires procurement. As he is currently conducting project procurement, of the following, which is an enterprise environmental factor that can influence this process? |  | List of preferred sellers that have been prequalified | Organizational policies | Financial policies and procedures regarding invoicing and payment processes | Contract management systems | Answer option d. | The best Answer is “Contract management systems” (Answer option d.) it is the only enterprise environmental factor that can influence the process. “List of preferred sellers that have been prequalified” (Answer option a.), “Organizational policies” (Answer option b.), and “Financial policies and procedures regarding invoicing and payment processes” (Answer option c.) are all organizational process assets not enterprise environmental factors.
Exam 8 | #144. You are reviewing the project benefits management plan to understand the “how” and ”when” the project will deliver its benefits. Which element does it include? |  | Strategic alignment | Alternatives recommendation | Project critical success factors | Alternatives | Answer option a. | Answer option a. “Strategic alignment” Answer option a. “Strategic alignment”
Exam 8 | #145. A project manager needs to know how the Control Quality process will verify compliance with it. Which input should he review? |  | Quality management plan | Quality measurement metrics | Quality metrics | Test and evaluation documents | Answer option c. | Answer option c. “Quality metrics”. A quality metric specifically describes a project or product attribute and how the Control Quality process will verify compliance with it. Some examples of quality metrics include the percentage of tasks completed on time, cost performance measured by CPI, failure rate, number of defects identified per day, total downtime per month, errors found per line of code, customer satisfaction scores, and percentage of requirements covered by the test plan as a measure of test coverage. Answer option c. “Quality metrics”. A quality metric specifically describes a project or product attribute and how the Control Quality process will verify compliance with it. Some examples of quality metrics include the percentage of tasks completed on time, cost performance measured by CPI, failure rate, number of defects identified per day, total downtime per month, errors found per line of code, customer satisfaction scores, and percentage of requirements covered by the test plan as a measure of test coverage.
Exam 8 | #146. Workarounds differ from contingency plans in that: |  | Contingency plans are planned in advance and workarounds are not planned in advance. | Workarounds are planned in advance and contingency plans are not planned in advance. | Contingency plans include plans for force majeure events, e.g. natural calamities, but workarounds are the residual risks in the project. | Workarounds only include plans for force majeure events, e.g. natural calamities | Answer option a. | Answer option a. Workaround. A response to a negative risk that has occurred. Distinguished from contingency plan in that a workaround is not planned in advance of the occurrence of the risk event. Answer option a. Workaround. A response to a negative risk that has occurred. Distinguished from contingency plan in that a workaround is not planned in advance of the occurrence of the risk event .
Exam 8 | #147. You are working on the monitor stakeholder engagement process. To obtain the strategies for the stakeholders’ communication, to which of the following should you refer? |  | Stakeholder register | Lessons learned register | Stakeholder engagement plan | Communications management plan | Answer option d. | Answer option d. “Communications management plan” Answer option d. “Communications management plan”
Exam 8 | #148. Due to the limitations in his company’s financial capacity, a project manager managing a mega construction project has decided to procure a major part of the project on a profit-sharing basis. Which source selection criteria would be the most decisive? |  | Delivery dates | Technical expertise and approach | Specific relevant experience | Financial stability of the firm | Answer option d. | since the financial capability is the issue that led to procurement in the first place, it only makes sense that “Financial stability of the firm” (Answer option d.) would be the most decisive source selection criteria.
Exam 8 | #149. The customer and project manager need to validate the scope of the deliverables. This will help to: |  | Ensure proper project selection | Create WBS | Obtain customer`s acceptance of the project deliverables | Mitigate project risks | Answer option c. | Answer option c. Validate Scope is the process of formalizing acceptance of the completed project deliverables. Validating scope includes reviewing deliverables with the customer or sponsor to ensure that they are completed satisfactorily and obtaining formal acceptance of deliverables by the customer or sponsor. Answer option c. Validate Scope is the process of formalizing acceptance of the completed project deliverables. Validating scope includes reviewing deliverables with the customer or sponsor to ensure that they are completed satisfactorily and obtaining formal acceptance of deliverables by the customer or sponsor.
Exam 8 | #150. One of Gary’s responsibilities as the PM in an agile team is ensuring compliance. As Gary is fulfilling this responsibility, he is likely to do which of the following? |  | Determine potential threats to compliance | Analyze the consequences of noncompliance | Measure the extent to which the project is in compliance. | All of the above | Answer option d. | In addition to all of these being part of the compliance requirements of a project, the following also need to be addressed: confirm project compliance requirements, classify compliance categories, use methods to support compliance, and determine necessary approach and action to address compliance needs.
Exam 8 | #151. Jack is managing a complex project with many ambiguities. The project sponsor advised him to use a technique in which the work to be accomplished in the near term is planned in detail, while the work in the future is planned at a higher level. Which of the following is the name of this technique? |  | Regression Analysis | Rolling Wave Planning | Resource Optimization Technique | Requirements Management Planning | Answer option b. | Answer option b. “Rolling Wave Planning”. An iterative planning technique in which the work to be accomplished in the near term is planned in detail, while the work in the future is planned at a higher level. Answer option b. “ Rolling Wave Planning”. An iterative planning technique in which the work to be accomplished in the near term is planned in detail, while the work in the future is planned at a higher level.
Exam 8 | #152. A technological advance, legal requirement, or social need refers to: |  | Issues that need to be managed in the project plan | Environmental factors that usually have detrimental effect on the project | Risks that have to be managed by the project manager | Factors contributing to the creation of the business case | Answer option d. | The business case is created as a result of one or more of the following: Market demand, Organizational need, Customer request, Technological Advance, Legal requirement, Ecological impacts, Social need.
Exam 8 | #153. All the following are valid inputs for "Identify Stakeholder" process EXCEPT: |  | Enterprise environmental factors | Procurement documents(if project is done as part of a contract) | Project scope statement | Project charter | Answer option c. | Project scope statement is output of Define Scope process.
Exam 8 | #154. You are the project manager in a company, which has a balanced matrix organizational structure. Who do you report to? |  | Functional Manager | Program Manager | Manager of Project Managers | Portfolio Sponsor | Answer option a. | Answer option a. The project manager reports to the functional manager in a balanced matrix organization. Answer option a. The project manager reports to the functional manager in a balanced matrix organization .
Exam 8 | #155. After evaluating the sellers’ proposals and reaching near satisfactory mutual agreement, there are some points of disagreement with the vendor. Which interpersonal skills can help you to conclude with a signed contract? |  | Leadership | Persuasion | Negotiation | Networking | Answer option c. | “Negotiation” Procurement negotiation clarifies the structure, rights, and obligations of the parties and other terms of the purchases so that mutual agreement can be reached before signing the contract. The final document language reflects all agreements reached. Negotiation concludes with a signed contract document or other formal agreement that can be executed by both buyer and seller.
Exam 8 | #156. You are the Product Owner of a highly effective Scrum team. This team keeps delivering on Sprints just as per the plan. Each time a Sprint is complete, you hold up a Sprint review session to discuss progress followed by a Sprint Retrospective where the team inspects the deliverable and selects the most important learnt items from the previous session. You are going to use a decision-making Scrum technique that is mostly used for decision-making rather than anything else. From the selections below, which technique is this: |  | Planning Poker | Dot Voting | Affinity Estimation | Shirt Sizing | Answer option d. | Shirt Sizing
Exam 8 | #157. You oversee a multinational team and stakeholders. How do you minimize mix-ups and misunderstandings in such a diverse group? |  | Regular video conferences and meetings | Regular training and workshops on cultural diversity and sensitivity. | Regular review of project status | Regular collocation of the team and stakeholders | Answer option b. | ”Regular training and workshops on cultural diversity and sensitivity”. Cultural awareness and sensitivity are important in a diverse team.
Exam 8 | #158. Janet had some social conversations with the project key stakeholders to build a good network of connections within and outside the company. In which dimension is she communicating? |  | Formal | Informal | Internal | External | Answer option b. | Answer option b. “Informal” the focus of the question is around the informal communication dimension. Answer option b. “Informal” the focus of the question is around the informal communication dimension.
Exam 8 | #159. Which of the following Tools/Techniques assists a Project Manager and his team to show how the various elements of a system relate? |  | Project Scope Statement | Trend charts | Flowcharting | Scatter Diagram | Answer option c. | “Flowcharting”. Flowcharts are process maps that define the sequence of steps and branching possibilities that exist for a process; d, Scatter Diagrams or correlation charts are used to determine a relationship between two dependent variables. Answers a. Project Scope Statement and b. Trend Charts do not apply and can be eliminated.
Exam 8 | #160. You have been assigned to do the cost estimation of an important work package. Your Project Manager has explained to you all the 20 components of the work package. You have calculated the individual cost of each component. Now you are adding up the cost of all 20 components to find the overall estimate. You have used which estimation technique while calculating the cost of the work package? |  | Parametric Estimation | Bottom-up Estimation | Three-point Estimation | Analogous Estimation | Answer option b. | “Bottom-up estimation” is a method of estimating project duration or cost by aggregating the estimates of the lower-level components of the WBS.
Exam 8 | #161. An organization has been successfully implementing Agile projects in the IT department, and now plans to expand these approaches to other departments. As the project manager in charge of the PMO, you are tasked to guide this initiative. How can you best support this type of organizational change? |  | Assess the capabilities of the teams in the other departments, and ensure they receive appropriate training prior to the implementation. | Use your positional influence with functional managers to secure buy-in for the change before doing anything else. | Treat the change process as an Agile project, using a backlog of changes and a Kanban board to track progress. | Use the successful experience in the IT department to plan the rollout of this initiative in a predictive fashion, tailoring risk management for each department. | Answer option c . | Answer option c. When implementing new Agile/hybrid approaches and changes at the organizational level, it is often common practice to treat the change process as an Agile project, treat every change as an experiment, test it for a short period of time, and determine its suitability or the need for further refinement. Answer option c . When implementing new Agile/hybrid approaches and changes at the organizational level, it is often common practice to treat the change process as an Agile project, treat every change as an experiment, test it for a short period of time, and determine its suitability or the need for further refinement.
Exam 8 | #162. Based on the attached above, which of the following statements is true? | images/image12.jpg | Task B cannot start before Task A finishes and Task C cannot start before Task B finishes. | Task B cannot start before Task A finishes and Task C cannot finish before Task B finishes. | Task B can start after Task A starts and Task C cannot finish before Task B finishes. | Task B can start after Task A starts and Task C cannot start before Task B finishes. | Answer option b. | Answer option b. Precedence Diagramming Method (PDM) Relationship Types are as below: Answer option b. Precedence Diagramming Method (PDM) Relationship Types are as below: Based on the diagram in the question, there is a finish-to-start dependency between Tasks A and B, and there is a finish-to-finish dependency between Tasks B and C. Based on the diagram in the question, there is a finish-to-start dependency between Tasks A and B, and there is a finish-to-finish dependency between Tasks B and C. Finish-to-start (FS): A logical relationship in which a successor activity cannot start until a predecessor activity has finished. Finish-to-start (FS): A logical relationship in which a successor activity cannot start until a predecessor activity has finished. Finish-to-finish (FF): A logical relationship in which a successor activity cannot finish until a predecessor activity has finished. Finish-to-finish (FF): A logical relationship in which a successor activity cannot finish until a predecessor activity has finished. Thus, the Answer is: Task B cannot start before Task B finishes and Task C cannot finish before Task B finishes Thus, the Answer is: Task B cannot start before Task B finishes and Task C cannot finish before Task B finishes | images/image13.jpg
Exam 8 | #163. Adam is investigating when and how to report project benefits; at the end of the project or at the end of each iteration or phase. This is an example of _____ . |  | Evolving trends in integration processes | Considerations for tailoring integration processes | Considerations for agile environments | Both A and B | Answer option d. | Answer option d. The description can fit both Expanding the project manager’s responsibilities as “Evolving trends in integration processes” (Answer option a.) and Benefits as a “Considerations for tailoring integration processes” (Answer option b.). The best answer is “Both A and B” (Answer d). Answer option d. The description can fit both Expanding the project manager’s responsibilities as “Evolving trends in integration processes” ( Answer option a. ) and Benefits as a “Considerations for tailoring integration processes” ( Answer option b. ). The best answer is “Both A and B” ( Answer d).
Exam 8 | #164. Emily is managing an international project. Two of the project team members are in the US, two of them are in India, and three people are working from Ireland. To build effective communication with the virtual project team, the project team is using video conferencing. The use of the video conferencing tool is an example of _____ . |  | Virtual teams | Colocation | Communication technology | Conflict management | Answer option c. | Answer option c. “Communication technology”. The globalization of projects has promoted the need for virtual teams that work on the same project, but are not co-located at the same site. The availability of communication technology such as email, audio conferencing, social media, web-based meetings, and video conferencing has made virtual teams feasible. Answer option c. “Communication technology”. The globalization of projects has promoted the need for virtual teams that work on the same project, but are not co-located at the same site. The availability of communication technology such as email, audio conferencing, social media, web-based meetings, and video conferencing has made virtual teams feasible.
Exam 8 | #165. Portfolio managers are responsible for managing: |  | Dependency on different projects | Operational projects only | Projects, programs and operations | Functional work and projects | Answer option c. | The relationship between portfolios, programs, and projects is such that a portfolio refers to a collection of projects, programs, sub-portfolios, and operations managed as a group to achieve strategic objectives.
Exam 8 | #166. As a Project Manager, you are explaining to your project team the difference between the Resource Histogram and Responsibility Assignment Matrix. What does a Resource Histogram show that a Responsibility Assignment Matrix does not? |  | Time | Activity | Inter-relationships | Person in charge of each activity | Answer option a. | “Time”. A Resource Histogram shows resource usage over time and is useful in planning and scheduling activities to optimize scheduling. The RAM chart assigns the b., activities, can show c., inter-relationships between members performing the activity, and d., the person accountable or responsible for the activity.
Exam 8 | #167. A project manager is facilitating an Agile workshop in a company that plans to adopt some Agile approaches for their projects. Most of the attendants have only worked with predictive approaches. One of them hears that Agile is about doing less work, but that is not what the project manager means. Which Agile principle is being discussed? |  | Deliver less but more frequently | Efficient communications | Simplicity | Deliver early and continuously | Answer option c. | The project manager is referring to the Agile principle of “Simplicity—the art of maximizing the amount of work not done—is essential.” Agile encourages doing the things that have the most impact, prioritizing, and building with a purpose.
Exam 8 | #168. Which of the following tools and/or techniques is NOT used in the Estimate Activity Resource process? |  | Alternatives Analysis | Bottom-Up Estimating | Make or Buy Analysis | Project Management Software | Answer option c. | Answer option c. “Make or Buy Analysis”. The Make or buy Analysis is a Tool & Tech used in Plan Procurements, not in the Estimate Activity Resources Process. Answers a. Alternatives Analysis, b. Bottom-Up Estimating, and d. Project Management Software are indeed tools used in estimating what resources will be required on the project. Answer option c. “ Make or Buy Analysis”. The Make or buy Analysis is a Tool & Tech used in Plan Procurements, not in the Estimate Activity Resources Process. Answers a. Alternatives Analysis, b. Bottom-Up Estimating, and d. Project Management Software are indeed tools used in estimating what resources will be required on the project.
Exam 8 | #169. You and your vendor have a dispute regarding payment terms and what is considered a minimum viable product as described in the contract. The negotiations are stalled and none of the parties is willing to reach an agreement. What should the project manager do next? |  | Initiate an alternative dispute resolution (ADR). | Request court resolution, as the vendor is in default. | Ask the legal team for advice on the most effective course of action. | Renegotiate if possible and re-baseline the agreement. | Answer option a. | Answer option a. Initiate an alternative dispute resolution (ADR). It is initiated after negotiations fail. Answer option a. Initiate an alternative dispute resolution (ADR). It is initiated after negotiations fail .
Exam 8 | #170. Mike is the quality manager on a project. Mike and his team have been waiting for quality testing of some models. He has been informed by the design head that there has been an unexpected delay and design completion will be delayed till next weekend. He shared that the reason for this delay is due to a couple of members of the design team who could not complete their assigned task within the allocated time slot. Which dependency has led to this delay in the project? |  | Mandatory dependency | External dependency | Discretionary dependency | Internal dependency | Answer option d. | Answer option d. “Internal dependencies” involve a precedence relationship between project activities and are generally inside the project team’s control. Answer option d. “Internal dependencies” involve a precedence relationship between project activities and are generally inside the project team’s control.
Exam 8 | #171. Dan is a Project Manager of a megaproject. He is doing the cost estimation of a work package that is to be outsourced to a seller. Dan’s team has told him that the work package is going to cost $200,000 based on the historical data of the company. There is a company policy that states that any deliverable costing above $150,000 requires an external professional estimate to serve as a benchmark for all the incoming bids regarding the work package. What is the technique used here for the estimate? |  | Source Selection Criteria | Request for Proposal | Independent Cost Estimate | Expert Opinion | Answer option c. | Answer option c. ”Independent Cost Estimate”. In large procurements, procuring organizations may elect to either prepare their independent estimate or have a cost estimate prepared by an outside professional estimator to serve as a benchmark on proposed responses. Answer option c. ”Independent Cost Estimate”. In large procurements, procuring organizations may elect to either prepare their independent estimate or have a cost estimate prepared by an outside professional estimator to serve as a benchmark on proposed responses.
Exam 8 | #172. A project to lay 10 miles of a petroleum pipeline was scheduled to be completed today, exactly 20 weeks after the start of the project. You receive a report that the project has a Schedule Performance Index (SPI) of 0.8. Based on this information, when would you expect the project to be completed? |  | 2 weeks early | In 5 more weeks | In 2 more weeks | In 10 more weeks | Answer option b. | Answer option b. In 5 more weeks: To solve this problem, you must first start out employing SPI, and then rely on your logical reasoning (and math!) skills from there on out. Think of it in 4 steps. Answer option b. In 5 more weeks: To solve this problem, you must first start out employing SPI, and then rely on your logical reasoning (and math!) skills from there on out. Think of it in 4 steps. Step 1: Perform SPI: SPI = EV/PV. In this problem, we know the SPI (0.8), and we know the PV (10 miles of a petroleum pipeline to be completed). The unknown is the EV. Therefore, 0.8 = ? / 10 miles. Playing easily with numbers, you should get: 0.8 = 8 / 10. Step 1: Perform SPI: SPI = EV/PV. In this problem, we know the SPI (0.8), and we know the PV (10 miles of a petroleum pipeline to be completed). The unknown is the EV. Therefore, 0.8 = ? / 10 miles. Playing easily with numbers, you should get: 0.8 = 8 / 10. Step 2: Determine the miles of pipeline that remain to be completed. You do this by subtracting the EV (8) from the PV (10): 10 – 8 = 2 miles of pipeline that remain to be completed. Step 2: Determine the miles of pipeline that remain to be completed. You do this by subtracting the EV (8) from the PV (10): 10 – 8 = 2 miles of pipeline that remain to be completed. Step 3: Now, you can determine the percentage of pipeline miles completed per week by dividing the pipeline miles completed by the weeks needed to complete 1 mile of the pipeline: 8 / 20 = 0.4. Step 3: Now, you can determine the percentage of pipeline miles completed per week by dividing the pipeline miles completed by the weeks needed to complete 1 mile of the pipeline: 8 / 20 = 0.4.
Exam 8 | #173. Project organization Tetra Inc. has engaged a vendor, Retro Solutions, for a deliverable. The deliverable is not up to the quality standards specified by Tetra Inc. They have requested the changes in the deliverable, but Retro Solutions is not agreeing to it. They have contested the changes and both parties have not been able to reach an agreement. Which technique will help in resolving this situation? |  | Dispute Management | Claim Administration | Alternative Dispute Resolution | Change Request | Answer option b. | Answer option b. “Claims Administration” is used in case of any contested changes between the buyer and the seller. If the parties themselves do not resolve a claim, it may have to be handled in accordance with alternative dispute resolution (ADR). Answer option b. “ Claims Administration” is used in case of any contested changes between the buyer and the seller. If the parties themselves do not resolve a claim, it may have to be handled in accordance with alternative dispute resolution (ADR).
Exam 8 | #174. A colleague from your team has sent you a report that you must present at a bidder conference. You received the report just 1 hour ago from the conference and realized that there are critical errors in the report. The best option is to: |  | Cancel the meeting and organize a meeting later. | Proceed to the meeting and tell the participants that the report has some errors. | Proceed to the meeting but let your colleague present the erroneous part. | Escalate the issue to your manager and ask your manager to cancel the meeting. | Answer option a. | Answer option a. Option A is the best choice. Answer option a. Option A is the best choice. Options B and C can impact the team’s motivation and your image negatively in the bidder conference Option D is about escalation, you should solve this problem by yourself. Options B and C can impact the team’s motivation and your image negatively in the bidder conference Options B and C can impact the team’s motivation and your image negatively in the bidder conference Option D is about escalation, you should solve this problem by yourself. Option D is about escalation, you should solve this problem by yourself.
Exam 8 | #175. After conducting project procurement successfully, what major outputs would you expect from the process? |  | Selected sellers | Agreement | Sellers’ proposal | Both A and B | Answer option d. | “Sellers’ proposal “(Answer option c.) is an input for the process. “Selected sellers“(Answer option a.) and “Agreement” (Answer option b.) are both major outputs of the process. The best answer is “Both A and B” “(Answer option d.).
Exam 8 | #176. Which of the following organizational process assets does not influence the Conduct Procurements Process? |  | Financial policies and procedures regarding invoicing and payment processes | Organizational policies that influence the selection of a seller | List of preferred sellers that have been prequalified | Contract management systems | Answer option d. | ”Financial Policies and procedures regarding invoicing and payment processes” (Answer option a.), “Organizational policies that influence the selection of a seller” (Answer option b.), and “List of preferred sellers that have been prequalified” (Answer option c.) are organizational process assets that can influence the Conduct Procurements process. The best answer is “Contract management systems” (Answer option d.).
Exam 8 | #177. In your software project, to finish an activity on time, you add one more developer to the same activity. This is an example of: |  | Risk Exploitation | Risk Sharing | Risk Enhancing | Risk Accepting | Answer option c. | Enhance. The enhance strategy is used to increase the probability and/or the positive impacts of an opportunity. Identifying and maximizing key drivers of these positive-impact risks may increase the probability of their occurrence. Examples of enhancing opportunities include adding more resources to an activity to finish early.
Exam 8 | #178. As a result of carrying out the acquired resources process, which enterprise environmental factors are updated? |  | Resource availability within the organization | Documentation related to acquiring resources | Documentation related to assigning and allocating resources | All of the above | Answer option a. | Answer option a. “Resource availability within the organization” Answer option a. “Resource availability within the organization”
Exam 8 | #179. One of the project team members misses deadlines frequently. The project manager set a one-on-one meeting with him to discuss the issue. During the meeting, the member explained that he is facing a family issue causing him to lose focus. The project manager showed his understanding of the situation but guided the team member to differentiate the work and personal life. Which interpersonal skills did the project manager use? |  | Motivating | Emotional intelligence | Influencing | Leadership | Answer option b. | Answer option b. “Emotional intelligence”. The ability to identify, assess, and manage the personal emotions of oneself and other people, as well as the collective emotions of groups of people. Answer option b. “Emotional intelligence”. The ability to identify, assess, and manage the personal emotions of oneself and other people, as well as the collective emotions of groups of people.
Exam 8 | #180. Bryan is studying the influence of rules, standards, and guidelines specific to the project application-area on the control quality process. Under which category do these elements fall? |  | Emerging practices | Enterprise environmental factors | Organizational process assets | Expert judgment | Answer option b. | Answer option b. “Enterprise environmental factors” Answer option b. “Enterprise environmental factors”

## exam9
Exam Name | Question | quesimgsrc | Answer1 | Answer2 | Answer3 | Answer4 | Correct-Answer | Explanation | answerimgsrc
Exam 9 | #1. Bill is the Scrum Master on a Scrum Team. The Scrum Team’s velocity is 24 story points per iteration (Sprint). There are 190 story points. Which of the following statements is true? |  | A Kanban board will display this information. | The project needs eight iterations (Sprints) to complete all project work. | Velocity is used to estimate the Scrum Team’s capacity. | This information can be tracked in the Product Backlog. | Answer option b. | Velocity is used to determine how long it will take to complete the work in each iteration (Sprint). If the team’s velocity is 24; 190/24 = 7.9 or ~ 8 total iterations (Sprints).
Exam 9 | #2. Carolyn is a Project Manager working on an Agile Technology project. The project is progressing well, but some of the development team members are having unnecessary conversations during the Sprint Planning Meetings. What should Carolyn do to eliminate the unnecessary conversation in future meetings? |  | Cancel the Planning Meetings moving forward. | Reduce the time limit and number of future Sprint Planning Meetings. | Increase the number of user stories for all future Sprints. | Escalate to Senior Management. | Answer option b. | Common practice is to place time limits (usually two-hours) on the Sprint Planning Meeting. This limit ensures the meeting focuses on sprint planning and creates a sense of urgency because two hours may not be enough time to plan everything out accordingly. This limit keeps everyone focused and eliminates unnecessary conversation.
Exam 9 | #3. The project manager asked Kim to develop a visual representation of the organization’s data described in business language and independent of any specific technology. The objective is to use this representation to identify where data integrity or other quality issues can arise. Which of the following does meet the above request? |  | Flowchart | Mind Map | Matrix Diagram | Logical Data Model | Answer option d. | Answer option d. “Logical Data Model” Answer option d. “Logical Data Model”
Exam 9 | #4. Which of the following is an example of push communication? |  | Meeting | E-Learning | Voice Mail | Instant Messaging | Answer option c. | Answer option c. “Voice Mail” is a one-way communication channel pushed from the sender to the receiver. Answer option c. “Voice Mail” is a one-way communication channel pushed from the sender to the receiver.
Exam 9 | #5. A project manager is working to identify the need for team development strategies based on variations, if any, during the project execution. Which input should he review? |  | Team charter | Project schedule | Project team assignments | Resource calendars | Answer option b. | Answer option b. ”Project schedule”. Answer option b. ”Project schedule”.
Exam 9 | #6. _____ document(s) the periods that each resource needed for the project is available for the project. |  | Resource calendars | Resource requirements | Resource management plan | Procurement management plan | Answer option a. | Answer option a. “Resource calendars” Answer option a. “Resource calendars”
Exam 9 | #7. ____ can be used to identify the root cause of the problem. |  | Affinity diagrams | Flowcharts | Fishbone diagrams | Histograms | Answer option c. | Answer option c. “Fishbone diagrams”. Cause-and-effect diagrams are also known as fishbone diagrams, why-why diagrams, or Ishikawa diagrams. This type of diagram breaks down the causes of the problem statement into discrete branches, helping to identify the main or root cause of the problem. Answer option c. “Fishbone diagrams”. Cause-and-effect diagrams are also known as fishbone diagrams, why-why diagrams, or Ishikawa diagrams. This type of diagram breaks down the causes of the problem statement into discrete branches, helping to identify the main or root cause of the problem.
Exam 9 | #8. _____ includes the examination of industry and specific seller capabilities. |  | Market research | Data analysis | Source selection analysis | Source selection criteria | Answer option a. | Answer option a. “Market research” Answer option a. “Market research”
Exam 9 | #9. Charlie is the Scrum Master for a complex Software Development Project using the Agile lifecycle. The development team is new to Agile and has been given a basic set of requirements which need further elaboration and review. After the Sprint (iteration), the Product Owner rejects all work developed by the Project Team. What should Charlie have done to prevent this situation? |  | Ensure the Product Owner works with the Development Team daily by providing product feedback. | Cancel the Sprint early after receiving feedback from the Product Owner. | Document the feedback in the Sprint Review session. | Advise the Product Owner to attend all daily standups. | Answer option a. | As Scrum Master, he/she should ensure alignment between the Product Owner (responsible for guiding the direction of the product) and the Development Team (responsible for executing project tasks/developing the product). Answer D. is incorrect, as the Product Owner is not a necessary attendee of daily standups.
Exam 9 | #10. The analysis of quality reports, test reports and performance reports are an example of _____ . |  | Root cause analysis | Process analysis | Document analysis | Alternatives analysis | Answer option c. | Answer option c. ”Document analysis” Answer option c. ”Document analysis”
Exam 9 | #11. Before the initiation of the system upgrade project, the project sponsor is developing a document to authorize further project management activities. Which document would he develop? |  | The project charters | Project business case | Project benefits management plan | None of the above | Answer option b. | Answer option b. “Project business case”. A documented economic feasibility study used to establish the validity of the benefits of a selected component lacking sufficient definition and that is used as a basis for the authorization of further project management activities. Answer option b. “Project business case”. A documented economic feasibility study used to establish the validity of the benefits of a selected component lacking sufficient definition and that is used as a basis for the authorization of further project management activities.
Exam 9 | #12. Kimberly is assigned to a project as an Agile Project Manager. The project Sponsor has asked how many defects have been found in the recent testing cycle. Kimberly, uncertain of the answer, hesitates to respond to the Sponsor. What is the BEST next step Kimberly should take? |  | Provide the Sponsor with a “guesstimate” number. | Take the Sponsor to the team area, where the “information radiator” with all project information is displayed. | Advise the Sponsor to contact the Scrum Master for the number of defects. | Advise the Sponsor an email will be sent with the number of defects at a later time. | Answer option b. | Agile focuses on transparency and managing all project information visually. In Agile, a project information radiator is used to communicate all related project information including test results, team velocity, Product Backlog items, etc.
Exam 9 | #13. The Close Project or Phase process involves all of the following except . |  | Final Updates to the Project Files | Project or Phase Closure and Historical Information documents | Handover of deliverables | Admin Management | Answer option d. | Answer option d. “Admin Management”. Final updates to the Project management Plan, Scope, Schedule, risk register, change management and risk impact documents; b., Document reviews associated with validated scope, customer acceptance, contract closure; and the Handover of the product of the project, the deliverables to the customer can be removed from consideration. Admin Management is the odd man out that is not associated with Close Project or Phase. Answer option d. “Admin Management”. Final updates to the Project management Plan, Scope, Schedule, risk register, change management and risk impact documents; b., Document reviews associated with validated scope, customer acceptance, contract closure; and the Handover of the product of the project, the deliverables to the customer can be removed from consideration. Admin Management is the odd man out that is not associated with Close Project or Phase.
Exam 9 | #14. Brian is the Project Manager for a newly developed Agile team. The team has determined several key features to deliver to the customer. How should these tasks be tackled by the team? |  | The features should be delivered a soon as possible, whether complete or not, to gather feedback from the customer. | The features should be held for delivery at the end of the project. | The features should be delivered according to the predictive project plan. | The features should be prioritized, tested, and delivered incrementally. | Answer option d. | Agile focuses on delivering features incrementally and iteratively, as the business value is improved continuously across the project.
Exam 9 | #15. What is the key benefit of the Control Procurements process? |  | It ensures that buyer’s performance meet the project’s requirements | It ensures that the seller’s performance meet the project’s requirements | It ensures that both the seller’s and buyer’s performance meet the project’s requirements | None of the above | Answer option c. | Answer option c. “It ensures that both the seller’s and buyer’s performance meet the project’s requirements” Answer option c. “It ensures that both the seller’s and buyer’s performance meet the project’s requirements”
Exam 9 | #16. During the Conduct Procurements process, all of the following may happen EXCEPT: |  | The team will receive bids or proposals. | The team will make changes and corrections to the contract. | The team will select sellers based on previously defined selection criteria. | The team awards a contract with a seller. | Answer option b. | Conduct Procurements is the process of obtaining seller responses, selecting a seller, and awarding a contract. Making changes and corrections are done during Control Procurements.
Exam 9 | #17. Jerry is a Scrum Manager at GlobalTech, a company new to Agile approaches. Halfway through the project, he notices that the team is underperforming due to delays in communication among team members, and a lack of understanding of work in progress (WIP). What should Jerry use to maintain and improve communication and build trust among team members? |  | Identify all team members as early as possible in the project. | Hold daily standup meetings. | Update the Stakeholder register. | Escalate to Senior Management. | Answer option b. | Daily Standups are facilitated by the Scrum Master to inform the development team on Work In Progress (WIP), improve communication, and highlight team impediments.
Exam 9 | #18. For the projects that are carried out under a formal contract, the principal inputs are ____ . |  | Statement of Work and Business Case | Statement of Work and Project Charter | Project Charter and Business Plan | Statement of Work and Project Document | Answer option a. | Answer option a. “Statement of Work and Business Case”. Initiating a Project requires a Project Charter, the document that formally authorizes the existence of a project and empowers the Project manager to apply organizational resources to realize the product service or result. If the source of the work is from an external contract, two required inputs to Develop Project Charter are the Statement of Work (what needs to be done) and the Business case, a document that justifies whether or not doing the work is worth the required investment. Through the process of elimination, Answer options b. and c. include the Project Charter which implies the Project has been approved. Answer d. includes a ‘Project Document’ which is too vague to be considered. Answer option a. “Statement of Work and Business Case”. Initiating a Project requires a Project Charter, the document that formally authorizes the existence of a project and empowers the Project manager to apply organizational resources to realize the product service or result. If the source of the work is from an external contract, two required inputs to Develop Project Charter are the Statement of Work (what needs to be done) and the Business case, a document that justifies whether or not doing the work is worth the required investment. Through the process of elimination, Answer options b. and c. include the Project Charter which implies the Project has been approved. Answer d. includes a ‘Project Document’ which is too vague to be considered.
Exam 9 | #19. Program management and portfolio management differ from project management in _____ . |  | Stakeholders | Life cycles | Resources | Their need for coordination | Answer option b. | Answer option b. ”Life cycles”. Program management and portfolio management differ from project management in their life cycles, activities, objectives, focus, and benefits. Answer option b. ”Life cycles”. Program management and portfolio management differ from project management in their life cycles, activities, objectives, focus, and benefits.
Exam 9 | #20. For the manage communication process, political climate and governance framework are _____ . |  | Emerging practices | Enterprise environmental factors | Organizational process assets | Expertise required for expert judgment | Answer option b. | Answer option b. “Enterprise environmental factors” Answer option b. “Enterprise environmental factors”
Exam 9 | #21. Which of the following is NOT a Control Quality Process Tool/Technique? |  | Quality Audit | Pareto Charts | Ishikawa Diagrams | Inspection | Answer option a. | Quality Audit: Remember Audits are typically used for Process Assurance; Control Quality is all about demonstrating, with evidenced data, the acceptance criteria associated with the product, its correctness has been met. Answers b., c., and d. need to be eliminated from consideration.
Exam 9 | #22. ________ is an example of an external Enterprise Environmental Factor. |  | Company methodology and organization | Company culture | Company infrastructure and capability | Government and industry standards and regulations | Answer option d. | Answer option d. “Government and industry standards and regulations”. All of the Answer options are Enterprise Environmental Factors. However, the keyword in the question is external; only Answer option d., Government and industry standards and regulations, is an external Enterprise Environmental Factors. All of the others are internal Enterprise Environmental Factors. Answer option d. “Government and industry standards and regulations”. All of the Answer options are Enterprise Environmental Factors. However, the keyword in the question is external; only Answer option d., Government and industry standards and regulations, is an external Enterprise Environmental Factors. All of the others are internal Enterprise Environmental Factors.
Exam 9 | #23. Taylor is the Product Owner of a new project that aims to develop facial recognition software for a university in the USA. The university has hired a consultant team to advise on the features needed to be developed in each sprint. He is working with the consultant team to determine the elements listed in the product backlog. However, he feels that the consultants want to go over his role's authority. What is a probable explanation for this? |  | The Product Owner should define the sprint's scope based on the time estimates set at the sprint planning event and the team's capacity for the next sprint and not an outside party. | The team should have the autonomy to plan the work for the project. | An outside consultant has no authority to determine the elements to be included in neither the product backlog nor the sprint backlog. | All of the above. | Answer option a. | Product owners have the competency to define the sprint’s scope and the items included in both the product and sprint backlog.
Exam 9 | #24. You are in the process of selecting a seller and awarding a contract. The process will involve receiving bids or proposals and applying defined selection criteria to select the seller who is qualified to perform the work. All of the following are inputs to this process except: |  | Seller Proposals | Make or Buy Decisions | Bidder Conferences | Procurement Management Plan | Answer option c. | Answer option c. “Bidder Conferences”. This question tests the student’s understanding of the ITOs of the Conduct Procurements process. Through elimination, Answer options a., b., and d. may be removed from consideration: all of these are indeed Inputs in the Conduct Procurements process. The exception here is Answer option c., Bidder Conferences, which is a Tool/Technique in the Conduct Procurements process, not an Input. Answer option c. “ Bidder Conferences”. This question tests the student’s understanding of the ITOs of the Conduct Procurements process. Through elimination, Answer options a., b., and d. may be removed from consideration: all of these are indeed Inputs in the Conduct Procurements process. The exception here is Answer option c., Bidder Conferences, which is a Tool/Technique in the Conduct Procurements process, not an Input .
Exam 9 | #25. During a daily standup, Mark (the Agile Coach) observes that many tasks remain inactive for a long amount of time without being worked on, thus impacting team productivity. What should Mark do next? |  | Increase the Work in Progress (WIP) limit. | Reduce the Work in Progress (WIP) limit. | Meet with the Technical Managers to discuss the team member allocation. | Facilitate a meeting with the Sponsor to determine an approach to resolve this issue. | Answer option b. | When the team has a large amount of work in progress (WIP), they delay the delivery of the feature/product. Reducing the WIP is a core property of Agile, allowing the team to focus on a set of activities to complete from end-to-end and understand their true work capacity.
Exam 9 | #26. _____ means the result either conforms or does not conform. |  | Variable sampling | Attribute sampling | Tolerances | Inspection | Answer option b. | Answer option b. “Attribute sampling”. Project managers may need to be familiar with sampling. Attribute sampling (the result either conforms or does not conform) and variable sampling (the result is rated on a continuous scale that measures the degree of conformity). Answer option b. “Attribute sampling”. Project managers may need to be familiar with sampling. Attribute sampling (the result either conforms or does not conform) and variable sampling (the result is rated on a continuous scale that measures the degree of conformity).
Exam 9 | #27. The desired result of the change driven by the project is described as_____ |  | The current state | The objective | The future state | Business Value | Answer option c. | Answer option c. “The future state”. The desired result of the change driven by the project is described as the future state. Answer option c. “The future state”. The desired result of the change driven by the project is described as the future state.
Exam 9 | #28. A Sprint (iteration) Planning session does NOT: |  | Prepares the backlog in an ordered list, usually in “story” form. | Encourages the team to work a cross functional unit including developer and testing roles. | Gather the team to discuss each story and place it into a Sprint (iteration). | Encourage the team to work in dedicated silos, so no one bothers them. | Answer option d. | The team does not work alone in silos, as Agile promotes team collaboration to deliver the feature/project.
Exam 9 | #29. _____ is sometimes called quality assurance. |  | Plan Quality | Manage Quality | Control Quality | All of the above | Answer option b. | Answer option b. “Manage Quality”. Manage Quality is sometimes called quality assurance, although Manage Quality has a broader definition than quality assurance as it is used in non-project work. Answer option b. “Manage Quality”. Manage Quality is sometimes called quality assurance, although Manage Quality has a broader definition than quality assurance as it is used in non-project work.
Exam 9 | #30. Kimberly is a Project Manager managing a 12-month Agile Project with 4-week Sprints (Iterations). She soon observes that some of the team members are not engaged in the project tasks and as a result, notices a decrease in team velocity/increase in schedule delays. What should Kimberly do to get the schedule back on track? |  | Discuss the issue with the Project Sponsor. | Facilitate a Sprint Retrospective and record lessons learned. | Reduce the Stories in future sprints to increase velocity. | Reset the Project Schedule with a later date. | Answer option b. | Facilitating a Sprint Retrospective is the approach to use. The Retrospective can address areas of improvement and other aspects relating to the team’s performance after each Sprint (iteration). Through this session, Kimberly can determine solutions to increase team engagement, schedule project work, and drive the project towards the product vision.
Exam 9 | #31. _____ is the features and functions that characterize a product, service, or result. |  | Scope baseline | Product scope | Project scope | WBS | Answer option b. | Answer option b. “Product scope” Answer option b. “Product scope”
Exam 9 | #32. Technology and stakeholder relations and trial engagements are examples of _____ . |  | Emerging practices for Project Procurement Management | Considerations for tailoring Project Procurement Management processes | Organizational process assets | Enterprise environmental factors | Answer option a. | Answer option a. “Emerging practices for Project Procurement Management”. Trends and emerging practices for Project Procurement Management include but are not limited to technology and stakeholder relations and trial engagements. Answer option a. “Emerging practices for Project Procurement Management”. Trends and emerging practices for Project Procurement Management include but are not limited to t echnology and stakeholder relations and trial engagements.
Exam 9 | #33. _____ is a significant point or event in a project. |  | Phase | Gate | Activity | Milestone | Answer option d. | Answer option d. ”Milestone” Answer option d. ”Milestone”
Exam 9 | #34. All of the following strategies are applicable for positive risks or opportunities EXCEPT: |  | Exploit | Enhance | Share | Mitigate | Answer option d. | Answer option d. Strategies for positive risks or opportunities are: Answer option d. Strategies for positive risks or opportunities are: Exploit Enhance Share Accept Exploit Exploit Enhance Enhance Share Share Accept Accept Mitigate is a strategy for negative risks or threats. Mitigate is a strategy for negative risks or threats .
Exam 9 | #35. You are working on providing the final project report. Which information can it provide? |  | Evidence that the completion criteria were met | Detailed description of the project or phase | Descriptive validation information for the final product | Both A and C | Answer option a. | Answer option a. “Evidence that the completion criteria were met”. Answer option a. “Evidence that the completion criteria were met”.
Exam 9 | #36. Key benefits of the “Develop Project Charter” process include all of the following except: |  | The Charter provides a well-defined project start and project boundaries | The Charter creates a formal record of Project | The Charter formally authorizes the budget of the Project | The Charter provides a direct way for Senior Management to accept and commit to the project | Answer option c. | Answer option c. “The Charter formally authorizes the budget of the Project”. Key benefits of developing a Project Charter include Answers a., Project Start and boundaries, b., it creates a formal record of the project, and d., it formalizes the acceptance and commitment of Senior Management to the success of the project. While Charter execution does commit the company to financially back the project, it does not define, create or commit to a project budget Answer option c. “The Charter formally authorizes the budget of the Project”. Key benefits of developing a Project Charter include Answers a., Project Start and boundaries, b., it creates a formal record of the project, and d., it formalizes the acceptance and commitment of Senior Management to the success of the project. While Charter execution does commit the company to financially back the project, it does not define, create or commit to a project budget
Exam 9 | #37. Dan asked his project team to vote on a decision during a meeting in the collect requirements process. The results were 14 votes for developing a new software application, 11 votes for using the existing software application, and 9 votes for procuring an external software application. The team decided to develop a new software application. According to the given votes, in which decision-making technique would they go for developing a new software application? |  | Autocracy | Unanimity | Majority | Plurality | Answer option d. | Answer option d. “Plurality” a decision is reached whereby the largest block in a group decides, even if a majority is not achieved. Answer option d. “Plurality” a decision is reached whereby the largest block in a group decides, even if a majority is not achieved.
Exam 9 | #38. _____ are physical or team resources for a project determined in advance. |  | Virtual teams | Critical resources | Pre-assignment | Scarce resources | Answer option c. | Answer option c. ”Pre-assignment”. When physical or team resources for a project are determined in advance, they are considered pre-assigned. Answer option c. ”Pre-assignment”. When physical or team resources for a project are determined in advance, they are considered pre-assigned.
Exam 9 | #39. According to the Agile Manifesto, which of the following should be valued more than contract negotiation? |  | Having a dedicated Procurement Manager. | Using motivated team members to deliver business value. | Customer Collaboration. | Multiple, defined contracts for each Procurement relationship between the buyer and seller. | Answer option c. | Answer option c. Customer collaboration is valued higher than contract negotiation. Answer option c. Customer collaboration is valued higher than contract negotiation.
Exam 9 | #40. According to directions of influence technique, a stakeholder who can be classified as upward is _____ . |  | Sponsor | Other project managers | Customer users | Government | Answer option a. | “Other project managers” (Answer option b.) are considered sideward. “Customer users” (Answer option c.) and “Government” (Answer option d.) are outward. The best Answer is “Sponsor” (Answer option a.)
Exam 9 | #41. Which of the following is NOT a Tool/Technique in the Identify Risks process? |  | Brainstorming | Risk Urgency Assessment | Delphi Technique | SWOT Analysis | Answer option b. | Answer option b. “Risk Urgency Assessment”. Identify Risks is all about a., Brainstorming, c., the anonymity of the Delphi technique and d., identifying Strengths, Weaknesses, Opportunities, and Threats which can be eliminated from consideration. Once all the risks are identified they are then qualified, where a tool, Risk Urgency Assessment is used to prioritize it among other identified risks on the project. Answer option b. “ Risk Urgency Assessment”. Identify Risks is all about a., Brainstorming, c., the anonymity of the Delphi technique and d., identifying Strengths, Weaknesses, Opportunities, and Threats which can be eliminated from consideration. Once all the risks are identified they are then qualified, where a tool, Risk Urgency Assessment is used to prioritize it among other identified risks on the project.
Exam 9 | #42. Which of the following is a distinctive characteristic that differentiates a program from a project? |  | Projects are temporary | Projects have definitive start and end | Programs drive change | Programs involve operational work | Answer option d. | “Projects are temporary” (Answer option a.) and “Projects have definitive start and end” (Answer option b.) are all characteristics for both projects and programs. “Programs drive change” (Answer option c.) projects drive change as well. The best Answer is “Programs involve operational work” (Answer option d.) as it is unique to programs and not a characteristic of projects.
Exam 9 | #43. How frequently does a project manager perform the Control Resources process? |  | Once at the end of each phase | Throughout the project | Once at the end of project | None of the above | Answer option b. | Answer option b. “Throughout the project” Answer option b. “Throughout the project”
Exam 9 | #44. Who is accountable for the development and maintenance of the project business case? |  | The Project team | The Project Sponsor | The Project manager | Both A and C | Answer option b. | “The Project team” (Answer option a.) is not involved in its development or maintenance of the business case as it is the responsibility of the project sponsor. “The Project manager” (Answer option c.) may assist the project sponsor but it is still the project sponsor responsibility. The best Answer is “The Project Sponsor” (Answer option b.)
Exam 9 | #45. Which is a benefit of the virtual team model? |  | Improved team morals | Save the expense of offices and all physical equipment | Higher levels of trust than other forms of teams | All of the above | Answer option b. | Answer option b. “Save the expense of offices and all physical equipment”. The virtual team model makes it possible to: Answer option b. “Save the expense of offices and all physical equipmen t”. The virtual team model makes it possible to: Form teams of people from the same organization who live in widespread geographic areas; Add special expertise to a project team even though the expert is not in the same geographic area; Incorporate employees who work from home offices; Form teams of people who work different shifts, hours, or days; Include people with mobility limitations or disabilities; Move forward with projects that would have been held or canceled due to travel expenses; and Save the expense of offices and all the physical equipment needed for employees. Form teams of people from the same organization who live in widespread geographic areas; Form teams of people from the same organization who live in widespread geographic areas; Add special expertise to a project team even though the expert is not in the same geographic area; Add special expertise to a project team even though the expert is not in the same geographic area; Incorporate employees who work from home offices; Incorporate employees who work from home offices; Form teams of people who work different shifts, hours, or days; Form teams of people who work different shifts, hours, or days; Include people with mobility limitations or disabilities; Include people with mobility limitations or disabilities; Move forward with projects that would have been held or canceled due to travel expenses; and Move forward with projects that would have been held or canceled due to travel expenses; and Save the expense of offices and all the physical equipment needed for employees. Save the expense of offices and all the physical equipment needed for employees.
Exam 9 | #46. _____ outlines and guides the selection of resources and assigns them to their respective activities. |  | Plan Resources | Acquire Resources | Develop team | Manage team | Answer option b. | Answer option b. “Acquire Resources”. Acquire Resources is the process of obtaining team members, facilities, equipment, materials, supplies, and other resources necessary to complete project work. Answer option b. “Acquire Resources”. Acquire Resources is the process of obtaining team members, facilities, equipment, materials, supplies, and other resources necessary to complete project work.
Exam 9 | #47. Which category of contracts involves setting a fixed total price for a defined product or project? |  | Time and material | Fixed price | Cost plus fixed fee | Cost plus incentive fee | Answer option b. | Answer option b. “Fixed-price” involves setting a fixed total price for a defined product. Answer option b. “Fixed-price” involves setting a fixed total price for a defined product.
Exam 9 | #48. Rachel, the Agile Project Manager, has created an Agile Team Charter for a new Software Development Project. What is NOT usually a part of Agile Team Charter? |  | Core Hours for the Development Team to work on project activities. | Ground rules for acceptable behavior in meetings. | Performance Index indicators (SPI, CPI) for the project. | Definition of Done to allow the team to determine what work is actually complete. | Answer option c. | Performance Index indicators are Earned Value Management metrics used in Waterfall project lifecycles.
Exam 9 | #49. As a Project Manager, you need to manage the stakeholders in your project. Which of the following descriptions may contain people not considered as stakeholders? |  | They are individuals and organizations involved in the project. | They are individuals and organizations that are in favor of the project. | They are individuals and organizations that get affected by the project. | They are individuals and organizations that provide finance to the project. | Answer option b. | Answer option b. They are individuals and organizations that support the project are stakeholders: Generically, a stakeholder is defined as ‘an individual, group, organization, who may affect, be affected by, or perceive itself to be affected by a decision, activity or outcome of a project. Answers a, c, and d clearly meet that definition. Answer b limits itself to supporters of the project but, both supporters or detractors can and should be considered stakeholders. Answer option b. They are individuals and organizations that support the project are stakeholders: Generically, a stakeholder is defined as ‘an individual, group, organization, who may affect, be affected by, or perceive itself to be affected by a decision, activity or outcome of a project. Answers a, c, and d clearly meet that definition. Answer b limits itself to supporters of the project but, both supporters or detractors can and should be considered stakeholders .
Exam 9 | #50. While performing the close project process, you are evaluating how the estimation of duration, cost, resources, and cost control was compared to the actual results. Which input would you need to review? |  | Assumption log | Basis of estimates | Cost, durations and resources estimates | Project baselines | Answer option b. | Answer option b. “Basis of estimates” indicates how the various estimates were derived and can be used to make a decision on how to respond to variances. Answer option b. “Basis of estimates” indicates how the various estimates were derived and can be used to make a decision on how to respond to variances.
Exam 9 | #51. Brian is in the middle of managing an agile project and realizes that too much upfront work leads to rework. This situation creates problems because his team is not delivering the required value in each iteration. What would be a possible course of action to fix the problem? |  | To measure the WIP during the beginning of the project and see the team's options to deliver value instead of designs. | Pace the rate at which work is delivered. | Organize user stories development by order of importance. | All of the above. | Answer option a. | By doing this and shortening iterations and creating a robust definition of done, we can prevent delivering too much upfront work.
Exam 9 | #52. A skilled project manager can capitalize on the strengths of all team members. All of the following are interpersonal skills that a project manager uses EXCEPT: |  | Leadership | Influencing | Socializing | Effective decision making | Answer option c. | Answer option c. Examples of interpersonal skills that a project manager uses most often include: Answer option c. Examples of interpersonal skills that a project manager uses most often include: Leadership Influencing Effective decision making Leadership Leadership Influencing Influencing Effective decision making Effective decision making
Exam 9 | #53. _____ records the team members and their roles and responsibilities for the project. |  | Resource calendars | Physical resource assignments | Project team assignments | Both B and C | Answer option c. | Answer option c. “Project team assignments” Answer option c. “Project team assignments”
Exam 9 | #54. The Cost Baseline is an output of _____ Cost Management process. |  | Estimate Costs | Estimate Activity Durations | Determine Budget | Plan Cost Management | Answer option c. | Determine Budget: The Determine Budget process aggregates the estimated costs of individual activities and/or work packages to establish an authorized cost baseline. Estimate Costs looks at individual work packages and activities, Determine Budget puts them together. Estimate duration is concerned with time, how long it will take to perform the work required to produce the deliverable; its Output are inputs to creating the schedule. Control Schedule is a M&C process that compares actual to the baseline to determine variances.
Exam 9 | #55. Brandon is an Agile Project Manager working with a newly developed Agile team. The Functional Manager is uncertain on the differences between Scrum and Agile methodologies. What should Brandon’s response be to the Functional Manager? |  | Kanban requires a project plan. | There are no WIP limits in Kanban. | Kanban teams employ a “pull” system. | Kanban teams plan their work in iterations (Sprints). | Answer option c. | Kanban employs a pull system, meaning when work is completed, it triggers someone to “pull” the next item in the queue onto the (Kanban) board to begin execution on that item. Kanban also sets “work in progress” (WIP) limits on how much work the team can have in place.
Exam 9 | #56. Rahul is the Scrum Master working for Company XYZ, a technology company new to Agile approaches. A senior executive is confused on the difference between a Sprint Review and Sprint Retrospective. What will be Rahul’s response? |  | Sprint Reviews are used to provide demonstrations of the product created by the team. Sprint Retrospectives are to discuss lessons learned. | Sprint Reviews demonstrate work completed in the Sprint (iteration). Sprint Retrospectives look at all work completed in the project. | Sprint Reviews are to discuss lessons learned. Sprint Retrospectives are used to provide demonstrations of the product created by the team. | Both meetings discuss the same topics and can be interchanged for each Sprint (iteration). | Answer option a. | Sprint Reviews are used to provide demonstrations of the product created by the team. Sprint Retrospectives are to discuss lessons learned.
Exam 9 | #57. Jerry, a Project Manager is managing a software implementation using a hybrid Waterfall and Agile lifecycle. During the sprint (iteration). The team encounters a technical issue that becomes an impediment to complete the next stories. What should Jerry do? |  | Ask a technical manager or Architect to determine a solution to the problem. | Work with the Technical Manager and Development Team to identify a solution. | Ask the Scrum Master to identify a solution. | Create a communication channel with the Senior Management Team to explore a possible solution. | Answer option b. | The Project Manager should serve as a Servant Leader, facilitating collaboration with the project team. On this Hybrid project, the Project Manager will want to facilitate discussions between the Technical Manager and Development Team to identify solutions and remove any impediments.
Exam 9 | #58. Sara is an Agile Project Manager working within an Agile PMO using an approved contractor to track the implementation of cloud-based software for her project. She, as the Procurement overseer, conducts a structured review of the work performed by the contractor. Which technique does this describe? |  | Payment System | Inspection | Contract Change Control | Grooming | Answer option b. | Inspection may involve a review of the work performed by the contractor. It is a structured process to ensure a mutual understanding between two parties on the work in progress.
Exam 9 | #59. Which of the following about organizational project management and organizational strategies is true? |  | Project management harmonizes its projects components and controls interdependencies | Portfolio management aligns with organizational strategies by selecting the right programs or projects | Portfolio management harmonizes its programs components and controls interdependencies | Portfolio management enables the achievement of organizational goals and objectives | Answer option b. | “Project management harmonizes its project components and controls interdependencies” (Answer option a.) and “Portfolio management harmonizes its program components and controls interdependencies” (Answer option c.) are descriptions of program management, not project management or portfolio management. “Portfolio management enables the achievement of organizational goals and objectives” (Answer option d.) is a description of project management, not Portfolio management. The best Answer is “Portfolio management aligns with organizational strategies by selecting the right programs or projects” (Answer option b.)
Exam 9 | #60. A project team is still in the "forming" stage. Which of the following characteristics would the team exhibit? |  | Members tend to be independent and not as open | Members are not collaborative or open to differing ideas and perspectives | The environment can become counterproductive | Both B and C | Answer option a. | Answer option a. “Members tend to be independent and not as open”. One of the models used to describe team development is the Tuckman ladder, which includes five stages of development that teams may go through. Although it is common for these stages to occur in order, it is not uncommon for a team to get stuck in a particular stage or regress to an earlier stage. Projects with team members who worked together in the past might skip a stage. Answer option a. “Members tend to be independent and not as open”. One of the models used to describe team development is the Tuckman ladder, which includes five stages of development that teams may go through. Although it is common for these stages to occur in order, it is not uncommon for a team to get stuck in a particular stage or regress to an earlier stage. Projects with team members who worked together in the past might skip a stage. Forming. This phase is where the team members meet and learn about the project and their formal roles and responsibilities. Team members tend to be independent and not as open in this phase. Storming. During this phase, the team begins to address the project work, technical decisions, and the project management approach. If team members are not collaborative or open to differing ideas and perspectives, the environment can become counterproductive. Norming. In this phase, team members begin to work together and adjust their work habits and behaviors to support the team. The team members learn to trust each other. Performing. Teams that reach the performing stage function as a well-organized unit. They are interdependent and work through issues smoothly and effectively. Forming. This phase is where the team members meet and learn about the project and their formal roles and responsibilities. Team members tend to be independent and not as open in this phase. Forming. This phase is where the team members meet and learn about the project and their formal roles and responsibilities. Team members tend to be independent and not as open in this phase. Storming. During this phase, the team begins to address the project work, technical decisions, and the project management approach. If team members are not collaborative or open to differing ideas and perspectives, the environment can become counterproductive. Storming. During this phase, the team begins to address the project work, technical decisions, and the project management approach. If team members are not collaborative or open to differing ideas and perspectives, the environment can become counterproductive. Norming. In this phase, team members begin to work together and adjust their work habits and behaviors to support the team. The team members learn to trust each other. Norming. In this phase, team members begin to work together and adjust their work habits and behaviors to support the team. The team members learn to trust each other. Performing. Teams that reach the performing stage function as a well-organized unit. They are interdependent and work through issues smoothly and effectively. Performing. Teams that reach the performing stage function as a well-organized unit. They are interdependent and work through issues smoothly and effectively. • Adjourning. In this phase, the team completes the work and moves on from the project. This typically occurs when staff is released from the project as deliverables are completed or as part of the Close Project or Phase process. • Adjourning. In this phase, the team completes the work and moves on from the project. This typically occurs when staff is released from the project as deliverables are completed or as part of the Close Project or Phase process.
Exam 9 | #61. Before Bill can start planning the details of an agile project in a logistics operator company SupplyTech, he begins to assess the company’s readiness to accept change. Bill proceeds in conducting an assessment, and concludes that the company is prepared for acceptable levels of change because of the following reasons EXCEPT: |  | The organization is willing to shift how it views, reviews, and assesses employees. | The organization focuses on short-term budgeting and metrics versus long-term goals. | The organization manages its talent and capabilities with a mature approach. | The organization's leaders are not always willing to change. | Answer option d. | Quality must be planned in and not inspected. This principle holds for all project management approaches. By using error-proofing methods, projects can be tailored to address quality issues.
Exam 9 | #62. Chris, an experienced Project Manager, has completed many Predictive style projects. Recently, he has been assigned to deliver a new text-to-speech software for a media and entertainment company VideoNow. Traditionally, Chris collects requirements in the planning process under the predictive approach of project management. However, he soon realizes that he will need to have a new strategy because of the high degree of change that this project will be going through. What would Chris do in this case? |  | Collect requirements at the beginning of the project and review them constantly. | Build a complete project plan | Try to keep change at a minimum to avoid higher risks. | Due to a high level of risk, implement an Agile approach – Establish recurring interactions with the customers. | Answer option d. | Regular interactions with the stakeholder community throughout the project mitigate risk, build trust, and support adjustments earlier in the project cycle, thus reducing costs and increasing the likelihood of success.
Exam 9 | #63. In the Control Costs process, changes to the project costs can result in change requests to the _______. |  | Cost baseline and/or other components of the project management plan | Components of the project management plan | Cost baseline | Cost forecasts | Answer option a. | Analysis of project performance may result in a change request to the cost baseline or other components of the project management plan.
Exam 9 | #64. When should a project manager perform the Control Procurements process? |  | At the beginning of the project | At the end of each phase | At the end of the project | Throughout the project as needed | Answer option d. | Answer option d. “Throughout the project as needed”. Project deliverables, interim milestones, and completed work might trigger the need to perform the control procurements process. Answer option d. “Throughout the project as needed”. Project deliverables, interim milestones, and completed work might trigger the need to perform the control procurements process.
Exam 9 | #65. _____ extend(s) the description of the activity by identifying multiple components associated with each activity. |  | WBS dictionary | Activity attributes | WBS | Activity list | Answer option b. | Answer option b. “Activity attributes” contains details about activities and its description. Answer option b. “Activity attributes” contains details about activities and its description.
Exam 9 | #66. Which of the following is an example of an intangible business value? |  | Fixtures | Market Share | Brand Recognition | None of the Above | Answer option c. | Answer option c. “Brand Recognition”. This is not a value that can be monetized easily. Answer option c. “Brand Recognition”. This is not a value that can be monetized easily.
Exam 9 | #67. _____ contains information communicated to risk owners and other affected stakeholders. |  | Stakeholder register | Risk report | Risk register | Issue log | Answer option b. | Answer option b. “Risk report”. A project document developed progressively throughout the Project Risk Management processes, which summarizes information on individual project risks and the level of overall project risk. Answer option b. “Risk report”. A project document developed progressively throughout the Project Risk Management processes, which summarizes information on individual project risks and the level of overall project risk.
Exam 9 | #68. _____ help(s) in managing the control quality activities in a structured manner. |  | Checklists | Check sheets | Statistical sampling | Both A and B | Answer option a. | Answer option a. “Checklists” Answer option a. “Checklists”
Exam 9 | #69. Which is not an input for the Conduct Procurements process? |  | Scope management plan | Project schedule | Procurement documentation | Bidder conferences | Answer option d. | “Scope management plan” (Answer option a), “Project schedule” (Answer option b.) and “Procurement documentation” (Answer option c.) are input for the process while “Bidder conferences” (Answer option d.) is a technique.
Exam 9 | #70. Paul is assessing the progress of the current sprint, and realizes the project has an SPI of 1.1 and a CPI of 1.06. What does this mean for his project? |  | An SPI > 1 means that we completed fewer features than planned, so we need to review why this is happening. And a CPI > 1 means that earned value outperforms actual costs. | An SPI > 1 means that we completed more features than planned, so we need to review why this is happening. And a CPI > 1 means that earned value outperforms actual costs. | An SPI > 1 means that we completed more features than planned, so we need to review why this is happening. And a CPI > 1 means that actual costs outperform earned value. | An SPI > 1 means that we completed fewer features than planned, so we need to review why this is happening. And a CPI > 1 means that actual costs outperform earned value. | Answer option b. | Completing more features than the plan is not something we would expect because we have clarity on how many features need to be developed in a single sprint. On the other hand, we can always be over, on, or under budget, so a CPI > 1 is possible.
Exam 9 | #71. Collectively, the project phases are known as ______. |  | Project Slack | Float | Project Life Cycle | Implementation time | Answer option c. | Answer option c. Project Life Cycle: Taken together – or “collectively” – all of the project phases are known as the Project Life Cycle. Answer options a., b., and d. should have been eliminated easily. Project Slack and Float are both Critical Path Method concepts narrowly defined as the amount of time for which an activity or the project itself may slip or be delayed without serious detrimental consequences. Implementation Time, one might reasonably guess, is the time required to complete all activities within the Implementation phase of the Project Life Cycle. Answer option c. Project Life Cycle: Taken together – or “collectively” – all of the project phases are known as the Project Life Cycle. Answer options a., b., and d. should have been eliminated easily. Project Slack and Float are both Critical Path Method concepts narrowly defined as the amount of time for which an activity or the project itself may slip or be delayed without serious detrimental consequences. Implementation Time, one might reasonably guess, is the time required to complete all activities within the Implementation phase of the Project Life Cycle .
Exam 9 | #72. Which of the following is an output for the validate scope process? |  | Accepted deliverables Techniques | Quality reports | Verified deliverables | Work performance data | Answer option a. | Answer option a. “Accepted deliverables” Answer option a. “Accepted deliverables”
Exam 9 | #73. _____ is a group of logically related project activities that culminates in the completion of one or more deliverables. |  | Project phase | Phase gate | Project life cycle | Project Management Process Group | Answer option a. . “ “ | Answer option a. “Phase gate” (Answer option b.) is a review at the end of a phase in which a decision is made to continue to the next phase, to continue with modification or to end a program or project. “Project life cycle” (Answer option c.) is the series of phases that a project passes through from its start to its completion. “Project Management Process Group” (Answer option d.) is a logical grouping of project management inputs, tools and techniques, and outputs. The best Answer is “Project phase” (Answer option a.) Answer option a. “Phase gate” (Answer option b.) is a review at the end of a phase in which a decision is made to continue to the next phase, to continue with modification or to end a program or project . “ Project life cycle” (Answer option c.) is the series of phases that a project passes through from its start to its completion. “ Project Management Process Group” (Answer option d.) is a logical grouping of project management inputs, tools and techniques, and outputs. The best Answer is “Project phase” (Answer option a.)
Exam 9 | #74. When you are a buyer, you should pay attention to all of the following in Control Procurements process EXCEPT: |  | Ensure that the seller’s performance meets the procurement requirements. | Monitoring payments to the seller. | Reviewing and documenting how well the seller is performing based on the contract. | Performing regular procurement audits. | Answer option d. | Answer option d. Control Procurements is the process of managing procurement relationships, monitoring contract performance, and making changes and corrections to contracts as appropriate. The key benefit of this process is that it ensures that both the seller’s and buyer’s performance meet procurement requirements according to the terms of the legal agreement. Both the buyer and the seller will administer the procurement contract for similar purposes. Each is required to ensure that both parties meet their contractual obligations and that their own legal rights are protected. Control Procurements also has a financial management component that involves monitoring payments to the seller. Answer option d. Control Procurements is the process of managing procurement relationships, monitoring contract performance, and making changes and corrections to contracts as appropriate. The key benefit of this process is that it ensures that both the seller’s and buyer’s performance meet procurement requirements according to the terms of the legal agreement. Both the buyer and the seller will administer the procurement contract for similar purposes. Each is required to ensure that both parties meet their contractual obligations and that their own legal rights are protected. Control Procurements also has a financial management component that involves monitoring payments to the seller. Procurement audits are one of the tools & techniques used in the Control Procurements process. Procurement audits are one of the tools & techniques used in the Control Procurements process .
Exam 9 | #75. In your project, you use the hierarchical representation of resources by category and type. This is an example of: |  | Project Chart | Organization Chart | Work Breakdown Structure | Resource Breakdown Structure | Answer option d. | The resource breakdown structure is a hierarchical representation of resources by category and type.
Exam 9 | #76. _____ is the authorized budget assigned to scheduled work. |  | Planned value (PV) | Earned value (EV) | Actual cost (AC) | Budget At completion (BAC) | Answer option a. | Answer option a. “Planned value (PV)”. Answer option a. “Planned value (PV)”.
Exam 9 | #77. Which of the following is not an input for the validate scope process? |  | Scope baseline | Quality reports | Deliverables | Work performance data | Answer option c. | Answer option c. “Deliverables” Answer option c. “Deliverables”
Exam 9 | #78. _____ describes the communications that are needed for the management of team or physical resources. |  | Resource management plan | Communications management plan | Stakeholder engagement plan | Stakeholder register | Answer option a. | Answer option a. “Resource management plan”. Answer option a. “Resource management plan”.
Exam 9 | #79. You know that making scope definition early is critical in a project. Because the cost impact of a scope change is _______. |  | Greatest in the middle of the project | Greatest at the early stages of the project | Greatest at the end of the project | Changing due to environmental factors | Answer option c. | The cost impact of the changes is the greatest towards the end of the project because the changes might cause cost increase or schedule delays. It is important to define the scope early in order to have a detailed plan of execution of the scope.
Exam 9 | #80. Which of the following is a phased budget used to measure and monitor cost performance? |  | Cost Baseline | Cost Management Plan | EAC | Chart of Accounts | Answer option a. | Cost Baseline: In the question, the keywords are “a phased budget.” Only Answer option a., “Cost Baseline,” is synonymous with “a phased budget.” Although “EAC” is a close second, Cost Baseline meets the PMBOK definition and is by far the better Answer.
Exam 9 | #81. _____ involves information exchange between individuals, typically face-to-face. |  | Pull communication | Push communication | Mass communication | Interpersonal communication | Answer option d. | Answer option d. “Interpersonal communication” Answer option d. “Interpersonal communication”
Exam 9 | #82. Bill is a Project Manager managing an Agile Project. How can the Bill ensure that the work flows smoothly through the team, with tasks assigned are performed correctly? |  | Conduct Sprint Retrospective Meeting at the end of each Sprint (iteration). | Ensure the Product Owner attends all daily standups. | Assign more resources to increase capacity. | Extend the duration of each Sprint (iteration). | Answer option a. | Retrospectives are used to correct processes and improve team processes and collaboration, held at the end of each Sprint (iteration).
Exam 9 | #83. Hillary is the Scrum Master for a renowned multinational company XYZ. Working within the company’s headquarters, Hiillary’s project team is in the middle of developing a new application for the company's customers. The team is about to complete the first sprint, and realize they are only able to complete 32 of the 40 story points accepted within the Sprint. What is the Schedule Performance Index (SPI) for this iteration? |  | We cannot calculate SPI because we deliver an agile project, not a waterfall one. | The concept of earned value does not apply to agile projects. | Since completed features and planned features are comparable, the SPI value is SPI=32/40=0.8, which means the team is working at 80% of the planned rate. | SPI can only be estimated for a whole project, not an individual sprint. | Answer option c. | Answer option c. Earned value for each sprint translates to completed features, and planned value translates to planned features. Then, we can use the formula: Answer option c. Earned value for each sprint translates to completed features, and planned value translates to planned features. Then, we can use the formula: SPI=Completed Features/Planned Features SPI= Completed Features/ Planned Features This formula allows us to translate SPI from a predictive to an agile approach quickly. This formula allows us to translate SPI from a predictive to an agile approach quickly.
Exam 9 | #84. You are the project manager of a social responsibility project in your city. An anticipated risk has just occurred in the project, and you started to implement the risk response plan associated with the risk. You are performing the _______ process. |  | Monitor Risks | Identify Risks | Plan Risk Responses | Perform Quantitative Risk Analysis | Answer option a. | Monitor Risks is the process of implementing risk response plans, tracking identified risks, monitoring residual risks, identifying new risks, and evaluating risk process effectiveness throughout the project.
Exam 9 | #85. Michael is an Agile Project Manager managing a software implementation project. The Sponsor asks the Project Manager to provide a high-level timeline of the release. What should Michael do? |  | Conduct a well-facilitated release planning meeting. | Perform risk analysis on the project. | Ask the Sponsor to provide this information. | Discuss the high-level summary in the next daily standup. | Answer option a. | Release planning is held at the beginning of each Sprint (iteration) providing a high-level summary timeline of the release schedule typically ranging between 6-12 months.
Exam 9 | #86. Time to do it right is an example of _____ . |  | Prevention Costs | Internal Failure Costs | Appraisal Costs | External Failure Costs | Answer option a. | Answer option a. “Prevention Costs”. Prevention Costs include (Build a quality product) Answer option a. “Prevention Costs”. Prevention Costs include (Build a quality product) Training Document processes Equipment Time to do it right Training Training Document processes Document processes Equipment Equipment Time to do it right Time to do it right
Exam 9 | #87. Sam is preparing a presentation of the project’s results to demonstrate its compliance with the project scope. Which document can assist him in achieving this objective? |  | Requirements documentation | Quality report | Quality control measurements | Requirements traceability matrix | Answer option a. | Answer option a. “Requirements documentation” is used to demonstrate compliance with the project scope. Answer option a. “Requirements documentation” is used to demonstrate compliance with the project scope.
Exam 9 | #88. You are the project manager of an automobile manufacturing project. To reduce the risk of “exceeding stop limit” thresholds, you decided to outsource the braking system of your automobile project to a well-known braking system producer in the industry. This risk response strategy is an example of: |  | Avoid | Mitigate | Transfer | Accept | Answer option b. | Answer option b. Risk mitigation is a risk response strategy whereby the project team acts to reduce the probability of occurrence or impact of a risk. Adopting less complex processes, conducting more tests, or choosing a more stable supplier are examples of mitigation actions. Answer option b. Risk mitigation is a risk response strategy whereby the project team acts to reduce the probability of occurrence or impact of a risk. Adopting less complex processes, conducting more tests, or choosing a more stable supplier are examples of mitigation actions. In this case, the risk of exceeding braking limit thresholds is mitigated by choosing a more stable supplier in braking systems In this case, the risk of exceeding braking limit thresholds is mitigated by choosing a more stable supplier in braking systems
Exam 9 | #89. The activity “Ship Container” in your network diagram has an early start of day 17, a late start of day 22, and a late finish of day 37. What is the activity duration? |  | 15 days | 16 days | 59 days | 14 days | Answer option b. | 16 days: The Critical Path Method is a key Tool/Technique in the Develop Schedule process. Activity Duration is always the positive difference between the Early Start date and the Early Finish date minus 1 or the Late Start date and Late Finish date plus 1. In this problem, the scenario provides the Late Start date – day 22 – and the Late Finish date – day 37. Therefore, 37 – 22 = 15 1 = 16, Answer option b.
Exam 9 | #90. In your new project, you have to provide a critical deliverable within five months, and you do not have time to go through the Conduct Procurements process. You decide to sign a contract with a supplier with whom your company has done some work in the past. The risk you are accepting in this situation is: |  | The ability of the supplier to deliver the goods | Collusion between the supplier and your team | Lack of proper scope definition | Lack of a legally binding agreement | Answer option a. | The ability of the supplier to deliver the goods: In taking multiple-choice tests, it should always be a rule of thumb to stick to the facts presented in the scenario and avoid making assumptions that are not supported by the facts, unless absolutely necessary. To say that this is collusion or lack of proper scope is to make assumptions: there is nothing in the scenario that would support such claims. Answer options b. and c, may be taken out of consideration. Option c. is also incorrect because there is a legally binding agreement: the scenario clearly states there is “a contract with the supplier.” This leaves only option a. as a viable choice. “The ability of the supplier to deliver the goods” is always a risk, anyway – even if you are dealing “with a supplier with whom your company has done some work in the past.
Exam 9 | #91. Brian is shaping an agile project for a technological enterprise CyberNet. The team is feeling uncertain about the direction of the project because no one seems responsible for guiding the direction of the product. Also, there is no clarity on how work is ranked based on its business value. What is the role that needs to be strengthened to solve these problems? |  | Scrum Master role. | Developer role. | Product Owner role. | Sponsor role. | Answer option c. | The product owner works with stakeholders, customers, and teams to define the product direction. Typically, product owners have a business background and bring deep subject matter expertise to the decisions.
Exam 9 | #92. Which of the following is an input for the close project process? |  | Verified deliverables | Validated deliverables | Accepted deliverables | Tested deliverables | Answer option c. | Answer option c. “Accepted deliverables”. Answer option c. “Accepted deliverables”.
Exam 9 | #93. Your project team identified a high-priority opportunity for your project. Your company lacks the required resources to perform the required actions to seize the opportunity. Which risk response strategy would you follow? |  | Escalate | Transfer | Share | Enhance | Answer option c. | Answer option c. ”Share”. Payment of a risk premium to the party taking on the opportunity. Answer option c. ”Share”. Payment of a risk premium to the party taking on the opportunity.
Exam 9 | #94. Which of the following is (sometimes) a disadvantage of Fixed Price contracts? |  | Less work for the buyer to manage | The seller has a strong incentive to control costs | The buyer knows the total price at the start of a project | Final costs may be more than the final cost on a Cost Reimbursable contract because Sellers often inflate their prices to cover their risk | Answer option d. | Answer option d. “Final costs may be more than the final cost on a Cost Reimbursable contract because Sellers often inflate their prices to cover their risk”. Fixed Cost Contracts rely heavily on both the buyer’s and the seller’s technical and cost expertise in the product service or result to be purchased. The seller must include his profit margin at the outset and the buyer’s risk is minimized in that he knows the total (fixed) price going in. Answers a., b., and c. are clear advantages to either the Buyer or the Seller. Answer option d. “ Final costs may be more than the final cost on a Cost Reimbursable contract because Sellers often inflate their prices to cover their risk”. Fixed Cost Contracts rely heavily on both the buyer’s and the seller’s technical and cost expertise in the product service or result to be purchased. The seller must include his profit margin at the outset and the buyer’s risk is minimized in that he knows the total (fixed) price going in. Answers a., b., and c. are clear advantages to either the Buyer or the Seller.
Exam 9 | #95. For Project Procurement management processes, changing contracting processes is an example of _____ . |  | Emerging practice | Consideration for tailoring | Enterprise environmental factor | Organizational process asset | Answer option a. | Answer option a. “Emerging practice”. Answer option a. “Emerging practice”.
Exam 9 | #96. As the project progresses, the cost of change is expected to ______ . |  | Reduce | Increase | Increase and later reduce | Has no effect | Answer option b. | Answer option b. “Increase”. The impact of Variables Based on Project Time, shows clearly that the Cost of Changes are typically expected to rise as work progresses from the start to the finish of the Project Life Cycle. Answer option b. “Increase”. The impact of Variables Based on Project Time, shows clearly that the Cost of Changes are typically expected to rise as work progresses from the start to the finish of the Project Life Cycle.
Exam 9 | #97. _____ is used to compare requirements to the actual results to determine if a change, corrective action or preventive action is necessary. |  | Requirements documentation | The requirements traceability matrix | The requirements management plan | The scope baseline | Answer option a. | Answer option a. “Requirements documentation”. A description of how individual requirements meet the business need for the project. Answer option a. “Requirements documentation”. A description of how individual requirements meet the business need for the project.
Exam 9 | #98. Requirements can be grouped into classifications allowing for further refinement and detail as the requirements are elaborated. These classifications may not include: |  | Solution Requirements | Business Requirements | Transition Requirements | Project Phase Requirements | Answer option d. | Answer option d. “Project Phase Requirements”. Requirements can be grouped into classifications allowing for further refinement and detail as the requirements are elaborated. These classifications include: Answer option d. “Project Phase Requirements”. Requirements can be grouped into classifications allowing for further refinement and detail as the requirements are elaborated. These classifications include: Business requirements. These describe the higher-level needs of the organization as a whole, such as business issues or opportunities, and reasons why a project has been undertaken. Stakeholder requirements. These describe needs of a stakeholder or stakeholder group. Solution requirements. These describe features, functions, and characteristics of the product, service, or result that will meet the business and stakeholder requirements. Solution requirements are further grouped into functional and nonfunctional requirements: Functional requirements. Functional requirements describe the behaviors of the product. Examples include actions, processes, data, and interactions that the product should execute. Nonfunctional requirements. Nonfunctional requirements supplement functional requirements and describe the environmental conditions or qualities required for the product to be effective. Examples include: reliability, security, performance, safety, level of service, supportability, retention/purge, etc. Transition and readiness requirements. These describe temporary capabilities, such as data conversion and training requirements, needed to transition from the current as-is state to the desired future state. Project requirements. These describe the actions, processes, or other conditions the project needs to meet. Examples include milestone dates, contractual obligations, constraints, etc. Quality requirements. These capture any condition or criteria needed to validate the successful completion of a project deliverable or fulfillment of other project requirements. Examples include tests, certifications, validations, etc. Business requirements. These describe the higher-level needs of the organization as a whole, such as business issues or opportunities, and reasons why a project has been undertaken. Business requirements. These describe the higher-level needs of the organization as a whole, such as business issues or opportunities, and reasons why a project has been undertaken. Stakeholder requirements. These describe needs of a stakeholder or stakeholder group. Stakeholder requirements. These describe needs of a stakeholder or stakeholder group. Solution requirements. These describe features, functions, and characteristics of the product, service, or result that will meet the business and stakeholder requirements. Solution requirements are further grouped into functional and nonfunctional requirements: Solution requirements. These describe features, functions, and characteristics of the product, service, or result that will meet the business and stakeholder requirements. Solution requirements are further grouped into functional and nonfunctional requirements: Functional requirements. Functional requirements describe the behaviors of the product. Examples include actions, processes, data, and interactions that the product should execute. Nonfunctional requirements. Nonfunctional requirements supplement functional requirements and describe the environmental conditions or qualities required for the product to be effective. Examples include: reliability, security, performance, safety, level of service, supportability, retention/purge, etc. Functional requirements. Functional requirements describe the behaviors of the product. Examples include actions, processes, data, and interactions that the product should execute. Functional requirements. Functional requirements describe the behaviors of the product. Examples include actions, processes, data, and interactions that the product should execute. Nonfunctional requirements. Nonfunctional requirements supplement functional requirements and describe the environmental conditions or qualities required for the product to be effective. Examples include: reliability, security, performance, safety, level of service, supportability, retention/purge, etc. Nonfunctional requirements. Nonfunctional requirements supplement functional requirements and describe the environmental conditions or qualities required for the product to be effective. Examples include: reliability, security, performance, safety, level of service, supportability, retention/purge, etc. Transition and readiness requirements. These describe temporary capabilities, such as data conversion and training requirements, needed to transition from the current as-is state to the desired future state. Transition and readiness requirements. These describe temporary capabilities, such as data conversion and training requirements, needed to transition from the current as-is state to the desired future state. Project requirements. These describe the actions, processes, or other conditions the project needs to meet. Examples include milestone dates, contractual obligations, constraints, etc. Project requirements. These describe the actions, processes, or other conditions the project needs to meet. Examples include milestone dates, contractual obligations, constraints, etc. Quality requirements. These capture any condition or criteria needed to validate the successful completion of a project deliverable or fulfillment of other project requirements. Examples include tests, certifications, validations, etc. Quality requirements. These capture any condition or criteria needed to validate the successful completion of a project deliverable or fulfillment of other project requirements. Examples include tests, certifications, validations, etc.
Exam 9 | #99. Michael, the Agile Project Manager, just started a new job in a global corporation, and he needs to manage change for the new agile projects he is assigned to develop. In the beginning, Michael is uncertain on the proper approach to implement and manage project changes. To gain a better understanding on Agile projects, Michael can: |  | Let the spirit of change go with the flow and manage each situation on a case-by-case basis. | Use Kanban boards to track progress, showing the new approaches already in use as "done," those under evaluation as "in progress," and those still waiting to be introduced as "to do." | Assess the organizational culture before trying to manage change. | Analyze the stakeholders to determine their expectations concerning agile project management. | Answer option b. | Answer option b. Using these tools to organize and manage the change implementation provides visibility into progress and models the implemented approaches. Rolling out changes transparently and appealingly improves the likelihood of their success. Answer option b. Using these tools to organize and manage the change implementation provides visibility into progress and models the implemented approaches. Rolling out changes transparently and appealingly improves the likelihood of their success.
Exam 9 | #100. _____ is the expected cost to finish all the remaining project work. |  | EAC | ETC | VAC | BAC | Answer option b. | Answer option b. “ETC”. Estimate to Complete (ETC) is the expected cost to finish all the remaining project work. Answer option b. “ETC”. Estimate to Complete (ETC) is the expected cost to finish all the remaining project work.
Exam 9 | #101. Trademarks, strategic alignment, and reputation are examples of_____ . |  | Project Initiation Context factors | Intangible elements | Tangible elements | Driver for change | Answer option b. “ | Answer option b. “Examples of intangible elements” Answer option b. “ Examples of intangible elements”
Exam 9 | #102. Which of the following is not an output of the Manage Quality process? |  | Quality reports | Test and evaluation documents | Verified deliverables | Change requests | Answer option c. | Answer option c. “Quality reports” (Answer option a.), “Test and evaluation documents” (Answer option b.) and “Change requests” (Answer option d.) are outputs of Manage Quality process. The best Answer is” Verified deliverables” (Answer option c.) is an output of control Quality. Answer option c. “Quality reports” ( Answer option a. ), “Test and evaluation documents” ( Answer option b. ) and “Change requests” ( Answer option d. ) are outputs of Manage Quality process. The best Answer is” Verified deliverables” ( Answer option c. ) is an output of control Quality.
Exam 9 | #103. People outside the immediate project team may own some risk response actions in the projects. Which interpersonal skills can help the project manager to encourage the risk owners to take necessary actions? |  | Facilitation | Influencing | Negotiation | Conflict management | Answer option b. | Influencing. Some risk response actions may be owned by people outside the immediate project team or who have other competing demands. The project manager or person responsible for facilitating the risk process may need to exercise influencing to encourage nominated risk owners to take necessary action where required.
Exam 9 | #104. An Agile team is experiencing unusual delays. These delays seem unexpected as they have a realistic plan reflected in the product backlog. What could one do to manage these delays and put the project back on track? |  | Eliminate user stories and pass them on to the next iteration. | Use kanban boards to see the flow of work and work in progress limits to understand the impact of the demands on the team or product. | Track and remove impediments reflected on an impediment board. | Both b and c. | Answer option d. | Making visual assessments of how work is flowing and what impediments you may be experiencing will allow you to put the project back on track as team members will know where things are going wrong and what actions they need to take.
Exam 9 | #105. A project manager of an IT project is working on the “Develop team” process. Among the outputs of the process, which of the following enterprise environmental factors updates should he expect? |  | Skill assessments | Reduced staff turnover rate | Training requirements | Personnel assessment | Answer option a. | Answer option a. “Skill assessments”. “Reduced staff turnover rate” (Answer option b.) is an indicator for a team’s effectiveness. “Training requirements” (Answer option c.) and “Personnel assessment” (Answer option d.) are Organizational process assets updates. Answer option a. “Skill assessments”. “Reduced staff turnover rate” ( Answer option b. ) is an indicator for a team’s effectiveness. “Training requirements” ( Answer option c. ) and “Personnel assessment” ( Answer option d. ) are Organizational process assets updates.
Exam 9 | #106. _____ is the amount of time a successor activity will be delayed with respect to a predecessor activity. |  | Activity duration | Lead | Lag | Milestone | Answer option c. | Answer option c. “Lag”. The amount of time whereby a successor activity will be delayed with respect to a predecessor activity. Answer option c. “Lag”. The amount of time whereby a successor activity will be delayed with respect to a predecessor activity.
Exam 9 | #107. Value analysis and value engineering are examples of _____ . |  | Problem solving | Process analysis | Product analysis | Context diagramming | Answer option c. | Answer option c. “Product analysis” Answer option c. “Product analysis”
Exam 9 | #108. Which is a factor that influences the selection of conflict resolution methods? |  | Motivation to resolve conflict on a long-term or short-term basis | Time pressure for resolving the conflict | Management requirements | Both A and B | Answer option d. | Answer option d. “Motivation to resolve conflict on a long-term or short-term basis” (Answer option a.) and “Time pressure for resolving the conflict” (Answer option b.) are factors that influence the selection of conflict resolution methods. The best Answer is “Both A and B” (Answer option d.). Answer option d. “Motivation to resolve conflict on a long-term or short-term basis” (Answer option a.) and “Time pressure for resolving the conflict” (Answer option b.) are factors that influence the selection of conflict resolution methods. The best Answer is “Both A and B” (Answer option d.).
Exam 9 | #109. _____ show a series of steps that lead to a defect, which helps in the manage quality process. |  | Flowcharts | Histograms | Matrix diagrams | Scatter diagrams | Answer option a. | Answer option a. “Flowcharts”. Flowcharts are also referred to as process maps because they display the sequence of steps and the branching possibilities that exist for a process that transforms one or more inputs into one or more outputs. Answer option a. “Flowcharts”. Flowcharts are also referred to as process maps because they display the sequence of steps and the branching possibilities that exist for a process that transforms one or more inputs into one or more outputs.
Exam 9 | #110. According to Herzberg’s theory, all of the following are motivating factors except _____. |  | Recognition | Responsibility | Advancement in career | Salary | Answer option d. | Answer option d. “Salary” is considered a hygiene factor, not a motivating factor. All of the other Answer options are considered motivating factors. Answer option d. “ Salary” is considered a hygiene factor, not a motivating factor. All of the other Answer options are considered motivating factors.
Exam 9 | #111. During procurement closure, a procurement audit includes all of the following except: |  | Reviewing the contract terms to ensure that they have all been met | Identifying successes and failures that should be recognized | Documenting lessons learned | Using the payment system to process consideration as per the terms of the contract | Answer option d. | Using the payment system to process consideration as per the terms of the contract: Reviewing the contract terms to ensure all have been met, identifying successes and failures (Historical Information and Lessons Learned) Answers a., b., and c., are all confirmed completed during the procurement audit. Answer d., Using the Payment System.., is a Tool & Tech used in the Control Procurements process.
Exam 9 | #112. Which of the following is not a consideration for tailoring project integration management processes? |  | Use of automated tools | Project life cycle | Development life cycle | Management approaches | Answer option a. | Answer option a. “Project life cycle” (Answer option b), “Development life cycle” (Answer option c.) and “Management approaches” (Answer option d.) are all considerations for tailoring project integration management processes and since the question is asking which is NOT a consideration for tailoring project integration management processes, thus they are not valid Answers. The best Answer is “Use of automated tools” (Answer option a.) since it is a trend for project integration management not a consideration for tailoring project integration management processes. Answer option a. “Project life cycle” (Answer option b), “ Development life cycle” (Answer option c.) and “ Management approaches” (Answer option d.) are all considerations for tailoring project integration management processes and since the question is asking which is NOT a consideration for tailoring project integration management processes, thus they are not valid Answers. The best Answer is “Use of automated tools” (Answer option a.) since it is a trend for project integration management not a consideration for tailoring project integration management processes.
Exam 9 | #113. An example of scope validation is _____ . |  | Reviewing the performance acceptability of an installed software module | Managing changes to the project schedule | Decomposing the WBS to a work package level | Performing a benefit/cost analysis to determine if we should proceed with the project | Answer option a. | “Reviewing the performance acceptability of an installed software module”. Scope Validation is the process in which the client (Customer/Sponsor, etc.) matches the product service or result to the defined Scope and Requirements, Answer a. Answer b., managing changes is done in the PICC process; c., Decomposing the WBS is part of the Scope definition process; and d., precedes the creation of the Charter, and is considered outside the boundaries of Project Management.
Exam 9 | #114. If a project SPI=1.05, CPI=1.1, BAC=$150K, EV=$50K, how is the project performing? |  | Under planned cost | On planned cost | Over-planned cost | On schedule | Answer option a. | Answer option a. “Under planned cost” since CPI =1.1 then the project is under planned cost. Answer option a. “Under planned cost” since CPI =1.1 then the project is under planned cost.
Exam 9 | #115. A project team functions as a well-organized unit. Which Tuckman ladder stage does this team stand? |  | Performing | Forming | Norming | Storming | Answer option a. | Answer option a. “Performing” Answer option a. “Performing”
Exam 9 | #116. Marion, an Agile Project Manager, is using an Agile approach to deliver business value. During each iteration (Sprint), Marion and the team begin to break down tasks into tangible components that have enough features and functionality to allow the customer to examine value and provide feedback to the team. Which of the following are true regarding these questions when using Scrum Methodology? |  | The team is creating the minimum viable product (MVP) and the Product Owner determines whether the business value has been achieved. | The Scrum Master will assign each task to the Development team members within each iteration (Sprint). | The project team will manage and organize the Product Backlog. | The Product Owner will be assigned as the Development Team lead to take on tasks within each iteration (Sprint). | Answer option a. | The MVP (Minimum Viable Product) is a component of work that contains the lowest tangible feature, function, or end result possible.
Exam 9 | #117. Christina is a Scrum Master working on a Software Development project working at Company 123. Recently, she has received project requirements and now wants to understand the team velocity. What should Christina review? |  | Kanban Board | Sprint Backlog | Scatter Diagram | Burndown Chart | Answer option d. | A burndown chart is a good visual used in Agile Projects to understand team velocity, and effectively monitor the project schedule.
Exam 9 | #118. ________ is an intentional activity that realigns the performance of the project work with the project management plan. |  | Corrective action | Preventive action | Defect repair | Risk escalation | Answer option b. | Preventive action is an intentional activity that ensures the future performance of the project work is aligned with the project management plan.
Exam 9 | #119. You are working as a project manager in an international company. If a skilled resource in the project team resigns, the risk response plan proposes to acquire a new resource from the IT department. If a skilled resource from the IT department cannot be provided, you will request a resource from the “Regional Expertise Group” of your company. Requesting resource from “Regional Expertise Group” is an example of: |  | Fallback Plan | Secondary Risk | Residual Risk | Contingency Plan | Answer option a. | A fallback plan can be developed for implementation if the selected strategy turns out not to be fully effective or if an accepted risk occurs.
Exam 9 | #120. Whose job is it to determine the priorities among projects in a company? |  | Project Manager | Sponsor | Senior Management | Project Team | Answer option c. | Senior Management: Project selection methods discussed in the Presentation are part of the Develop Project Charter process. The PMBOK standard highlights that business case assessment, approval and funding are handled external to project boundaries, the starting point when the project is authorized. It is Senior Managers, not Project Managers, who “determine the priorities among projects in a company.” Therefore, by elimination, Answer options Project Manager, Sponsor and the Project Team are removed from consideration.
Exam 9 | #121. Responsibility, respect, fairness, and honesty are defined by the global project management community as _____ . |  | Aspirational standards | Mandatory standards | The most important values | Optional standards | Answer option c. | The global project management community defines responsibility, respect, fairness, and honesty as the most important values.
Exam 9 | #122. Robin is a Scrum Master working on an Agile project. Robin facilitates a daily stand-up every morning with the Agile team. What is NOT a reason to host daily stand-ups? |  | Removing impediments from the team. | Ensure a smooth workflow for all project tasks through the team. | Reporting to Senior Management. | Align on what has been accomplished up until this point within the iteration (Sprint). | Answer option c. | While everyone (including Senior Management) is welcome to join stand-ups, they aren’t specifically held to report to Senior Management.
Exam 9 | #123. Which is not a tool or technique for the Conduct Procurements process? |  | Make-or-buy analysis | Proposal evaluation | Negotiation | Source selection analysis | Answer option a. | Answer option a. “Make-or-buy analysis”. Following are the tools and techniques for Conduct Procurements process: Answer option a. “Make-or-buy analysis”. Following are the tools and techniques for Conduct Procurements process: 1) Expert judgment 1) Expert judgment 2) Advertising 2) Advertising 3) Bidder conferences 3) Bidder conferences 4) Data analysis 4) Data analysis 5) Proposal evaluation 5) Proposal evaluation 6) Interpersonal and team skills 6) Interpersonal and team skills 7) Negotiation 7) Negotiation
Exam 9 | #124. Critical path method is an important tool for Juan, who tries to develop a schedule for his project. He uses it to estimate the minimum project duration and determine the amount of schedule flexibility on the logical network paths within the schedule model. What should Juan not consider during this step? |  | Activities total float | Activities resource limitations | Activities early start and late start | Activities early finish and late finish | Answer option b. | Answer option b. “Activities resource limitations” Answer option b. “Activities resource limitations”
Exam 9 | #125. _____ documents how the project and product scope will be controlled. |  | Scope baseline | Requirements traceability matrix | Scope management plan | Change management plan | Answer option c. | Answer option c. “Scope management plan” Answer option c. “Scope management plan”
Exam 9 | #126. Which of the following settlement methods is preferred for all claims and disputes? |  | Negotiation | Alternative dispute resolution | Influencing | ADR | Answer option a. | Answer option a. “Negotiation”. The settlement of all claims and disputes through negotiation is the preferred method. Answer option a. “Negotiation”. The settlement of all claims and disputes through negotiation is the preferred method.
Exam 9 | #127. _____ is about using project processes effectively. It involves following and meeting standards to assure stakeholders that the final product will meet their needs, expectations, and requirements. |  | Plan Quality | Manage Quality | Quality assurance | Control Quality | Answer option c. | Answer option c. “Quality assurance”. Quality assurance is about using project processes effectively. It involves following and meeting standards to assure stakeholders that the final product will meet their needs, expectations, and requirements. Answer option c. “Quality assurance”. Quality assurance is about using project processes effectively. It involves following and meeting standards to assure stakeholders that the final product will meet their needs, expectations, and requirements.
Exam 9 | #128. Thomas is a Development Team member on a new Agile Project delivering a new scheduling software. As a Development Team member, what should be Thomas’s first question to guide his work? |  | How much does the project cost? | How long will the project take to be completed? | What is the business value? | How large is the Development Team? | Answer option c. | Agile projects focus primarily on delivering business value, working closely with customers to ensure that the value is always correct.
Exam 9 | #129. Alex is a project manager closing his internal IT upgrade project. Which is not an input for this process? |  | Lessons learned register | Change log | Procurement management plan | Lessons learned repository | Answer option d. | Answer option d. ”Lessons learned repository” is not one of Close project inputs Answer option d. ”Lessons learned repository” is not one of Close project inputs
Exam 9 | #130. Mary, the Product Owner of an Agile project wants to understand if the team will be able to deliver all 28 story points planned for the current sprint. The burndown chart shows that from day 4 to 8, the remaining story points to be developed remain unchanged. Why is this of concern? |  | There is nothing to worry about as the planned burndown line considers this tendency. | This situation means work is not progressing as planned, and delivery is at risk. | The customer is resisting the deliverables because they are not prepared to manage changes associated with accelerated delivery. | The product owner did not understand the features needed for each sprint. | Answer option b. | Burndown charts help see where the project is going overtime. If delivery is at risk, the project manager may need to complete work up to the point where quality is not compromised, and the following story points may need to be included in the next iteration.
Exam 9 | #131. Life cycle approach, resource availability and project dimensions are examples of _____ . |  | Emerging practices for project schedule management | Considerations for tailoring Project Schedule Management | Organizational process assets | Enterprise environmental factors | Answer option b. | Answer option b. “Considerations for tailoring Project Schedule Management” Answer option b. “Considerations for tailoring Project Schedule Management”
Exam 9 | #132. Sara is managing a new formed Lean Project Team. She wants to ensure full alignment across all team members. If the team decides to use the Kaizen approach, what will be the result of this approach? |  | Decreased Productivity. | Increased project risks and costs. | Continuous improvement and changes for good. | Shortened Sprints (iterations) to meet the project schedule. | Answer option c. | Kaizen is a lean methodology used to continually improve product service, product quality, and eliminate waste.
Exam 9 | #133. Which of the following is not a characteristic of projects? |  | They drive change within organizations | They have an organizational scope that changes with the strategic objectives | They enable business value creation to organizations | They are initiated in response to factors acting upon their organizations | Answer option b. | Answer option b. “They have an organizational scope that changes with the strategic objectives” is relevant to portfolios, not projects. Answer option b. “They have an organizational scope that changes with the strategic objectives” is relevant to portfolios, not projects.
Exam 9 | #134. Which of the following is not a characteristic of projects? |  | Unique product | Repetitive in nature | Temporary | Drive change | Answer option b. | Answer option b. The best Answer is “Repetitive in nature” (option b.) is a characteristic of operational activities. “Unique product” (Answer option a.), “Temporary” (Answer option c.) and “Drive change” (Answer option d.) are all characteristics of projects. Answer option b. The best Answer is “Repetitive in nature” (option b.) is a characteristic of operational activities. “Unique product” (Answer option a.), “Temporary” (Answer option c.) and “Drive change” (Answer option d.) are all characteristics of projects .
Exam 9 | #135. Chris, an Agile Project Manager, is assigned to software development project InfoTech. The senior management team suggests that Chris drafts a refined and detailed project plan up front in order to begin project work. What project management approach is being suggested to Chris? |  | Predictive Approach | Agile Approach | Iterative Approach | None of the above | Answer option a. | Predictive project management approaches rely on developing a fully defined project plan in the early planning stages of the project.
Exam 9 | #136. Bill is an Agile Project Manager, assigned to a software development project using the agile approach. While developing a full Scrum team, he realizes there is a vacancy on the team – a key member responsible for facilitating all Scrum meetings and removing team impediments. Which role should Bill be looking to fill on the team? |  | Product Owner | Sponsor | Scrum Master | Dev Team Lead | Answer option c. | The Scrum Master is responsible for facilitating Scrum team meetings and removing impediments preventing Development Team members from executing activities in each iteration (Sprint).
Exam 9 | #137. Templates, monitoring & reporting tools are examples of _____ . |  | Emerging practices for project schedule management | Considerations for tailoring Project Schedule Management | Organizational process assets | Enterprise environmental factors | Answer option c. | Answer option c. “Organizational process assets” Answer option c. “Organizational process assets”
Exam 9 | #138. While performing the control resources process, the project manager wanted to check the number and type of used resources. Which input should he review? |  | Resource breakdown structure | Resource requirements | Work performance data | Physical resource assignments | Answer option c. | Answer option c. “Work performance data”. Work performance data contains data on project status such as which activities have started, their progress (e.g., actual duration, remaining duration, and physical percent complete), and which activities have finished. Answer option c. “Work performance data”. Work performance data contains data on project status such as which activities have started, their progress (e.g., actual duration, remaining duration, and physical percent complete), and which activities have finished.
Exam 9 | #139. Bill is a Project Manager working for Software Development company InfoLead. Recently, the company has decided to transition from a Waterfall approach to Agile. Bill mentions to the Functional Managers that the transitioning to Agile will enable the team to better respond to change and meet customer expectations. Why is this? |  | The Agile team completes all deliverables in one iteration (Sprint). | All planning is done upfront, aligning all team members on what needs to be done for the entire project. | The Agile team works directly with the business representatives to prioritize the delivered value on a recurring basis. | Value is determined by the Agile Team, so development is easy and efficient. | Answer option c. | Collaboration with business representatives (through face-to-face meetings, documentation, conference calls, etc.) is a recurring process in Agile. The team collaborates with the business on the expectations of project deliverables.
Exam 9 | #140. Which of the following is a model of the development life cycle? |  | Iterative | Adaptive | Predictive | All of the above | Answer option d. | Answer option d. “Iterative” (Answer option a.), “Adaptive” (Answer option b.) and “Predictive” (Answer option c.) are all models of the development life cycle. The best Answer is “All of the above” (Answer option d.) Answer option d. “ Iterative ” (Answer option a.), “ Adaptive ” (Answer option b.) and “ Predictive ” (Answer option c.) are all models of the development life cycle . The best Answer is “ All of the above ” (Answer option d.)
Exam 9 | #141. While directing the project work, Alex was assessing the influence of existing facilities and capital equipment on the process. This is an example of _____ . |  | Emerging practices | Enterprise environmental factors | Organizational process assets | Expert judgment | Answer option b. | Answer option b. “Enterprise environmental factors” Answer option b. “Enterprise environmental factors”
Exam 9 | #142. Sue has just been hired on as an Agile Methodology Coach in a shoe-manufacturing global brand Vigor. Upon joining the company, she has identified an opportunity to improve the company's supply chain by developing a product tracking software that will allow all parties involved to know the status of each model from design, production, and delivery to the customer. However, she also has noticed that people are used to working in their departments and hardly collaborate with other areas. This situation represents a problem for any agile initiatives because: |  | Work concentrates in silos which creates dependencies that do not favor accelerated delivery. | Sue will have to train people from all areas in the agile approach. | Resistance to change is high. | Both a and c are correct. | Answer option d. | Answer option d. Companies with department silos show higher resistance to change rates than companies working with process flow. The tendency to work only for one’s area shows that processes are not connected, and therefore, collaboration is challenging. It is harder to implement projects that will affect the supply chain without collaboration. Answer option d. Companies with department silos show higher resistance to change rates than companies working with process flow. The tendency to work only for one’s area shows that processes are not connected, and therefore, collaboration is challenging. It is harder to implement projects that will affect the supply chain without collaboration.
Exam 9 | #143. Which of the following is NOT true about the Project Life Cycle? |  | Cost and staffing levels are low at the start, peak as the work is carried out and drop rapidly as the project draws to a close. | Stakeholder influences are greatest towards the end of the project | Risk and uncertainty are greatest at the start of the project | Cost of changes increases as the project approaches completion | Answer option b. | Answer option b. “Stakeholder influences are greatest towards the end of the project”. Through the process of elimination, Answer options a., c., and d. are true and should be removed from consideration. Answer b. contends that the stakeholder influences are greatest at the end of the project, not so, or at least if they are something is dreadfully wrong. Stakeholders should be involved early on in defining requirements and expectations. Those requirements and expectations are used when defining the scope of the project; decomposed into the WBS and again into the activity level setting the schedule and budget in motion. Their early agreement allows the work to progress with a minimum of surprises toward the end of the Project Life Cycle. Toward the end, the stakeholders are updated as to progress, not influencing change. Answer option b. “Stakeholder influences are greatest towards the end of the project”. Through the process of elimination, Answer options a., c., and d. are true and should be removed from consideration. Answer b. contends that the stakeholder influences are greatest at the end of the project, not so, or at least if they are something is dreadfully wrong. Stakeholders should be involved early on in defining requirements and expectations. Those requirements and expectations are used when defining the scope of the project; decomposed into the WBS and again into the activity level setting the schedule and budget in motion. Their early agreement allows the work to progress with a minimum of surprises toward the end of the Project Life Cycle. Toward the end, the stakeholders are updated as to progress, not influencing change.
Exam 9 | #144. The system factors include _____ . |  | Standards and guidelines | Organizational structure types | Processes and procedures | Ready to use templates | Answer option b. | Answer option b. “Organizational structure types”. The system factors include but are not limited to: Answer option b. “Organizational structure types”. The system factors include but are not limited to: Management elements, Governance frameworks, and Organizational structure types. Management elements, Management elements, Governance frameworks, and Governance frameworks, and Organizational structure types. Organizational structure types.
Exam 9 | #145. The____ is a key input into the Plan Stakeholder Engagement process. |  | Stakeholder Register | Project Management Plan Updates | Risk Register | Analytical Techniques | Answer option a. | Stakeholder Register: Key inputs to the Stakeholder Management Plan include the Project Management Plan, the Stakeholder Register created in the Identify Stakeholders Initiation process, EEFs and OPAs. The Stakeholder Management Plan is a subsidiary plan of the Project Management Plan when developed as an Output of this process. The Risk Register is an input and Output of many of the risk focused processes and Analytical Techniques are tools, not an input.
Exam 9 | #146. _____ involve a relationship between project activities and non-project activities. |  | External dependencies | Internal dependencies | Mandatory dependencies | Discretionary dependencies | Answer option a. | Answer option a. “External dependencies”. A relationship between project activities and non-project activities. Answer option a. “External dependencies”. A relationship between project activities and non-project activities.
Exam 9 | #147. During control procurement, procurement documentation may be updated because of _____ . |  | Performed activities during the procurement process | Unapproved contract changes | Changes to the resource requirements | All of the above | Answer option b. | Answer option b. “Unapproved contract changes” Procurement documentation that may be updated includes the contract with all supporting schedules, requested unapproved contract changes, and approved change requests. Answer option b. “Unapproved contract changes” Procurement documentation that may be updated includes the contract with all supporting schedules, requested unapproved contract changes, and approved change requests.
Exam 9 | #148. _____ is the amount of time a successor activity can advance with respect to a predecessor activity. |  | Activity duration | Lag | Lead | Milestone | Answer option c. | Answer option c. “Lead”. Answer option c. “Lead”.
Exam 9 | #149. Outputs of the Control Costs process include all of the following except . |  | Cost Forecasts | Change Requests | Work performance information | Cost Baseline | Answer option d. | Cost Baseline: Control Costs is all about monitoring the status of the project to update the project costs and manages changes to the cost baseline. The key advantage is to determine and use variances to take corrective actions and minimize risks. Calculated CV, SV, CPI, SPI, and other EVM values are considered Work Performance Information. Analysis of the Control Costs data, corrective or preventive Change Requests to adjust the Cost Baseline or other components may result. Cost Forecasts, a calculated or re-estimated EAC is documented and communicated to Stakeholders. The exception is the Cost Baseline itself. It is an Output of Determine Budget process.
Exam 9 | #150. Sam is a project manager seeking to identify all aspects of effective communication, including the choice of appropriate technologies, methods, and techniques. Which process is he performing? |  | Manage Communications | Plan Communications management | Monitor Stakeholders engagement | Monitor Communications | Answer option a. | Answer option a. “Manage Communications” Answer option a. “Manage Communications”
Exam 9 | #151. You are about to complete your project planning. Which is not an output project document? |  | Quality control measurements | Project schedule network diagram | Management reviews | Project schedule | Answer option c. | Answer option c. “Management reviews” is a component of the project management plan, not a document. Answer option c. “Management reviews” is a component of the project management plan, not a document.
Exam 9 | #152. _____ can point to and focus on the processes that may be out of control and may jeopardize meeting the specified requirements or stakeholders’ expectations. |  | Root cause analysis | Process analysis | Document analysis | Alternatives analysis | Answer option c. | Answer option c. “Document analysis”. Answer option c. “Document analysis”.
Exam 9 | #153. During the project execution, you decided to procure a part of the project scope from an external supplier. To classify this supplier according to directions of influence data-representation technique, which way would you place them? |  | Upward | Downward | Outward | Sideward | Answer option c. | Answer option c. “Outward”. Stakeholder groups and their representatives outside the project team, such as suppliers, government departments, the public, end-users, and regulators. Answer option c. “Outward”. S takeholder groups and their representatives outside the project team, such as suppliers, government departments, the public, end-users, and regulators.
Exam 9 | #154. Project cost control includes _____ . |  | Monitoring work performance against funds expended | Influencing the factors that create changes to the authorized schedule baseline | Preventing approved changes from being included in the reported cost | All of the above | Answer option a. | Answer option a. “Monitoring work performance against funds expended”. Project cost control includes: Answer option a. “Monitoring work performance against funds expended”. Project cost control includes: Influencing the factors that create changes to the authorized cost baseline; Ensuring that all change requests are acted on in a timely manner; Managing the actual changes when and as they occur; Ensuring that cost expenditures do not exceed the authorized funding by period, by WBS component, by activity, and in total for the project; Influencing the factors that create changes to the authorized cost baseline; Influencing the factors that create changes to the authorized cost baseline; Ensuring that all change requests are acted on in a timely manner; Ensuring that all change requests are acted on in a timely manner; Managing the actual changes when and as they occur; Managing the actual changes when and as they occur; Ensuring that cost expenditures do not exceed the authorized funding by period, by WBS component, by activity, and in total for the project; Ensuring that cost expenditures do not exceed the authorized funding by period, by WBS component, by activity, and in total for the project; Monitoring cost performance to isolate and understand variances from the approved cost baseline; Monitoring cost performance to isolate and understand variances from the approved cost baseline; Monitoring cost performance to isolate and understand variances from the approved cost baseline; Monitoring cost performance to isolate and understand variances from the approved cost baseline; Monitoring work performance against funds expended; Monitoring work performance against funds expended; Monitoring work performance against funds expended; Preventing unapproved changes from being included in the reported cost or resource usage; Informing appropriate stakeholders of all approved changes and associated cost; and Bringing expected cost overruns within acceptable limits Preventing unapproved changes from being included in the reported cost or resource usage; Preventing unapproved changes from being included in the reported cost or resource usage; Informing appropriate stakeholders of all approved changes and associated cost; and Informing appropriate stakeholders of all approved changes and associated cost; and Bringing expected cost overruns within acceptable limits Bringing expected cost overruns within acceptable limits
Exam 9 | #155. _____ is the budget associated with the authorized work that has been completed. |  | Planned value (PV) | Earned value (EV) | Actual cost (AC) | Budget At completion (BAC) | Answer option b. | Answer option b. “Earned value (EV)”. (EV) is a measure of work performed expressed in terms of the budget authorized for that work. It is the budget associated with the authorized work that has been completed. Answer option b. “Earned value (EV)”. (EV) is a measure of work performed expressed in terms of the budget authorized for that work. It is the budget associated with the authorized work that has been completed.
Exam 9 | #156. Which of the following processes formalize the completed project deliverables acceptance? |  | Validate scope | Control scope | Close Phase | Close Project | Answer option a. | Answer option a. “Validate scope” process formalizes the completed project deliverables acceptance. Answer option a. “ Validate scope ” process formalizes the completed project deliverables acceptance .
Exam 9 | #157. _____ process helps managing procurement relationships; monitoring contract performance and making changes and corrections as appropriate; and closing out contracts. |  | Plan Procurements | Conduct Procurements | Manage Procurements | Control Procurements | Answer option d. | Answer option d. “Control Procurements”. Control Procurements is the process of managing procurement relationships, monitoring contract performance and making changes and corrections as appropriate, and closing out contracts. Answer option d. “Control Procurements”. Control Procurements is the process of managing procurement relationships, monitoring contract performance and making changes and corrections as appropriate, and closing out contracts.
Exam 9 | #158. Based on Maslow’s hierarchy of needs pyramid, which of the following is at the top?? |  | Safety | Social | Esteem | Self-actualization | Answer option d. | Based on Maslow’s Hierarchy of Needs, people are not motivated to work by security or money. The highest motivation is to contribute and use their skills, self-actualization.
Exam 9 | #159. Which of the following is also known as Failure Costs? |  | Internal costs | Prevention costs | Cost of Defects | Cost of Poor Quality | Answer option d. | Cost of Poor Quality: Cost of Quality is a Tool/Technique used to develop the Plan Quality Management process.
Exam 9 | #160. You are the Project Manager of a time-critical project. One of your sellers is causing you a lot of trouble: most of the seller's deliverables are late and below the agreed quality levels, and you have little confidence in this company's ability to complete the project. What should you do? |  | Meet with the seller to discover the cause of the problem | Assign a group within your team to meet with the seller and reassign project work so that the seller has easier work to accomplish | Terminate the seller for convenience and hire another seller | Provide some of your own staff to augment the seller's staff | Answer option c. | Answer option c. “Terminate the seller for convenience and hire another seller”. Conduct Procurements monitors the contracts with sellers providing deliverables required by the project. Performance Details are collected and if it is below (contract) expectations early termination is a reasonable action for default, cause or convenience. All other Answers provided are precluded by his delivery history. If project Scope, Cost or Time are in jeopardy, Terminating the agreement is a logical action. Answer option c. “Terminate the seller for convenience and hire another seller”. Conduct Procurements monitors the contracts with sellers providing deliverables required by the project. Performance Details are collected and if it is below (contract) expectations early termination is a reasonable action for default, cause or convenience. All other Answers provided are precluded by his delivery history. If project Scope, Cost or Time are in jeopardy, Terminating the agreement is a logical action.
Exam 9 | #161. Within an Agile Project, the role of a Project Manager may or may not be used. What other roles within an Agile team reflect responsibilities similar to those of a Project Manager? |  | Scrum Master | Team Facilitator | Project Team Lead | All of the above | Answer option d. | Although the role of Project Manager within Agile practices is constantly debated, the Agile Practice Guide calls the Project Manager role as Team Facilitator, Scrum Master, or Project Team Lead.
Exam 9 | #162. The use of the knowledge base portal in a project is an example of _____ . |  | Explicit knowledge | Tacit knowledge | Direct knowledge | All of the above | Answer option a. | Answer option a. “Explicit knowledge” is the knowledge that can be codified through images and words and is usually inputted into a knowledge base. Answer option a. “Explicit knowledge” is the knowledge that can be codified through images and words and is usually inputted into a knowledge base.
Exam 9 | #163. Which is not one of the enterprise environmental factors internal to the organization? |  | Infrastructure | Resource availability | Financial considerations | Geographic distribution of facilities and resources | Answer option c. | Answer option c. “Infrastructure” (Answer option a), “Resource availability” (Answer option b.) and “Geographic distribution of facilities and resources” (Answer option d.) are all Enterprise environmental factors internal to the organization and since the question is asking which is NOT Internal Enterprise environmental factors, thus they are not valid Answers. The best Answer is “Financial considerations” (Answer option c.) since it is an EEF external to the organization. Answer option c. “Infrastructure” (Answer option a), “ Resource availability” (Answer option b.) and “ Geographic distribution of facilities and resources” (Answer option d.) are all Enterprise environmental factors internal to the organization and since the question is asking which is NOT Internal Enterprise environmental factors, thus they are not valid Answers. The best Answer is “Financial considerations” (Answer option c.) since it is an EEF external to the organization.
Exam 9 | #164. _____ contains information about requirements, including how to validate them. |  | Requirements documentation | The requirements traceability matrix | The requirements management plan | The scope baseline | Answer option b. | Answer option b. “The requirements traceability matrix”. Answer option b. “The requirements traceability matrix”.
Exam 9 | #165. The IT support desk manager is one of your project’s stakeholders. After applying the planned engagement strategy with the IT support desk manager, his attitude towards the project became less aggressive. She has a better understanding of the project benefits now. What was her previous engagement level? |  | Unaware | Resistant | Neutral | Supportive | Answer option b. | Answer option b. The case hints that the IT support desk manager was aggressive and does not fully understand the project benefits which means she was “Resistant”. Answer option b. The case hints that the IT support desk manager was aggressive and does not fully understand the project benefits which means she was “Resistant”.
Exam 9 | #166. Which of the following is not an output of the implement risk responses process? |  | Project team assignments update | Risk report | Change requests | Issue log update | Answer option b. | Answer option b. “Risk report” Answer option b. “Risk report”
Exam 9 | #167. John is developing a detailed description of the project and product. Which process is he performing? |  | Define Scope | Create WBS | Plan Scope Management | Collect Requirements | Answer option a. | Answer option a. “Define Scope” Answer option a. “Define Scope”
Exam 9 | #168. All of the following are techniques used for resolving conflict EXCEPT: |  | Withdraw | Reconcile | Supervising | Collaboration | Answer option c. | Answer option c. There are five general techniques for resolving a conflict. Answer option c. There are five general techniques for resolving a conflict. Withdraw/Avoid Smooth/Accommodate Compromise/Reconcile Force/Direct Collaborate/Problem Solve Withdraw/Avoid Withdraw/Avoid Smooth/Accommodate Smooth/Accommodate Compromise/Reconcile Compromise/Reconcile Force/Direct Force/Direct Collaborate/Problem Solve Collaborate/Problem Solve
Exam 9 | #169. Sally is analyzing and evaluating the quality of the processes and deliverables of the project against the standards of the requirements specified. Which input should she review in this process? |  | Quality metrics | Quality control measurements | Quality reports | Quality management plan | Answer option b. | Answer option b. “Quality control measurements” Answer option b. “Quality control measurements”
Exam 9 | #170. _____ can be used to identify process gaps and flaws. |  | Affinity diagrams | Flowcharts | Fishbone diagrams | Histograms | Answer option b. | Answer option b. “Flowcharts”. The depiction in a diagram format of the inputs, process actions, and outputs of one or more processes within a system. Answer option b. “Flowcharts”. The depiction in a diagram format of the inputs, process actions, and outputs of one or more processes within a system.
Exam 9 | #171. Which of the following is NOT a Tool/Technique for the Determine Budget process? |  | Cost Aggregation | Reserve Analysis | Funding Limit Reconciliation | Resource Calendars | Answer option d. | “Resource Calendars”. This question tests the student’s understanding of the ITOs of the Determine Budget process. Through elimination, Answer options a., b., and c. may be removed from consideration: all of these are Tools/Techniques of the Determine Budget process. The only exception is option d., Resource Calendars, which is an Output of the Plan Resource Management updated in the Acquire Resource process and used as an input by many other project processes.
Exam 9 | #172. Internal service level agreements (SLAs) is an example of _____ . |  | Contracts | Purchase orders | Agreements | All of the above | Answer option c. | Answer option c. “Agreements”. A contract between a service provider (either internal or external) and the end-user that defines the level of service expected from the service provider. Answer option c. “Agreements”. A contract between a service provider (either internal or external) and the end-user that defines the level of service expected from the service provider.
Exam 9 | #173. Which of the following is NOT a function of the Program Management Office? |  | Administrative support to Project Managers and team members | Consolidation of individual project status reports into the program and corporate reports including exception reporting | Responsibility for quality audit and assurance across the organization | Coordination of resource allocation across all projects | Answer option c. | Responsible for quality audit and assurance across the organization: A Program Management Office could well be responsible for ensuring that projects or programs within its purview achieve a measure of quality. However, being “responsible for quality audit and assurance across the organization” implies a responsibility far beyond the scope of a PMO. This is a responsibility more appropriately owned by the organization’s Quality department, not
Exam 9 | #174. At which stage does the project manager release the staff from the project? |  | Forming | Storming | Norming | Adjourning | Answer option d. | Answer option d. “Adjourning”. In this phase, the team completes the work and moves on from the project. This typically occurs when staff is released from the project as deliverables are completed or as part of the Close Project or Phase process. Answer option d. “Adjourning”. In this phase, the team completes the work and moves on from the project. This typically occurs when staff is released from the project as deliverables are completed or as part of the Close Project or Phase process.
Exam 9 | #175. Which of the following do stakeholders’ stakes include? |  | Interest, power and influence | Interest, rights and knowledge | Interest, impact and influence | Power, impact and contribution | Answer option b. | “Interest, power and influence” (Answer option a.) power and influence are not stakeholders stakes. “Interest, impact and influence” (Answer option c.) impact and influence are not stakeholders stakes. “Power, impact and contribution” (Answer option d.) impact and power are not stakeholders stakes. The best Answer is “Interest, rights and knowledge” (Answer option b.)
Exam 9 | #176. Which of the following can be categorized as tacit knowledge? |  | Insights | Information written on knowledge base | Process is drawn on flowchart | Managerial financial report | Answer option a. | “Information written on knowledge base” (Answer option b.), “Process is drawn on flowchart” (Answer option c.) and “Managerial financial report” (Answer option d.) are all forms of explicit knowledge. The best Answer is “Insights” (Answer option a.)
Exam 9 | #177. Which is true about the project, programs, and portfolios regarding operational activities? |  | Projects and programs don’t include operational activities | Projects and Portfolios include operational activities | Programs and Portfolios include operational activities | Projects, programs and Portfolios don’t include operational activities | Answer option c. | “Projects and programs don’t include operational activities” (Answer option a.) Programs include operational activities, “Projects and Portfolios include operational activities” (Answer option b.) Projects do not include operational activities. “Projects, programs, and Portfolios don’t include operational activities” (Answer option d.) programs and Portfolios include operational activities. The best Answer is “Programs and Portfolios include operational activities” (Answer option c.)
Exam 9 | #178. Oliver is formalizing the acceptance of the completed project deliverables. Which process is he performing? |  | Define Scope | Create WBS | Validate Scope | Control Scope | Answer option c. | Answer option c. “Validate Scope”. The process of formalizing acceptance of the completed project deliverables. Answer option c. “Validate Scope”. The process of formalizing acceptance of the completed project deliverables.
Exam 9 | #179. When is the best time in a project for performing the “Manage Project Knowledge” process to have the most benefit? |  | Once at the beginning of the project | Once at the end of the project | Throughout the project | At the beginning of each phase or iteration | Answer option c. | “Throughout the project”. Project knowledge should be managed throughout the project from initiation to closure. Therefore, the best Answer is option c.
Exam 9 | #180. In your project, you are comparing the performance measurement baseline against the actual schedule and cost performance. This is an example of: |  | Earned Value Performance | Variance Analysis | Trend Analysis | Critical Path Method | Answer option a. | Earned value performance compares the performance measurement baseline to actual schedule and cost performance.